## AIPEX DATA working copy
Work ID | Line of Business | PROGRAM CLASSIFICATION | Program NAME | FEATURE TYPE | Predicted RepairType | Location | Required Work Completion Date | Planned Year | Project Duration (days) | Outage Duration (days) | Projected Project Start Date | Driver Safety | Driver Operational | Driver Environment | Driver Regulatory | Driver Compliance | StandardCost | ProjectedCost | Actual Cost | January | February | March | April | May | June | July | August | September | October | November | December | Total | Burn Rate | Financial Budget Type | Fully Scoped | OUTAGE TYPE (UNIT, PLANT, STATION, PIPELINE) | OutageConfirmed | OutagePlanned | outageRequired | detailsScoped | designCompleted | longLeadMaterialsOrdered | resourcesIdentified | transferCompressor | permitsReceived | siteVisitsPerformed | stakeholdersEngaged | stakeholdersSupport | projectReimburseable | projectPlanEst | Project Scope Readiness | Project Engeering/ Design | Project Funding | Project Permits | Project Stakeholder Engagement | Project Procurement & SCM | Project Resource Mgmt | Project Outage Mgmt | Project Execution Schedule & Contractor Support | Project Readiness Percentage | Project Readiness Ranking | Priority Scope Clarity | Priority Impact Assessment | Priority Safety Requirement | Priority Commercial Capacity Reliabiilty | Priority Outage Impacts | Regulatory Compliance | Priority Ranking Percentage | Priority Ranking | PROJECTED FLOW IMPACT (M^3/DAY) | COST IMPACT /DAY | DESIRED THROUGHPUT CAPACITY (M^3/DAY) | PROJECTED CAPACITY IMPACT | CAPACITY LOSS DUE TO UNPLANNED EVENT (M^3 /DAY) | DURATION OF DOWNTIME FROM UNPLANNED EVENT (NO. OF DAYS)
1 | L1 | FACILITY | CIVIL |  | REPAIR- STRUCTURE | Calgary | 2025-03-31 | 2025 | 167 | 0 | 2024-10-15 | low | low | high | med | med | 195000 | 209751 | 233723 | 0 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 175.2379 | EXPENSE | Yes | NO | n |  |  |  | x | x | x | NR |  |  | x | x |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 5 | 3 | 5 | 3 | 4 | 1 | 70% | 7 |  | 4522
2 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Toronto | 2026-07-31 | 2026 | 139 | 4 | 2026-03-14 | low | med | high | med | high | 2446435 | 2171872 | 2212990 | 0 | 0 | 244643.5 | 978574 | 978574 | 244643.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2446435 | 271.7058 | CAPITAL | Yes | Unit outage | x | x | x | x | x | x | x | NR | x | x | x | x | no | x | 3 | 5 | 2 | 2 | 5 | 5 | 5 | 5 | 1 | 73.33% | 8 | 2 | 1 | 5 | 1 | 2 | 1 | 40% | 4 |  | 9580.8769
3 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2026-12-31 | 2025 | 180 | 4 | 2026-07-04 | med | high | low | low | low | 1800000 | 1864493 | 1802540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 720000 | 720000 | 180000 | 1800000 | 87.159 | EXPENSE | Yes | Derate/low flow Pipe segment | x | x | x | x | x | NR | x | x | x | x | x |  | No | Yes | 5 | 1 | 1 | 4 | 2 | 5 | 1 | 5 | 4 | 62.22% | 6 | 4 | 4 | 1 | 3 | 3 | 3 | 60% | 6 |  | 8429.71
4 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Montreal | 2026-12-31 | 2026 | 220 | 2 | 2026-05-25 | med | high | high | med | high | 190000 | 175087 | 174680 | 0 | 38000 | 76000 | 76000 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 380000 | 40.7081 | EXPENSE | No | Derate/low flow Pipe segment |  |  | x | x | x | no | x | x | x | [5 empty] | 3 | 1 | 4 | 3 | 1 | 4 | 1 | 5 | 4 | 57.78% | 6 | 1 | 3 | 1 | 4 | 4 | 2 | 50% | 5 |  | 8756
5 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | North Bay | 2026-03-31 | 2026 | 100 | 5 | 2025-12-21 | low | high | med | high | med | 400000 | 611769 | 669250 | 80000 | 160000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 85.7283 | EXPENSE | Yes | Pipeline segment | x | x | x | x | x | Yes | x | NR | NR | NR | NR | NR | No | Yes | 4 | 5 | 2 | 3 | 1 | 4 | 5 | 5 | 3 | 71.11% | 8 | 5 | 5 | 1 | 5 | 1 | 1 | 60% | 6 |  | 52
6 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2026-07-31 | 2025 | 200 | 4 | 2026-01-12 | high | med | med | high | low | 650000 | 778878 | 779764 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 0 | 0 | 0 | 650000 | 65.902 | EXPENSE | Yes | Derate/low flow Pipe segment | x | x | x | x | x | Yes | x | x | Yes | Yes | Yes |  | No | No | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 77.78% | 8 | 3 | 1 | 1 | 1 | 1 | 4 | 36.67% | 4 |  | 4526
7 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | SLEEVE | Ottawa | 2026-10-31 | 2026 | 200 | 5 | 2026-04-14 | low | high | high | low | low | 300000 | 306500 | 310745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 120000 | 120000 | 0 | 0 | 300000 | 27.2404 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | Yes | Yes | 2 | 3 | 2 | 1 | 3 | 1 | 5 | 1 | 3 | 46.67% | 5 | 4 | 5 | 1 | 4 | 2 | 3 | 63.33% | 7 |  | 258
8 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Regina | 2026-03-31 | 2025 | 198 | 4 | 2025-09-14 | low | med | low | low | low | 1555220 | 1812532 | 1821625 | 0 | 0 | 0 | 466566 | 933132 | 155522 | 0 | 0 | 0 | 0 | 0 | 0 | 1555220 | 52.8301 | CAPITAL | Yes | Unit outage |  | X |  |  |  | Yes | no | no | no | Yes | no | no | Yes | Yes | 5 | 5 | 1 | 3 | 3 | 1 | 4 | 4 | 1 | 60% | 6 | 1 | 4 | 1 | 4 | 1 | 2 | 43.33% | 5 |  | 4785
9 | L2 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Regina | 2026-03-31 | 2025 | 168 | 7 | 2025-10-14 | low | high | high | high | low | 588848 | 535508 | 456687 | 58884.8 | 235539.2 | 235539.2 | 58884.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588848 | 77.556 | EXPENSE | Yes | Unit outage | X | X | X | X |  | Yes | Yes | no | no | no | Yes | no | no | no | 2 | 3 | 2 | 1 | 5 | 2 | 3 | 1 | 3 | 48.89% | 5 | 4 | 2 | 1 | 3 | 4 | 2 | 53.33% | 6 |  | 4101.0339
10 | L1 | FACILITY | SCADA |  | UPDATE CONTROL ROOM | Toronto | 2026-12-31 | 2025 | 126 | 4 | 2026-08-27 | med | low | med | med | med | 1670000 | 1693220 | 1676269 | 0 | 501000 | 1002000 | 167000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1670000 | 100.3146 | CAPITAL | Yes | Station outage |  |  | X |  | X | no | Yes | no | Yes | no | no | no | Yes | Yes | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 5 | 2 | 1 | 5 | 4 | 4 | 70% | 7 |  | 22170.3266
11 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2026-10-31 | 2026 | 100 | 5 | 2026-07-23 | med | med | low | low | med | 400000 | 465754 | 469856 | 40000 | 160000 | 160000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 159.1014 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | Yes | Yes | no | Yes | no | Yes | Yes | no | 4 | 5 | 3 | 4 | 5 | 3 | 4 | 5 | 4 | 82.22% | 9 | 2 | 5 | 1 | 2 | 1 | 5 | 53.33% | 6 |  | 842.9817
12 | L1 | FACILITY | SCADA |  | UPDATE CONTROL ROOM | Toronto | 2027-03-31 | 2027 | 126 | 4 | 2026-11-25 | med | low | med | med | med | 1670000 | 1793220 | 1676269 | 501000 | 1002000 | 167000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1670000 | 100.3146 | CAPITAL | Yes | Station outage |  |  | X |  | X | no | Yes | no | Yes | no | no | no | Yes | Yes | 1 | 2 | 2 | 1 | 1 | 5 | 1 | 2 | 2 | 37.78% | 4 | 2 | 3 | 1 | 4 | 2 | 4 | 53.33% | 6 |  | 10182.1737
12 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Calgary | 2026-03-31 | 2026 | 150 | 8 | 2025-11-01 | high | med | med | high | low | 450000 | 958642 | 975845 | 0 | 0 | 0 | 90000 | 180000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 83.0189 | CAPITAL | No | Pipeline segment |  | X |  | X |  | Yes | Yes | no | Yes | Yes | no | no | Yes | Yes | 2 | 3 | 2 | 3 | 4 | 3 | 4 | 3 | 2 | 57.78% | 6 | 1 | 4 | 1 | 3 | 2 | 3 | 46.67% | 5 |  | 842.9817
13 | L3 | FACILITY | SCADA |  | UPDATE CONTROL ROOM | Edmonton | 2028-10-31 | 2028 | 279 | 2 | 2028-01-26 | med | high | high | med | med | 1485000 | 1410317 | 1412591 | 445500 | 891000 | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 132.6576 | CAPITAL | No | Station outage |  |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | no | 2 | 5 | 2 | 1 | 4 | 3 | 1 | 1 | 4 | 51.11% | 6 | 1 | 4 | 1 | 1 | 1 | 2 | 33.33% | 4 |  | 3981
13 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2026-03-31 | 2026 | 200 | 5 | 2025-09-12 | high | med | high | low | low | 450000 | 505744 | 505000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 180000 | 45000 | 0 | 450000 | 32.772 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | Yes | no | no | no | Yes | Yes | no | 1 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 35.56% | 4 | 3 | 4 | 1 | 1 | 3 | 5 | 56.67% | 6 |  | 13420.4072
14 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Montreal | 2026-12-31 | 2026 | 250 | 5 | 2026-04-25 | low | low | med | med | med | 500000 | 534470 | 533637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 147.3292 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | no | Yes | no | no | Yes | 5 | 1 | 1 | 4 | 4 | 4 | 1 | 5 | 2 | 60% | 6 | 1 | 1 | 1 | 5 | 5 | 5 | 60% | 6 |  | 1727.2647
15 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Toronto | 2026-07-31 | 2026 | 175 | 8 | 2026-02-06 | med | high | high | low | med | 300000 | 387000 | 435200 | 60000 | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 180.0007 | CAPITAL | Yes | Pipeline segment | X |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 35.56% | 4 | 2 | 4 | 1 | 5 | 2 | 3 | 56.67% | 6 |  | 1578
16 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2026-10-31 | 2025 | 180 | 4 | 2026-05-04 | low | high | high | high | low | 2000000 | 2085890 | 2014691 | 200000 | 800000 | 800000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 488.9487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | no | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 33.33% | 4 | 1 | 4 | 1 | 1 | 3 | 5 | 50% | 5 |  | 3506.8708
17 | L2 | FACILITY | MECHANICAL |  | PSV REPLACE | Saskatoon | 2026-07-31 | 2025 | 251 | 2 | 2025-11-22 | high | high | low | low | med | 65716 | 80320 | 72802 | 19714.8 | 39429.6 | 6571.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65716 | 2325.1948 | EXPENSE | No | no | X |  | X |  | X | Yes | Yes | no | no | no | no | Yes | Yes | Yes | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 26.67% | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 23.33% | 3 |  | 18109.7232
18 | L2 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Ottawa | 2025-03-31 | 2025 | 120 | 4 | 2024-12-01 | low | low | low | low | low | 2100000 | 2520000 | 2454250 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 840000 | 840000 | 210000 | 0 | 0 | 2100000 | 40.3349 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | no | no | no | no | no | Yes | no | 3 | 5 | 2 | 4 | 4 | 4 | 4 | 5 | 3 | 75.56% | 8 | 2 | 5 | 1 | 2 | 3 | 1 | 46.67% | 5 |  | 3981.0002
19 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2025-12-31 | 2025 | 185 | 2 | 2025-06-29 | high | low | med | low | low | 650000 | 689531 | 725189 | 65000 | 260000 | 260000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 242.8512 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X | X | no | no | no | Yes | no | Yes | Yes | Yes | no | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 33.33% | 4 | 3 | 1 | 1 | 2 | 2 | 3 | 40% | 4 |  | 20815.3255
20 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | North Bay | 2026-03-31 | 2025 | 318 | 4 | 2025-05-17 | low | low | high | med | med | 1782115 | 1872852 | 1850714 | 0 | 0 | 0 | 0 | 0 | 534634.5 | 1069269 | 178211.5 | 0 | 0 | 0 | 0 | 1782115 | 40.9465 | EXPENSE | Yes | Unit outage |  |  | X | X | X | no | Yes | no | no | no | Yes | no | Yes | Yes | 4 | 2 | 2 | 3 | 2 | 1 | 5 | 5 | 2 | 57.78% | 6 | 5 | 5 | 1 | 5 | 2 | 3 | 70% | 7 |  | 425
21 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Regina | 2026-03-31 | 2025 | 136 | 4 | 2025-11-15 | low | med | med | low | med | 1850000 | 1837033 | 1893775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 740000 | 740000 | 185000 | 1850000 | 38.7086 | CAPITAL | Yes | Unit outage |  | X |  | X |  | no | Yes | no | no | Yes | Yes | Yes | no | no | 5 | 5 | 3 | 3 | 4 | 4 | 5 | 1 | 4 | 75.56% | 8 | 5 | 2 | 1 | 1 | 2 | 1 | 40% | 4 |  | 278.7236
22 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2027-03-31 | 2025 | 200 | 4 | 2026-09-12 | med | high | high | high | high | 2000000 | 2473474 | 2450004 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 2000000 | 25.7224 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | no | Yes | no | no | no | Yes | Yes | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 2 | 5 | 66.67% | 6 | 2 | 5 | 5 | 1 | 2 | 3 | 60% | 6 |  | 278.7236
23 | L2 | PIPE INTEGRITY | EXCAVATION | ECOR | RECOAT | Saskatoon | 2025-07-31 | 2025 | 100 | 3 | 2025-04-22 | low | high | low | med | low | 400000 | 450563 | 409107 | 0 | 0 | 0 | 40000 | 160000 | 160000 | 40000 | 0 | 0 | 0 | 0 | 0 | 400000 | 135.4595 | EXPENSE | No | Pipeline segment |  | X |  |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 4 | 4 | 4 | 1 | 3 | 4 | 1 | 5 | 3 | 64.44% | 6 | 1 | 5 | 5 | 4 | 1 | 5 | 70% | 7 |  | 278.7236
24 | L3 | PIPE INTEGRITY | EXCAVATION | ECOR | RECOAT | Saskatoon | 2025-10-31 | 2025 | 100 | 3 | 2025-07-23 | low | high | low | med | high | 400000 | 450041 | 489250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 122.5032 | EXPENSE | Yes | Pipeline segment | X |  |  | X |  | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 3 | 2 | 2 | 4 | 3 | 2 | 1 | 1 | 44.44% | 5 | 5 | 4 | 5 | 4 | 4 | 3 | 83.33% | 9 |  | 203.1281
25 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Regina | 2026-12-31 | 2026 | 150 | 7 | 2026-08-03 | low | med | med | high | med | 2275112 | 2782481 | 2834679 | 0 | 0 | 0 | 0 | 0 | 227511.2 | 910044.8 | 910044.8 | 227511.2 | 0 | 0 | 0 | 2275112 | 1776.9185 | CAPITAL | Yes | Unit outage | X | X |  |  |  | no | Yes | Yes | Yes | no | Yes | no | Yes | no | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 3 | 40% | 4 | 4 | 5 | 5 | 5 | 3 | 4 | 86.67% | 9 |  | 203.1281
26 | L1 | PIPE INTEGRITY | EXCAVATION | ICOR | RECOAT | Toronto | 2025-07-31 | 2025 | 150 | 3 | 2025-03-03 | high | med | high | med | med | 500000 | 509283 | 509602 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 500000 | 148.1189 | EXPENSE | Yes | Pipeline segment | X |  | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 5 | 5 | 1 | 4 | 4 | 5 | 5 | 3 | 4 | 80% | 8 | 5 | 3 | 5 | 3 | 2 | 1 | 63.33% | 7 |  | 203.1281
27 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Regina | 2025-10-31 | 2025 | 150 | 15 | 2025-06-03 | low | low | low | low | med | 450000 | 715279 | 728240 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 184.0435 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | Yes | no | no | no | no | no | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 37.78% | 4 | 4 | 5 | 1 | 2 | 3 | 1 | 53.33% | 6 |  | 853.1382
28 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Saskatoon | 2025-10-31 | 2025 | 125 | 4 | 2025-06-28 | med | med | med | high | high | 450000 | 419931 | 446058 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 34.5922 | CAPITAL | No | derate/low flow Pipe segment | X | X |  |  | X | Yes | no | no | no | Yes | no | no | Yes | Yes | 3 | 1 | 2 | 4 | 3 | 2 | 4 | 5 | 2 | 57.78% | 6 | 4 | 5 | 1 | 1 | 5 | 2 | 60% | 6 |  | 23717.2367
29 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Montreal | 2026-07-31 | 2026 | 200 | 8 | 2026-01-12 | high | high | low | low | high | 500000 | 520373 | 521000 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 16.0911 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 4 | 2 | 5 | 1 | 3 | 3 | 1 | 4 | 2 | 55.56% | 6 | 2 | 3 | 1 | 3 | 3 | 2 | 46.67% | 5 |  | 746.1723
30 | L3 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Edmonton | 2025-07-31 | 2025 | 140 | 7 | 2025-03-13 | med | low | low | high | high | 2926827 | 2801872 | 2905463 | 0 | 878048.1 | 1756096.2 | 292682.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2926827 | 35.5747 | CAPITAL | Yes | Unit outage | X |  |  |  |  | no | Yes | no | no | no | no | Yes | Yes | no | 3 | 4 | 3 | 2 | 1 | 3 | 3 | 4 | 5 | 62.22% | 6 | 5 | 3 | 1 | 5 | 2 | 1 | 56.67% | 6 |  | 1174.9707
31 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2026-12-31 | 2026 | 180 | 5 | 2026-07-04 | low | high | high | low | low | 450000 | 515075 | 534568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 45000 | 0 | 360000 | 450000 | 23.9593 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | Yes | no | no | Yes | Yes | no | Yes | 3 | 3 | 2 | 1 | 4 | 3 | 5 | 3 | 1 | 55.56% | 6 | 1 | 2 | 1 | 2 | 3 | 4 | 43.33% | 5 |  | 13677.1818
32 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Saskatoon | 2025-12-31 | 2025 | 180 | 15 | 2025-07-04 | high | low | high | med | med | 450000 | 529718 | 528784 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 270.4653 | CAPITAL | No | Pipeline segment |  | X |  |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 2 | 2 | 44.44% | 5 | 1 | 4 | 1 | 4 | 3 | 4 | 56.67% | 6 |  | 16021.8416
33 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2025-10-31 | 2025 | 275 | 7 | 2025-01-29 | low | med | low | high | low | 450000 | 542580 | 545780 | 45000 | 45000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 104.3547 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 4 | 2 | 4 | 2 | 4 | 5 | 2 | 3 | 4 | 66.67% | 6 | 1 | 5 | 1 | 2 | 4 | 1 | 46.67% | 5 |  | 7007.9205
34 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2025-03-31 | 2025 | 185 | 4 | 2024-09-27 | high | low | high | high | med | 650000 | 789531 | 768189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 650000 | 48.6768 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | no | Yes | no | Yes | Yes | Yes | Yes | no | 4 | 2 | 4 | 3 | 2 | 3 | 4 | 4 | 5 | 68.89% | 6 | 2 | 1 | 1 | 5 | 2 | 1 | 40% | 4 |  | 7007.9205
35 | L2 | FACILITY | ELECTRICAL |  | MCC | Calgary | 2025-03-31 | 2025 | 127 | 2 | 2024-11-24 | low | med | med | low | low | 300000 | 222067 | 990619 | 30000 | 30000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 342.7961 | CAPITAL | Yes | Unit outage | X | X | X |  |  | Yes | no | Yes | no | Yes | no | Yes | Yes | no | 4 | 3 | 1 | 5 | 3 | 1 | 5 | 2 | 1 | 55.56% | 6 | 2 | 4 | 1 | 4 | 1 | 3 | 50% | 5 |  | 18.4662
36 | L3 | PIPE INTEGRITY | EXCAVATION | ECOR | RECOAT | Regina | 2025-10-31 | 2025 | 100 | 5 | 2025-07-23 | high | low | low | med | med | 400000 | 550000 | 559415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 194.4749 | EXPENSE | Yes | Pipeline segment |  |  |  | X | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 1 | 2 | 3 | 2 | 1 | 1 | 4 | 1 | 4 | 42.22% | 5 | 1 | 1 | 1 | 4 | 3 | 2 | 40% | 4 |  | 1685.9635
37 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2025-12-31 | 2025 | 200 | 3 | 2025-06-14 | low | low | low | low | low | 650000 | 620531 | 625189 | 0 | 0 | 0 | 0 | 65000 | 65000 | 520000 | 0 | 0 | 0 | 0 | 0 | 650000 | 26.0956 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 31.11% | 4 | 2 | 1 | 1 | 1 | 3 | 5 | 43.33% | 5 |  | 1685.9635
38 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Quebec City | 2025-10-31 | 2025 | 220 | 2 | 2025-03-25 | high | med | low | med | low | 75000 | 85254 | 95452 | 0 | 0 | 0 | 0 | 22500 | 45000 | 7500 | 0 | 0 | 0 | 0 | 0 | 75000 | 156.8587 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 22.22% | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 30% | 3 |  | 778.6578
39 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2026-12-31 | 2026 | 170 | 4 | 2026-07-14 | med | high | high | med | high | 450000 | 852538 | 857775 | 0 | 0 | 0 | 0 | 45000 | 45000 | 360000 | 0 | 0 | 0 | 0 | 0 | 450000 | 35.5286 | CAPITAL | No | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | Yes | Yes | Yes | Yes | no | 2 | 4 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 40% | 4 | 1 | 4 | 1 | 5 | 2 | 1 | 46.67% | 5 |  | 121.8769
40 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | North Bay | 2025-12-31 | 2025 | 181 | 4 | 2025-07-03 | low | high | high | high | med | 2494653 | 2370566 | 2526101 | 0 | 0 | 0 | 0 | 748395.9 | 1496791.8 | 249465.3 | 0 | 0 | 0 | 0 | 0 | 2494653 | 35.1989 | CAPITAL | Yes | Unit outage | X | X | X | X |  | no | no | no | Yes | Yes | no | no | no | Yes | 2 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 37.78% | 4 | 3 | 2 | 1 | 4 | 4 | 5 | 63.33% | 7 |  | 643.2391
41 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | CUTOUT | Edmonton | 2025-07-31 | 2025 | 180 | 8 | 2025-02-01 | med | high | med | high | med | 450000 | 452014 | 454644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 45000 | 360000 | 0 | 0 | 450000 | 26.015 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | Yes | Yes | 1 | 4 | 2 | 1 | 2 | 1 | 4 | 1 | 2 | 40% | 4 | 3 | 5 | 5 | 3 | 5 | 4 | 83.33% | 9 |  | 267.7598
42 | L3 | PIPE INTEGRITY | EXCAVATION | ECOR | RECOAT | Ottawa | 2026-12-31 | 2026 | 200 | 4 | 2026-06-14 | high | high | high | high | med | 400000 | 449044 | 455180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 18.1227 | CAPITAL | No | Pipeline segment | X | X |  |  |  | no | Yes | no | Yes | no | no | no | Yes | no | 1 | 5 | 1 | 1 | 5 | 3 | 3 | 1 | 1 | 46.67% | 5 | 2 | 1 | 5 | 3 | 1 | 5 | 56.67% | 6 |  | 267.7598
43 | L2 | PIPE INTEGRITY | EXCAVATION | ECOR | RECOAT | Ottawa | 2025-12-31 | 2025 | 200 | 2 | 2025-06-14 | low | high | high | high | low | 350000 | 534618 | 575616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 280000 | 350000 | 502.8679 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | no | Yes | no | no | no | no | Yes | no | no | 3 | 4 | 2 | 5 | 5 | 3 | 1 | 5 | 1 | 64.44% | 6 | 2 | 2 | 5 | 3 | 1 | 1 | 46.67% | 5 |  | 267.7598
44 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANNUAL SURVEY | Calgary | 2026-10-31 | 2026 | 180 | 5 | 2026-05-04 | high | med | high | high | low | 780000 | 1376437 | 1313514 | 0 | 0 | 0 | 0 | 234000 | 468000 | 78000 | 0 | 0 | 0 | 0 | 0 | 780000 | 98.0993 | EXPENSE | Yes | NO outage | X | X | X | X | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 3 | 4 | 1 | 5 | 4 | 5 | 4 | 4 | 1 | 68.89% | 6 | 1 | 3 | 5 | 5 | 3 | 4 | 70% | 7 |  | 17599.3754
45 | L1 | FACILITY | SCADA |  | REPAIR | Regina | 2025-03-31 | 2025 | 141 | 1 | 2024-11-10 | low | low | med | low | med | 78215 | 790617 | 78706 | 0 | 0 | 0 | 0 | 7821.5 | 7821.5 | 62572 | 0 | 0 | 0 | 0 | 0 | 78215 | 76.5462 | EXPENSE | Yes | plant outage |  |  | X | X |  | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 4 | 5 | 2 | 5 | 2 | 5 | 2 | 4 | 3 | 71.11% | 8 | 3 | 2 | 5 | 2 | 4 | 2 | 60% | 6 |  | 7024.2246
46 | L1 | FACILITY | ELECTRICAL |  | MCC | Montreal | 2025-10-31 | 2025 | 160 | 2 | 2025-05-24 | med | low | low | med | low | 538000 | 544824 | 479305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161400 | 322800 | 53800 | 0 | 0 | 538000 | 70.4069 | EXPENSE | No | plant outage | X | X |  | X |  | no | no | no | no | no | Yes | no | no | Yes | 5 | 5 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 60% | 6 | 4 | 1 | 1 | 1 | 3 | 4 | 46.67% | 5 |  | 1591.1704
47 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-REMEDITION | Montreal | 2025-10-31 | 2025 | 200 | 5 | 2025-04-14 | high | med | med | med | low | 850000 | 850026 | 8543747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 85000 | 680000 | 0 | 0 | 850000 | 76.5526 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 3 | 2 | 1 | 5 | 3 | 4 | 3 | 4 | 3 | 62.22% | 7 | 4 | 2 | 1 | 4 | 2 | 3 | 53.33% | 6 |  | 6832.4917
48 | L2 | PIPE INTEGRITY | EXCAVATION | ECOR | RECOAT | North Bay | 2025-03-31 | 2025 | 100 | 5 | 2024-12-21 | med | low | high | low | low | 400000 | 495918 | 472825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 320000 | 0 | 0 | 400000 | 414.8802 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | Yes | 3 | 3 | 1 | 5 | 2 | 1 | 1 | 4 | 5 | 55.56% | 6 | 1 | 5 | 1 | 4 | 5 | 4 | 66.67% | 7 |  | 330
49 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | RECOAT | North Bay | 2025-12-31 | 2025 | 100 | 4 | 2025-09-22 | low | low | med | high | low | 400000 | 491000 | 485000 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 400000 | 1266.3815 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 2 | 4 | 1 | 2 | 1 | 3 | 4 | 2 | 1 | 44.44% | 5 | 4 | 2 | 1 | 2 | 4 | 2 | 50% | 5 |  | 5845
50 | L1 | FACILITY | MECHANICAL |  | VALVE | Saskatoon | 2025-03-31 | 2025 | 358 | 2 | 2024-04-07 | high | high | low | high | high | 433976 | 480247 | 522109 | 0 | 0 | 86795.2 | 173590.4 | 0 | 173590.4 | 0 | 0 | 0 | 0 | 0 | 0 | 433976 | 166.3938 | EXPENSE | No | Station outage | X |  | X | X | X | Yes | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 5 | 4 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 44.44% | 5 | 1 | 1 | 1 | 5 | 4 | 1 | 43.33% | 5 |  | 5732.8906
51 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Calgary | 2025-10-31 | 2025 | 190 | 4 | 2025-04-24 | med | high | high | low | high | 125000 | 110410 | 107380 | 0 | 0 | 37500 | 75000 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 565.0045 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | Yes | no | Yes | no | Yes | 1 | 4 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 35.56% | 4 | 1 | 1 | 1 | 2 | 4 | 2 | 36.67% | 4 |  | 3077.9635
52 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | North Bay | 2025-03-31 | 2025 | 150 | 4 | 2024-11-01 | med | high | low | high | med | 1250000 | 1281952 | 1285422 | 0 | 0 | 0 | 125000 | 125000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 72.2212 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  | X | no | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 3 | 1 | 2 | 3 | 5 | 2 | 1 | 2 | 1 | 44.44% | 5 | 5 | 3 | 1 | 2 | 4 | 5 | 66.67% | 7 |  | 5097.2605
53 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Ottawa | 2025-12-31 | 2025 | 200 | 15 | 2025-06-14 | low | high | low | low | low | 450000 | 986403 | 1000404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 45000 | 360000 | 0 | 450000 | 103.1048 | CAPITAL | No | Pipeline segment | X |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 5 | 5 | 1 | 3 | 5 | 5 | 5 | 2 | 4 | 77.78% | 8 | 4 | 5 | 5 | 2 | 2 | 1 | 63.33% | 7 |  | 13582.277
54 | L3 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Toronto | 2025-12-31 | 2025 | 143 | 4 | 2025-08-10 | high | med | low | high | med | 1661943 | 1679277 | 1613482 | 0 | 0 | 0 | 498582.9 | 997165.8 | 166194.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1661943 | 12.8453 | CAPITAL | Yes | Unit outage | X |  |  |  | X | no | no | no | no | no | no | no | Yes | no | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 2 | 71.11% | 8 | 4 | 5 | 5 | 4 | 3 | 4 | 83.33% | 9 |  | 7709.8457
55 | L3 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Regina | 2025-12-31 | 2025 | 247 | 7 | 2025-04-28 | high | low | low | low | low | 900542 | 960268 | 1273533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 720433.6 | 0 | 0 | 0 | 760433.6 | 141.4185 | EXPENSE | Yes | Unit outage |  | X | X | X | X | no | Yes | Yes | no | no | no | no | no | Yes | 5 | 2 | 1 | 4 | 4 | 4 | 4 | 3 | 1 | 62.22% | 7 | 5 | 2 | 5 | 2 | 5 | 4 | 76.67% | 8 |  | 7110.0938
56 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2026-07-31 | 2026 | 200 | 3 | 2026-01-12 | low | high | high | med | low | 500000 | 534135 | 576815 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 200000 | 50000 | 0 | 0 | 500000 | 91.6522 | CAPITAL | Yes | PIpeline segment | X |  |  | X |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 5 | 1 | 2 | 4 | 3 | 1 | 5 | 5 | 5 | 68.89% | 7 | 3 | 4 | 5 | 5 | 2 | 1 | 66.67% | 7 |  | 4391.6369
57 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Montreal | 2025-12-31 | 2025 | 200 | 4 | 2025-06-14 | high | high | low | high | high | 300000 | 505538 | 508025 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 98.783 | EXPENSE | Yes | Pipeline segment | X |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 2 | 5 | 1 | 2 | 1 | 4 | 2 | 3 | 1 | 46.67% | 5 | 1 | 1 | 5 | 5 | 2 | 3 | 56.67% | 6 |  | 4314.1949
58 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Ottawa | 2027-10-31 | 2027 | 175 | 8 | 2027-05-09 | med | high | high | high | med | 750000 | 838059 | 852793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 600000 | 0 | 750000 | 279.986 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | Yes | no | Yes | Yes | no | Yes | no | no | 2 | 5 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 37.78% | 4 | 5 | 4 | 5 | 5 | 1 | 1 | 70% | 7 |  | 4858.8867
59 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | WINNIPEG | 2025-12-31 | 2025 | 150 | 8 | 2025-08-03 | low | med | low | high | high | 450000 | 428864 | 428750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 45000 | 360000 | 0 | 0 | 450000 | 56.9979 | CAPITAL | Yes | Pipeline segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | no | no | no | 2 | 1 | 2 | 2 | 2 | 4 | 1 | 3 | 1 | 40% | 4 | 1 | 5 | 5 | 2 | 5 | 5 | 76.67% | 8 |  | 2178.0735
60 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | WINNIPEG | 2025-07-31 | 2025 | 150 | 8 | 2025-03-03 | med | low | med | med | med | 450000 | 816716 | 810460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 45000 | 360000 | 0 | 450000 | 30.4676 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | Yes | Yes | Yes | no | Yes | no | Yes | no | Yes | 5 | 5 | 1 | 3 | 3 | 5 | 5 | 3 | 3 | 73.33% | 8 | 1 | 4 | 1 | 4 | 3 | 2 | 50% | 5 |  | 1090.5382
61 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Montreal | 2026-12-31 | 2026 | 232 | 4 | 2026-05-13 | med | med | low | high | high | 1083938 | 1109932 | 1042157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108393.8 | 108393.8 | 867150.4 | 1083938 | 96.1454 | CAPITAL | Yes | Unit outage | X | X |  |  | X | no | no | Yes | no | no | Yes | Yes | no | Yes | 2 | 1 | 1 | 1 | 4 | 5 | 4 | 2 | 1 | 46.67% | 5 | 1 | 2 | 1 | 4 | 5 | 4 | 56.67% | 6 |  | 8501.4285
62 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Edmonton | 2025-03-31 | 2025 | 200 | 8 | 2024-09-12 | high | low | high | med | med | 350000 | 310639 | 310032 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 280000 | 0 | 0 | 0 | 0 | 350000 | 4.3752 | CAPITAL | No | Pipeline segment | X | X | X |  | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 4 | 46.67% | 5 | 2 | 1 | 1 | 3 | 4 | 1 | 40% | 4 |  | 4052.0846
63 | L3 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Ottawa | 2025-10-31 | 2025 | 61 | 2 | 2025-08-31 | low | high | high | med | high | 450000 | 672690 | 653162 | 0 | 0 | 0 | 45000 | 45000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 373.8206 | CAPITAL | Yes | Derate/low flow Pipe segment | X | X | X |  | X | Yes | no | no | Yes | Yes | Yes | no | Yes | no | 2 | 4 | 3 | 1 | 3 | 4 | 1 | 2 | 5 | 55.56% | 6 | 3 | 2 | 1 | 1 | 1 | 4 | 40% | 4 |  | 6062.6028
64 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2025-03-31 | 2025 | 318 | 4 | 2024-05-17 | med | med | med | med | low | 2601688 | 2675222 | 2315263 | 0 | 0 | 0 | 260168.8 | 260168.8 | 2081350.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2601688 | 218.5955 | CAPITAL | Yes | Unit outage |  | X | X |  | X | no | Yes | Yes | Yes | no | no | Yes | Yes | Yes | 5 | 4 | 3 | 4 | 1 | 2 | 2 | 3 | 3 | 60% | 6 | 2 | 2 | 1 | 3 | 3 | 5 | 53.33% | 6 |  | 2610.3898
65 | L2 | FACILITY | MEASUREMENT |  | RTU REPLACMENT | WINNIPEG | 2025-12-31 | 2025 | 258 | 3 | 2025-04-17 | med | high | med | high | low | 500000 | 524966 | 511278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 400000 | 0 | 500000 | 61.7752 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X |  |  | Yes | no | no | Yes | Yes | no | no | Yes | Yes | 2 | 3 | 2 | 1 | 5 | 1 | 1 | 1 | 5 | 46.67% | 5 | 1 | 5 | 1 | 4 | 2 | 5 | 60% | 6 |  | 241.5599
66 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2025-07-31 | 2025 | 180 | 5 | 2025-02-01 | med | med | low | high | low | 350000 | 451173 | 453222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 280000 | 350000 | 22.175 | EXPENSE | Yes | Pipeline segment | X | X | X |  |  | Yes | no | no | no | Yes | no | no | Yes | no | 4 | 1 | 5 | 4 | 4 | 5 | 1 | 3 | 2 | 64.44% | 7 | 3 | 4 | 1 | 4 | 5 | 5 | 73.33% | 8 |  | 4995.3897
67 | L1 | FACILITY | ELECTRICAL |  | REPLACE | WINNIPEG | 2027-12-31 | 2025 | 247 | 1 | 2027-04-28 | high | high | high | low | low | 467637 | 559382 | 690691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467637 | 0 | 0 | 467637 | 297.3869 | CAPITAL | No | Station outage |  | X |  | X |  | Yes | no | Yes | no | no | Yes | Yes | no | no | 5 | 1 | 3 | 3 | 5 | 3 | 3 | 2 | 4 | 64.44% | 7 | 1 | 3 | 1 | 5 | 2 | 2 | 46.67% | 5 |  | 6993.5456
68 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Regina | 2025-10-31 | 2025 | 52 | 4 | 2025-09-09 | high | low | med | high | high | 3188591 | 3052434 | 3104640 | 0 | 0 | 0 | 0 | 0 | 0 | 318859.1 | 1275436.4 | 1275436.4 | 318859.1 | 0 | 0 | 3188591 | 81.1583 | CAPITAL | Yes | Unit outage |  |  |  | X |  | Yes | Yes | no | Yes | no | no | Yes | no | Yes | 2 | 5 | 1 | 2 | 5 | 5 | 4 | 1 | 1 | 57.78% | 6 | 1 | 5 | 1 | 4 | 5 | 4 | 66.67% | 7 |  | 222.8052
69 | L1 | FACILITY | ELECTRICAL |  | REPLACE | WINNIPEG | 2025-12-31 | 2025 | 247 | 3 | 2025-04-28 | high | high | high | low | low | 467637 | 559382 | 690691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140291.1 | 140291.1 | 187054.8 | 0 | 0 | 467637 | 297.3869 | EXPENSE | No | Station outage |  | X |  | X |  | Yes | no | Yes | no | no | Yes | Yes | no | no | 4 | 5 | 3 | 2 | 2 | 1 | 4 | 1 | 2 | 53.33% | 6 | 4 | 1 | 1 | 1 | 4 | 1 | 40% | 4 |  | 7007.9205
69 | L3 | FACILITY | MEASUREMENT |  | CALIBRATION | Toronto | 2025-07-31 | 2025 | 270 | 3 | 2024-11-03 | high | high | low | high | med | 200000 | 217554 | 217574 | 20000 | 160000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 128.3733 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X | X | X | Yes | Yes | no | Yes | no | Yes | no | no | no | 3 | 2 | 4 | 2 | 5 | 4 | 3 | 2 | 5 | 66.67% | 7 | 1 | 1 | 1 | 4 | 4 | 3 | 46.67% | 5 |  | 840.2082
70 | L1 | FACILITY | ELECTRICAL |  | REPLACE | Ottawa | 2028-10-31 | 2028 | 253 | 5 | 2028-02-21 | high | med | high | low | high | 955474 | 1284363 | 1254585 | 0 | 0 | 95547.4 | 95547.4 | 764379.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 955474 | 17.7519 | CAPITAL | No | Station outage |  |  |  | X |  | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 2 | 4 | 1 | 1 | 3 | 4 | 4 | 3 | 4 | 57.78% | 6 | 5 | 3 | 1 | 2 | 1 | 3 | 50% | 5 |  | 32.5005
70 | L1 | FACILITY | EXCAVATION | Dent | SURVEY | Ottawa | 2025-10-31 | 2025 | 80 | 1 | 2025-08-12 | high | high | med | low | high | 60000 | 43630 | 45456 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 2019.9872 | EXPENSE | No | Unit outage |  |  | X | X |  | Yes | Yes | Yes | no | Yes | no | no | no | no | 2 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 42.22% | 5 | 3 | 3 | 1 | 2 | 2 | 5 | 53.33% | 6 |  | 5000
71 | L1 | FACILITY | ELECTRICAL |  | REPLACE | Quebec City | 2028-07-31 | 2028 | 75 | 2 | 2028-05-17 | low | low | med | high | med | 309820 | 355289 | 371994 | 0 | 0 | 0 | 0 | 0 | 309820 | 0 | 0 | 0 | 0 | 0 | 0 | 309820 | 249.175 | CAPITAL | No | Station outage | X | X |  | X |  | no | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 5 | 4 | 2 | 1 | 2 | 5 | 1 | 3 | 3 | 57.78% | 6 | 5 | 1 | 1 | 1 | 2 | 2 | 40% | 4 |  | 3220.812
71 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2026-10-31 | 2026 | 120 | 15 | 2026-07-03 | low | low | low | high | high | 450000 | 680678 | 686152 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 22.4512 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | no | Yes | no | no | 3 | 5 | 4 | 2 | 2 | 1 | 5 | 3 | 5 | 66.67% | 7 | 5 | 3 | 1 | 2 | 5 | 3 | 63.33% | 7 |  | 646
72 | L1 | FACILITY | MECHANICAL |  | VALVE | North Bay | 2025-03-31 | 2025 | 219 | 5 | 2024-08-24 | med | high | med | high | low | 250000 | 168943 | 233667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 200000 | 0 | 0 | 250000 | 342.4579 | CAPITAL | Yes | Station outage | X | X | X | X |  | Yes | no | no | Yes | no | no | no | Yes | no | 3 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 4 | 48.89% | 5 | 3 | 3 | 1 | 3 | 1 | 5 | 53.33% | 6 |  | 289
73 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2025-03-31 | 2025 | 150 | 4 | 2024-11-01 | med | med | high | med | low | 500000 | 608924 | 630832 | 100000 | 350000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 93.0837 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | Yes | Yes | no | no | 4 | 4 | 3 | 4 | 1 | 2 | 4 | 1 | 1 | 53.33% | 6 | 2 | 3 | 1 | 3 | 1 | 5 | 50% | 5 |  | 347
74 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2025-12-31 | 2025 | 150 | 4 | 2025-08-03 | low | high | low | low | low | 350000 | 379330 | 377636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 280000 | 350000 | 415.9262 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | no | no | no | Yes | Yes | Yes | no | Yes | 4 | 2 | 4 | 3 | 3 | 5 | 2 | 5 | 5 | 73.33% | 8 | 4 | 3 | 1 | 5 | 5 | 5 | 76.67% | 8 |  | 158885
75 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2025-07-31 | 2025 | 150 | 5 | 2025-03-03 | med | low | high | med | low | 1800000 | 1855522 | 1845724 | 360000 | 1260000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 87.5976 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 5 | 5 | 2 | 3 | 1 | 3 | 1 | 4 | 60% | 6 | 3 | 5 | 1 | 2 | 2 | 1 | 46.67% | 5 |  | 1207.7993
76 | L3 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Toronto | 2025-03-31 | 2025 | 170 | 5 | 2024-10-12 | high | high | high | high | med | 650000 | 788878 | 779764 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 260000 | 260000 | 65000 | 0 | 0 | 650000 | 27.6329 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 5 | 4 | 3 | 2 | 1 | 1 | 5 | 5 | 4 | 66.67% | 7 | 1 | 3 | 1 | 1 | 5 | 1 | 40% | 4 |  | 1785
77 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Quebec City | 2025-07-31 | 2025 | 246 | 4 | 2024-11-27 | med | med | high | high | low | 2615905 | 2573335 | 2610990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261590.5 | 1046362 | 1046362 | 261590.5 | 2615905 | 294.0372 | CAPITAL | Yes | unit outage | [5 empty] | Yes | no | no | Yes | no | Yes | no | Yes | no | 1 | 5 | 1 | 2 | 5 | 3 | 5 | 2 | 3 | 60% | 6 | 3 | 3 | 1 | 2 | 3 | 2 | 46.67% | 5 |  | 898
78 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2025-12-31 | 2025 | 250 | 5 | 2025-04-25 | low | high | high | high | med | 300000 | 295522 | 295724 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 0 | 0 | 300000 | 110.9054 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | no | no | Yes | no | no | Yes | Yes | Yes | 4 | 1 | 3 | 4 | 4 | 2 | 3 | 1 | 4 | 57.78% | 6 | 1 | 1 | 1 | 2 | 3 | 2 | 33.33% | 4 |  | 172.2548
79 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2025-10-31 | 2025 | 250 | 5 | 2025-02-23 | low | high | med | med | low | 1250000 | 1350000 | 1450000 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 1000000 | 0 | 0 | 0 | 0 | 1250000 | 96.934 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 5 | 44.44% | 5 | 2 | 1 | 1 | 5 | 4 | 5 | 60% | 6 |  | 172.2548
80 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Regina | 2027-12-31 | 2027 | 250 | 15 | 2027-04-25 | low | low | med | high | med | 450000 | 453975 | 454237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 29.298 | CAPITAL | No | Pipeline segment | X |  |  | X | X | no | Yes | no | Yes | no | no | no | no | Yes | 1 | 4 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 42.22% | 5 | 2 | 3 | 1 | 4 | 4 | 5 | 63.33% | 7 |  | 191.3942
81 | L2 | FACILITY | MECHANICAL |  | VALVE | Quebec City | 2025-03-31 | 2025 | 82 | 5 | 2025-01-08 | med | low | low | med | high | 350000 | 451468 | 447048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 280000 | 0 | 0 | 350000 | 331.1789 | CAPITAL | No | Unit outage | X |  | X |  | X | Yes | Yes | no | no | no | no | Yes | no | Yes | 5 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 42.22% | 5 | 1 | 4 | 1 | 5 | 2 | 4 | 56.67% | 6 |  | 382.7885
82 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Quebec City | 2025-05-31 | 2025 | 120 | 7 | 2025-01-31 | high | med | low | high | low | 450000 | 1514932 | 1512774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 7.2499 | CAPITAL | No | pipeline segment | X | X | X |  | X | no | no | no | no | no | no | no | Yes | Yes | 5 | 4 | 2 | 1 | 5 | 2 | 1 | 5 | 1 | 57.78% | 6 | 2 | 1 | 1 | 4 | 4 | 2 | 46.67% | 5 |  | 173.2929
83 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Winnipeg | 2027-12-31 | 2027 | 108 | 4 | 2027-09-14 | high | med | low | low | high | 797261 | 334282 | 1027178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79726.1 | 79726.1 | 637808.8 | 0 | 797261 | 128.8384 | EXPENSE | No | Unit outage | X |  | X | X | X | no | Yes | Yes | Yes | Yes | no | no | no | Yes | 5 | 5 | 5 | 1 | 2 | 3 | 3 | 5 | 3 | 71.11% | 8 | 2 | 2 | 1 | 1 | 2 | 5 | 43.33% | 5 |  | 900.2043
84 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2026-10-31 | 2026 | 100 | 4 | 2026-07-23 | med | low | low | high | low | 750000 | 789882 | 779817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 750000 | 4.1819 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | no | no | no | no | no | Yes | Yes | no | no | 2 | 1 | 1 | 1 | 2 | 3 | 4 | 1 | 5 | 44.44% | 5 | 2 | 1 | 1 | 1 | 3 | 4 | 40% | 4 |  | 749.7244
85 | L1 | FACILITY | ELECTRICAL |  | BATTERY REPLACEMENT | Montreal | 2025-03-31 | 2025 | 158 | 2 | 2024-10-24 | med | med | low | med | high | 50000 | 56313 | 57545 | 0 | 0 | 0 | 5000 | 5000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 98.5476 | EXPENSE | No | Station outage | X |  | X | X | X | no | Yes | Yes | no | no | no | no | no | no | 5 | 5 | 2 | 2 | 3 | 5 | 4 | 1 | 1 | 62.22% | 7 | 2 | 3 | 1 | 4 | 3 | 4 | 56.67% | 6 |  | 41798.5165
86 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2027-03-31 | 2027 | 120 | 7 | 2026-12-01 | low | med | low | high | med | 650000 | 698448 | 697296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 650000 | 28.5018 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | no | Yes | no | no | Yes | 1 | 1 | 3 | 1 | 5 | 2 | 2 | 1 | 4 | 44.44% | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 23.33% | 3 |  | 32.5005
87 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | North Bay | 2027-10-31 | 2027 | 100 | 7 | 2027-07-23 | high | low | low | med | med | 350000 | 370016 | 378399 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 140000 | 35000 | 0 | 0 | 0 | 350000 | 96.1798 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | no | no | no | Yes | Yes | 5 | 2 | 2 | 2 | 3 | 1 | 3 | 3 | 1 | 48.89% | 5 | 2 | 3 | 1 | 5 | 4 | 3 | 60% | 6 |  | 1022.4116
88 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Ottawa | 2025-10-31 | 2025 | 280 | 4 | 2025-01-24 | high | med | high | high | high | 1924395 | 1930813 | 1914572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577318.5 | 1154637 | 192439.5 | 1924395 | 99.4896 | CAPITAL | Yes | Unit outage |  | X |  | X | X | Yes | Yes | no | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 1 | 2 | 4 | 1 | 5 | 1 | 1 | 44.44% | 5 | 2 | 3 | 1 | 2 | 4 | 2 | 46.67% | 5 |  | 1022.4116
89 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Saskatoon | 2026-03-31 | 2026 | 120 | 8 | 2025-12-01 | high | low | med | med | high | 450000 | 480343 | 480758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 450000 | 89.4674 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 5 | 4 | 5 | 5 | 1 | 3 | 2 | 1 | 3 | 64.44% | 7 | 4 | 1 | 1 | 2 | 3 | 1 | 40% | 4 |  | 458
90 | L3 | FACILITY | MECHANICAL |  | FUEL GAS HEATING | Ottawa | 2025-10-31 | 2025 | 343 | 4 | 2024-11-22 | low | low | high | low | low | 750000 | 715433 | 758806 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 74.4943 | EXPENSE | No | Unit outage | X |  |  | X | X | no | no | no | Yes | Yes | no | no | Yes | no | 4 | 1 | 2 | 3 | 1 | 5 | 5 | 2 | 5 | 62.22% | 7 | 5 | 5 | 1 | 1 | 3 | 5 | 66.67% | 7 |  | 13420.4072
91 | L2 | FACILITY | ELECTRICAL |  | BATTERY REPLACEMENT | Ottawa | 2025-07-31 | 2025 | 125 | 4 | 2025-03-28 | high | med | med | high | low | 50000 | 58484 | 52324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 50000 | 170.5508 | EXPENSE | Yes | Unit outage | X | X | X |  | X | Yes | no | Yes | no | no | Yes | Yes | no | no | 3 | 3 | 3 | 2 | 1 | 4 | 1 | 2 | 1 | 44.44% | 5 | 2 | 4 | 1 | 1 | 5 | 5 | 60% | 6 |  | 4447
92 | L1 | FACILITY | MECHANICAL |  | FUEL GAS HEATING | Montreal | 2025-03-31 | 2025 | 314 | 3 | 2024-05-21 | med | high | med | med | high | 450000 | 486795 | 483739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 450000 | 318.952 | CAPITAL | Yes | Unit outage |  |  | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 5 | 2 | 4 | 5 | 2 | 4 | 2 | 1 | 3 | 62.22% | 7 | 3 | 2 | 1 | 1 | 1 | 1 | 30% | 3 |  | 4487
92 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2026-07-31 | 2026 | 100 | 6 | 2026-04-22 | med | med | low | med | high | 350000 | 677837 | 682856 | 0 | 35000 | 140000 | 105000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 68.0307 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 2 | 1 | 2 | 1 | 5 | 4 | 4 | 3 | 1 | 51.11% | 6 | 1 | 1 | 1 | 2 | 2 | 1 | 26.67% | 3 |  | 20000
93 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Quebec City | 2025-12-31 | 2025 | 250 | 8 | 2025-04-25 | med | med | low | med | high | 650000 | 686027 | 682144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 650000 | 108.8597 | CAPITAL | No | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | no | Yes | Yes | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 26.67% | 3 |  | 2078
94 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Saskatoon | 2025-12-31 | 2025 | 205 | 7 | 2025-06-09 | high | low | low | med | med | 1800000 | 1964493 | 1902540 | 0 | 0 | 0 | 0 | 0 | 180000 | 720000 | 720000 | 180000 | 0 | 0 | 0 | 1800000 | 55.4393 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 5 | 4 | 4 | 2 | 1 | 2 | 4 | 2 | 4 | 62.22% | 7 | 5 | 1 | 1 | 1 | 4 | 5 | 56.67% | 6 |  | 1875
95 | L1 | FACILITY | CIVIL |  | BUILDING REPAIR | Quebec City | 2025-10-31 | 2025 | 133 | 1 | 2025-06-20 | med | med | med | low | low | 85000 | 85685 | 82589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25500 | 51000 | 8500 | 85000 | 1753.282 | EXPENSE | No | Unit outage |  | X |  |  | X | no | no | Yes | no | Yes | Yes | Yes | Yes | no | 5 | 4 | 3 | 5 | 4 | 1 | 1 | 1 | 1 | 55.56% | 6 | 2 | 4 | 1 | 5 | 4 | 1 | 56.67% | 6 |  | 7718.869
96 | L2 | FACILITY | CIVIL |  | BUILDING REPAIR | Calgary | 2029-12-31 | 2029 | 75 | 0 | 2029-10-17 | high | high | med | low | med | 95000 | 96308 | 94522 | 0 | 9500 | 9500 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 | 491.4807 | EXPENSE | Yes | NO | X |  | X | X |  | no | no | no | Yes | Yes | no | no | no | no | 1 | 5 | 1 | 1 | 5 | 1 | 2 | 1 | 3 | 44.44% | 5 | 2 | 3 | 5 | 4 | 3 | 5 | 73.33% | 8 |  | 20000
96 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2025-12-31 | 2025 | 250 | 4 | 2025-04-25 | med | low | med | low | med | 450000 | 856958 | 888680 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 450000 | 64.1787 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 3 | 2 | 1 | 3 | 4 | 5 | 4 | 1 | 2 | 55.56% | 6 | 2 | 5 | 5 | 1 | 3 | 3 | 63.33% | 7 |  | 7718.869
97 | L1 | FACILITY | CIVIL |  | BUILDING REPAIR | Edmonton | 2028-07-31 | 2028 | 150 | 0 | 2028-03-03 | med | high | low | high | low | 200000 | 222276 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 160000 | 0 | 0 | 200000 | 850.7175 | EXPENSE | Yes | NO | X |  |  | X | X | Yes | no | Yes | no | Yes | no | Yes | no | no | 3 | 1 | 2 | 2 | 4 | 4 | 4 | 2 | 4 | 57.78% | 6 | 1 | 1 | 1 | 4 | 4 | 3 | 46.67% | 5 |  | 203.1281
97 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Calgary | 2026-12-31 | 2026 | 169 | 4 | 2026-07-15 | high | low | med | high | med | 1880538 | 2506702 | 2514549 | 0 | 564161.4 | 1128322.8 | 188053.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1880538 | 53.9499 | CAPITAL | Yes | Unit outage |  |  | X | X | X | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 1 | 1 | 1 | 1 | 5 | 5 | 3 | 1 | 3 | 46.67% | 5 | 1 | 2 | 1 | 1 | 2 | 5 | 40% | 4 |  | 6993.5456
98 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Toronto | 2025-10-31 | 2025 | 56 | 4 | 2025-09-05 | low | high | low | low | high | 1594549 | 1595132 | 1599106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159454.9 | 637819.6 | 637819.6 | 159454.9 | 0 | 1594549 | 37.5721 | CAPITAL | Yes | Unit outage |  | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | no | no | 3 | 3 | 4 | 2 | 3 | 2 | 3 | 4 | 5 | 64.44% | 7 | 2 | 4 | 5 | 5 | 4 | 3 | 76.67% | 8 |  | 1475
99 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Saskatoon | 2025-07-31 | 2025 | 80 | 4 | 2025-05-12 | med | low | high | high | low | 3872272 | 3820379 | 3865247 | 0 | 0 | 0 | 0 | 0 | 0 | 387227.2 | 1548908.8 | 1548908.8 | 387227.2 | 0 | 0 | 3872272 | 213.8378 | CAPITAL | Yes | Unit outage | X |  |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 2 | 2 | 1 | 1 | 5 | 1 | 4 | 1 | 3 | 44.44% | 5 | 4 | 4 | 5 | 5 | 1 | 2 | 70% | 7 |  | 636.4681
100 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2025-12-31 | 2025 | 100 | 4 | 2025-09-22 | high | low | low | high | high | 400000 | 445632 | 446927 | 0 | 0 | 0 | 0 | 80000 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 93.8623 | EXPENSE | No | Pipeline segment |  | X |  | X | X | no | no | no | no | Yes | no | Yes | no | no | 1 | 2 | 2 | 1 | 2 | 4 | 4 | 2 | 1 | 42.22% | 5 | 4 | 5 | 5 | 3 | 1 | 4 | 73.33% | 8 |  | 25393.3666
101 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2025-07-31 | 2025 | 304 | 4 | 2024-09-30 | med | med | low | high | low | 3275751 | 3384117 | 3338163 | 0 | 0 | 0 | 0 | 0 | 327575.1 | 1310300.4 | 1310300.4 | 327575.1 | 0 | 0 | 0 | 3275751 | 57.8611 | CAPITAL | Yes | Unit outage | X |  | X | X | X | Yes | no | no | Yes | no | no | Yes | Yes | no | 5 | 1 | 5 | 4 | 5 | 5 | 2 | 1 | 5 | 73.33% | 8 | 3 | 1 | 1 | 4 | 2 | 2 | 43.33% | 5 |  | 2369.8282
102 | L3 | FACILITY | MEASUREMENT |  | RTU UPGRADE | Calgary | 2028-12-31 | 2025 | 49 | 4 | 2028-11-12 | high | med | high | low | low | 10000 | 11107 | 10762 | 0 | 0 | 0 | 0 | 1000 | 4000 | 4000 | 1000 | 0 | 0 | 0 | 0 | 10000 | 131.8611 | CAPITAL | Yes | Pipeline segment | X |  |  |  |  | no | no | no | Yes | no | no | Yes | Yes | Yes | 2 | 5 | 2 | 2 | 5 | 4 | 2 | 2 | 3 | 60% | 6 | 5 | 1 | 1 | 5 | 4 | 5 | 70% | 7 |  | 2369.8282
103 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Regina | 2026-03-31 | 2026 | 150 | 4 | 2025-11-01 | low | med | med | high | high | 650000 | 666455 | 695432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 260000 | 260000 | 65000 | 0 | 650000 | 12.1249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 4 | 2 | 1 | 2 | 3 | 5 | 4 | 2 | 4 | 60% | 6 | 5 | 3 | 1 | 5 | 4 | 2 | 66.67% | 7 |  | 3138.8656
104 | L2 | FACILITY | MECHANICAL |  | SCRUBBER TANK | Ottawa | 2027-07-31 | 2027 | 14 | 1 | 2027-07-17 | med | low | high | med | high | 85000 | 88751 | 82561 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 2167.9338 | CAPITAL | Yes | Unit outage | X |  |  | X | X | no | no | Yes | Yes | Yes | Yes | no | Yes | Yes | 5 | 2 | 3 | 2 | 5 | 3 | 3 | 1 | 1 | 55.56% | 6 | 3 | 1 | 5 | 2 | 1 | 2 | 46.67% | 5 |  | 2610.3898
104 | L3 | FACILITY | ELECTRICAL |  | SWITCHGEAR | Montreal | 2026-07-31 | 2026 | 303 | 5 | 2025-10-01 | med | high | med | high | low | 90000 | 93359 | 94586 | 9000 | 0 | 9000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 14.4786 | CAPITAL | No | Station outage |  | X | X | X |  | no | no | Yes | Yes | no | Yes | Yes | no | no | 4 | 5 | 2 | 4 | 2 | 5 | 4 | 4 | 2 | 71.11% | 8 | 1 | 4 | 1 | 5 | 2 | 1 | 46.67% | 5 |  | 3138.8656
105 | L3 | FACILITY | MECHANICAL |  | SCRUBBER TANK | Saskatoon | 2026-12-31 | 2026 | 281 | 1 | 2026-03-25 | high | med | med | high | high | 36136 | 62047 | 60412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3613.6 | 14454.4 | 21681.6 | 0 | 39749.6 | 558.5679 | EXPENSE | No | Unit outage | X | X |  | X | X | Yes | Yes | no | no | no | Yes | no | no | Yes | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 35.56% | 4 | 1 | 2 | 1 | 1 | 3 | 3 | 36.67% | 4 |  | 560.1412
105 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Ottawa | 2025-10-31 | 2025 | 254 | 8 | 2025-02-19 | med | low | med | med | med | 1109165 | 1300190 | 1349541 | 0 | 0 | 0 | 0 | 110916.5 | 443666 | 665499 | 0 | 0 | 0 | 0 | 0 | 1220081.5 | 31.5139 | CAPITAL | Yes | Unit outage |  |  | X | X | X | Yes | Yes | no | Yes | no | no | no | no | no | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 3 | 3 | 1 | 4 | 3 | 5 | 63.33% | 7 |  | 14928.9944
106 | L2 | FACILITY | MECHANICAL |  | SILENCER | Quebec City | 2026-03-31 | 2026 | 82 | 5 | 2026-01-08 | med | low | low | med | high | 350000 | 451468 | 357048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 8000 | 0 | 10000 | 331.1789 | CAPITAL | No | Unit outage | X |  | X |  | X | Yes | Yes | no | no | no | no | Yes | no | Yes | 4 | 2 | 2 | 5 | 3 | 5 | 3 | 3 | 3 | 66.67% | 7 | 1 | 4 | 1 | 1 | 4 | 3 | 46.67% | 5 |  | 6832.4917
106 | L1 | FACILITY | MECHANICAL |  | FURNACE | Calgary | 2025-03-31 | 2025 | 314 | 3 | 2024-05-21 | med | high | med | med | high | 50000 | 66795 | 63739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 15000 | 25000 | 5000 | 0 | 50000 | 318.952 | CAPITAL | Yes | Unit outage |  |  | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 4 | 3 | 2 | 4 | 1 | 3 | 5 | 5 | 2 | 64.44% | 7 | 5 | 1 | 1 | 4 | 2 | 1 | 46.67% | 5 |  | 25393.37
107 | L1 | FACILITY | MECHANICAL |  | SILENCER | Calgary | 2026-12-31 | 2026 | 157 | 0 | 2026-07-27 | med | med | med | high | low | 185000 | 123781 | 120636 | 0 | 0 | 0 | 18500 | 74000 | 74000 | 18500 | 0 | 0 | 0 | 0 | 0 | 185000 | 1019.9258 | EXPENSE | Yes | no |  | X | X |  |  | no | no | Yes | no | no | no | Yes | no | Yes | 3 | 2 | 2 | 1 | 4 | 2 | 5 | 4 | 2 | 55.56% | 6 | 5 | 5 | 1 | 4 | 3 | 4 | 73.33% | 8 |  | 121.8769
107 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2025-12-31 | 2025 | 250 | 4 | 2025-04-25 | low | low | med | high | high | 450000 | 743098 | 791931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 450000 | 94.2513 | CAPITAL | Yes | Pipeline segment |  |  | X |  | X | Yes | no | no | Yes | Yes | Yes | Yes | Yes | no | 5 | 1 | 1 | 2 | 2 | 3 | 1 | 4 | 3 | 48.89% | 5 | 1 | 4 | 1 | 4 | 4 | 4 | 60% | 6 |  | 4487
108 | L1 | FACILITY | MEASUREMENT |  | GALVNIC 902 | Calgary | 2026-12-31 | 2026 | 15 | 2 | 2026-12-16 | high | med | high | low | low | 500000 | 585820 | 624457 | 0 | 0 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 500000 | 112.7741 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | Yes | no | Yes | no | no | no | Yes | Yes | no | 4 | 1 | 3 | 1 | 3 | 4 | 2 | 2 | 5 | 55.56% | 6 | 3 | 2 | 1 | 4 | 5 | 4 | 63.33% | 7 |  | 5097.2605
108 | L1 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Toronto | 2025-12-31 | 2025 | 200 | 8 | 2025-06-14 | med | high | high | med | high | 1000000 | 1821878 | 1824096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 400000 | 500000 | 0 | 0 | 1000000 | 99.9422 | EXPENSE | Yes | NO outage |  | X | X | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | Yes | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 33.33% | 4 | 1 | 3 | 1 | 4 | 2 | 1 | 40% | 4 |  | 211.3988
109 | L1 | FACILITY | MECHANICAL |  | SILENCER | Edmonton | 2026-12-31 | 2026 | 282 | 3 | 2026-03-24 | high | med | high | low | high | 185000 | 196584 | 210005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | 74000 | 92500 | 0 | 0 | 185000 | 57.8961 | CAPITAL | Yes | Unit outage | X |  | X |  | X | Yes | no | no | Yes | Yes | Yes | no | no | Yes | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 33.33% | 4 | 4 | 5 | 1 | 3 | 2 | 4 | 63.33% | 7 |  | 560.1412
109 | L1 | FACILITY | MEASUREMENT |  | METER | Montreal | 2025-07-31 | 2025 | 24 | 2 | 2025-07-07 | low | high | high | high | high | 500000 | 507208 | 516812 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 500000 | 7.2213 | CAPITAL | No | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 5 | 4 | 3 | 2 | 4 | 5 | 4 | 2 | 4 | 73.33% | 8 | 4 | 2 | 1 | 3 | 2 | 2 | 46.67% | 5 |  | 477.3811
110 | L3 | FACILITY | CIVIL |  | REPAIR- ROOFING | Ottawa | 2025-03-31 | 2025 | 251 | 2 | 2024-07-23 | med | med | high | med | high | 480000 | 516685 | 485455 | 0 | 144000 | 288000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | 33.6052 | EXPENSE | Yes | Station outage | X |  |  | X | X | Yes | Yes | Yes | no | Yes | no | no | Yes | Yes | 4 | 1 | 2 | 5 | 5 | 4 | 2 | 1 | 1 | 55.56% | 6 | 1 | 5 | 5 | 4 | 4 | 2 | 70% | 7 |  | 5347.325
111 | L1 | FACILITY | SCADA |  | REPAIR | Edmonton | 2026-12-31 | 2026 | 69 | 1 | 2026-10-23 | high | high | high | med | high | 233665 | 331213 | 297607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23366.5 | 93466 | 116832.5 | 0 | 233665 | 41.7722 | EXPENSE | Yes | Station outage |  |  |  | X |  | Yes | no | no | no | Yes | no | no | Yes | no | 2 | 5 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 53.33% | 6 | 4 | 4 | 5 | 5 | 3 | 2 | 76.67% | 8 |  | 4542.743
112 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | low | high | low | med | low | 350000 | 669911 | 695057 | 0 | 105000 | 0 | 105000 | 70000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 54.5821 | EXPENSE | No | Pipeline segment | X |  |  |  | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 5 | 5 | 1 | 5 | 1 | 5 | 1 | 2 | 4 | 64.44% | 7 | 3 | 4 | 5 | 1 | 3 | 3 | 63.33% | 7 |  | 1486.7011
113 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | med | high | high | low | med | 350000 | 344031 | 340632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 350000 | 122.8607 | CAPITAL | No | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | no | Yes | no | Yes | Yes | 2 | 2 | 1 | 3 | 1 | 2 | 5 | 1 | 4 | 46.67% | 5 | 3 | 4 | 1 | 1 | 1 | 5 | 50% | 5 |  | 2679.5194
114 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | med | med | low | high | med | 350000 | 339702 | 391874 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 350000 | 109.8564 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | no | no | no | no | no | no | no | Yes | Yes | 4 | 4 | 5 | 2 | 5 | 3 | 5 | 3 | 3 | 75.56% | 8 | 5 | 4 | 5 | 2 | 1 | 4 | 70% | 7 |  | 2679.5194
115 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Toronto | 2026-07-31 | 2026 | 207 | 8 | 2026-01-05 | high | low | high | low | high | 550000 | 661009 | 682588 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 111.3269 | EXPENSE | Yes | Pipeline segment | X |  | X | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 1 | 1 | 2 | 1 | 3 | 2 | 4 | 3 | 3 | 44.44% | 5 | 5 | 4 | 5 | 4 | 2 | 1 | 70% | 7 |  | 1072.7658
116 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Saskatoon | 2027-12-31 | 2027 | 144 | 8 | 2027-08-09 | high | high | high | low | low | 550000 | 623179 | 603094 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 59.7386 | EXPENSE | No | Pipeline segment |  | X |  | X | X | Yes | no | no | no | no | no | no | no | Yes | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 33.33% | 4 | 3 | 2 | 1 | 1 | 2 | 2 | 36.67% | 4 |  | 3333.1342
117 | L3 | FACILITY | SCADA |  | REPAIR | Edmonton | 2025-10-31 | 2025 | 279 | 2 | 2025-01-25 | med | high | high | med | med | 1485000 | 1410317 | 1385913 | 148500 | 594000 | 742500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000 | 132.6576 | CAPITAL | No | Station outage |  |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | no | 4 | 3 | 1 | 2 | 5 | 3 | 2 | 1 | 4 | 55.56% | 6 | 3 | 4 | 1 | 3 | 3 | 5 | 63.33% | 7 |  | 1117.2047
118 | L1 | FACILITY | SCADA |  | REPAIR | Regina | 2028-03-31 | 2028 | 141 | 1 | 2027-11-11 | low | low | med | low | med | 78215 | 790617 | 78706 | 0 | 0 | 0 | 39107.5 | 39107.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78215 | 76.5462 | EXPENSE | Yes | plant outage |  |  | X | X |  | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 5 | 5 | 4 | 3 | 4 | 4 | 1 | 2 | 3 | 68.89% | 7 | 3 | 1 | 1 | 2 | 3 | 1 | 36.67% | 4 |  | 842.9817
118 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Montreal | 2025-07-31 | 2025 | 170 | 8 | 2025-02-11 | low | med | low | low | high | 550000 | 590681 | 591056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 275000 | 110000 | 0 | 0 | 550000 | 280 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | Yes | 3 | 1 | 3 | 2 | 4 | 4 | 4 | 3 | 4 | 62.22% | 7 | 5 | 2 | 1 | 2 | 1 | 3 | 46.67% | 5 |  | 1117.2047
119 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Calgary | 2025-12-31 | 2025 | 118 | 7 | 2025-09-04 | high | med | low | med | med | 1032128 | 1501619 | 1608733 | 0 | 103212.8 | 0 | 0 | 0 | 0 | 103212.8 | 825702.4 | 0 | 0 | 0 | 0 | 1032128 | 58.9784 | EXPENSE | Yes | Unit outage | X |  |  | X |  | no | no | Yes | no | Yes | no | Yes | Yes | Yes | 3 | 4 | 3 | 2 | 5 | 3 | 2 | 5 | 1 | 62.22% | 7 | 4 | 4 | 1 | 1 | 4 | 5 | 63.33% | 7 |  | 45.3112
120 | L1 | FACILITY | SCADA |  | REPAIR | Edmonton | 2027-12-31 | 2027 | 69 | 2 | 2027-10-23 | high | high | high | med | high | 233665 | 331213 | 297607 | 23366.5 | 93466 | 116832.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233665 | 41.7722 | EXPENSE | Yes | Station outage |  |  |  | X |  | Yes | no | no | no | Yes | no | no | Yes | no | 2 | 5 | 2 | 1 | 4 | 2 | 3 | 2 | 1 | 48.89% | 5 | 2 | 2 | 5 | 1 | 3 | 1 | 46.67% | 5 |  | 842.9817
120 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2026-10-31 | 2026 | 100 | 5 | 2026-07-23 | high | low | low | high | low | 400000 | 391992 | 396981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 160000 | 200000 | 0 | 400000 | 279.7384 | EXPENSE | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 4 | 5 | 5 | 2 | 3 | 3 | 1 | 4 | 3 | 66.67% | 7 | 3 | 3 | 1 | 1 | 1 | 1 | 33.33% | 4 |  | 1300.7103
121 | L3 | FACILITY | SCADA |  | REPAIR | Saskatoon | 2029-10-31 | 2029 | 60 | 1 | 2029-09-01 | low | low | high | high | low | 302123 | 363184 | 376832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30212.3 | 120849.2 | 120849.2 | 30212.3 | 302123 | 25.1853 | EXPENSE | Yes | Unit outage | X | X |  | X |  | no | Yes | Yes | no | Yes | no | no | Yes | no | 4 | 3 | 4 | 4 | 2 | 3 | 1 | 3 | 3 | 60% | 6 | 3 | 4 | 5 | 5 | 1 | 4 | 73.33% | 8 |  | 4487
121 | L3 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Edmonton | 2028-12-31 | 2028 | 258 | 3 | 2028-04-17 | high | low | med | low | high | 450000 | 557154 | 582280 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 450000 | 124.1453 | CAPITAL | No | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | no | no | no | Yes | Yes | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 28.89% | 3 | 4 | 3 | 1 | 5 | 5 | 1 | 63.33% | 7 |  | 263.7275
122 | L3 | FACILITY | CIVIL |  | REPAIR - ROOFING | Ottawa | 2027-03-31 | 2027 | 251 | 2 | 2026-07-23 | med | med | high | med | high | 480000 | 516685 | 560955 | 0 | 0 | 0 | 0 | 48000 | 192000 | 240000 | 0 | 0 | 0 | 0 | 0 | 480000 | 33.6052 | EXPENSE | Yes | NO | X |  |  | X | X | Yes | Yes | Yes | no | Yes | no | no | Yes | Yes | 5 | 4 | 2 | 3 | 3 | 5 | 5 | 4 | 5 | 80% | 8 | 5 | 2 | 5 | 3 | 1 | 3 | 63.33% | 7 |  | 842.9817
122 | L1 | FACILITY | AUTOMATION & CONTROLS |  | UNIT CONTROLS OBS | Edmonton | 2025-12-31 | 2025 | 279 | 5 | 2025-03-27 | high | med | med | high | med | 1625081 | 1659514 | 1659910 | 0 | 0 | 0 | 0 | 0 | 0 | 162508.1 | 650032.4 | 812540.5 | 0 | 0 | 0 | 1625081 | 227.1562 | CAPITAL | No | Station outage | X | X | X |  | X | Yes | no | no | no | Yes | no | no | no | Yes | 1 | 4 | 1 | 1 | 1 | 4 | 5 | 2 | 3 | 48.89% | 5 | 3 | 5 | 1 | 4 | 4 | 4 | 70% | 7 |  | 18394.3019
123 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2028-10-31 | 2028 | 153 | 2 | 2028-05-31 | med | low | high | high | med | 500000 | 550475 | 595557 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 0 | 0 | 0 | 0 | 500000 | 117.2576 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 4 | 1 | 5 | 3 | 1 | 2 | 5 | 3 | 4 | 62.22% | 7 | 5 | 4 | 5 | 5 | 3 | 2 | 80% | 8 |  | 14995.8254
124 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2027-10-31 | 2027 | 122 | 5 | 2027-07-01 | med | low | med | low | low | 350000 | 340105 | 340380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 350000 | 81.2986 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | no | no | 3 | 4 | 4 | 5 | 1 | 2 | 3 | 3 | 1 | 57.78% | 6 | 1 | 1 | 5 | 4 | 2 | 3 | 53.33% | 6 |  | 76225.6763
125 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2025-12-31 | 2025 | 200 | 5 | 2025-06-14 | med | high | high | high | high | 500000 | 724601 | 722346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 0 | 0 | 500000 | 98.531 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | no | no | no | Yes | 4 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 53.33% | 6 | 3 | 5 | 5 | 1 | 5 | 2 | 70% | 7 |  | 16.9273
126 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | low | high | med | med | low | 350000 | 332474 | 335000 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 350000 | 37.7222 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | Yes | 5 | 3 | 5 | 2 | 5 | 2 | 4 | 1 | 2 | 64.44% | 7 | 2 | 2 | 1 | 4 | 3 | 5 | 56.67% | 6 |  | 16.9273
127 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2025-12-31 | 2025 | 190 | 15 | 2025-06-24 | low | med | low | low | low | 350000 | 499124 | 498275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 350000 | 77.5311 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | no | Yes | no | Yes | 3 | 3 | 5 | 3 | 4 | 5 | 2 | 2 | 5 | 71.11% | 8 | 5 | 3 | 1 | 1 | 2 | 2 | 46.67% | 5 |  | 560.1412
128 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2025-07-31 | 2025 | 200 | 4 | 2025-01-12 | med | low | high | low | high | 400000 | 350785 | 393433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 160000 | 200000 | 400000 | 109.3207 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 3 | 1 | 3 | 2 | 2 | 1 | 5 | 1 | 4 | 48.89% | 5 | 5 | 4 | 1 | 4 | 1 | 4 | 63.33% | 7 |  | 560.1412
129 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | Calgary | 2025-10-31 | 2025 | 120 | 1 | 2025-07-03 | high | high | high | med | med | 190000 | 173510 | 142860 | 0 | 0 | 0 | 0 | 0 | 19000 | 76000 | 95000 | 0 | 0 | 0 | 0 | 190000 | 670.6684 | EXPENSE | No | NO | X |  | X |  |  | Yes | no | Yes | no | Yes | Yes | no | no | Yes | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 4 | 37.78% | 4 | 4 | 2 | 1 | 2 | 2 | 3 | 46.67% | 5 |  | 10535.7532
130 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | WINNIPEG | 2025-12-31 | 2025 | 134 | 8 | 2025-08-19 | high | high | high | low | med | 350000 | 522998 | 520888 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 350000 | 74.8121 | CAPITAL | No | Pipeline segment | X | X |  | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 2 | 2 | 3 | 5 | 4 | 2 | 1 | 3 | 55.56% | 6 | 4 | 4 | 1 | 3 | 5 | 5 | 73.33% | 8 |  | 16059.7772
131 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Winnipeg | 2025-03-31 | 2025 | 163 | 12 | 2024-10-19 | high | low | high | med | high | 3691558 | 3641880 | 3680790 | 0 | 0 | 0 | 0 | 0 | 369155.8 | 1476623.2 | 1845779 | 0 | 0 | 0 | 0 | 3691558 | 87.54 | EXPENSE | Yes | Unit outage | [5 empty] | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 5 | 2 | 5 | 2 | 1 | 5 | 5 | 5 | 1 | 68.89% | 7 | 1 | 3 | 1 | 5 | 3 | 2 | 50% | 5 |  | 10182.1737
132 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2027-03-31 | 2027 | 180 | 8 | 2026-10-02 | high | med | med | med | high | 350000 | 411473 | 413108 | 35000 | 140000 | 140000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 142.0502 | CAPITAL | No | Pipeline segment | X | X | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 1 | 1 | 1 | 1 | 5 | 4 | 5 | 1 | 1 | 44.44% | 5 | 1 | 1 | 1 | 1 | 1 | 2 | 23.33% | 3 |  | 2310.5725
133 | L2 | FACILITY | ELECTRICAL |  | UPS | Toronto | 2025-10-31 | 2025 | 278 | 2 | 2025-01-26 | low | high | med | med | high | 330000 | 298120 | 287115 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 92.8794 | EXPENSE | No | Unit outage | X |  | X |  |  | Yes | Yes | no | no | Yes | no | no | no | Yes | 4 | 2 | 1 | 2 | 3 | 4 | 2 | 1 | 5 | 53.33% | 6 | 4 | 4 | 1 | 2 | 5 | 5 | 70% | 7 |  | 2369.8282
134 | L3 | FACILITY | MEASUREMENT |  | RTU REPLACMENT | Winnipeg | 2025-07-31 | 2025 | 60 | 3 | 2025-06-01 | low | low | low | med | low | 500000 | 498050 | 493468 | 50000 | 200000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 25.2562 | CAPITAL | Yes | Derate/low flow Pipe segment |  | X | X | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 5 | 44.44% | 5 | 1 | 3 | 1 | 4 | 3 | 3 | 50% | 5 |  | 2491.953
135 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2025-03-31 | 2025 | 169 | 4 | 2024-10-13 | low | high | high | low | high | 4185667 | 4675386 | 4686248 | 0 | 0 | 0 | 0 | 0 | 4185667 | 0 | 0 | 0 | 0 | 0 | 0 | 4185667 | 7.2742 | CAPITAL | Yes | Unit outage |  | X | X | X |  | no | no | no | Yes | no | Yes | Yes | no | Yes | 4 | 3 | 3 | 5 | 1 | 3 | 4 | 2 | 3 | 62.22% | 7 | 2 | 5 | 5 | 3 | 4 | 1 | 66.67% | 7 |  | 16593.6851
136 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2026-07-31 | 2026 | 180 | 8 | 2026-02-01 | med | med | low | med | low | 350000 | 466242 | 460097 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 82.7364 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 5 | 1 | 1 | 4 | 3 | 3 | 3 | 3 | 2 | 55.56% | 6 | 1 | 3 | 1 | 3 | 5 | 4 | 56.67% | 6 |  | 2480.6254
137 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2025-12-31 | 2025 | 187 | 7 | 2025-06-27 | low | med | med | low | high | 450000 | 531429 | 533699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 450000 | 69.7306 | CAPITAL | No | Pipeline segment | X | X |  | X | X | Yes | Yes | Yes | no | Yes | Yes | Yes | no | no | 4 | 4 | 2 | 2 | 5 | 3 | 2 | 5 | 3 | 66.67% | 7 | 4 | 4 | 1 | 1 | 5 | 2 | 56.67% | 6 |  | 2480.6254
138 | L1 | FACILITY | MECHANICAL |  | INSPECTION | Calgary | 2025-12-31 | 2025 | 157 | 0 | 2025-07-27 | med | med | med | high | low | 90265 | 123781 | 120636 | 0 | 0 | 0 | 0 | 90265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90265 | 1019.9258 | EXPENSE | Yes | no |  | X | X |  |  | no | no | Yes | no | no | no | Yes | no | Yes | 3 | 1 | 4 | 5 | 5 | 1 | 1 | 5 | 2 | 60% | 6 | 1 | 5 | 5 | 4 | 1 | 4 | 66.67% | 7 |  | 31873.2921
139 | L1 | FACILITY | AUTOMATION & CONTROLS |  | HMI | Ottawa | 2025-12-31 | 2025 | 313 | 5 | 2025-02-21 | med | low | low | high | high | 160778 | 130462 | 158048 | 0 | 0 | 0 | 0 | 0 | 0 | 16077.8 | 64311.2 | 80389 | 0 | 0 | 0 | 160778 | 675.1875 | CAPITAL | No | Station outage |  |  | X |  |  | Yes | Yes | Yes | no | no | no | no | no | Yes | 4 | 2 | 5 | 2 | 3 | 3 | 3 | 4 | 1 | 60% | 6 | 1 | 3 | 1 | 1 | 3 | 2 | 36.67% | 4 |  | 728.1385
140 | L1 | FACILITY | MECHANICAL |  | INSPECTION | Quebec City | 2025-12-31 | 2025 | 277 | 3 | 2025-03-29 | low | high | med | high | med | 80000 | 125864 | 126584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 32000 | 40000 | 0 | 80000 | 2112.101 | EXPENSE | No | Unit outage |  |  | X | X | X | no | Yes | no | no | no | Yes | Yes | Yes | Yes | 1 | 3 | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 35.56% | 4 | 4 | 5 | 5 | 5 | 1 | 4 | 80% | 8 |  | 1117.205
140 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Ottawa | 2025-12-31 | 2025 | 260 | 8 | 2025-04-15 | low | med | low | high | high | 450000 | 465673 | 462884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 450000 | 110.153 | CAPITAL | No | Pipeline segment | X | X | X |  | X | no | no | Yes | Yes | Yes | no | no | no | no | 5 | 5 | 1 | 4 | 5 | 5 | 4 | 4 | 4 | 82.22% | 9 | 3 | 1 | 1 | 4 | 3 | 3 | 50% | 5 |  | 495.1227
141 | L1 | FACILITY | MECHANICAL |  | INSPECTION | Ottawa | 2026-12-31 | 2026 | 28 | 3 | 2026-12-03 | med | med | med | med | high | 115534 | 130783 | 138219 | 0 | 0 | 0 | 0 | 115534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115534 | 7.203 | EXPENSE | No | Pipeline segment |  | X |  | X | X | no | Yes | Yes | no | Yes | no | Yes | Yes | Yes | 5 | 4 | 1 | 5 | 3 | 2 | 3 | 1 | 3 | 60% | 6 | 2 | 3 | 1 | 5 | 4 | 3 | 60% | 6 |  | 778.6578
141 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Toronto | 2025-12-31 | 2025 | 58 | 4 | 2025-11-03 | med | low | high | med | low | 732345 | 820669 | 850502 | 0 | 0 | 0 | 0 | 73234.5 | 292938 | 366172.5 | 0 | 0 | 0 | 0 | 0 | 732345 | 252.6817 | EXPENSE | Yes | Unit outage | [5 empty] | no | no | no | Yes | no | Yes | Yes | Yes | Yes | 1 | 5 | 2 | 2 | 3 | 1 | 2 | 3 | 3 | 48.89% | 5 | 2 | 3 | 1 | 4 | 5 | 5 | 66.67% | 7 |  | 5521.3731
142 | L3 | PIPE INTEGRITY | ILI | CORROSION | INSPECTION RUN | Edmonton | 2026-12-31 | 2026 | 75 | 4 | 2026-10-17 | med | med | med | low | low | 2450000 | 2254742 | 2248761 | 0 | 245000 | 245000 | 0 | 1960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450000 | 57.9714 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 1 | 4 | 1 | 1 | 4 | 5 | 1 | 1 | 4 | 48.89% | 5 | 5 | 5 | 1 | 5 | 2 | 5 | 76.67% | 8 |  | 1174.9707
142 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Winnipeg | 2025-12-31 | 2025 | 120 | 8 | 2025-09-02 | low | med | med | med | low | 450000 | 400384 | 400364 | 0 | 0 | 90000 | 0 | 0 | 45000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 450000 | 36.7014 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 4 | 5 | 1 | 4 | 2 | 1 | 1 | 1 | 5 | 53.33% | 6 | 4 | 3 | 1 | 1 | 5 | 3 | 56.67% | 6 |  | 3220.812
143 | L1 | FACILITY | MAJOR EQUIP |  | INSPECTION RUN | Quebec City | 2026-07-31 | 2026 | 164 | 4 | 2026-02-17 | high | med | high | med | low | 2772163 | 2866364 | 2829718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277216.3 | 1108865.2 | 1386081.5 | 2772163 | 24.2482 | EXPENSE | Yes | Unit outage |  | X | X | X |  | no | Yes | Yes | no | no | Yes | Yes | Yes | no | 4 | 5 | 3 | 1 | 4 | 5 | 1 | 1 | 2 | 57.78% | 6 | 4 | 4 | 1 | 3 | 4 | 1 | 56.67% | 6 |  | 241.5599
143 | L1 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Regina | 2025-03-31 | 2025 | 285 | 3 | 2024-06-19 | low | low | med | low | low | 600000 | 620865 | 695427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 240000 | 300000 | 600000 | 2608.6464 | CAPITAL | Yes | Derate/low flow Pipe segment | X |  | X | X |  | no | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 3 | 2 | 3 | 2 | 4 | 5 | 4 | 1 | 2 | 57.78% | 6 | 2 | 5 | 5 | 2 | 4 | 2 | 66.67% | 7 |  | 6039.0018
144 | L3 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Saskatoon | 2025-10-31 | 2025 | 240 | 4 | 2025-03-05 | low | high | high | high | med | 1982860 | 1977099 | 1931924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198286 | 793144 | 991430 | 1982860 | 41.9558 | CAPITAL | Yes | Unit outage | X |  | X | X |  | no | no | no | no | no | no | no | no | Yes | 5 | 5 | 5 | 4 | 5 | 1 | 5 | 3 | 3 | 80% | 8 | 3 | 2 | 1 | 4 | 3 | 4 | 56.67% | 6 |  | 13659.1884
145 | L1 | FACILITY | ELECTRICAL |  | MCC | North Bay | 2026-07-31 | 2026 | 235 | 1 | 2025-12-08 | med | med | high | med | high | 750000 | 736911 | 779627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 300000 | 375000 | 750000 | 41.4867 | EXPENSE | Yes | Station outage |  | X |  |  |  | Yes | no | Yes | no | no | Yes | Yes | Yes | no | 4 | 3 | 5 | 4 | 2 | 5 | 3 | 2 | 3 | 68.89% | 7 | 3 | 3 | 1 | 3 | 1 | 1 | 40% | 4 |  | 13659.1884
146 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Winnipeg | 2026-03-31 | 2026 | 100 | 5 | 2025-12-21 | high | low | low | med | low | 400000 | 424413 | 424247 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 400000 | 13.6895 | CAPITAL | No | Pipeline segment | X | X |  | X | X | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 5 | 1 | 5 | 3 | 4 | 2 | 4 | 1 | 4 | 64.44% | 7 | 5 | 3 | 1 | 5 | 2 | 5 | 70% | 7 |  | 17906.9371
147 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2025-03-31 | 2025 | 80 | 4 | 2025-01-10 | med | low | high | low | med | 400000 | 487955 | 487622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 81.7758 | EXPENSE | No | Pipeline segment | X | X | X |  |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 3 | 5 | 5 | 4 | 2 | 3 | 3 | 1 | 2 | 62.22% | 7 | 2 | 3 | 1 | 4 | 1 | 2 | 43.33% | 5 |  | 21537.8368
148 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Saskatoon | 2026-07-31 | 2026 | 120 | 15 | 2026-04-02 | med | low | high | high | high | 450000 | 994397 | 956898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 450000 | 61.6448 | CAPITAL | Yes | Pipeline segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | no | Yes | Yes | 2 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 5 | 51.11% | 6 | 4 | 2 | 1 | 5 | 3 | 2 | 56.67% | 6 |  | 2973.4021
149 | L2 | FACILITY | MEASUREMENT |  | CALIBRATION | Quebec City | 2025-12-31 | 2025 | 152 | 3 | 2025-08-01 | high | high | med | high | med | 200000 | 241162 | 217137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 100000 | 40000 | 0 | 0 | 200000 | 108.4626 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  | X | X | no | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | 4 | 1 | 2 | 1 | 2 | 4 | 4 | 4 | 5 | 60% | 6 | 3 | 1 | 1 | 1 | 4 | 4 | 46.67% | 5 |  | 19639.8665
150 | L1 | FACILITY | MAJOR EQUIP |  | MINOR OH | Quebec City | 2025-12-31 | 2025 | 222 | 7 | 2025-05-23 | med | med | med | high | med | 1540000 | 1677575 | 1687601 | 308000 | 1078000 | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540000 | 63.4775 | CAPITAL | Yes | Unit outage | X |  | X |  | X | no | Yes | Yes | no | no | no | Yes | no | no | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22.22% | 3 | 5 | 3 | 1 | 5 | 1 | 3 | 60% | 6 |  | 5776.4313
151 | L3 | FACILITY | ELECTRICAL |  | UPS | Quebec City | 2026-12-31 | 2026 | 79 | 2 | 2026-10-13 | high | low | low | low | low | 330000 | 354236 | 386497 | 0 | 0 | 0 | 33000 | 132000 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | 198.3414 | EXPENSE | Yes | Unit outage |  |  | X |  | X | Yes | no | no | no | Yes | Yes | no | Yes | Yes | 2 | 2 | 3 | 1 | 5 | 4 | 1 | 1 | 1 | 44.44% | 5 | 3 | 3 | 1 | 2 | 5 | 2 | 53.33% | 6 |  | 2166.5828
152 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | North Bay | 2025-10-31 | 2025 | 250 | 8 | 2025-02-23 | low | med | med | med | low | 450000 | 495726 | 469706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 450000 | 19.694 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 2 | 4 | 2 | 2 | 3 | 1 | 5 | 1 | 4 | 53.33% | 6 | 5 | 1 | 1 | 1 | 1 | 5 | 46.67% | 5 |  | 6487.5816
153 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2025-10-31 | 2025 | 287 | 7 | 2025-01-17 | low | med | high | high | low | 1800000 | 2095522 | 2095724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 720000 | 900000 | 0 | 0 | 1800000 | 35.0188 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | no | no | no | 3 | 3 | 2 | 2 | 2 | 1 | 5 | 4 | 4 | 57.78% | 6 | 5 | 4 | 1 | 4 | 5 | 4 | 76.67% | 8 |  | 1083.35
154 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2027-12-31 | 2025 | 216 | 7 | 2027-05-29 | low | low | med | low | med | 2100000 | 2089588 | 2100050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 840000 | 1050000 | 0 | 0 | 2100000 | 1745.308 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | Yes | no | no | no | no | no | Yes | 5 | 3 | 4 | 5 | 2 | 3 | 5 | 1 | 1 | 64.44% | 7 | 4 | 3 | 1 | 4 | 1 | 3 | 53.33% | 6 |  | 1184.9141
155 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Winnipeg | 2025-12-31 | 2025 | 100 | 4 | 2025-09-22 | high | high | high | high | med | 400000 | 453423 | 450247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 160000 | 200000 | 400000 | 167.1303 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 5 | 2 | 5 | 1 | 4 | 3 | 5 | 1 | 64.44% | 7 | 5 | 2 | 1 | 4 | 2 | 3 | 56.67% | 6 |  | 1846.6194
156 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Ottawa | 2025-10-31 | 2025 | 250 | 8 | 2025-02-23 | high | high | low | low | low | 450000 | 434113 | 437206 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 0 | 450000 | 51.5723 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 4 | 5 | 2 | 2 | 3 | 3 | 5 | 3 | 3 | 66.67% | 7 | 2 | 4 | 1 | 5 | 4 | 4 | 66.67% | 7 |  | 1846.6194
157 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Calgary | 2025-10-31 | 2025 | 180 | 8 | 2025-05-04 | low | low | med | med | high | 450000 | 510412 | 516874 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 450000 | 19.5924 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | no | no | no | no | no | no | Yes | 4 | 2 | 4 | 2 | 5 | 1 | 2 | 3 | 1 | 53.33% | 6 | 4 | 4 | 1 | 1 | 2 | 5 | 56.67% | 6 |  | 9580.8769
158 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | high | med | low | high | low | 400000 | 827809 | 927128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 160000 | 200000 | 0 | 0 | 400000 | 245.1045 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | no | no | 4 | 3 | 3 | 5 | 4 | 4 | 4 | 1 | 3 | 68.89% | 7 | 2 | 5 | 1 | 3 | 2 | 5 | 60% | 6 |  | 8429.71
159 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Saskatoon | 2026-07-31 | 2026 | 125 | 8 | 2026-03-28 | high | high | low | med | med | 650000 | 808987 | 803329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 260000 | 325000 | 0 | 650000 | 57.38 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 2 | 2 | 5 | 3 | 3 | 4 | 2 | 3 | 60% | 6 | 1 | 1 | 1 | 3 | 1 | 5 | 40% | 4 |  | 425
160 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Saskatoon | 2026-10-31 | 2026 | 180 | 8 | 2026-05-04 | low | med | med | high | low | 450000 | 857877 | 866522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 450000 | 121.3811 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | no | no | Yes | no | no | Yes | no | no | Yes | 5 | 4 | 3 | 3 | 4 | 5 | 5 | 5 | 4 | 84.44% | 9 | 1 | 3 | 1 | 3 | 3 | 3 | 46.67% | 5 |  | 5875
161 | L1 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Regina | 2025-07-31 | 2025 | 282 | 7 | 2024-10-22 | high | low | med | med | med | 450000 | 428727 | 466800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 450000 | 526.2579 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 4 | 2 | 4 | 1 | 1 | 5 | 5 | 5 | 5 | 71.11% | 8 | 4 | 1 | 1 | 5 | 4 | 1 | 53.33% | 6 |  | 48755
162 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | North Bay | 2025-07-31 | 2025 | 157 | 4 | 2025-02-24 | low | low | med | high | med | 2481256 | 2167672 | 2503476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248125.6 | 992502.4 | 1240628 | 2481256 | 33.9898 | CAPITAL | Yes | Unit outage |  | X | X | X | X | Yes | no | Yes | no | Yes | no | Yes | no | Yes | 4 | 1 | 1 | 3 | 2 | 5 | 2 | 1 | 5 | 53.33% | 6 | 4 | 4 | 1 | 4 | 4 | 4 | 70% | 7 |  | 25777
163 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2026-07-31 | 2026 | 100 | 8 | 2026-04-22 | low | med | med | high | med | 350000 | 374581 | 382853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 350000 | 166.8084 | CAPITAL | Yes | Pipeline segment |  | X |  | X |  | no | no | no | Yes | Yes | Yes | no | no | no | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 5 | 4 | 1 | 3 | 5 | 3 | 70% | 7 |  | 5522
164 | L1 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Edmonton | 2028-12-31 | 2028 | 200 | 8 | 2028-06-14 | low | high | high | low | high | 750000 | 861410 | 860656 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 750000 | 15.3529 | EXPENSE | No | NO outage |  | X | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | no | 5 | 5 | 2 | 5 | 4 | 5 | 4 | 3 | 4 | 82.22% | 9 | 5 | 5 | 5 | 1 | 3 | 5 | 80% | 8 |  | 4101.0339
165 | L2 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Regina | 2025-07-31 | 2025 | 93 | 4 | 2025-04-29 | high | high | high | high | low | 1800000 | 1807733 | 1857547 | 0 | 180000 | 720000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 102.2668 | EXPENSE | No | Pipeline segment | X |  | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 4 | 44.44% | 5 | 3 | 4 | 1 | 5 | 1 | 5 | 63.33% | 7 |  | 22170.3266
166 | L3 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Ottawa | 2025-07-31 | 2025 | 339 | 7 | 2024-08-26 | med | low | high | low | low | 785672 | 787730 | 801700 | 0 | 0 | 0 | 0 | 0 | 0 | 78567.2 | 628537.6 | 78567.2 | 0 | 0 | 0 | 785672 | 210.2277 | EXPENSE | Yes | Unit outage | X |  |  |  | X | Yes | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 3 | 3 | 3 | 4 | 1 | 2 | 1 | 5 | 3 | 55.56% | 6 | 4 | 2 | 1 | 5 | 1 | 5 | 60% | 6 |  | 842.9817
167 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | WINNIPEG | 2025-10-31 | 2025 | 289 | 7 | 2025-01-15 | med | med | high | low | low | 1807464 | 1640026 | 1584985 | 0 | 0 | 0 | 0 | 180746.4 | 722985.6 | 903732 | 0 | 0 | 0 | 0 | 0 | 1807464 | 163.8288 | CAPITAL | Yes | Unit outage |  |  | X | X |  | Yes | no | Yes | no | no | no | Yes | Yes | no | 2 | 3 | 1 | 3 | 2 | 5 | 3 | 1 | 4 | 53.33% | 6 | 5 | 4 | 1 | 1 | 1 | 1 | 43.33% | 5 |  | 842.9817
169 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2026-07-31 | 2026 | 150 | 7 | 2026-03-03 | high | low | high | low | high | 400000 | 555442 | 55668 | 0 | 520337.6 | 520337.6 | 130084.4 | 1300844 | 130084.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2601688 | 71.2228 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | no | Yes | Yes | Yes | no | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 4 | 35.56% | 4 | 5 | 2 | 1 | 3 | 3 | 1 | 50% | 5 |  | 1727.2647
170 | L3 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Saskatoon | 2025-03-31 | 2025 | 255 | 2 | 2024-07-19 | med | high | high | low | med | 255000 | 299343 | 290897 | 0 | 0 | 0 | 0 | 25500 | 102000 | 127500 | 0 | 0 | 0 | 0 | 0 | 255000 | 627.0632 | EXPENSE | Yes | Unit outage | X |  |  | X |  | Yes | no | no | no | Yes | no | no | Yes | no | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 4 | 2 | 1 | 1 | 5 | 5 | 60% | 6 |  | 2588
171 | L3 | FACILITY | MAJOR EQUIP |  | MINOR OH | North Bay | 2025-10-31 | 2025 | 205 | 8 | 2025-04-09 | low | low | low | med | med | 1556876 | 1569750 | 1524237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467062.8 | 934125.6 | 155687.6 | 0 | 0 | 1556876 | 163.9144 | CAPITAL | Yes | Unit outage |  | X | X |  | X | no | Yes | no | Yes | no | no | no | no | Yes | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 31.11% | 4 | 5 | 2 | 1 | 4 | 3 | 1 | 53.33% | 6 |  | 3506.8708
172 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Ottawa | 2026-07-31 | 2026 | 100 | 7 | 2026-04-22 | high | med | high | low | med | 450000 | 525700 | 525468 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 0 | 450000 | 53.7439 | CAPITAL | No | Pipeline segment | X |  |  |  |  | Yes | Yes | no | no | no | Yes | Yes | no | Yes | 1 | 3 | 1 | 2 | 3 | 5 | 5 | 1 | 5 | 57.78% | 6 | 2 | 2 | 1 | 5 | 2 | 5 | 56.67% | 6 |  | 18109.7232
173 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2025-07-31 | 2025 | 180 | 8 | 2025-02-01 | med | high | low | low | low | 350000 | 780645 | 788090 | 35000 | 140000 | 105000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 117.9206 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | no | 5 | 5 | 2 | 3 | 5 | 2 | 1 | 3 | 4 | 66.67% | 7 | 1 | 1 | 1 | 4 | 1 | 5 | 43.33% | 5 |  | 3981.0002
174 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2025-03-31 | 2025 | 150 | 8 | 2024-11-01 | high | high | low | high | low | 500000 | 685306 | 681669 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 0 | 0 | 0 | 0 | 0 | 500000 | 68.6381 | CAPITAL | Yes | Pipeline segment | X |  | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 5 | 48.89% | 5 | 1 | 2 | 1 | 2 | 1 | 2 | 30% | 3 |  | 20815.3255
175 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2025-12-31 | 2025 | 200 | 4 | 2025-06-14 | med | low | med | low | med | 500000 | 509915 | 513929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 0 | 0 | 500000 | 72.3249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | no | no | no | no | Yes | no | no | 2 | 5 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 42.22% | 5 | 2 | 2 | 1 | 5 | 5 | 4 | 63.33% | 7 |  | 48955
176 | L3 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Toronto | 2026-12-31 | 2026 | 63 | 4 | 2026-10-29 | low | high | low | med | high | 1034944 | 1055596 | 1050204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103494.4 | 413977.6 | 517472 | 0 | 0 | 1034944 | 19.5223 | EXPENSE | Yes | Unit outage | X |  |  |  | X | no | Yes | no | no | Yes | Yes | no | no | no | 5 | 1 | 4 | 4 | 5 | 3 | 3 | 5 | 4 | 75.56% | 8 | 3 | 1 | 1 | 3 | 3 | 2 | 43.33% | 5 |  | 278.7236
177 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Winnipeg | 2025-07-31 | 2025 | 180 | 8 | 2025-02-01 | high | high | low | low | low | 450000 | 806609 | 803956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 450000 | 84.9423 | CAPITAL | No | pipeline segment | X | X | X | X |  | no | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 5 | 3 | 4 | 4 | 1 | 4 | 3 | 4 | 68.89% | 7 | 4 | 2 | 1 | 1 | 3 | 1 | 40% | 4 |  | 278.7236
178 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2025-12-31 | 2025 | 156 | 4 | 2025-07-28 | low | high | low | low | med | 1186829 | 1367226 | 1320125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118682.9 | 474731.6 | 593414.5 | 0 | 0 | 1186829 | 111.2313 | CAPITAL | Yes | Unit outage |  |  | X | X | X | Yes | no | Yes | Yes | no | no | Yes | no | no | 4 | 4 | 1 | 1 | 3 | 1 | 4 | 4 | 3 | 55.56% | 6 | 5 | 2 | 1 | 1 | 1 | 5 | 50% | 5 |  | 278.7236
179 | L2 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Winnipeg | 2026-12-31 | 2026 | 257 | 7 | 2026-04-18 | med | low | high | high | low | 1500000 | 1506928 | 1495675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 600000 | 750000 | 1500000 | 33.796 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | Yes | no | no | Yes | no | no | Yes | no | no | 5 | 1 | 1 | 1 | 5 | 5 | 2 | 3 | 5 | 62.22% | 7 | 4 | 4 | 1 | 3 | 2 | 1 | 50% | 5 |  | 203.1281
181 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-REMEDITION | Calgary | 2026-12-31 | 2026 | 150 | 8 | 2026-08-03 | high | low | low | low | med | 850000 | 951968 | 9054634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 340000 | 425000 | 850000 | 41.9164 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | Yes | no | Yes | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 37.78% | 4 | 1 | 5 | 1 | 2 | 5 | 5 | 63.33% | 7 |  | 203.1281
182 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2025-12-31 | 2025 | 100 | 5 | 2025-09-22 | low | med | high | high | low | 350000 | 320570 | 315873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 350000 | 375.5287 | EXPENSE | No | Pipeline segment |  |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | Yes | 4 | 1 | 2 | 1 | 5 | 3 | 4 | 2 | 5 | 60% | 6 | 1 | 1 | 1 | 3 | 2 | 1 | 30% | 3 |  | 853.1382
183 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2025-07-31 | 2025 | 185 | 8 | 2025-01-27 | high | med | high | low | med | 350000 | 449452 | 496903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 350000 | 34.9002 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 2 | 4 | 2 | 1 | 4 | 3 | 3 | 2 | 1 | 48.89% | 5 | 5 | 4 | 5 | 2 | 2 | 3 | 70% | 7 |  | 23717.2367
184 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Regina | 2025-10-31 | 2025 | 250 | 8 | 2025-02-23 | med | med | low | low | low | 450000 | 424655 | 452754 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 450000 | 95.8703 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | no | no | Yes | no | no | no | no | Yes | 4 | 3 | 5 | 3 | 2 | 4 | 1 | 3 | 4 | 64.44% | 7 | 1 | 4 | 5 | 1 | 5 | 5 | 70% | 7 |  | 746.1723
185 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2025-10-31 | 2025 | 200 | 4 | 2025-04-14 | med | high | med | low | med | 350000 | 354302 | 387376 | 0 | 140000 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 71.1665 | EXPENSE | No | Pipeline segment |  | X |  |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | 3 | 2 | 1 | 5 | 3 | 4 | 3 | 5 | 5 | 68.89% | 7 | 4 | 5 | 5 | 1 | 1 | 4 | 66.67% | 7 |  | 1174.9707
186 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Quebec City | 2027-10-31 | 2027 | 198 | 4 | 2027-04-16 | high | low | high | low | med | 1585134 | 2069708 | 2046698 | 0 | 0 | 0 | 0 | 0 | 158513.4 | 634053.6 | 792567 | 0 | 0 | 0 | 0 | 1585134 | 40.7977 | CAPITAL | Yes | unit outage | X | X |  | X | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 4 | 2 | 5 | 3 | 2 | 2 | 4 | 3 | 1 | 57.78% | 6 | 2 | 2 | 1 | 5 | 1 | 2 | 43.33% | 5 |  | 13677.1818
187 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2026-12-31 | 2026 | 250 | 8 | 2026-04-25 | high | med | med | low | low | 450000 | 531419 | 534750 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 76.4614 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | no | no | 5 | 1 | 5 | 5 | 4 | 3 | 5 | 2 | 4 | 75.56% | 8 | 1 | 2 | 1 | 4 | 5 | 3 | 53.33% | 6 |  | 16021.8416
188 | L2 | FACILITY | ELECTRICAL |  | SWITCHGEAR | Calgary | 2025-12-31 | 2025 | 84 | 1 | 2025-10-08 | med | low | high | high | med | 90000 | 82153 | 84314 | 0 | 0 | 0 | 0 | 9000 | 36000 | 45000 | 0 | 0 | 0 | 0 | 0 | 90000 | 3472.2193 | EXPENSE | No | Unit outage | X |  |  |  |  | no | no | no | Yes | no | no | no | Yes | Yes | 1 | 2 | 1 | 3 | 2 | 5 | 1 | 1 | 4 | 44.44% | 5 | 1 | 4 | 1 | 5 | 5 | 1 | 56.67% | 6 |  | 7007.9205
189 | L2 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | North Bay | 2025-12-31 | 2025 | 333 | 6 | 2025-02-01 | high | high | med | high | low | 371262 | 634614 | 653309 | 37126.2 | 148504.8 | 185631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371262 | 175.9698 | EXPENSE | Yes | Unit outage |  | X | X | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 31.11% | 4 | 5 | 4 | 1 | 5 | 3 | 1 | 63.33% | 7 |  | 7007.9205
190 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANNUAL SURVEY | Winnipeg | 2025-07-31 | 2025 | 180 | 8 | 2025-02-01 | med | med | low | low | high | 780000 | 737705 | 703302 | 0 | 0 | 0 | 0 | 0 | 0 | 234000 | 468000 | 78000 | 0 | 0 | 0 | 780000 | 228.8332 | EXPENSE | Yes | NO outage | X | X |  | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | no | 1 | 1 | 1 | 3 | 2 | 1 | 5 | 2 | 1 | 37.78% | 4 | 3 | 3 | 1 | 5 | 3 | 5 | 66.67% | 7 |  | 18.4662
191 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANNUAL SURVEY | Saskatoon | 2026-10-31 | 2026 | 180 | 10 | 2026-05-04 | med | med | med | high | high | 750000 | 701993 | 706058 | 0 | 0 | 0 | 0 | 75000 | 300000 | 375000 | 0 | 0 | 0 | 0 | 0 | 750000 | 34.5922 | EXPENSE | No | NO outage | X | X |  |  | X | Yes | no | no | no | Yes | no | no | Yes | Yes | 1 | 4 | 2 | 2 | 1 | 2 | 4 | 2 | 2 | 44.44% | 5 | 4 | 4 | 1 | 5 | 3 | 2 | 63.33% | 7 |  | 19639.8665
191 | L2 | FACILITY | CIVIL |  | GRADING AND DRAINAGE | Calgary | 2027-12-31 | 2027 | 34 | 0 | 2027-11-27 | high | high | med | low | med | 150000 | 186308 | 194522 | 0 | 0 | 0 | 15000 | 60000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 491.4807 | EXPENSE | Yes | NO | X |  | X | X |  | no | no | no | Yes | Yes | no | no | no | no | 2 | 4 | 1 | 3 | 2 | 5 | 2 | 2 | 3 | 53.33% | 6 | 4 | 4 | 1 | 2 | 5 | 5 | 70% | 7 |  | 1685.9635
192 | L1 | FACILITY | CIVIL |  | GRADING AND DRAINAGE | Calgary | 2026-05-31 | 2026 | 45 | 0 | 2026-04-16 | low | low | high | med | med | 200000 | 209751 | 203723 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 80000 | 100000 | 0 | 0 | 0 | 200000 | 175.2379 | EXPENSE | Yes | NO |  |  |  |  | x | x | x | NR |  |  | x | x |  |  | 4 | 4 | 3 | 1 | 4 | 3 | 4 | 1 | 4 | 62.22% | 7 | 5 | 1 | 1 | 4 | 2 | 5 | 60% | 6 |  | 18394.3019
192 | L2 | FACILITY | MECHANICAL |  | SILENCER REPLACEMENT | North Bay | 2029-07-31 | 2029 | 312 | 5 | 2028-09-22 | med | low | low | high | high | 445318 | 524510 | 591817 | 0 | 0 | 0 | 44531.8 | 178127.2 | 222659 | 0 | 0 | 0 | 0 | 0 | 0 | 445318 | 132.8976 | CAPITAL | No | Unit outage | X | X |  | X |  | no | no | Yes | no | no | no | no | Yes | Yes | 4 | 2 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 44.44% | 5 | 1 | 3 | 1 | 1 | 2 | 5 | 43.33% | 5 |  | 22170.33
193 | L2 | FACILITY | MEASUREMENT |  | FUEL GAS UPGRADE | Saskatoon | 2025-12-31 | 2025 | 80 | 4 | 2025-10-12 | low | high | med | low | low | 1000000 | 943838 | 956534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 400000 | 500000 | 0 | 0 | 1000000 | 37.951 | CAPITAL | Yes | Derate/low flow Pipe segment |  | X |  | X | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 5 | 3 | 1 | 4 | 4 | 4 | 4 | 3 | 1 | 64.44% | 7 | 5 | 3 | 1 | 5 | 1 | 2 | 56.67% | 6 |  | 778.6578
194 | L2 | FACILITY | MEASUREMENT |  | H2S GAS SAMPLER | Edmonton | 2025-12-31 | 2025 | 182 | 4 | 2025-07-02 | low | low | low | low | high | 500000 | 532566 | 580507 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 500000 | 200.8491 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X | X | no | Yes | no | no | no | no | no | no | no | 2 | 2 | 1 | 1 | 4 | 1 | 2 | 1 | 5 | 42.22% | 5 | 5 | 4 | 1 | 3 | 4 | 1 | 60% | 6 |  | 278.7236
194 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Winnipeg | 2028-10-31 | 2028 | 175 | 8 | 2028-05-09 | med | low | med | med | high | 550000 | 585478 | 580917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 550000 | 28.2991 | EXPENSE | No | Pipeline segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 2 | 3 | 3 | 1 | 1 | 5 | 1 | 2 | 3 | 46.67% | 5 | 2 | 5 | 1 | 3 | 5 | 3 | 63.33% | 7 |  | 121.8769
195 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Toronto | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | low | low | high | med | low | 450000 | 448450 | 489906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 450000 | 134.4344 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | no | no | Yes | Yes | Yes | no | no | Yes | 1 | 5 | 3 | 2 | 1 | 5 | 4 | 2 | 1 | 53.33% | 6 | 3 | 2 | 1 | 2 | 3 | 1 | 40% | 4 |  | 643.2391
196 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2025-12-31 | 2025 | 122 | 15 | 2025-08-31 | high | high | high | low | high | 450000 | 692798 | 634137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 450000 | 890.1864 | CAPITAL | No | Pipeline segment |  | X | X | X | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 2 | 4 | 1 | 3 | 4 | 4 | 4 | 2 | 5 | 64.44% | 7 | 1 | 4 | 1 | 2 | 4 | 1 | 43.33% | 5 |  | 267.7598
197 | L1 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Quebec City | 2026-07-31 | 2026 | 231 | 6 | 2025-12-12 | high | low | high | high | med | 616752 | 629177 | 648523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61675.2 | 246700.8 | 308376 | 0 | 0 | 616752 | 105.1513 | EXPENSE | Yes | Unit outage |  |  | X |  | X | Yes | Yes | no | no | no | no | no | Yes | Yes | 3 | 4 | 2 | 4 | 3 | 3 | 3 | 3 | 4 | 64.44% | 7 | 1 | 3 | 1 | 1 | 3 | 4 | 43.33% | 5 |  | 267.7598
198 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2025-12-31 | 2025 | 100 | 4 | 2025-09-22 | high | med | low | high | med | 1500000 | 1550829 | 1550305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 600000 | 750000 | 0 | 0 | 1500000 | 143.1102 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 3 | 2 | 1 | 2 | 2 | 2 | 5 | 5 | 2 | 53.33% | 6 | 4 | 3 | 1 | 1 | 3 | 3 | 50% | 5 |  | 267.7598
199 | L2 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Ottawa | 2025-12-31 | 2025 | 364 | 6 | 2025-01-01 | high | high | low | low | low | 741595 | 765559 | 799216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74159.5 | 296638 | 370797.5 | 741595 | 13.3787 | CAPITAL | Yes | Unit outage |  |  | X | X |  | no | Yes | Yes | no | no | no | no | Yes | no | 3 | 5 | 2 | 3 | 3 | 3 | 5 | 4 | 3 | 68.89% | 7 | 5 | 1 | 1 | 4 | 1 | 1 | 43.33% | 5 |  | 17599.3754
200 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Montreal | 2026-10-31 | 2026 | 125 | 8 | 2026-06-28 | med | high | high | high | low | 550000 | 551865 | 564621 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 0 | 0 | 550000 | 86.0466 | EXPENSE | Yes | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 4 | 2 | 2 | 2 | 1 | 3 | 5 | 2 | 3 | 53.33% | 6 | 4 | 3 | 1 | 4 | 4 | 2 | 60% | 6 |  | 7024.2246
201 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Quebec City | 2027-07-31 | 2027 | 250 | 5 | 2026-11-23 | low | med | low | med | low | 300000 | 385848 | 388631 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 0 | 300000 | 71.0178 | EXPENSE | Yes | Pipeline segment |  |  |  | X |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 5 | 2 | 2 | 2 | 1 | 1 | 2 | 4 | 44.44% | 5 | 4 | 4 | 1 | 4 | 4 | 4 | 70% | 7 |  | 1591.1704
202 | L3 | FACILITY | MAJOR EQUIP |  | GG MINOR VSV | Quebec City | 2026-10-31 | 2026 | 150 | 8 | 2026-06-03 | low | med | high | low | high | 726541 | 798772 | 810709 | 0 | 0 | 0 | 0 | 0 | 72654.1 | 290616.4 | 363270.5 | 0 | 0 | 0 | 0 | 726541 | 97.8209 | EXPENSE | Yes | Unit outage |  | X |  |  |  | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 1 | 3 | 1 | 2 | 4 | 2 | 4 | 3 | 2 | 48.89% | 5 | 4 | 3 | 1 | 5 | 4 | 5 | 73.33% | 8 |  | 6832.4917
203 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2025-07-31 | 2025 | 120 | 15 | 2025-04-02 | high | high | high | med | med | 450000 | 489758 | 489076 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 0 | 450000 | 56.3678 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | Yes | no | no | no | no | no | no | no | no | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 2 | 5 | 53.33% | 6 | 5 | 3 | 1 | 4 | 4 | 5 | 73.33% | 8 |  | 4785
204 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Edmonton | 2027-12-31 | 2027 | 120 | 10 | 2027-09-02 | low | high | high | low | high | 300000 | 373417 | 385508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 120000 | 150000 | 0 | 300000 | 204.7502 | EXPENSE | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 5 | 3 | 1 | 3 | 5 | 2 | 3 | 3 | 1 | 57.78% | 6 | 2 | 3 | 1 | 1 | 2 | 2 | 36.67% | 4 |  | 3358
205 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Saskatoon | 2026-12-31 | 2026 | 175 | 8 | 2026-07-09 | high | high | med | med | med | 300000 | 384800 | 409516 | 0 | 0 | 0 | 0 | 30000 | 120000 | 150000 | 0 | 0 | 0 | 0 | 0 | 300000 | 193.3484 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | no | Yes | Yes | no | no | Yes | Yes | Yes | 5 | 1 | 3 | 2 | 3 | 1 | 2 | 4 | 3 | 53.33% | 6 | 1 | 4 | 1 | 1 | 2 | 1 | 33.33% | 4 |  | 5732.8906
206 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2025-12-31 | 2025 | 250 | 8 | 2025-04-25 | high | med | high | low | low | 650000 | 1109127 | 1023937 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 0 | 0 | 650000 | 53.022 | CAPITAL | No | Pipeline segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 3 | 3 | 3 | 2 | 4 | 5 | 2 | 2 | 5 | 64.44% | 7 | 5 | 1 | 1 | 5 | 1 | 4 | 56.67% | 6 |  | 3077.9635
207 | L1 | FACILITY | ELECTRICAL |  | INSPECTION | Ottawa | 2025-07-31 | 2025 | 150 | 1 | 2025-03-03 | med | high | high | med | low | 30000 | 31441 | 49618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 12000 | 15000 | 0 | 0 | 30000 | 2061.9972 | EXPENSE | Yes | Station outage |  |  |  |  | X | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 4 | 3 | 4 | 5 | 1 | 2 | 1 | 2 | 3 | 55.56% | 6 | 3 | 2 | 1 | 5 | 4 | 2 | 56.67% | 6 |  | 5097.2605
208 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2025-10-31 | 2025 | 181 | 4 | 2025-05-03 | high | low | low | low | med | 1800000 | 1789522 | 1832500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 720000 | 900000 | 0 | 1800000 | 2.6813 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 1 | 5 | 1 | 1 | 4 | 5 | 1 | 2 | 1 | 46.67% | 5 | 1 | 5 | 1 | 3 | 1 | 4 | 50% | 5 |  | 13582.277
209 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2026-07-31 | 2026 | 217 | 7 | 2025-12-26 | med | high | low | high | high | 2000000 | 2020848 | 2089578 | 200000 | 800000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 304.5368 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X | X | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 68.89% | 7 | 4 | 2 | 1 | 2 | 4 | 3 | 53.33% | 6 |  | 7709.8457
210 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Toronto | 2025-08-31 | 2025 | 150 | 15 | 2025-04-03 | med | med | low | high | high | 550000 | 899341 | 906308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 550000 | 44.7596 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | no | Yes | Yes | Yes | Yes | no | Yes | no | 5 | 5 | 3 | 2 | 5 | 5 | 4 | 3 | 5 | 82.22% | 9 | 3 | 5 | 5 | 1 | 2 | 1 | 56.67% | 6 |  | 7110.0938
211 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Toronto | 2027-10-31 | 2027 | 348 | 4 | 2026-11-17 | med | low | high | high | med | 3926870 | 3987955 | 3963500 | 1963435 | 1963435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3926870 | 132.3115 | CAPITAL | Yes | Unit outage | X | X | X | X |  | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 4 | 4 | 5 | 1 | 4 | 2 | 1 | 2 | 1 | 53.33% | 6 | 5 | 1 | 1 | 2 | 3 | 5 | 56.67% | 6 |  | 4391.6369
212 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Ottawa | 2025-07-31 | 2025 | 200 | 10 | 2025-01-12 | med | med | low | low | low | 300000 | 323560 | 360010 | 0 | 0 | 0 | 0 | 30000 | 120000 | 150000 | 0 | 0 | 0 | 0 | 0 | 300000 | 86.1551 | EXPENSE | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | Yes | Yes | Yes | no | no | 2 | 1 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 33.33% | 4 | 2 | 1 | 1 | 3 | 4 | 4 | 50% | 5 |  | 4314.1949
214 | L3 | FACILITY | MEASUREMENT |  | FLOW CONTROL | Quebec City | 2025-12-31 | 2025 | 177 | 3 | 2025-07-07 | high | med | med | high | high | 450000 | 457167 | 480837 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 0 | 450000 | 193.479 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | Yes | no | no | no | no | no | Yes | no | no | 4 | 2 | 4 | 5 | 2 | 4 | 2 | 3 | 5 | 68.89% | 7 | 5 | 2 | 5 | 4 | 4 | 5 | 83.33% | 9 |  | 2178.0735
215 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Saskatoon | 2025-12-31 | 2025 | 350 | 8 | 2025-01-15 | low | high | high | low | low | 1823036 | 1792775 | 1824513 | 0 | 0 | 0 | 0 | 182303.6 | 729214.4 | 911518 | 0 | 0 | 0 | 0 | 0 | 1823036 | 137.9035 | EXPENSE | Yes | Unit outage |  | X |  | X |  | Yes | no | Yes | no | Yes | Yes | Yes | Yes | Yes | 1 | 4 | 2 | 1 | 4 | 2 | 2 | 3 | 5 | 53.33% | 6 | 1 | 5 | 5 | 4 | 1 | 4 | 66.67% | 7 |  | 1090.5382
216 | L3 | FACILITY | MAJOR EQUIP |  | MINOR OH | Regina | 2026-10-31 | 2025 | 175 | 4 | 2026-05-09 | low | high | low | med | med | 1901410 | 1806853 | 1810108 | 190141 | 0 | 190141 | 1521128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1901410 | 68.9019 | CAPITAL | Yes | Unit outage |  | X | X |  | X | Yes | Yes | Yes | Yes | Yes | no | no | Yes | no | 1 | 5 | 3 | 1 | 3 | 3 | 2 | 2 | 2 | 48.89% | 5 | 5 | 4 | 5 | 5 | 1 | 4 | 80% | 8 |  | 8501.4285
217 | L1 | FACILITY | MECHANICAL |  | PSV REPLACE | Quebec City | 2028-12-31 | 2025 | 277 | 2 | 2028-03-29 | low | high | med | high | med | 45000 | 45864 | 46584 | 0 | 0 | 0 | 0 | 4500 | 18000 | 22500 | 0 | 0 | 0 | 0 | 0 | 45000 | 2112.101 | EXPENSE | No | Unit outage |  |  | X | X | X | no | Yes | no | no | no | Yes | Yes | Yes | Yes | 2 | 5 | 1 | 1 | 4 | 4 | 3 | 2 | 3 | 55.56% | 6 | 2 | 5 | 1 | 3 | 4 | 4 | 63.33% | 7 |  | 4052.0846
218 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Saskatoon | 2026-10-31 | 2025 | 150 | 10 | 2026-06-03 | med | low | high | low | med | 450000 | 452055 | 421982 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 450000 | 100.5902 | CAPITAL | No | pipeline segment outage |  | X | X |  | X | no | Yes | no | no | no | Yes | no | no | Yes | 2 | 3 | 1 | 2 | 2 | 5 | 3 | 1 | 3 | 48.89% | 5 | 3 | 3 | 1 | 5 | 2 | 3 | 56.67% | 6 |  | 6062.6028
219 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | North Bay | 2029-03-31 | 2029 | 116 | 4 | 2028-12-05 | med | high | med | high | med | 3179675 | 3341721 | 3333892 | 0 | 0 | 0 | 0 | 0 | 317967.5 | 1271870 | 1589837.5 | 0 | 0 | 0 | 0 | 3179675 | 3.1976 | CAPITAL | Yes | Unit outage | X |  | X | X |  | no | Yes | Yes | no | no | no | no | Yes | no | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 42.22% | 5 | 4 | 5 | 5 | 2 | 2 | 4 | 73.33% | 8 |  | 2610.3898
220 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Montreal | 2026-12-31 | 2026 | 200 | 10 | 2026-06-14 | high | high | med | high | high | 300000 | 275080 | 295529 | 0 | 0 | 0 | 0 | 30000 | 120000 | 150000 | 0 | 0 | 0 | 0 | 0 | 300000 | 32.563 | EXPENSE | No | Pipeline segment |  |  | X | X | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 5 | 4 | 5 | 4 | 5 | 3 | 2 | 1 | 4 | 73.33% | 8 | 1 | 3 | 1 | 4 | 2 | 5 | 53.33% | 6 |  | 2898
221 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Winnipeg | 2025-12-31 | 2025 | 120 | 15 | 2025-09-02 | med | low | low | low | high | 450000 | 466475 | 465002 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 13.0596 | CAPITAL | No | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 5 | 4 | 1 | 3 | 5 | 5 | 5 | 4 | 5 | 82.22% | 9 | 1 | 3 | 1 | 3 | 3 | 3 | 46.67% | 5 |  | 4522
222 | L2 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Quebec City | 2027-03-31 | 2027 | 170 | 7 | 2026-10-12 | high | high | low | med | high | 928800 | 1327497 | 1407658 | 0 | 0 | 0 | 0 | 92880 | 371520 | 464400 | 0 | 0 | 0 | 0 | 0 | 928800 | 43.8908 | EXPENSE | Yes | Unit outage | X | X |  | X |  | no | no | no | Yes | no | no | Yes | no | no | 1 | 4 | 1 | 3 | 4 | 2 | 2 | 2 | 2 | 46.67% | 5 | 3 | 5 | 1 | 2 | 3 | 1 | 50% | 5 |  | 9580.877
223 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Quebec City | 2027-12-31 | 2027 | 200 | 8 | 2027-06-14 | low | med | low | high | med | 550000 | 478617 | 519000 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 3.8339 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 1 | 3 | 4 | 4 | 2 | 4 | 3 | 3 | 60% | 6 | 3 | 5 | 5 | 3 | 3 | 2 | 70% | 7 |  | 8429.71
224 | L2 | FACILITY | ELECTRICAL |  | MCC | North Bay | 2025-12-31 | 2025 | 204 | 2 | 2025-06-10 | high | low | med | low | high | 750000 | 739078 | 750000 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 750000 | 426.8693 | EXPENSE | Yes | Unit outage |  | X | X | X | X | Yes | no | no | no | Yes | no | no | no | no | 4 | 1 | 1 | 1 | 1 | 5 | 3 | 5 | 3 | 53.33% | 6 | 2 | 3 | 1 | 3 | 4 | 1 | 46.67% | 5 |  | 8756
225 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2027-12-31 | 2027 | 140 | 8 | 2027-08-13 | med | high | low | med | high | 500000 | 986111 | 989500 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 0 | 0 | 0 | 500000 | 89.8531 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 5 | 40% | 4 | 3 | 1 | 1 | 2 | 1 | 2 | 33.33% | 4 |  | 5875
226 | L1 | FACILITY | MECHANICAL |  | AERIAL COOLER FAN | Edmonton | 2025-12-31 | 2025 | 200 | 3 | 2025-06-14 | high | med | high | low | high | 185000 | 196584 | 210005 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | 74000 | 92500 | 0 | 0 | 0 | 185000 | 57.8961 | EXPENSE | Yes | Unit outage | X |  | X |  | X | Yes | no | no | Yes | Yes | Yes | no | no | Yes | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 33.33% | 4 | 1 | 1 | 1 | 2 | 4 | 1 | 33.33% | 4 |  | 4526
227 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2025-07-31 | 2025 | 215 | 10 | 2024-12-28 | med | high | high | low | high | 350000 | 362980 | 373520 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 0 | 350000 | 1124.6434 | EXPENSE | No | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 3 | 2 | 3 | 4 | 4 | 4 | 1 | 2 | 1 | 53.33% | 6 | 3 | 2 | 1 | 1 | 1 | 1 | 30% | 3 |  | 258
228 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Winnipeg | 2025-10-31 | 2025 | 269 | 8 | 2025-02-04 | med | high | high | high | high | 350000 | 1071481 | 1076796 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 0 | 350000 | 137.4312 | CAPITAL | No | Pipeline segment |  |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 26.67% | 3 | 2 | 3 | 1 | 4 | 1 | 5 | 53.33% | 6 |  | 4785
229 | L1 | FACILITY | ELECTRICAL |  | INSPECTION | Regina | 2026-12-31 | 2026 | 20 | 0 | 2026-12-11 | low | low | high | high | low | 125000 | 142713 | 120217 | 0 | 0 | 12500 | 50000 | 62500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 791.2163 | EXPENSE | Yes | NO | X | X | X | X | X | Yes | Yes | Yes | Yes | no | Yes | no | no | no | 4 | 5 | 2 | 4 | 1 | 3 | 4 | 3 | 5 | 68.89% | 7 | 4 | 1 | 1 | 5 | 1 | 1 | 43.33% | 5 |  | 4101.034
230 | L1 | FACILITY | ELECTRICAL |  | INSPECTION | Ottawa | 2027-07-31 | 2027 | 150 | 0 | 2027-03-03 | med | high | high | med | low | 30000 | 31441 | 49618 | 0 | 0 | 3000 | 12000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 2061.9972 | EXPENSE | Yes | NO |  |  |  |  | X | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 3 | 4 | 3 | 3 | 2 | 5 | 4 | 2 | 5 | 68.89% | 7 | 4 | 3 | 1 | 1 | 4 | 3 | 53.33% | 6 |  | 211.3988
230 | L2 | FACILITY | MECHANICAL |  | VALVE | Edmonton | 2025-03-31 | 2025 | 25 | 4 | 2025-03-06 | low | high | med | high | high | 251839 | 174561 | 183348 | 0 | 0 | 0 | 25183.9 | 100735.6 | 125919.5 | 0 | 0 | 0 | 0 | 0 | 0 | 251839 | 311.0511 | EXPENSE | No | Unit outage | X | X | X | X | X | no | no | no | Yes | no | Yes | no | no | Yes | 2 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 46.67% | 5 | 3 | 3 | 1 | 1 | 4 | 5 | 56.67% | 6 |  | 3981.0002
231 | L1 | FACILITY | ELECTRICAL |  | INSPECTION | Regina | 2030-12-31 | 2030 | 20 | 0 | 2030-12-11 | low | low | high | high | low | 125000 | 142713 | 120217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 50000 | 62500 | 0 | 0 | 125000 | 791.2163 | EXPENSE | Yes | NO | X | X | X | X | X | Yes | Yes | Yes | Yes | no | Yes | no | no | no | 3 | 1 | 1 | 1 | 3 | 5 | 3 | 5 | 1 | 51.11% | 6 | 1 | 1 | 1 | 4 | 3 | 1 | 36.67% | 4 |  | 16059.78
231 | L3 | FACILITY | ELECTRICAL |  | REPAIR | WINNIPEG | 2025-12-31 | 2025 | 143 | 1 | 2025-08-10 | low | high | high | med | med | 95000 | 94555 | 98500 | 0 | 9500 | 38000 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 | 244.17 | EXPENSE | Yes | Unit outage |  | X | X |  |  | Yes | Yes | no | no | no | no | no | no | no | 2 | 3 | 2 | 3 | 2 | 1 | 3 | 2 | 5 | 51.11% | 6 | 4 | 5 | 5 | 4 | 2 | 2 | 73.33% | 8 |  | 842.9817
232 | L1 | FACILITY | MECHANICAL |  | VALVE | Saskatoon | 2026-03-31 | 2026 | 358 | 5 | 2025-04-07 | high | high | low | high | high | 433976 | 480247 | 522109 | 0 | 43397.6 | 173590.4 | 216988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433976 | 166.3938 | EXPENSE | No | Station outage | X |  | X | X | X | Yes | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 5 | 3 | 4 | 2 | 5 | 4 | 2 | 3 | 3 | 68.89% | 7 | 2 | 3 | 1 | 5 | 2 | 1 | 46.67% | 5 |  | 3506.8708
232 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Saskatoon | 2025-12-31 | 2025 | 23 | 7 | 2025-12-08 | med | low | high | low | med | 2823542 | 2769725 | 2750123 | 0 | 0 | 0 | 282354.2 | 1129416.8 | 1411771 | 0 | 0 | 0 | 0 | 0 | 0 | 2823542 | 9.3293 | CAPITAL | Yes | unit outage |  | X | X |  |  | no | no | Yes | no | no | no | Yes | Yes | no | 3 | 1 | 4 | 1 | 1 | 2 | 3 | 3 | 1 | 42.22% | 5 | 3 | 1 | 1 | 4 | 3 | 3 | 50% | 5 |  | 842.9817
233 | L3 | FACILITY | ELECTRICAL |  | INSPECTION | Quebec City | 2027-07-31 | 2027 | 340 | 1 | 2026-08-25 | low | high | high | high | high | 122000 | 116044 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 48800 | 61000 | 0 | 0 | 122000 | 30.7999 | EXPENSE | No | Pipeline segment |  |  |  |  | X | no | Yes | Yes | no | Yes | no | no | no | no | 2 | 4 | 1 | 1 | 4 | 3 | 2 | 2 | 3 | 48.89% | 5 | 5 | 2 | 1 | 5 | 3 | 3 | 63.33% | 7 |  | 267.7598
234 | L1 | FACILITY | MECHANICAL |  | VALVE | North Bay | 2028-03-31 | 2028 | 219 | 5 | 2027-08-25 | med | high | med | high | low | 450000 | 468943 | 433667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 450000 | 342.4579 | CAPITAL | Yes | Station outage | X | X | X | X |  | Yes | no | no | Yes | no | no | no | Yes | no | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 73.33% | 8 | 1 | 5 | 1 | 1 | 2 | 4 | 46.67% | 5 |  | 778.6578
233 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Calgary | 2025-07-31 | 2025 | 184 | 8 | 2025-01-28 | high | high | high | med | high | 250000 | 257881 | 301469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 100000 | 125000 | 0 | 0 | 250000 | 14.7788 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X |  | no | no | Yes | Yes | no | no | Yes | no | Yes | 1 | 2 | 2 | 1 | 2 | 4 | 5 | 2 | 3 | 48.89% | 5 | 2 | 2 | 1 | 2 | 4 | 2 | 43.33% | 5 |  | 13420.41
234 | L1 | FACILITY | MECHANICAL |  | VALVE | North Bay | 2028-03-31 | 2028 | 307 | 5 | 2027-05-29 | med | med | low | high | low | 433200 | 517641 | 649931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43320 | 173280 | 216600 | 0 | 0 | 433200 | 219.2823 | EXPENSE | Yes | Unit outage |  | X | X | X |  | Yes | no | no | Yes | Yes | no | Yes | no | Yes | 2 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 5 | 40% | 4 | 3 | 5 | 1 | 4 | 1 | 2 | 53.33% | 6 |  | 4101.0339
234 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | high | med | high | high | low | 350000 | 359833 | 352678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 350000 | 78.3491 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 2 | 4 | 1 | 1 | 4 | 3 | 3 | 1 | 2 | 46.67% | 5 | 3 | 1 | 1 | 3 | 3 | 1 | 40% | 4 |  | 1727.265
235 | L1 | FACILITY | MECHANICAL |  | VALVE | Montreal | 2027-12-31 | 2027 | 154 | 1 | 2027-07-30 | med | low | low | high | high | 44130 | 32124 | 357621 | 0 | 0 | 0 | 4413 | 17652 | 22065 | 0 | 0 | 0 | 0 | 0 | 0 | 44130 | 515.144 | EXPENSE | Yes | Unit outage | X | X | X |  |  | Yes | no | Yes | no | Yes | Yes | Yes | no | no | 2 | 2 | 1 | 3 | 4 | 1 | 2 | 1 | 2 | 40% | 4 | 2 | 2 | 1 | 1 | 2 | 3 | 36.67% | 4 |  | 1486.7011
235 | L3 | FACILITY | AUTOMATION & CONTROLS |  | INSPECTION | North Bay | 2030-03-31 | 2030 | 60 | 1 | 2030-01-30 | med | med | low | med | low | 25000 | 22000 | 27000 | 0 | 2500 | 10000 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 15603.7999 | EXPENSE | Yes | Unit outage |  | X | X |  |  | Yes | no | Yes | no | no | no | no | no | Yes | 3 | 3 | 2 | 1 | 2 | 4 | 4 | 1 | 2 | 48.89% | 5 | 3 | 3 | 1 | 3 | 3 | 4 | 56.67% | 6 |  | 1578
236 | L2 | FACILITY | MECHANICAL |  | VALVE | Saskatoon | 2026-07-31 | 2026 | 78 | 2 | 2026-05-14 | med | high | med | med | high | 81392 | 85842 | 104351 | 0 | 0 | 0 | 0 | 8139.2 | 32556.8 | 40696 | 0 | 0 | 0 | 0 | 0 | 81392 | 790.6318 | EXPENSE | Yes | Unit outage | X |  | X | X | X | no | no | Yes | no | no | no | Yes | Yes | no | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 40% | 4 | 5 | 4 | 1 | 1 | 2 | 3 | 53.33% | 6 |  | 14995.8254
236 | L1 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Edmonton | 2025-03-31 | 2025 | 140 | 5 | 2024-11-11 | med | med | med | med | med | 600000 | 676586 | 653711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 240000 | 300000 | 0 | 0 | 600000 | 3.5349 | EXPENSE | No | pipeline segment outage |  | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | Yes | no | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 28.89% | 3 | 3 | 2 | 1 | 4 | 3 | 3 | 53.33% | 6 |  | 3506.871
237 | L2 | FACILITY | MECHANICAL |  | VALVE | Saskatoon | 2028-10-31 | 2028 | 240 | 1 | 2028-03-05 | med | low | high | low | high | 27434 | 27379 | 163584 | 0 | 0 | 0 | 0 | 2743.4 | 10973.6 | 13717 | 0 | 0 | 0 | 0 | 0 | 27434 | 596.282 | CAPITAL | Yes | Unit outage |  |  |  | X | X | Yes | Yes | no | no | no | no | Yes | no | no | 4 | 4 | 2 | 4 | 1 | 3 | 5 | 3 | 3 | 64.44% | 7 | 4 | 4 | 1 | 1 | 4 | 5 | 63.33% | 7 |  | 425
237 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2027-07-31 | 2027 | 100 | 8 | 2027-04-22 | med | high | high | med | low | 400000 | 836064 | 996142 | 0 | 0 | 0 | 0 | 40000 | 160000 | 200000 | 0 | 0 | 0 | 0 | 0 | 400000 | 188.6819 | EXPENSE | Yes | Pipeline segment |  | X |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 4 | 2 | 4 | 3 | 4 | 2 | 4 | 5 | 4 | 71.11% | 8 | 3 | 2 | 1 | 3 | 1 | 4 | 46.67% | 5 |  | 18109.72
238 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Montreal | 2026-03-31 | 2026 | 250 | 7 | 2025-07-24 | med | high | low | high | med | 4635660 | 4788708 | 4799585 | 0 | 0 | 0 | 463566 | 1854264 | 2317830 | 0 | 0 | 0 | 0 | 0 | 0 | 4635660 | 12.2021 | CAPITAL | Yes | Unit outage |  |  | X | X | X | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 4 | 44.44% | 5 | 5 | 5 | 5 | 3 | 4 | 1 | 76.67% | 8 |  | 3981
239 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2025-12-31 | 2025 | 205 | 4 | 2025-06-09 | low | low | low | high | med | 950000 | 951400 | 9573713 | 0 | 0 | 0 | 95000 | 380000 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 165.7118 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | no | no | no | Yes | 2 | 1 | 1 | 2 | 2 | 4 | 3 | 2 | 3 | 44.44% | 5 | 1 | 2 | 1 | 4 | 2 | 3 | 43.33% | 5 |  | 20815.33
240 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2025-07-31 | 2025 | 240 | 4 | 2024-12-03 | high | low | low | low | high | 650000 | 720531 | 725189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 260000 | 325000 | 650000 | 732.8044 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  |  | no | Yes | Yes | Yes | Yes | no | no | no | no | 4 | 3 | 4 | 3 | 4 | 5 | 3 | 2 | 5 | 73.33% | 8 | 1 | 1 | 1 | 2 | 4 | 5 | 46.67% | 5 |  | 425
241 | L3 | FACILITY | MAJOR EQUIP |  | REPAIR | Saskatoon | 2025-07-31 | 2025 | 180 | 1 | 2025-02-01 | high | med | high | high | low | 95000 | 85000 | 87000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 38000 | 47500 | 95000 | 62.0325 | EXPENSE | Yes | Unit outage | X |  |  | X | X | Yes | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 5 | 2 | 3 | 4 | 2 | 1 | 2 | 2 | 53.33% | 6 | 5 | 2 | 1 | 5 | 5 | 3 | 70% | 7 |  | 2789
242 | L2 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Toronto | 2025-12-31 | 2025 | 49 | 2 | 2025-11-12 | med | low | low | med | low | 430601 | 714721 | 1089646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258360.6 | 215300.5 | 0 | 0 | 473661.1 | 253.0524 | EXPENSE | Yes | Unit outage |  | X | X | X | X | no | no | no | no | no | no | no | Yes | no | 2 | 1 | 2 | 1 | 2 | 4 | 3 | 1 | 5 | 46.67% | 5 | 5 | 1 | 1 | 4 | 2 | 3 | 53.33% | 6 |  | 5878
243 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Quebec City | 2026-10-31 | 2026 | 180 | 4 | 2026-05-04 | low | high | med | low | med | 650000 | 680531 | 685189 | 0 | 0 | 0 | 65000 | 260000 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 146.1537 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | no | no | Yes | Yes | no | Yes | no | Yes | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 3 | 35.56% | 4 | 1 | 1 | 1 | 1 | 3 | 5 | 40% | 4 |  | 2789
244 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2025-07-31 | 2025 | 265 | 7 | 2024-11-08 | low | high | low | low | med | 2100000 | 2124910 | 2128330 | 0 | 0 | 0 | 210000 | 840000 | 1050000 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 12.9047 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | no | no | no | no | Yes | no | 2 | 4 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 46.67% | 5 | 2 | 4 | 1 | 1 | 1 | 3 | 40% | 4 |  | 5666
245 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Winnipeg | 2025-03-31 | 2025 | 84 | 4 | 2025-01-06 | high | high | low | med | med | 1300000 | 1324785 | 1350260 | 0 | 0 | 0 | 0 | 0 | 130000 | 520000 | 650000 | 0 | 0 | 0 | 0 | 1300000 | 119.9716 | EXPENSE | No | Pipeline segment | X |  |  |  | X | Yes | no | no | Yes | Yes | no | no | Yes | no | 5 | 1 | 2 | 5 | 2 | 2 | 4 | 2 | 2 | 55.56% | 6 | 4 | 5 | 5 | 3 | 3 | 4 | 80% | 8 |  | 2789
246 | L2 | FACILITY | CIVIL |  | RICKWELL | Regina | 2025-07-31 | 2025 | 126 | 0 | 2025-03-27 | low | low | low | med | low | 22000 | 27923 | 35476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 8800 | 11000 | 0 | 0 | 22000 | 6532.7976 | EXPENSE | No | no | X | X |  | X |  | Yes | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 5 | 42.22% | 5 | 5 | 2 | 5 | 1 | 1 | 2 | 53.33% | 6 |  | 2588
247 | L3 | FACILITY | MAJOR EQUIP |  | INSPECTION | Winnipeg | 2025-12-31 | 2025 | 118 | 4 | 2025-09-04 | high | high | med | med | med | 2252939 | 2587340 | 2606499 | 0 | 0 | 675881.7 | 1351763.4 | 225293.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2252939 | 39.0549 | EXPENSE | Yes | unit outage | X | X |  |  | X | no | Yes | Yes | Yes | no | Yes | Yes | no | no | 4 | 3 | 3 | 5 | 4 | 2 | 2 | 5 | 2 | 66.67% | 7 | 3 | 1 | 1 | 1 | 1 | 5 | 40% | 4 |  | 8792
248 | L2 | FACILITY | CIVIL |  | RICKWELL | Regina | 2026-07-31 | 2026 | 126 | 0 | 2026-03-27 | low | low | low | med | low | 42000 | 27923 | 35476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 16800 | 21000 | 0 | 0 | 42000 | 6532.7976 | EXPENSE | No | NO | X | X |  | X |  | Yes | Yes | Yes | Yes | no | no | Yes | no | no | 4 | 4 | 3 | 5 | 3 | 5 | 5 | 4 | 3 | 80% | 8 | 2 | 3 | 1 | 3 | 3 | 2 | 46.67% | 5 |  | 21537.84
248 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | Regina | 2025-12-31 | 2025 | 188 | 4 | 2025-06-26 | high | med | med | high | med | 400000 | 393878 | 395581 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 0 | 400000 | 318.2127 | EXPENSE | No | Pipeline segment | X |  |  | X | X | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 5 | 3 | 1 | 2 | 4 | 4 | 4 | 2 | 1 | 57.78% | 6 | 2 | 5 | 1 | 2 | 3 | 5 | 60% | 6 |  | 23717.24
249 | L2 | FACILITY | ELECTRICAL |  | LIGHTING | Calgary | 2025-03-31 | 2025 | 40 | 2 | 2025-02-19 | low | high | high | high | med | 65000 | 68457 | 71500 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 26000 | 32500 | 0 | 0 | 0 | 65000 | 13553.4352 | EXPENSE | No | NO | X |  |  | X | X | Yes | Yes | Yes | no | Yes | no | no | no | Yes | 3 | 2 | 1 | 2 | 3 | 2 | 2 | 3 | 4 | 48.89% | 5 | 1 | 4 | 1 | 3 | 5 | 2 | 53.33% | 6 |  | 746.1723
250 | L3 | FACILITY | AUTOMATION & CONTROLS |  | DVC UPGRADE | Edmonton | 2025-03-31 | 2025 | 64 | 2 | 2025-01-26 | med | low | high | high | med | 65500 | 67177 | 69089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65500 | 0 | 0 | 0 | 65500 | 399.787 | EXPENSE | No | Unit outage | X |  |  |  | X | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 3 | 1 | 37.78% | 4 | 1 | 2 | 1 | 2 | 1 | 5 | 40% | 4 |  | 1174.971
251 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | Quebec City | 2027-07-31 | 2027 | 162 | 8 | 2027-02-19 | high | low | med | med | low | 500000 | 879950 | 872100 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 0 | 0 | 0 | 500000 | 59.654 | CAPITAL | No | Pipeline segment |  | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 4 | 1 | 4 | 2 | 3 | 3 | 1 | 5 | 3 | 57.78% | 6 | 2 | 4 | 1 | 3 | 1 | 1 | 40% | 4 |  | 13677.18
252 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | Toronto | 2027-07-31 | 2027 | 153 | 8 | 2027-02-28 | low | med | med | low | low | 350000 | 350821 | 350947 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 250.7139 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | no | no | no | Yes | 2 | 4 | 3 | 3 | 5 | 4 | 4 | 3 | 4 | 71.11% | 8 | 1 | 5 | 1 | 2 | 3 | 5 | 56.67% | 6 |  | 16021.84
253 | L2 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | North Bay | 2025-10-31 | 2025 | 72 | 5 | 2025-08-20 | low | low | high | med | med | 400000 | 527515 | 518701 | 0 | 0 | 0 | 0 | 0 | 40000 | 160000 | 200000 | 0 | 0 | 0 | 0 | 400000 | 129.2729 | EXPENSE | No | Pipeline segment | X | X |  | X |  | no | Yes | Yes | Yes | no | no | no | Yes | no | 1 | 5 | 1 | 3 | 2 | 1 | 4 | 2 | 3 | 48.89% | 5 | 3 | 3 | 1 | 1 | 1 | 3 | 40% | 4 |  | 7007.921
254 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | North Bay | 2025-10-31 | 2025 | 16 | 8 | 2025-10-15 | med | low | high | med | high | 350000 | 364592 | 366431 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 350000 | 134.8065 | EXPENSE | No | Pipeline segment | X | X |  |  | X | Yes | no | Yes | Yes | no | no | no | no | no | 1 | 1 | 1 | 1 | 1 | 3 | 4 | 2 | 2 | 35.56% | 4 | 3 | 2 | 1 | 5 | 2 | 5 | 60% | 6 |  | 7007.921
255 | L1 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Saskatoon | 2025-10-31 | 2025 | 120 | 2 | 2025-07-03 | med | low | low | high | med | 350000 | 535575 | 525049 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 38.5967 | EXPENSE | Yes | Unit outage | X | X | X |  |  | Yes | Yes | no | no | no | no | Yes | no | Yes | 1 | 5 | 1 | 3 | 1 | 5 | 2 | 2 | 1 | 46.67% | 5 | 4 | 3 | 1 | 4 | 2 | 2 | 53.33% | 6 |  | 1588
256 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | North Bay | 2025-12-31 | 2025 | 317 | 4 | 2025-02-17 | high | low | med | high | low | 1900000 | 2185889 | 2217656 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 760000 | 950000 | 0 | 0 | 0 | 1900000 | 102.6811 | CAPITAL | Yes | Unit outage | X |  | X |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 1 | 4 | 1 | 2 | 5 | 2 | 3 | 1 | 4 | 51.11% | 6 | 3 | 2 | 1 | 1 | 5 | 3 | 50% | 5 |  | 1685.963
257 | L3 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Ottawa | 2026-10-31 | 2026 | 120 | 4 | 2026-07-03 | med | high | high | high | med | 3878690 | 3880067 | 3887753 | 0 | 0 | 0 | 0 | 0 | 0 | 387869 | 1551476 | 1939345 | 0 | 0 | 0 | 3878690 | 4.671 | EXPENSE | Yes | Unit outage |  |  | X | X | X | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 3 | 2 | 4 | 4 | 5 | 5 | 1 | 2 | 4 | 66.67% | 7 | 3 | 4 | 1 | 2 | 2 | 1 | 43.33% | 5 |  | 1685.963
258 | L2 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Montreal | 2028-12-31 | 2025 | 148 | 2 | 2028-08-05 | low | high | high | med | med | 674006 | 553524 | 137499 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 202201.8 | 337003 | 134801.2 | 0 | 1074006 | 20.4003 | EXPENSE | Yes | Unit outage |  | X |  | X | X | Yes | Yes | no | Yes | Yes | no | Yes | no | Yes | 1 | 3 | 1 | 2 | 4 | 3 | 4 | 2 | 2 | 48.89% | 5 | 2 | 5 | 1 | 1 | 1 | 3 | 43.33% | 5 |  | 778.6578
259 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | INSPECTION | Quebec City | 2026-12-31 | 2026 | 182 | 8 | 2026-07-02 | high | high | high | low | med | 600000 | 670309 | 670000 | 0 | 0 | 0 | 60000 | 240000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 28.6028 | EXPENSE | No | pipeline segment outage |  |  | X |  | X | Yes | no | no | no | no | Yes | no | Yes | Yes | 2 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 2 | 35.56% | 4 | 2 | 2 | 1 | 4 | 3 | 1 | 43.33% | 5 |  | 121.8769
261 | L2 | FACILITY | ELECTRICAL |  | TEG | Montreal | 2027-12-31 | 2025 | 174 | 4 | 2027-07-10 | high | med | high | med | low | 150000 | 129579 | 122080 | 0 | 0 | 0 | 0 | 0 | 15000 | 120000 | 15000 | 0 | 0 | 0 | 0 | 150000 | 81.6263 | CAPITAL | No | Station outage |  |  |  | X | X | Yes | no | no | Yes | no | Yes | no | no | Yes | 4 | 5 | 2 | 2 | 3 | 5 | 3 | 1 | 1 | 57.78% | 6 | 3 | 2 | 1 | 4 | 5 | 1 | 53.33% | 6 |  | 267.7598
262 | L2 | FACILITY | AUTOMATION & CONTROLS |  | GAS DETECTOR SYSTEM | Toronto | 2025-12-31 | 2025 | 288 | 1 | 2025-03-18 | high | low | low | high | med | 50000 | 57500 | 57000 | 0 | 0 | 0 | 0 | 0 | 5000 | 20000 | 25000 | 0 | 0 | 0 | 0 | 50000 | 183.8574 | CAPITAL | No | Unit outage |  |  |  | X |  | no | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 5 | 2 | 4 | 3 | 1 | 1 | 4 | 3 | 3 | 57.78% | 6 | 3 | 3 | 1 | 2 | 4 | 2 | 50% | 5 |  | 267.7598
263 | L2 | FACILITY | MEASUREMENT |  | GAS SAMPLER | WINNIPEG | 2027-12-31 | 2027 | 258 | 4 | 2027-04-17 | med | high | med | high | low | 450000 | 424966 | 431278 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 450000 | 61.7752 | CAPITAL | No | Derate/low flow Pipe segment |  | X | X |  |  | Yes | no | no | Yes | Yes | no | no | Yes | Yes | 3 | 3 | 4 | 3 | 1 | 1 | 2 | 3 | 5 | 55.56% | 6 | 1 | 2 | 1 | 5 | 4 | 5 | 60% | 6 |  | 13677.1818
263 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | INSPECTION | Winnipeg | 2025-12-31 | 2025 | 227 | 8 | 2025-05-18 | low | low | high | high | high | 450000 | 401590 | 401803 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 0 | 450000 | 118.806 | EXPENSE | No | pipeline segment outage | X | X |  |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 2 | 2 | 1 | 1 | 2 | 2 | 4 | 3 | 5 | 48.89% | 5 | 3 | 3 | 1 | 4 | 1 | 2 | 46.67% | 5 |  | 267.7598
264 | L1 | FACILITY | MEASUREMENT |  | GAS SAMPLER | Montreal | 2027-07-31 | 2027 | 24 | 4 | 2027-07-07 | low | high | high | high | high | 500000 | 507208 | 536812 | 0 | 25184 | 100736 | 125920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251840 | 7.2213 | CAPITAL | No | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 4 | 3 | 2 | 1 | 4 | 1 | 2 | 5 | 3 | 55.56% | 6 | 5 | 4 | 5 | 1 | 5 | 2 | 73.33% | 8 |  | 22170.33
264 | L1 | FACILITY | MAJOR EQUIP |  | INSPECTION | Quebec City | 2027-12-31 | 2025 | 49 | 4 | 2027-11-12 | low | low | low | med | med | 850000 | 886000 | 910000 | 0 | 0 | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 112.7399 | EXPENSE | Yes | Unit outage |  | X |  | X | X | no | no | Yes | Yes | no | no | no | no | Yes | 3 | 1 | 4 | 4 | 5 | 2 | 2 | 5 | 5 | 68.89% | 7 | 3 | 3 | 1 | 3 | 2 | 3 | 50% | 5 |  | 17599.38
265 | L2 | FACILITY | ELECTRICAL |  | GG MAJOR OH | Edmonton | 2026-07-31 | 2026 | 328 | 0 | 2025-09-06 | med | high | low | med | med | 11149 | 11184 | 16043 | 0 | 0 | 0 | 0 | 25184 | 100736 | 125920 | 0 | 0 | 0 | 0 | 0 | 251840 | 17454.8659 | EXPENSE | No | NO |  |  | X | X | X | Yes | Yes | no | Yes | no | Yes | no | no | Yes | 2 | 3 | 1 | 3 | 3 | 1 | 4 | 3 | 3 | 51.11% | 6 | 2 | 5 | 1 | 2 | 2 | 3 | 50% | 5 |  | 3138.8656
265 | L1 | FACILITY | MECHANICAL |  | SILENCER REPLACEMENT | North Bay | 2027-03-31 | 2025 | 307 | 5 | 2026-05-28 | med | med | low | high | low | 450000 | 417641 | 449931 | 0 | 0 | 0 | 0 | 25184 | 100736 | 125920 | 0 | 0 | 0 | 0 | 0 | 251840 | 219.2823 | CAPITAL | Yes | Unit outage |  | X | X | X |  | Yes | no | no | Yes | Yes | no | Yes | no | Yes | 2 | 1 | 1 | 2 | 3 | 4 | 2 | 3 | 3 | 46.67% | 5 | 2 | 4 | 1 | 5 | 4 | 2 | 60% | 6 |  | 7024.225
266 | L2 | FACILITY | AUTOMATION & CONTROLS |  | INSPECTION | Calgary | 2025-12-31 | 2025 | 86 | 1 | 2025-10-06 | low | low | high | low | med | 47791 | 35167 | 38921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25184 | 100736 | 125920 | 0 | 0 | 251840 | 2496.1206 | EXPENSE | No | Unit outage | [5 empty] | Yes | Yes | no | Yes | Yes | no | Yes | no | no | 4 | 1 | 3 | 1 | 1 | 4 | 3 | 3 | 5 | 55.56% | 6 | 5 | 4 | 5 | 4 | 5 | 1 | 80% | 8 |  | 1591.17
267 | L3 | FACILITY | MECHANICAL |  | SKID | WINNIPEG | 2026-10-31 | 2026 | 163 | 4 | 2026-05-21 | low | med | low | high | low | 220000 | 250475 | 374000 | 0 | 0 | 0 | 25184 | 100736 | 125920 | 0 | 0 | 0 | 0 | 0 | 0 | 251840 | 430.5675 | EXPENSE | Yes | Unit outage | [5 empty] | no | Yes | Yes | no | no | Yes | Yes | no | Yes | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 40% | 4 | 5 | 5 | 5 | 1 | 2 | 4 | 73.33% | 8 |  | 263.7275
267 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2025-12-31 | 2025 | 280 | 4 | 2025-03-26 | high | high | low | high | low | 2100000 | 2014910 | 2018330 | 0 | 0 | 0 | 630000 | 1260000 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 61.0855 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 2 | 3 | 1 | 1 | 5 | 3 | 2 | 2 | 5 | 53.33% | 6 | 2 | 4 | 5 | 2 | 4 | 5 | 73.33% | 8 |  | 6832.492
268 | L3 | FACILITY | MECHANICAL |  | SKID | Saskatoon | 2026-12-31 | 2026 | 80 | 1 | 2026-10-12 | high | med | med | high | high | 36136 | 62047 | 60412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25184 | 100736 | 125920 | 0 | 0 | 251840 | 558.5679 | EXPENSE | No | Unit outage | X | X |  | X | X | Yes | Yes | no | no | no | Yes | no | no | Yes | 4 | 2 | 2 | 2 | 4 | 5 | 3 | 2 | 3 | 60% | 6 | 2 | 1 | 1 | 3 | 1 | 2 | 33.33% | 4 |  | 10182.1737
268 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | Quebec City | 2025-07-31 | 2025 | 94 | 8 | 2025-04-28 | low | low | low | low | low | 500000 | 677573 | 672660 | 25184 | 100736 | 125920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251840 | 11.9354 | EXPENSE | No | Pipeline segment |  |  | X |  |  | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 3 | 1 | 4 | 5 | 3 | 4 | 5 | 2 | 4 | 68.89% | 7 | 1 | 4 | 1 | 4 | 2 | 2 | 46.67% | 5 |  | 25885
269 | L2 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Saskatoon | 2025-07-31 | 2025 | 90 | 4 | 2025-05-02 | low | high | med | med | med | 1606464 | 1926241 | 1980196 | 0 | 0 | 0 | 0 | 160646.4 | 0 | 0 | 160646.4 | 1285171.2 | 0 | 0 | 0 | 1606464 | 48.566 | EXPENSE | Yes | Unit outage | X |  | X | X | X | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 5 | 4 | 2 | 2 | 5 | 4 | 5 | 5 | 4 | 80% | 8 | 4 | 1 | 1 | 1 | 1 | 1 | 30% | 3 |  | 5845
270 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | Edmonton | 2025-07-31 | 2025 | 139 | 5 | 2025-03-14 | med | med | med | med | low | 400000 | 425230 | 434107 | 0 | 0 | 0 | 25184 | 100736 | 125920 | 0 | 0 | 0 | 0 | 0 | 0 | 251840 | 383.2311 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | no | Yes | no | Yes | no | no | Yes | no | 4 | 5 | 3 | 4 | 3 | 5 | 4 | 1 | 5 | 75.56% | 8 | 4 | 3 | 1 | 1 | 2 | 1 | 40% | 4 |  | 5732.891
271 | L1 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Winnipeg | 2025-03-31 | 2025 | 74 | 4 | 2025-01-16 | low | low | high | low | low | 1000000 | 995898 | 947471 | 0 | 0 | 0 | 0 | 100000 | 800000 | 100000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 78.2163 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X | X | Yes | no | no | no | no | no | Yes | no | Yes | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 5 | 1 | 55.56% | 6 | 5 | 4 | 1 | 2 | 2 | 2 | 53.33% | 6 |  | 3077.963
272 | L2 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | Winnipeg | 2025-03-31 | 2025 | 87 | 5 | 2025-01-03 | high | high | high | low | high | 400000 | 493729 | 468570 | 40000 | 320000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 162.7571 | EXPENSE | No | Pipeline segment | X | X |  |  | X | no | Yes | Yes | Yes | no | no | Yes | no | Yes | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 48.89% | 5 | 2 | 5 | 5 | 1 | 3 | 1 | 56.67% | 6 |  | 5097.261
273 | L2 | FACILITY | EXCAVATION | Corrosion | INSPECTION | Calgary | 2025-10-31 | 2025 | 34 | 1 | 2025-09-27 | low | med | high | low | med | 250000 | 203595 | 211700 | 0 | 0 | 0 | 0 | 25000 | 200000 | 25000 | 0 | 0 | 0 | 0 | 0 | 250000 | 218.414 | EXPENSE | No | Station outage |  |  |  |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 35.56% | 4 | 2 | 5 | 5 | 2 | 1 | 4 | 63.33% | 7 |  | 13582.28
274 | L1 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | Calgary | 2026-10-31 | 2026 | 236 | 8 | 2026-03-09 | low | low | low | med | low | 450000 | 444446 | 445417 | 0 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 450000 | 145.3755 | CAPITAL | No | Pipeline segment |  |  | X | X | X | Yes | no | Yes | Yes | Yes | no | Yes | Yes | Yes | 5 | 4 | 5 | 3 | 5 | 5 | 5 | 1 | 2 | 77.78% | 8 | 3 | 3 | 1 | 2 | 1 | 2 | 40% | 4 |  | 7709.846
275 | L2 | PIPE INTEGRITY | EXCAVATION | ECOR | INSPECTION | Calgary | 2026-12-31 | 2026 | 176 | 8 | 2026-07-08 | high | low | med | high | high | 450000 | 858949 | 899364 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 44.4078 | CAPITAL | Yes | pipeline segment | X | X |  |  | X | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 2 | 5 | 3 | 2 | 4 | 4 | 3 | 2 | 1 | 57.78% | 6 | 1 | 3 | 1 | 3 | 1 | 3 | 40% | 4 |  | 7110.094
276 | L2 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Winnipeg | 2025-07-31 | 2025 | 150 | 2 | 2025-03-03 | med | low | low | med | high | 850000 | 795426 | 800000 | 0 | 0 | 0 | 85000 | 680000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 287.411 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 3 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 40% | 4 | 2 | 5 | 1 | 5 | 2 | 4 | 63.33% | 7 |  | 4391.637
277 | L2 | FACILITY | MEASUREMENT |  | RTU REPLACMENT | Edmonton | 2027-12-31 | 2025 | 182 | 5 | 2027-07-02 | low | low | low | low | high | 600000 | 622566 | 628050 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 480000 | 60000 | 0 | 0 | 0 | 600000 | 200.8491 | CAPITAL | No | Derate/low flow Pipe segment | X |  | X | X | X | no | Yes | no | no | no | no | no | no | no | 4 | 4 | 5 | 3 | 5 | 1 | 5 | 1 | 5 | 73.33% | 8 | 2 | 2 | 1 | 4 | 3 | 4 | 53.33% | 6 |  | 4314.195
278 | L2 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Saskatoon | 2025-10-31 | 2025 | 150 | 4 | 2025-06-03 | low | med | med | low | high | 1000000 | 1135786 | 1204048 | 0 | 0 | 100000 | 400000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 336.0415 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 1 | 1 | 1 | 4 | 4 | 1 | 3 | 2 | 44.44% | 5 | 3 | 1 | 1 | 4 | 2 | 1 | 40% | 4 |  | 4858.887
279 | L3 | FACILITY | ELECTRICAL |  | BATTERY REPLACEMENT | Ottawa | 2025-12-31 | 2025 | 361 | 4 | 2025-01-04 | high | low | high | high | high | 50000 | 42012 | 49443 | 5000 | 40000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 91.8973 | EXPENSE | No | Unit outage |  |  |  |  | X | no | no | no | no | Yes | Yes | Yes | no | Yes | 2 | 4 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 40% | 4 | 1 | 4 | 1 | 5 | 1 | 4 | 53.33% | 6 |  | 2178.073
280 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2026-03-31 | 2026 | 150 | 8 | 2025-11-01 | med | high | med | med | high | 500000 | 567194 | 567060 | 0 | 0 | 0 | 0 | 400000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 49.109 | EXPENSE | No | Pipeline segment | X | X |  |  |  | Yes | Yes | no | no | Yes | no | no | Yes | Yes | 4 | 2 | 2 | 4 | 5 | 1 | 3 | 2 | 5 | 62.22% | 7 | 3 | 2 | 1 | 2 | 4 | 2 | 46.67% | 5 |  | 1090.538
281 | L1 | FACILITY | CIVIL |  | REPAIR- STRUCTURE | Edmonton | 2025-07-31 | 2025 | 150 | 0 | 2025-03-03 | med | high | low | high | low | 135000 | 222276 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 108000 | 13500 | 0 | 0 | 0 | 135000 | 850.7175 | EXPENSE | Yes | NO | X |  |  | X | X | Yes | no | Yes | no | Yes | no | Yes | no | no | 3 | 4 | 1 | 2 | 3 | 2 | 2 | 3 | 4 | 53.33% | 6 | 3 | 5 | 1 | 1 | 2 | 4 | 53.33% | 6 |  | 8501.429
282 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Edmonton | 2026-07-31 | 2026 | 150 | 8 | 2026-03-03 | med | med | med | high | med | 350000 | 306367 | 304154 | 0 | 0 | 0 | 0 | 280000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 56.2148 | CAPITAL | Yes | Pipeline segment |  | X | X |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 5 | 46.67% | 5 | 5 | 5 | 5 | 2 | 4 | 4 | 83.33% | 9 |  | 4052.085
283 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2026-03-31 | 2026 | 100 | 8 | 2025-12-21 | low | high | med | low | med | 350000 | 306322 | 304238 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 280000 | 35000 | 0 | 0 | 0 | 350000 | 104.2124 | CAPITAL | No | Pipeline segment | X | X | X |  | X | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 1 | 5 | 2 | 1 | 3 | 2 | 2 | 2 | 48.89% | 5 | 1 | 5 | 1 | 5 | 1 | 3 | 53.33% | 6 |  | 6062.603
284 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2025-12-31 | 2025 | 153 | 2 | 2025-07-31 | med | med | high | high | low | 300000 | 351489 | 352567 | 0 | 0 | 0 | 0 | 30000 | 240000 | 30000 | 0 | 0 | 0 | 0 | 0 | 300000 | 256.8876 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  | X | X | Yes | Yes | no | Yes | Yes | no | no | no | no | 3 | 4 | 1 | 1 | 3 | 3 | 3 | 5 | 2 | 55.56% | 6 | 3 | 3 | 1 | 1 | 1 | 5 | 46.67% | 5 |  | 2610.39
285 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2027-12-31 | 2027 | 85 | 8 | 2027-10-07 | med | low | med | low | med | 350000 | 393527 | 393520 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 21.7053 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | no | Yes | no | no | Yes | no | Yes | 5 | 3 | 2 | 4 | 2 | 4 | 5 | 4 | 3 | 71.11% | 8 | 1 | 2 | 1 | 5 | 2 | 2 | 43.33% | 5 |  | 241.5599
286 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2026-12-31 | 2026 | 150 | 8 | 2026-08-03 | high | low | med | med | high | 400000 | 857316 | 863023 | 0 | 0 | 0 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 0 | 0 | 0 | 400000 | 42.7227 | CAPITAL | No | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 2 | 3 | 3 | 5 | 1 | 2 | 5 | 4 | 62.22% | 7 | 4 | 4 | 5 | 1 | 2 | 5 | 70% | 7 |  | 4995.39
287 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2027-03-31 | 2027 | 150 | 8 | 2026-11-01 | low | med | low | low | low | 350000 | 420028 | 448094 | 0 | 0 | 0 | 0 | 35000 | 280000 | 35000 | 0 | 0 | 0 | 0 | 0 | 350000 | 90.2519 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | no | 4 | 5 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 42.22% | 5 | 1 | 4 | 1 | 2 | 1 | 5 | 46.67% | 5 |  | 6993.546
288 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2025-12-31 | 2025 | 150 | 8 | 2025-08-03 | low | high | med | low | low | 350000 | 354238 | 347119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 280000 | 35000 | 0 | 0 | 350000 | 61.5753 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 4 | 3 | 4 | 5 | 1 | 2 | 4 | 3 | 4 | 66.67% | 7 | 3 | 1 | 1 | 5 | 5 | 1 | 53.33% | 6 |  | 222.8052
289 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Calgary | 2025-10-31 | 2025 | 240 | 4 | 2025-03-05 | low | high | med | low | high | 2982904 | 2699996 | 2955454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298290.4 | 2386323.2 | 298290.4 | 0 | 0 | 2982904 | 23.1267 | CAPITAL | Yes | Unit outage | X |  |  | X |  | Yes | Yes | Yes | Yes | no | Yes | no | Yes | Yes | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 33.33% | 4 | 2 | 2 | 1 | 5 | 1 | 3 | 46.67% | 5 |  | 840.2082
290 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2025-12-31 | 2025 | 216 | 4 | 2025-05-29 | med | low | low | high | low | 1900000 | 1959945 | 1963759 | 0 | 0 | 0 | 190000 | 1520000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 28.0968 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | Yes | 4 | 2 | 2 | 3 | 3 | 2 | 3 | 5 | 2 | 57.78% | 6 | 2 | 2 | 1 | 3 | 4 | 1 | 43.33% | 5 |  | 5000
291 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Montreal | 2025-10-31 | 2025 | 150 | 4 | 2025-06-03 | low | high | med | low | low | 1373131 | 1565762 | 1690696 | 0 | 0 | 0 | 0 | 137313.1 | 1098504.8 | 137313.1 | 0 | 0 | 0 | 0 | 0 | 1373131 | 21.1703 | CAPITAL | Yes | Unit outage | X |  | X |  | X | Yes | no | no | Yes | no | no | no | Yes | no | 1 | 5 | 2 | 1 | 2 | 1 | 5 | 1 | 1 | 42.22% | 5 | 5 | 1 | 1 | 2 | 4 | 1 | 46.67% | 5 |  | 646
292 | L2 | FACILITY | MAJOR EQUIP |  | MINOR OH | Ottawa | 2025-10-31 | 2025 | 60 | 4 | 2025-09-01 | med | med | med | med | med | 828894 | 814607 | 881165 | 0 | 0 | 0 | 82889.4 | 663115.2 | 82889.4 | 0 | 0 | 0 | 0 | 0 | 0 | 828894 | 106.3061 | CAPITAL | Yes | Unit outage |  | X | X | X |  | no | Yes | Yes | no | Yes | Yes | Yes | no | Yes | 4 | 1 | 4 | 3 | 3 | 3 | 3 | 2 | 4 | 60% | 6 | 2 | 5 | 1 | 5 | 3 | 2 | 60% | 6 |  | 289
293 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2026-03-31 | 2026 | 180 | 8 | 2025-10-02 | low | low | high | high | low | 350000 | 401605 | 407547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 280000 | 35000 | 0 | 0 | 350000 | 7.1499 | CAPITAL | No | Pipeline segment | X |  |  | X |  | no | no | Yes | no | no | no | Yes | no | Yes | 1 | 4 | 2 | 3 | 4 | 1 | 2 | 1 | 1 | 42.22% | 5 | 5 | 5 | 1 | 3 | 1 | 2 | 56.67% | 6 |  | 347
294 | L1 | FACILITY | MECHANICAL |  | BOILER PIPING | Ottawa | 2025-12-31 | 2025 | 28 | 3 | 2025-12-03 | med | med | med | med | high | 1155340 | 1307830 | 1382190 | 0 | 0 | 115534 | 924272 | 115534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155340 | 7.203 | EXPENSE | No | unit outage |  | X |  | X | X | no | Yes | Yes | no | Yes | no | Yes | Yes | Yes | 4 | 5 | 1 | 4 | 5 | 2 | 5 | 4 | 1 | 68.89% | 7 | 1 | 3 | 1 | 2 | 4 | 3 | 46.67% | 5 |  | 158885
295 | L2 | FACILITY | MEASUREMENT |  | METER | North Bay | 2028-12-31 | 2025 | 36 | 5 | 2028-11-25 | med | high | low | low | med | 50000 | 50000 | 42368 | 0 | 0 | 0 | 0 | 15000 | 25000 | 10000 | 0 | 0 | 0 | 0 | 0 | 50000 | 118.532 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | no | Yes | no | no | no | Yes | Yes | 2 | 4 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 40% | 4 | 1 | 5 | 1 | 3 | 2 | 3 | 50% | 5 |  | 1207.799
296 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2025-12-31 | 2025 | 120 | 15 | 2025-09-02 | med | low | low | low | low | 450000 | 505184 | 505568 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 15.392 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | no | no | Yes | 2 | 5 | 3 | 2 | 3 | 1 | 5 | 3 | 3 | 60% | 6 | 2 | 3 | 1 | 3 | 3 | 5 | 56.67% | 6 |  | 1785
297 | L3 | FACILITY | ELECTRICAL |  | TEG | Quebec City | 2027-07-31 | 2027 | 85 | 1 | 2027-05-07 | low | high | high | high | high | 150000 | 156044 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000 | 30.7999 | EXPENSE | No | unit outage |  |  |  |  | X | no | Yes | Yes | no | Yes | no | no | no | no | 3 | 3 | 2 | 5 | 3 | 2 | 3 | 1 | 2 | 53.33% | 6 | 2 | 4 | 1 | 1 | 4 | 1 | 43.33% | 5 |  | 898
298 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Calgary | 2026-12-31 | 2026 | 120 | 8 | 2026-09-02 | low | med | low | med | med | 750000 | 900542 | 936801 | 0 | 0 | 75000 | 600000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 120.5022 | EXPENSE | Yes | Pipeline segment | X | X | X |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 5 | 3 | 2 | 2 | 5 | 3 | 4 | 1 | 3 | 62.22% | 7 | 2 | 3 | 1 | 2 | 2 | 4 | 46.67% | 5 |  | 172.2548
299 | L3 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Winnipeg | 2026-12-31 | 2026 | 187 | 4 | 2026-06-27 | high | med | low | high | low | 524525 | 270026 | 443557 | 0 | 0 | 0 | 0 | 52452.5 | 419620 | 52452.5 | 0 | 0 | 0 | 0 | 0 | 524525 | 84.5636 | EXPENSE | Yes | Unit outage | X | X | X | X | X | Yes | Yes | no | no | no | no | no | Yes | Yes | 3 | 4 | 1 | 3 | 2 | 4 | 4 | 4 | 1 | 57.78% | 6 | 5 | 4 | 1 | 1 | 3 | 3 | 56.67% | 6 |  | 172.2548
300 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Ottawa | 2026-10-31 | 2026 | 100 | 5 | 2026-07-23 | high | low | high | med | high | 450000 | 679319 | 635544 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 35.2892 | CAPITAL | No | pipeline segment outage | X |  | X | X | X | Yes | Yes | Yes | no | no | Yes | no | no | no | 4 | 5 | 2 | 4 | 4 | 1 | 5 | 2 | 4 | 68.89% | 7 | 3 | 2 | 1 | 1 | 4 | 1 | 40% | 4 |  | 191.3942
301 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Edmonton | 2027-12-31 | 2027 | 100 | 4 | 2027-09-22 | med | med | med | low | low | 500000 | 544088 | 579248 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 152.364 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | no | Yes | no | Yes | Yes | no | Yes | Yes | 1 | 3 | 1 | 1 | 2 | 5 | 1 | 1 | 2 | 37.78% | 4 | 5 | 3 | 1 | 2 | 3 | 4 | 60% | 6 |  | 382.7885
302 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2025-12-31 | 2025 | 180 | 8 | 2025-07-04 | low | med | med | med | low | 450000 | 360834 | 399482 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 177.3607 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | Yes | no | no | Yes | no | Yes | no | no | 2 | 3 | 3 | 1 | 3 | 2 | 3 | 3 | 3 | 51.11% | 6 | 1 | 3 | 1 | 1 | 2 | 5 | 43.33% | 5 |  | 173.2929
303 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2027-07-31 | 2027 | 200 | 4 | 2027-01-12 | high | low | high | high | high | 3536540 | 3511282 | 3586508 | 0 | 0 | 0 | 0 | 0 | 353654 | 2829232 | 353654 | 0 | 0 | 0 | 0 | 3536540 | 202.5027 | CAPITAL | Yes | Unit outage | X |  | X |  | X | Yes | Yes | Yes | no | no | no | Yes | no | Yes | 5 | 5 | 3 | 2 | 5 | 5 | 1 | 3 | 1 | 66.67% | 7 | 1 | 5 | 1 | 5 | 2 | 2 | 53.33% | 6 |  | 900.2043
304 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2025-12-31 | 2025 | 200 | 8 | 2025-06-14 | high | low | high | med | med | 500000 | 498707 | 498210 | 0 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 152.9866 | EXPENSE | No | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | Yes | no | no | no | no | 4 | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 5 | 66.67% | 7 | 3 | 1 | 1 | 3 | 5 | 5 | 60% | 6 |  | 749.7244
305 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2025-03-31 | 2025 | 240 | 4 | 2024-08-03 | high | high | med | high | med | 1500000 | 1812742 | 1842116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 1200000 | 150000 | 0 | 0 | 1500000 | 34.0888 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 2 | 2 | 2 | 2 | 5 | 5 | 2 | 1 | 3 | 53.33% | 6 | 1 | 5 | 1 | 4 | 5 | 3 | 63.33% | 7 |  | 41798.52
307 | L2 | FACILITY | EXCAVATION | SCC | SURVEY | WINNIPEG | 2027-12-31 | 2025 | 85 | 1 | 2027-10-07 | med | low | high | high | high | 95000 | 90034 | 90206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 76000 | 9500 | 0 | 95000 | 353.2194 | EXPENSE | Yes | Station outage |  |  |  | X |  | no | no | Yes | no | Yes | no | no | no | no | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 3 | 33.33% | 4 | 5 | 3 | 1 | 1 | 2 | 2 | 46.67% | 5 |  | 1022.412
308 | L1 | FACILITY | MEASUREMENT |  | CALIBRATION | Calgary | 2027-12-31 | 2027 | 15 | 3 | 2027-12-16 | high | med | high | low | low | 200000 | 185820 | 184457 | 0 | 0 | 0 | 0 | 20000 | 160000 | 20000 | 0 | 0 | 0 | 0 | 0 | 200000 | 112.7741 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | Yes | no | Yes | no | no | no | Yes | Yes | no | 5 | 1 | 3 | 2 | 4 | 1 | 4 | 2 | 3 | 55.56% | 6 | 4 | 2 | 1 | 4 | 3 | 1 | 50% | 5 |  | 1022.412
309 | L1 | FACILITY | EXCAVATION | Dent | SURVEY | Ottawa | 2028-10-31 | 2028 | 85 | 1 | 2028-08-07 | high | high | med | low | high | 60000 | 83630 | 85456 | 0 | 0 | 6000 | 48000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 2019.9872 | EXPENSE | No | Unit outage |  |  | X | X |  | Yes | Yes | Yes | no | Yes | no | no | no | no | 3 | 2 | 3 | 3 | 4 | 1 | 1 | 3 | 1 | 46.67% | 5 | 2 | 1 | 1 | 2 | 5 | 3 | 46.67% | 5 |  | 1685.9635
310 | L2 | FACILITY | EXCAVATION | SCC | SURVEY | Edmonton | 2026-12-31 | 2025 | 85 | 1 | 2026-10-07 | med | low | high | high | high | 95000 | 100034 | 108206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 76000 | 9500 | 0 | 95000 | 353.2194 | EXPENSE | Yes | Station outage |  |  |  | X |  | no | no | Yes | no | Yes | no | no | no | no | 4 | 3 | 3 | 5 | 3 | 1 | 4 | 4 | 5 | 71.11% | 8 | 4 | 5 | 1 | 5 | 2 | 2 | 63.33% | 7 |  | 3077.9635
310 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Edmonton | 2027-03-31 | 2025 | 150 | 2 | 2026-11-01 | high | low | low | low | high | 600000 | 598833 | 611085 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 60000 | 360000 | 60000 | 0 | 0 | 600000 | 218.6029 | CAPITAL | No | pipeline segment outage | X |  | X | X |  | no | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 1 | 2 | 3 | 2 | 4 | 5 | 3 | 2 | 55.56% | 6 | 4 | 5 | 5 | 4 | 4 | 4 | 86.67% | 9 |  | 425
311 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2025-10-31 | 2025 | 214 | 4 | 2025-03-31 | low | low | med | high | high | 4617354 | 4365331 | 4340535 | 0 | 0 | 461735.4 | 3693883.2 | 461735.4 | 0 | 0 | 0 | 0 | 4617354 | 0 | 0 | 9234708 | 70.5186 | CAPITAL | Yes | Unit outage |  |  | X |  |  | no | Yes | no | Yes | no | Yes | Yes | no | no | 4 | 3 | 4 | 4 | 2 | 2 | 5 | 5 | 1 | 66.67% | 7 | 4 | 5 | 5 | 2 | 3 | 4 | 76.67% | 8 |  | 4447
312 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Calgary | 2026-10-31 | 2026 | 80 | 5 | 2026-08-12 | high | low | high | high | low | 400000 | 522720 | 529911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 400000 | 242.1342 | CAPITAL | No | Pipeline segment |  |  |  | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 4 | 2 | 5 | 1 | 4 | 3 | 4 | 3 | 64.44% | 7 | 2 | 1 | 1 | 2 | 2 | 1 | 30% | 3 |  | 20000
313 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2025-10-31 | 2025 | 160 | 5 | 2025-05-24 | med | high | low | med | low | 400000 | 408000 | 425000 | 0 | 0 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 218.7171 | EXPENSE | Yes | pipeline segment |  |  | X | X | X | no | no | no | no | no | Yes | Yes | Yes | no | 5 | 2 | 1 | 2 | 5 | 5 | 2 | 5 | 1 | 62.22% | 7 | 1 | 3 | 1 | 4 | 2 | 3 | 46.67% | 5 |  | 2078
314 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2026-10-31 | 2026 | 172 | 5 | 2026-05-12 | low | high | med | med | high | 500000 | 586296 | 558571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 500000 | 163.365 | CAPITAL | No | Pipeline segment |  | X | X | X | X | no | no | Yes | no | no | no | Yes | no | no | 2 | 5 | 3 | 2 | 4 | 2 | 4 | 2 | 1 | 55.56% | 6 | 1 | 1 | 1 | 2 | 4 | 2 | 36.67% | 4 |  | 1875
315 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2025-12-31 | 2025 | 106 | 4 | 2025-09-16 | high | high | med | high | high | 500000 | 501652 | 545736 | 0 | 0 | 0 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 500000 | 41.1751 | EXPENSE | No | Pipeline segment |  | X | X |  |  | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 5 | 5 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 53.33% | 6 | 5 | 4 | 1 | 3 | 3 | 2 | 60% | 6 |  | 7718.869
316 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2025-12-31 | 2025 | 200 | 8 | 2025-06-14 | low | med | med | med | low | 500000 | 513241 | 519365 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 5.9556 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | no | 5 | 3 | 1 | 2 | 3 | 3 | 3 | 2 | 4 | 57.78% | 6 | 2 | 1 | 1 | 1 | 4 | 2 | 36.67% | 4 |  | 7718.869
317 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Regina | 2026-07-31 | 2026 | 330 | 4 | 2025-09-04 | low | high | high | high | high | 750000 | 1804556 | 813074 | 0 | 0 | 0 | 75000 | 600000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 83.977 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  | X | Yes | Yes | no | no | Yes | no | no | no | no | 3 | 1 | 4 | 2 | 2 | 2 | 3 | 2 | 3 | 48.89% | 5 | 3 | 1 | 1 | 3 | 2 | 3 | 43.33% | 5 |  | 6993.546
318 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2025-07-31 | 2025 | 343 | 4 | 2024-08-22 | low | high | low | med | high | 750000 | 853330 | 827797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 375000 | 150000 | 750000 | 200.4576 | EXPENSE | No | Derate/low flow Pipe segment | [5 empty] | no | no | no | no | Yes | Yes | no | no | Yes | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 28.89% | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 23.33% | 3 |  | 1475
319 | L1 | FACILITY | MEASUREMENT |  | METER REPLACEMENT | Calgary | 2025-12-31 | 2025 | 128 | 2 | 2025-08-25 | high | med | med | low | low | 600000 | 648079 | 627388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 480000 | 60000 | 0 | 0 | 600000 | 30.6378 | CAPITAL | No | pipeline segment outage |  |  |  | X | X | no | no | no | Yes | no | Yes | Yes | Yes | no | 4 | 1 | 3 | 1 | 1 | 3 | 1 | 5 | 1 | 44.44% | 5 | 5 | 4 | 5 | 4 | 5 | 5 | 93.33% | 10 |  | 636.4681
321 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Quebec City | 2025-12-31 | 2025 | 164 | 4 | 2025-07-20 | high | med | high | med | low | 2772163 | 2866364 | 2829718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 831648.9 | 1663297.8 | 277216.3 | 0 | 2772163 | 24.2482 | CAPITAL | Yes | Unit outage |  | X | X | X |  | no | Yes | Yes | no | no | Yes | Yes | Yes | no | 2 | 2 | 2 | 2 | 1 | 4 | 3 | 1 | 1 | 40% | 4 | 1 | 5 | 1 | 1 | 5 | 1 | 46.67% | 5 |  | 2369.828
322 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2027-03-31 | 2027 | 85 | 8 | 2027-01-05 | med | high | low | high | med | 400000 | 582895 | 585540 | 0 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 199.4572 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 3 | 2 | 1 | 1 | 2 | 4 | 5 | 4 | 5 | 60% | 6 | 1 | 4 | 1 | 3 | 5 | 4 | 60% | 6 |  | 2369.828
323 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2025-10-31 | 2025 | 298 | 2 | 2025-01-06 | high | low | med | high | high | 450000 | 422239 | 452847 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 172.7549 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 4 | 3 | 3 | 2 | 3 | 5 | 1 | 2 | 60% | 6 | 1 | 2 | 1 | 2 | 3 | 3 | 40% | 4 |  | 3138.866
324 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Montreal | 2025-12-31 | 2025 | 200 | 8 | 2025-06-14 | high | low | med | high | high | 500000 | 949928 | 991050 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 59.9299 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | Yes | Yes | no | no | no | Yes | no | Yes | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 28.89% | 3 | 3 | 1 | 1 | 2 | 5 | 1 | 43.33% | 5 |  | 3138.866
325 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Ottawa | 2026-03-31 | 2026 | 267 | 8 | 2025-07-07 | med | high | med | high | high | 450000 | 929329 | 985745 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 900000 | 24.4952 | CAPITAL | No | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 3 | 5 | 4 | 1 | 1 | 4 | 1 | 2 | 5 | 57.78% | 6 | 4 | 5 | 1 | 3 | 4 | 4 | 70% | 7 |  | 14928.99
326 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2025-12-31 | 2025 | 120 | 4 | 2025-09-02 | high | high | med | med | med | 1500000 | 1517309 | 1577293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 1200000 | 150000 | 0 | 1500000 | 56.1178 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  |  | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | no | 3 | 4 | 2 | 2 | 1 | 2 | 3 | 3 | 4 | 53.33% | 6 | 5 | 1 | 1 | 2 | 3 | 3 | 50% | 5 |  | 4785
328 | L2 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Quebec City | 2025-07-31 | 2025 | 158 | 8 | 2025-02-23 | high | med | low | low | low | 2262383 | 2018438 | 2390176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226238.3 | 1809906.4 | 226238.3 | 0 | 2262383 | 110.1232 | CAPITAL | Yes | Unit outage |  | X | X | X |  | no | no | no | no | no | Yes | no | Yes | no | 2 | 4 | 2 | 1 | 1 | 4 | 2 | 3 | 5 | 53.33% | 6 | 5 | 1 | 1 | 4 | 2 | 4 | 56.67% | 6 |  | 211.3988
329 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2025-03-31 | 2025 | 148 | 4 | 2024-11-03 | med | med | low | low | med | 750000 | 844261 | 865990 | 0 | 75000 | 600000 | 75000 | 0 | 0 | 0 | 75000 | 600000 | 75000 | 0 | 0 | 1500000 | 55.7589 | CAPITAL | Yes | Unit outage |  |  | X |  |  | Yes | Yes | no | no | no | no | no | Yes | Yes | 5 | 4 | 1 | 2 | 2 | 5 | 1 | 2 | 2 | 53.33% | 6 | 3 | 3 | 1 | 4 | 3 | 4 | 60% | 6 |  | 477.3811
330 | L3 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Ottawa | 2029-07-31 | 2029 | 265 | 8 | 2028-11-08 | med | low | high | low | low | 785672 | 787730 | 801700 | 78567.2 | 628537.6 | 78567.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785672 | 210.2277 | CAPITAL | Yes | Unit outage | X |  |  |  | X | Yes | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 5 | 2 | 4 | 5 | 4 | 4 | 1 | 1 | 3 | 64.44% | 7 | 2 | 5 | 1 | 5 | 2 | 1 | 53.33% | 6 |  | 6993.546
330 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2025-03-31 | 2025 | 70 | 4 | 2025-01-20 | low | med | med | high | high | 2850000 | 2954019 | 2922819 | 285000 | 2280000 | 285000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850000 | 148.0887 | CAPITAL | Yes | Unit outage |  | X | X | X | X | Yes | Yes | no | Yes | Yes | Yes | no | no | no | 5 | 1 | 4 | 5 | 1 | 3 | 1 | 4 | 3 | 60% | 6 | 2 | 2 | 1 | 4 | 5 | 1 | 50% | 5 |  | 5347.325
331 | L3 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Regina | 2027-10-31 | 2027 | 175 | 4 | 2027-05-09 | low | high | low | med | med | 1901410 | 1806853 | 1810108 | 0 | 0 | 0 | 0 | 190141 | 1521128 | 190141 | 0 | 0 | 0 | 0 | 0 | 1901410 | 68.9019 | CAPITAL | Yes | Unit outage |  | X | X |  | X | Yes | Yes | Yes | Yes | Yes | no | no | Yes | no | 3 | 5 | 1 | 2 | 3 | 2 | 4 | 3 | 5 | 62.22% | 7 | 3 | 4 | 1 | 3 | 1 | 4 | 53.33% | 6 |  | 1117.205
331 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Edmonton | 2026-03-31 | 2026 | 151 | 8 | 2025-10-31 | med | med | low | high | med | 550000 | 583881 | 573876 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 440000 | 55000 | 0 | 0 | 0 | 550000 | 11.6418 | EXPENSE | No | Pipeline segment |  | X |  | X | X | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 2 | 5 | 2 | 3 | 4 | 5 | 5 | 1 | 1 | 62.22% | 7 | 3 | 2 | 1 | 4 | 4 | 3 | 56.67% | 6 |  | 4542.743
332 | L1 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | North Bay | 2028-12-31 | 2028 | 317 | 7 | 2028-02-18 | high | low | med | high | low | 1900000 | 2185889 | 2217656 | 0 | 190000 | 1520000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 102.6811 | CAPITAL | Yes | Unit outage | X |  | X |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 4 | 1 | 1 | 4 | 3 | 2 | 3 | 5 | 2 | 55.56% | 6 | 3 | 4 | 1 | 1 | 1 | 5 | 50% | 5 |  | 9580.877
332 | L1 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Saskatoon | 2025-07-31 | 2025 | 122 | 1 | 2025-03-31 | low | low | high | med | med | 500000 | 528341 | 545697 | 0 | 0 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 500000 | 8.6875 | CAPITAL | No | Derate/low flow Pipe segment |  | X |  | X | X | Yes | Yes | no | no | no | Yes | no | Yes | Yes | 3 | 2 | 2 | 4 | 1 | 4 | 4 | 4 | 4 | 62.22% | 7 | 5 | 3 | 1 | 5 | 4 | 5 | 76.67% | 8 |  | 1486.701
333 | L3 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Montreal | 2026-10-31 | 2026 | 61 | 4 | 2026-08-31 | low | high | med | low | low | 1373131 | 1565762 | 1690696 | 137313.1 | 1098504.8 | 137313.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373131 | 21.1703 | CAPITAL | Yes | Unit outage | X |  | X |  | X | Yes | no | no | Yes | no | no | no | Yes | no | 2 | 2 | 2 | 2 | 3 | 1 | 5 | 1 | 2 | 44.44% | 5 | 3 | 3 | 5 | 2 | 2 | 5 | 66.67% | 7 |  | 18.4662
333 | L3 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Edmonton | 2025-07-31 | 2025 | 266 | 4 | 2024-11-07 | high | med | high | high | high | 1638449 | 1676663 | 1652332 | 0 | 0 | 0 | 163844.9 | 1310759.2 | 163844.9 | 0 | 0 | 0 | 0 | 0 | 0 | 1638449 | 39.814 | CAPITAL | Yes | Unit outage | [5 empty] | no | no | Yes | no | no | no | no | Yes | Yes | 4 | 5 | 3 | 4 | 1 | 5 | 3 | 5 | 3 | 73.33% | 8 | 4 | 1 | 1 | 3 | 3 | 2 | 46.67% | 5 |  | 2679.519
334 | L3 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Calgary | 2027-12-31 | 2027 | 49 | 5 | 2027-11-12 | high | med | high | low | low | 600000 | 710728 | 716277 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 600000 | 131.8611 | CAPITAL | Yes | Pipeline segment | X |  |  |  |  | no | no | no | Yes | no | no | Yes | Yes | Yes | 1 | 5 | 3 | 2 | 3 | 4 | 2 | 1 | 1 | 48.89% | 5 | 2 | 2 | 1 | 5 | 3 | 3 | 53.33% | 6 |  | 8429.71
335 | L2 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Ottawa | 2027-10-31 | 2027 | 209 | 8 | 2027-04-05 | med | med | med | med | med | 828894 | 814607 | 881165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82889.4 | 663115.2 | 82889.4 | 0 | 0 | 828894 | 106.3061 | CAPITAL | Yes | Unit outage |  | X | X | X |  | no | Yes | Yes | no | Yes | Yes | Yes | no | Yes | 1 | 1 | 1 | 1 | 4 | 5 | 4 | 2 | 3 | 48.89% | 5 | 2 | 4 | 1 | 4 | 1 | 1 | 43.33% | 5 |  | 1685.9635
334 | L2 | FACILITY | ELECTRICAL |  | ARC FLASH | Saskatoon | 2025-10-31 | 2025 | 137 | 1 | 2025-06-16 | med | high | med | low | low | 200000 | 236500 | 271402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 160000 | 20000 | 0 | 0 | 200000 | 32.9312 | EXPENSE | No | Station outage | [5 empty] | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 5 | 4 | 4 | 5 | 2 | 1 | 2 | 1 | 4 | 62.22% | 7 | 5 | 4 | 1 | 4 | 3 | 1 | 60% | 6 |  | 2679.519
335 | L1 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Regina | 2028-03-31 | 2028 | 285 | 4 | 2027-06-20 | low | low | med | low | low | 600000 | 820865 | 995427 | 0 | 0 | 0 | 0 | 0 | 60000 | 480000 | 60000 | 0 | 0 | 0 | 0 | 600000 | 2608.6464 | CAPITAL | Yes | Derate/low flow Pipe segment | X |  | X | X |  | no | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 2 | 5 | 1 | 3 | 4 | 1 | 2 | 1 | 2 | 46.67% | 5 | 2 | 2 | 1 | 5 | 3 | 2 | 50% | 5 |  | 17599.38
335 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Winnipeg | 2025-07-31 | 2025 | 309 | 4 | 2024-09-25 | high | med | med | med | med | 2561570 | 2666593 | 2738152 | 0 | 256157 | 2049256 | 256157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2561570 | 79.2889 | CAPITAL | Yes | Unit outage |  |  |  |  | X | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 35.56% | 4 | 1 | 3 | 1 | 1 | 2 | 5 | 43.33% | 5 |  | 1072.766
336 | L2 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Winnipeg | 2026-07-31 | 2026 | 309 | 4 | 2025-09-25 | high | med | med | med | med | 2561570 | 2666593 | 2738152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256157 | 2049256 | 256157 | 0 | 0 | 2561570 | 79.2889 | CAPITAL | Yes | Unit outage |  |  |  |  | X | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 1 | 3 | 2 | 1 | 4 | 3 | 4 | 2 | 1 | 46.67% | 5 | 2 | 1 | 5 | 3 | 5 | 2 | 60% | 6 |  | 172.2548
337 | L2 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Winnipeg | 2028-10-31 | 2028 | 36 | 8 | 2028-09-25 | med | low | med | high | low | 250000 | 410869 | 416879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 200000 | 25000 | 0 | 250000 | 692.039 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X |  | no | Yes | Yes | Yes | Yes | Yes | no | no | no | 1 | 3 | 3 | 3 | 5 | 4 | 4 | 1 | 5 | 64.44% | 7 | 5 | 4 | 1 | 2 | 1 | 5 | 60% | 6 |  | 14928.9944
336 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2025-12-31 | 2025 | 267 | 15 | 2025-04-08 | low | med | low | low | high | 500000 | 554230 | 580197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 500000 | 6.3304 | CAPITAL | No | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | no | no | no | 4 | 3 | 3 | 4 | 2 | 1 | 5 | 2 | 2 | 57.78% | 6 | 5 | 5 | 5 | 2 | 1 | 4 | 73.33% | 8 |  | 3333.134
337 | L2 | FACILITY | ELECTRICAL |  | ARC FLASH | Toronto | 2027-10-31 | 2027 | 278 | 2 | 2027-01-26 | low | high | med | med | high | 200000 | 298120 | 287115 | 0 | 0 | 0 | 0 | 60000 | 100000 | 40000 | 0 | 0 | 0 | 0 | 0 | 200000 | 92.8794 | EXPENSE | No | Unit outage | X |  | X |  |  | Yes | Yes | no | no | Yes | no | no | no | Yes | 4 | 1 | 2 | 5 | 1 | 4 | 3 | 1 | 5 | 57.78% | 6 | 1 | 1 | 1 | 1 | 3 | 5 | 40% | 4 |  | 7007.921
338 | L2 | FACILITY | ELECTRICAL |  | AUX GEN | Ottawa | 2026-07-31 | 2026 | 125 | 5 | 2026-03-28 | high | med | med | high | low | 1200000 | 1158484 | 1172324 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 960000 | 120000 | 0 | 0 | 0 | 1200000 | 170.5508 | CAPITAL | Yes | Unit outage | X | X | X |  | X | Yes | no | Yes | no | no | Yes | Yes | no | no | 4 | 3 | 4 | 5 | 2 | 5 | 3 | 2 | 5 | 73.33% | 8 | 2 | 1 | 1 | 4 | 1 | 3 | 40% | 4 |  | 4314.1949
339 | L1 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Edmonton | 2025-03-31 | 2025 | 348 | 5 | 2024-04-17 | med | med | med | med | med | 600000 | 676586 | 653711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 360000 | 60000 | 0 | 0 | 600000 | 3.5349 | EXPENSE | No | pipeline segment outage |  | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | Yes | no | 4 | 4 | 3 | 2 | 4 | 2 | 1 | 5 | 2 | 60% | 6 | 5 | 5 | 5 | 2 | 2 | 2 | 70% | 7 |  | 2480.625
337 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Edmonton | 2025-12-31 | 2025 | 21 | 4 | 2025-12-10 | high | med | low | low | high | 1533520 | 1146998 | 1139804 | 153352 | 153352 | 1226816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1533520 | 74.326 | CAPITAL | Yes | Unit outage |  |  |  | X |  | no | Yes | Yes | no | Yes | no | Yes | no | Yes | 5 | 1 | 3 | 4 | 2 | 2 | 5 | 1 | 4 | 60% | 6 | 2 | 1 | 1 | 3 | 4 | 5 | 53.33% | 6 |  | 1117.205
338 | L2 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Saskatoon | 2026-12-31 | 2026 | 80 | 5 | 2026-10-12 | low | high | med | low | low | 600000 | 643838 | 656534 | 0 | 180000 | 360000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 37.951 | CAPITAL | Yes | Derate/low flow Pipe segment |  | X |  | X | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 2 | 4 | 73.33% | 8 | 1 | 3 | 1 | 2 | 5 | 2 | 46.67% | 5 |  | 1875
339 | L1 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Regina | 2026-07-31 | 2026 | 301 | 4 | 2025-10-03 | low | low | low | high | high | 1382799 | 1819616 | 1863930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414839.7 | 829679.4 | 138279.9 | 0 | 1382799 | 76.9403 | CAPITAL | Yes | Unit outage |  | X | X |  |  | Yes | Yes | Yes | no | no | no | Yes | no | Yes | 5 | 2 | 5 | 1 | 3 | 5 | 3 | 2 | 4 | 66.67% | 7 | 2 | 4 | 1 | 4 | 3 | 1 | 50% | 5 |  | 4542.743
340 | L1 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | North Bay | 2030-12-31 | 2030 | 43 | 4 | 2030-11-18 | low | high | med | low | high | 1171635 | 1299309 | 1278867 | 0 | 0 | 0 | 117163.5 | 937308 | 117163.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1171635 | 109.1523 | CAPITAL | Yes | Unit outage | X |  |  | X | X | no | Yes | no | Yes | no | no | Yes | Yes | no | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 35.56% | 4 | 2 | 3 | 1 | 1 | 5 | 5 | 56.67% | 6 |  | 48755
338 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Saskatoon | 2027-12-31 | 2025 | 150 | 10 | 2027-08-03 | low | low | med | high | low | 450000 | 562796 | 571191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 107.4224 | CAPITAL | No | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | no | no | no | no | Yes | Yes | 4 | 3 | 1 | 4 | 2 | 1 | 1 | 2 | 5 | 51.11% | 6 | 3 | 3 | 1 | 2 | 1 | 5 | 50% | 5 |  | 1117.205
339 | L3 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Calgary | 2027-12-31 | 2027 | 180 | 5 | 2027-07-04 | med | med | high | high | high | 500000 | 666612 | 617199 | 0 | 0 | 0 | 0 | 400000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 120.2789 | CAPITAL | No | Derate/low flow Pipe segment |  |  |  |  | X | no | no | no | no | Yes | no | Yes | Yes | Yes | 4 | 1 | 4 | 1 | 2 | 4 | 2 | 5 | 5 | 62.22% | 7 | 4 | 1 | 1 | 5 | 4 | 1 | 53.33% | 6 |  | 6487.5816
340 | L2 | FACILITY | MEASUREMENT |  | FLOW COMPUTER | Winnipeg | 2026-07-31 | 2026 | 80 | 4 | 2026-05-12 | high | high | low | high | low | 600000 | 715110 | 717320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 360000 | 60000 | 0 | 600000 | 200.2629 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 4 | 1 | 2 | 5 | 4 | 1 | 1 | 4 | 4 | 57.78% | 6 | 1 | 4 | 1 | 3 | 5 | 5 | 63.33% | 7 |  | 172.2548
339 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Edmonton | 2026-07-31 | 2026 | 274 | 10 | 2025-10-30 | med | med | low | med | low | 550000 | 480203 | 490541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 440000 | 55000 | 0 | 550000 | 101.2735 | EXPENSE | Yes | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 2 | 4 | 1 | 2 | 1 | 5 | 3 | 1 | 5 | 53.33% | 6 | 2 | 5 | 1 | 1 | 3 | 1 | 43.33% | 5 |  | 45.3112
340 | L2 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Quebec City | 2028-12-31 | 2028 | 267 | 4 | 2028-04-08 | low | med | med | high | high | 1820507 | 1988450 | 1950473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546152.1 | 1092304.2 | 182050.7 | 1820507 | 45.6177 | CAPITAL | Yes | Unit outage |  |  |  | X | X | Yes | no | no | no | Yes | no | no | no | Yes | 2 | 2 | 2 | 2 | 1 | 2 | 4 | 2 | 4 | 46.67% | 5 | 1 | 1 | 5 | 4 | 5 | 2 | 60% | 6 |  | 853.1382
341 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | WINNIPEG | 2026-07-31 | 2026 | 120 | 10 | 2026-04-02 | med | low | med | med | med | 450000 | 516716 | 510460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 450000 | 30.4676 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | Yes | Yes | Yes | no | Yes | no | Yes | no | Yes | 5 | 2 | 3 | 1 | 3 | 1 | 4 | 5 | 1 | 55.56% | 6 | 4 | 1 | 1 | 1 | 4 | 3 | 46.67% | 5 |  | 203.1281
340 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2025-03-31 | 2025 | 170 | 4 | 2024-10-12 | high | low | high | med | high | 400000 | 488222 | 477827 | 0 | 0 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 202.8834 | CAPITAL | Yes | Pipeline segment |  | X |  | X | X | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 1 | 2 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 35.56% | 4 | 4 | 5 | 5 | 4 | 2 | 1 | 70% | 7 |  | 1300.71
341 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Calgary | 2029-12-31 | 2029 | 331 | 5 | 2029-02-03 | high | med | high | high | low | 450000 | 476437 | 473514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 98.0993 | CAPITAL | Yes | Derate/low flow Pipe segment | X | X | X | X | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 4 | 3 | 4 | 5 | 1 | 3 | 4 | 1 | 1 | 57.78% | 6 | 5 | 4 | 1 | 4 | 3 | 4 | 70% | 7 |  | 22170.3266
342 | L3 | FACILITY | MECHANICAL |  | PT MINOR OH | Winnipeg | 2025-10-31 | 2025 | 80 | 1 | 2025-08-12 | low | med | low | med | med | 45961 | 50735 | 45396 | 0 | 0 | 4596.1 | 36768.8 | 4596.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45961 | 77.6998 | EXPENSE | No | Unit outage |  | X |  |  | X | Yes | Yes | no | no | Yes | Yes | no | Yes | no | 5 | 5 | 3 | 4 | 4 | 5 | 4 | 5 | 3 | 84.44% | 9 | 2 | 5 | 1 | 4 | 5 | 3 | 66.67% | 7 |  | 5347.325
343 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Toronto | 2028-12-31 | 2028 | 150 | 10 | 2028-08-03 | med | high | high | med | high | 450000 | 821878 | 824096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 99.9422 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | Yes | 4 | 3 | 2 | 4 | 4 | 3 | 5 | 1 | 1 | 60% | 6 | 1 | 3 | 5 | 4 | 3 | 4 | 66.67% | 7 |  | 4101.034
341 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | WINNIPEG | 2026-12-31 | 2026 | 142 | 15 | 2026-08-11 | med | med | high | med | low | 450000 | 481653 | 480764 | 0 | 0 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 450000 | 90.3714 | CAPITAL | No | Pipeline segment | X | X | X |  |  | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 4 | 2 | 3 | 5 | 1 | 3 | 1 | 5 | 1 | 55.56% | 6 | 3 | 2 | 1 | 5 | 1 | 3 | 50% | 5 |  | 263.7275
342 | L3 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Saskatoon | 2027-10-31 | 2027 | 200 | 4 | 2027-04-14 | med | high | low | high | med | 1980019 | 1980030 | 1987975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594005.7 | 1188011.4 | 198001.9 | 1980019 | 68.0789 | CAPITAL | Yes | Unit outage | X | X | X |  | X | Yes | Yes | Yes | no | no | no | Yes | no | Yes | 5 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 3 | 46.67% | 5 | 3 | 4 | 1 | 5 | 4 | 5 | 73.33% | 8 |  | 267.7598
343 | L2 | FACILITY | AUTOMATION & CONTROLS |  | RACK REPLACE | Calgary | 2026-03-31 | 2026 | 40 | 0 | 2026-02-19 | low | high | high | high | med | 65062 | 68457 | 71500 | 0 | 0 | 0 | 0 | 0 | 6506.2 | 52049.6 | 6506.2 | 0 | 0 | 0 | 0 | 65062 | 13553.4352 | EXPENSE | No | NO | X |  |  | X | X | Yes | Yes | Yes | no | Yes | no | no | no | Yes | 1 | 4 | 1 | 1 | 2 | 5 | 5 | 2 | 2 | 51.11% | 6 | 4 | 4 | 1 | 1 | 2 | 4 | 53.33% | 6 |  | 5776.431
342 | L1 | FACILITY | ELECTRICAL |  | SWITCHGEAR | Ottawa | 2027-10-31 | 2027 | 253 | 2 | 2027-02-20 | high | med | high | low | high | 95000 | 128436 | 125458 | 28500 | 57000 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 | 17.7519 | CAPITAL | No | Station outage |  |  |  | X |  | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 4 | 37.78% | 4 | 4 | 2 | 5 | 4 | 1 | 4 | 66.67% | 7 |  | 18394.3
343 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Ottawa | 2028-10-31 | 2028 | 99 | 8 | 2028-07-24 | high | low | high | med | high | 450000 | 379319 | 375544 | 0 | 0 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 450000 | 35.2892 | CAPITAL | No | pipeline segment outage | X |  | X | X | X | Yes | Yes | Yes | no | no | Yes | no | no | no | 5 | 5 | 3 | 4 | 5 | 4 | 4 | 1 | 3 | 75.56% | 8 | 1 | 4 | 1 | 3 | 4 | 5 | 60% | 6 |  | 17599.3754
344 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Montreal | 2028-07-31 | 2028 | 200 | 5 | 2028-01-13 | low | high | med | low | low | 600000 | 851724 | 857404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 360000 | 60000 | 600000 | 116.0893 | CAPITAL | Yes | pipeline segment outage |  | X |  | X | X | no | no | no | no | Yes | Yes | no | Yes | Yes | 2 | 5 | 1 | 3 | 2 | 5 | 4 | 2 | 1 | 55.56% | 6 | 1 | 3 | 1 | 2 | 1 | 1 | 30% | 3 |  | 4101.0339
343 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | North Bay | 2025-12-31 | 2025 | 120 | 8 | 2025-09-02 | med | med | high | low | med | 250000 | 200338 | 234729 | 0 | 0 | 0 | 0 | 0 | 25000 | 200000 | 25000 | 0 | 0 | 0 | 0 | 250000 | 167.215 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 5 | 3 | 2 | 5 | 5 | 5 | 2 | 4 | 80% | 8 | 1 | 5 | 5 | 5 | 4 | 5 | 83.33% | 9 |  | 14995.83
344 | L2 | FACILITY | MECHANICAL |  | TANK PROG | Edmonton | 2025-03-31 | 2025 | 25 | 4 | 2025-03-06 | low | high | med | high | high | 1100000 | 1174561 | 1183348 | 330000 | 660000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 311.0511 | EXPENSE | No | Unit outage | X | X | X | X | X | no | no | no | Yes | no | Yes | no | no | Yes | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 40% | 4 | 3 | 3 | 1 | 3 | 1 | 4 | 50% | 5 |  | 7007.9205
344 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2025-12-31 | 2025 | 100 | 4 | 2025-09-22 | high | low | high | med | high | 1500000 | 1450980 | 1458652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 1200000 | 150000 | 0 | 1500000 | 118.0594 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 5 | 4 | 4 | 4 | 2 | 5 | 5 | 1 | 5 | 77.78% | 8 | 5 | 1 | 1 | 3 | 3 | 4 | 56.67% | 6 |  | 76225.68
345 | L3 | FACILITY | MECHANICAL |  | TANK PROG | North Bay | 2027-07-31 | 2027 | 79 | 3 | 2027-05-13 | low | high | high | med | med | 1150304 | 1155846 | 1150070 | 0 | 0 | 0 | 345091.2 | 690182.4 | 115030.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1150304 | 465.7694 | EXPENSE | Yes | Unit outage |  | X |  |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 4 | 2 | 3 | 3 | 3 | 4 | 1 | 4 | 1 | 55.56% | 6 | 5 | 1 | 1 | 3 | 3 | 2 | 50% | 5 |  | 382.7885
345 | L3 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Quebec City | 2026-10-31 | 2026 | 250 | 8 | 2026-02-23 | med | low | med | high | high | 4585000 | 4680012 | 4700046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458500 | 3668000 | 458500 | 0 | 4585000 | 91.5834 | CAPITAL | Yes | Station outage |  |  | X |  |  | no | Yes | Yes | no | Yes | no | no | no | Yes | 4 | 4 | 1 | 1 | 4 | 2 | 1 | 2 | 2 | 46.67% | 5 | 3 | 3 | 1 | 2 | 5 | 3 | 56.67% | 6 |  | 16.9273
346 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2025-07-31 | 2025 | 100 | 4 | 2025-04-22 | high | low | low | low | med | 750000 | 710189 | 719044 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 61.5579 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  | X | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 2 | 3 | 5 | 1 | 2 | 3 | 2 | 5 | 57.78% | 6 | 5 | 1 | 1 | 2 | 2 | 4 | 50% | 5 |  | 16.9273
347 | L2 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Calgary | 2025-07-31 | 2025 | 138 | 2 | 2025-03-15 | med | med | low | high | low | 279976 | 354614 | 246324 | 27997.6 | 0 | 0 | 0 | 0 | 0 | 195983.2 | 55995.2 | 0 | 0 | 0 | 0 | 279976 | 87.9804 | EXPENSE | Yes | Unit outage | X |  |  | X | X | no | Yes | Yes | Yes | no | Yes | no | no | Yes | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 28.89% | 3 | 3 | 4 | 1 | 4 | 2 | 2 | 53.33% | 6 |  | 560.1412
348 | L3 | PIPE INTEGRITY | L&R |  | TETHER | Winnipeg | 2025-12-31 | 2025 | 259 | 7 | 2025-04-16 | med | low | low | med | low | 850000 | 892844 | 905260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 510000 | 85000 | 850000 | 1023.831 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | Yes | no | Yes | no | Yes | no | 2 | 4 | 2 | 3 | 5 | 2 | 1 | 2 | 5 | 57.78% | 6 | 4 | 5 | 1 | 2 | 1 | 2 | 50% | 5 |  | 560.1412
349 | L1 | PIPE INTEGRITY | L&R |  | TETHER | Quebec City | 2025-12-31 | 2025 | 329 | 4 | 2025-02-05 | low | low | low | high | high | 450000 | 447194 | 557595 | 0 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 450000 | 159.9953 | EXPENSE | Yes | Unit outage | X | X |  | X |  | no | Yes | no | Yes | Yes | Yes | no | no | Yes | 2 | 4 | 1 | 1 | 3 | 3 | 3 | 2 | 4 | 51.11% | 6 | 5 | 1 | 1 | 1 | 4 | 3 | 50% | 5 |  | 10535.75
350 | L1 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Saskatoon | 2025-03-31 | 2025 | 160 | 4 | 2024-10-22 | med | high | low | high | high | 6620000 | 6515868 | 6632189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1986000 | 3972000 | 662000 | 6620000 | 33.0673 | CAPITAL | No | Station outage |  | X |  | X |  | no | no | Yes | Yes | no | Yes | no | Yes | Yes | 2 | 1 | 1 | 1 | 2 | 5 | 3 | 3 | 5 | 51.11% | 6 | 4 | 1 | 1 | 3 | 4 | 5 | 60% | 6 |  | 16059.78
351 | L3 | PIPE INTEGRITY | L&R |  | TETHER | North Bay | 2025-03-31 | 2025 | 65 | 8 | 2025-01-25 | med | med | med | low | high | 850000 | 792844 | 805260 | 0 | 0 | 0 | 0 | 255000 | 510000 | 85000 | 0 | 0 | 0 | 0 | 0 | 850000 | 190.1713 | EXPENSE | No | Pipeline segment |  |  |  | X | X | Yes | no | no | no | no | Yes | no | no | no | 2 | 5 | 2 | 1 | 2 | 1 | 1 | 1 | 5 | 44.44% | 5 | 1 | 5 | 1 | 1 | 2 | 3 | 43.33% | 5 |  | 10182.17
352 | L2 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Montreal | 2025-07-31 | 2025 | 44 | 8 | 2025-06-17 | med | med | high | low | high | 3500000 | 3705220 | 3754725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 2800000 | 350000 | 3500000 | 42.5944 | CAPITAL | No | Station outage | X | X | X | X |  | Yes | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 3 | 1 | 5 | 2 | 5 | 1 | 4 | 1 | 55.56% | 6 | 4 | 1 | 1 | 4 | 2 | 5 | 56.67% | 6 |  | 2310.573
353 | L3 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Quebec City | 2027-10-31 | 2027 | 53 | 8 | 2027-09-08 | med | low | med | high | high | 4585000 | 4680012 | 4700046 | 0 | 0 | 0 | 0 | 0 | 0 | 1375500 | 2751000 | 458500 | 0 | 0 | 0 | 4585000 | 91.5834 | CAPITAL | Yes | Station outage |  |  | X |  |  | no | Yes | Yes | no | Yes | no | no | no | Yes | 5 | 4 | 2 | 3 | 2 | 5 | 2 | 1 | 3 | 60% | 6 | 5 | 1 | 1 | 1 | 5 | 3 | 53.33% | 6 |  | 458
353 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2025-07-31 | 2025 | 85 | 4 | 2025-05-07 | med | high | low | low | high | 400000 | 405834 | 452505 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 400000 | 98.3964 | EXPENSE | No | pipeline segment outage |  |  |  |  | X | no | Yes | Yes | Yes | no | no | no | Yes | no | 3 | 5 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 53.33% | 6 | 5 | 1 | 1 | 2 | 4 | 3 | 53.33% | 6 |  | 2369.828
354 | L3 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Winnipeg | 2027-12-31 | 2027 | 259 | 4 | 2027-04-16 | med | low | low | med | low | 2500500 | 2557663 | 2756617 | 0 | 0 | 0 | 0 | 750150 | 1500300 | 250050 | 0 | 0 | 0 | 0 | 0 | 2500500 | 1023.831 | CAPITAL | No | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | Yes | no | Yes | no | Yes | no | 4 | 1 | 2 | 2 | 3 | 4 | 4 | 3 | 3 | 57.78% | 6 | 5 | 3 | 1 | 2 | 3 | 3 | 56.67% | 6 |  | 20000
355 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Regina | 2025-03-31 | 2025 | 31 | 4 | 2025-02-28 | high | med | low | high | low | 1587641 | 1549493 | 1648557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158764.1 | 635056.4 | 793820.5 | 0 | 0 | 1587641 | 78.6423 | CAPITAL | Yes | Unit outage |  |  |  |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | no | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 28.89% | 3 | 3 | 1 | 1 | 3 | 4 | 1 | 43.33% | 5 |  | 16593.69
356 | L1 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Saskatoon | 2028-03-31 | 2028 | 160 | 4 | 2027-10-23 | med | high | low | high | high | 6620000 | 6005868 | 6132189 | 0 | 1986000 | 3972000 | 662000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6620000 | 33.0673 | CAPITAL | No | Station outage |  | X |  | X |  | no | no | Yes | Yes | no | Yes | no | Yes | Yes | 3 | 5 | 2 | 3 | 3 | 2 | 4 | 5 | 5 | 71.11% | 8 | 1 | 4 | 1 | 2 | 1 | 1 | 33.33% | 4 |  | 1875
356 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | North Bay | 2025-07-31 | 2025 | 100 | 8 | 2025-04-22 | low | high | low | high | high | 350000 | 327934 | 382673 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 350000 | 32.9463 | CAPITAL | No | pipeline segment outage | X | X |  |  |  | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 2 | 4 | 46.67% | 5 | 5 | 1 | 1 | 2 | 3 | 5 | 56.67% | 6 |  | 2480.625
357 | L2 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Montreal | 2027-07-31 | 2027 | 44 | 8 | 2027-06-17 | med | med | high | low | high | 3500000 | 3561440 | 3450325 | 0 | 0 | 350000 | 2800000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 42.5944 | CAPITAL | No | Station outage | X | X | X | X |  | Yes | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 5 | 2 | 5 | 2 | 2 | 1 | 1 | 3 | 53.33% | 6 | 5 | 2 | 1 | 5 | 3 | 5 | 70% | 7 |  | 7718.869
357 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2025-03-31 | 2025 | 85 | 7 | 2025-01-05 | med | low | high | high | high | 1900000 | 1977581 | 1989278 | 190000 | 760000 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 94.5144 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | no | no | Yes | Yes | Yes | Yes | Yes | no | 3 | 2 | 4 | 3 | 4 | 2 | 4 | 1 | 1 | 53.33% | 6 | 2 | 4 | 1 | 5 | 5 | 2 | 63.33% | 7 |  | 2480.625
358 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | North Bay | 2025-12-31 | 2025 | 150 | 4 | 2025-08-03 | med | high | low | low | med | 250000 | 252651 | 244871 | 75000 | 150000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 56.4922 | EXPENSE | No | NO |  |  | X | X |  | no | Yes | no | Yes | no | no | Yes | no | no | 3 | 1 | 1 | 3 | 3 | 1 | 4 | 1 | 4 | 46.67% | 5 | 3 | 5 | 1 | 5 | 2 | 4 | 66.67% | 7 |  | 31873.29
359 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2025-12-31 | 2025 | 91 | 4 | 2025-10-01 | high | low | high | high | high | 1321805 | 1359803 | 1610853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396541.5 | 793083 | 132180.5 | 0 | 1321805 | 121.8677 | CAPITAL | Yes | Unit outage |  |  |  |  | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 4 | 4 | 3 | 4 | 1 | 2 | 5 | 2 | 2 | 60% | 6 | 1 | 2 | 1 | 1 | 1 | 2 | 26.67% | 3 |  | 728.1385
360 | L2 | FACILITY | ELECTRICAL |  | REPAIR | Edmonton | 2025-07-31 | 2025 | 328 | 1 | 2024-09-06 | med | high | low | med | med | 11149 | 11184 | 16043 | 0 | 0 | 1114.9 | 8919.2 | 1114.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11149 | 17454.8659 | EXPENSE | No | Unit outage |  |  | X | X | X | Yes | Yes | no | Yes | no | Yes | no | no | Yes | 2 | 3 | 2 | 2 | 1 | 4 | 2 | 1 | 5 | 48.89% | 5 | 1 | 1 | 1 | 2 | 3 | 1 | 30% | 3 |  | 495.1227
361 | L2 | FACILITY | ELECTRICAL |  | REPAIR | Calgary | 2027-12-31 | 2027 | 84 | 1 | 2027-10-08 | med | low | high | high | med | 84459 | 82153 | 84314 | 25337.7 | 50675.4 | 8445.9 | 0 | 0 | 0 | 0 | 0 | 25337.7 | 50675.4 | 8445.9 | 0 | 168918 | 3472.2193 | EXPENSE | No | Unit outage | X |  |  |  |  | no | no | no | Yes | no | no | no | Yes | Yes | 5 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 44.44% | 5 | 3 | 5 | 5 | 1 | 5 | 3 | 73.33% | 8 |  | 48885
361 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Winnipeg | 2025-10-31 | 2025 | 150 | 4 | 2025-06-03 | med | low | med | high | low | 250000 | 260869 | 306879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 250000 | 692.039 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X |  | no | Yes | Yes | Yes | Yes | Yes | no | no | no | 3 | 1 | 1 | 4 | 3 | 5 | 3 | 1 | 1 | 48.89% | 5 | 2 | 4 | 1 | 1 | 1 | 1 | 33.33% | 4 |  | 5521.373
362 | L1 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Toronto | 2025-12-31 | 2025 | 75 | 4 | 2025-10-17 | high | high | med | med | med | 850000 | 850944 | 820000 | 0 | 85000 | 680000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 24.4354 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X |  | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 1 | 3 | 3 | 4 | 5 | 3 | 2 | 4 | 60% | 6 | 4 | 1 | 1 | 1 | 4 | 3 | 46.67% | 5 |  | 3220.812
363 | L3 | FACILITY | ELECTRICAL |  | REPAIR | WINNIPEG | 2027-12-31 | 2027 | 143 | 1 | 2027-08-10 | low | high | high | med | med | 95000 | 94555 | 98500 | 28500 | 57000 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 | 244.17 | EXPENSE | Yes | Unit outage |  | X | X |  |  | Yes | Yes | no | no | no | no | no | no | no | 2 | 5 | 1 | 2 | 5 | 4 | 4 | 3 | 4 | 66.67% | 7 | 4 | 4 | 1 | 3 | 4 | 3 | 63.33% | 7 |  | 2310.573
363 | L3 | FACILITY | SCADA |  | UPDATE | Saskatoon | 2025-10-31 | 2025 | 60 | 1 | 2025-09-01 | low | low | high | high | low | 302123 | 363184 | 376832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90636.9 | 181273.8 | 30212.3 | 302123 | 25.1853 | EXPENSE | Yes | Unit outage | X | X |  | X |  | no | Yes | Yes | no | Yes | no | no | Yes | no | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 2 | 2 | 37.78% | 4 | 2 | 3 | 1 | 1 | 1 | 5 | 43.33% | 5 |  | 6039.002
364 | L3 | FACILITY | ELECTRICAL |  | REPAIR | Ottawa | 2026-12-31 | 2026 | 361 | 2 | 2026-01-04 | high | low | high | high | high | 431398 | 442012 | 396443 | 0 | 129419.4 | 258838.8 | 43139.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431398 | 91.8973 | EXPENSE | No | Unit outage |  |  |  |  | X | no | no | no | no | Yes | Yes | Yes | no | Yes | 5 | 2 | 1 | 3 | 1 | 4 | 1 | 1 | 1 | 42.22% | 5 | 1 | 5 | 1 | 3 | 3 | 3 | 53.33% | 6 |  | 278.7236
364 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Winnipeg | 2025-12-31 | 2025 | 249 | 4 | 2025-04-26 | high | high | high | low | high | 1191808 | 1997991 | 1907322 | 357542.4 | 715084.8 | 119180.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1191808 | 134.8642 | CAPITAL | Yes | Unit outage | X | X |  |  |  | no | Yes | Yes | Yes | no | no | no | Yes | no | 2 | 4 | 3 | 2 | 1 | 5 | 5 | 1 | 4 | 60% | 6 | 1 | 2 | 1 | 1 | 5 | 4 | 46.67% | 5 |  | 13659.19
365 | L2 | FACILITY | ELECTRICAL |  | REPAIR | North Bay | 2028-12-31 | 2028 | 260 | 1 | 2028-04-15 | low | med | med | high | low | 72155 | 105817 | 122539 | 0 | 0 | 0 | 0 | 7215.5 | 57724 | 7215.5 | 0 | 0 | 0 | 0 | 0 | 72155 | 447.0085 | EXPENSE | No | Unit outage | X |  | X | X | X | Yes | Yes | Yes | no | no | no | no | no | no | 3 | 3 | 2 | 3 | 5 | 2 | 1 | 3 | 2 | 53.33% | 6 | 3 | 3 | 1 | 4 | 4 | 5 | 66.67% | 7 |  | 2679.5194
365 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Toronto | 2025-03-31 | 2025 | 200 | 15 | 2024-09-12 | low | high | med | high | high | 500000 | 530563 | 545236 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 60.5912 | CAPITAL | No | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 4 | 3 | 2 | 5 | 2 | 2 | 5 | 2 | 1 | 57.78% | 6 | 4 | 1 | 1 | 4 | 4 | 3 | 56.67% | 6 |  | 13659.19
366 | L2 | FACILITY | ELECTRICAL |  | REPAIR | Quebec City | 2028-12-31 | 2028 | 100 | 1 | 2028-09-22 | low | high | high | high | high | 169186 | 202725 | 248152 | 0 | 0 | 50755.8 | 101511.6 | 16918.6 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 569186 | 678.633 | EXPENSE | Yes | Unit outage | [5 empty] | no | no | no | Yes | Yes | Yes | no | no | Yes | 5 | 2 | 4 | 1 | 3 | 2 | 4 | 3 | 4 | 62.22% | 7 | 4 | 1 | 5 | 3 | 2 | 2 | 56.67% | 6 |  | 7110.094
366 | L3 | FACILITY | MECHANICAL |  | LUBE OIL | Winnipeg | 2025-12-31 | 2025 | 43 | 3 | 2025-11-18 | low | low | med | high | med | 210079 | 216658 | 176508 | 0 | 63023.7 | 126047.4 | 21007.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210079 | 540.6712 | EXPENSE | Yes | Unit outage |  | X | X | X | X | Yes | no | no | no | Yes | Yes | no | no | no | 5 | 1 | 1 | 3 | 2 | 5 | 1 | 5 | 3 | 57.78% | 6 | 1 | 2 | 1 | 3 | 1 | 2 | 33.33% | 4 |  | 2491.953
367 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Regina | 2025-07-31 | 2025 | 301 | 4 | 2024-10-03 | low | low | low | high | high | 1382799 | 1819616 | 1863930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414839.7 | 829679.4 | 138279.9 | 0 | 1382799 | 76.9403 | CAPITAL | Yes | Unit outage |  | X | X |  |  | Yes | Yes | Yes | no | no | no | Yes | no | Yes | 5 | 4 | 1 | 4 | 3 | 1 | 1 | 3 | 3 | 55.56% | 6 | 5 | 1 | 1 | 4 | 1 | 4 | 53.33% | 6 |  | 21537.84
368 | L2 | FACILITY | MECHANICAL |  | LUBE OIL | Quebec City | 2027-12-31 | 2027 | 90 | 4 | 2027-10-02 | high | med | low | med | med | 150000 | 340832 | 422706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 105000 | 15000 | 0 | 150000 | 208.588 | EXPENSE | No | Unit outage |  |  | X | X |  | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 28.89% | 3 | 5 | 4 | 5 | 1 | 5 | 5 | 83.33% | 9 |  | 4526
368 | L2 | FACILITY | MECHANICAL |  | INSTRUMENT AIR | Quebec City | 2025-12-31 | 2025 | 227 | 3 | 2025-05-18 | high | med | low | med | med | 300000 | 340832 | 422706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 300000 | 208.588 | EXPENSE | No | Unit outage |  |  | X | X |  | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 5 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 4 | 51.11% | 6 | 1 | 4 | 1 | 3 | 1 | 5 | 50% | 5 |  | 2973.402
369 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | Winnipeg | 2028-12-31 | 2028 | 224 | 5 | 2028-05-21 | med | med | med | low | low | 250000 | 276609 | 286072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 250000 | 96.9233 | EXPENSE | Yes | NO | [5 empty] | Yes | no | Yes | Yes | Yes | no | no | Yes | no | 3 | 5 | 1 | 1 | 5 | 1 | 5 | 4 | 3 | 62.22% | 7 | 2 | 1 | 1 | 5 | 1 | 5 | 50% | 5 |  | 19639.87
370 | L2 | FACILITY | ELECTRICAL |  | LIGHTING | North Bay | 2029-12-31 | 2025 | 260 | 1 | 2029-04-15 | low | med | med | high | low | 72000 | 85817 | 122539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 50400 | 7200 | 0 | 0 | 72000 | 447.0085 | EXPENSE | No | Unit outage | X |  | X | X | X | Yes | Yes | Yes | no | no | no | no | no | no | 3 | 1 | 2 | 5 | 5 | 3 | 1 | 4 | 1 | 55.56% | 6 | 3 | 2 | 1 | 3 | 2 | 3 | 46.67% | 5 |  | 5776.431
371 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Winnipeg | 2027-03-31 | 2027 | 232 | 8 | 2026-08-11 | high | low | high | med | med | 300000 | 469283 | 461267 | 30000 | 240000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 143.1483 | EXPENSE | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 3 | 1 | 4 | 5 | 1 | 2 | 2 | 5 | 5 | 62.22% | 7 | 2 | 3 | 1 | 5 | 4 | 5 | 66.67% | 7 |  | 2166.583
372 | L2 | FACILITY | MEASUREMENT |  | RTU REPLACMENT | Toronto | 2025-10-31 | 2025 | 360 | 1 | 2024-11-05 | med | low | high | low | low | 450000 | 427047 | 435720 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 149.6713 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X |  | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | 2 | 1 | 2 | 2 | 1 | 2 | 5 | 2 | 3 | 44.44% | 5 | 4 | 3 | 5 | 1 | 3 | 2 | 60% | 6 |  | 6487.582
373 | L1 | FACILITY | AUTOMATION & CONTROLS |  | HMI | Ottawa | 2025-12-31 | 2025 | 172 | 1 | 2025-07-12 | med | low | high | med | high | 260000 | 246638 | 246725 | 78000 | 156000 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000 | 670.8523 | EXPENSE | Yes | Station outage |  | X | X | X |  | Yes | no | no | Yes | Yes | Yes | no | no | no | 2 | 4 | 1 | 1 | 1 | 5 | 5 | 3 | 1 | 51.11% | 6 | 5 | 1 | 1 | 3 | 1 | 1 | 40% | 4 |  | 1083.35
374 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2025-10-31 | 2025 | 150 | 8 | 2025-06-03 | high | med | high | med | high | 300000 | 296541 | 294310 | 0 | 30000 | 240000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 86.2445 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | Yes | no | Yes | no | Yes | Yes | no | Yes | 2 | 4 | 1 | 2 | 1 | 2 | 2 | 2 | 5 | 46.67% | 5 | 1 | 5 | 1 | 5 | 4 | 5 | 70% | 7 |  | 1184.914
375 | L2 | FACILITY | MECHANICAL |  | HVAC COMP BLD | Ottawa | 2027-07-31 | 2027 | 14 | 1 | 2027-07-17 | med | low | high | med | high | 150000 | 168751 | 162561 | 0 | 0 | 0 | 0 | 15000 | 120000 | 15000 | 0 | 0 | 0 | 0 | 0 | 150000 | 2167.9338 | EXPENSE | Yes | Unit outage | X |  |  | X | X | no | no | Yes | Yes | Yes | Yes | no | Yes | Yes | 5 | 4 | 1 | 3 | 1 | 2 | 4 | 1 | 5 | 57.78% | 6 | 4 | 5 | 1 | 3 | 3 | 1 | 56.67% | 6 |  | 646
375 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2026-07-31 | 2026 | 200 | 7 | 2026-01-12 | med | low | high | med | high | 2000000 | 2451951 | 2464009 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 4000000 | 287.5273 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 4 | 44.44% | 5 | 1 | 3 | 1 | 1 | 2 | 5 | 43.33% | 5 |  | 1846.619
376 | L1 | FACILITY | MECHANICAL |  | HVAC REPAIR | Montreal | 2028-12-31 | 2028 | 154 | 1 | 2028-07-30 | med | low | low | high | high | 44130 | 32124 | 357621 | 0 | 0 | 0 | 0 | 13239 | 26478 | 4413 | 0 | 0 | 0 | 0 | 0 | 44130 | 515.144 | EXPENSE | Yes | Unit outage | X | X | X |  |  | Yes | no | Yes | no | Yes | Yes | Yes | no | no | 5 | 4 | 2 | 4 | 3 | 3 | 1 | 3 | 4 | 64.44% | 7 | 5 | 4 | 1 | 2 | 2 | 5 | 63.33% | 7 |  | 263.7275
376 | L2 | FACILITY | MEASUREMENT |  | RTU REPLACMENT | North Bay | 2025-12-31 | 2025 | 223 | 2 | 2025-05-22 | low | high | low | med | high | 500000 | 554000 | 558562 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 240.276 | CAPITAL | No | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | Yes | no | no | no | no | Yes | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 26.67% | 3 | 5 | 1 | 1 | 3 | 4 | 4 | 60% | 6 |  | 1846.619
377 | L3 | FACILITY | MECHANICAL |  | HVAC REPAIR | Montreal | 2026-10-31 | 2026 | 353 | 1 | 2025-11-12 | high | high | low | med | low | 35220 | 30060 | 31745 | 0 | 0 | 0 | 0 | 3522 | 28176 | 3522 | 0 | 0 | 0 | 0 | 0 | 35220 | 327.759 | EXPENSE | Yes | Unit outage |  |  |  | X | X | Yes | Yes | Yes | no | no | no | no | no | no | 4 | 3 | 1 | 1 | 2 | 4 | 5 | 1 | 3 | 53.33% | 6 | 1 | 2 | 5 | 2 | 2 | 4 | 53.33% | 6 |  | 728.1385
378 | L2 | FACILITY | MECHANICAL |  | HVAC REPAIR | Saskatoon | 2026-10-31 | 2026 | 240 | 1 | 2026-03-05 | med | low | high | low | high | 28000 | 27379 | 26358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | 16800 | 2800 | 28000 | 596.282 | EXPENSE | Yes | Unit outage |  |  |  | X | X | Yes | Yes | no | no | no | no | Yes | no | no | 1 | 4 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 40% | 4 | 3 | 1 | 1 | 2 | 4 | 4 | 50% | 5 |  | 48885
377 | L2 | FACILITY | MECHANICAL |  | PSV REPLACE | Regina | 2025-12-31 | 2025 | 86 | 4 | 2025-10-06 | high | high | high | high | high | 50000 | 44785 | 48410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 30000 | 5000 | 0 | 50000 | 578.2064 | EXPENSE | Yes | Unit outage | X |  | X |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | no | no | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 26.67% | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 36.67% | 4 |  | 9580.877
378 | L2 | FACILITY | MECHANICAL |  | HVAC REPLACEMENT | North Bay | 2027-07-31 | 2027 | 312 | 5 | 2026-09-22 | med | low | low | high | high | 50000 | 52451 | 59181 | 0 | 0 | 0 | 0 | 0 | 5000 | 40000 | 5000 | 0 | 0 | 0 | 0 | 50000 | 132.8976 | CAPITAL | No | Unit outage | X | X |  | X |  | no | no | Yes | no | no | no | no | Yes | Yes | 3 | 5 | 5 | 2 | 2 | 1 | 1 | 2 | 5 | 57.78% | 6 | 5 | 4 | 1 | 4 | 5 | 4 | 76.67% | 8 |  | 643.2391
378 | L1 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Ottawa | 2028-07-31 | 2028 | 206 | 2 | 2028-01-07 | med | med | low | med | med | 350000 | 387958 | 348402 | 0 | 0 | 0 | 35000 | 280000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 338.5852 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 5 | 3 | 4 | 2 | 4 | 2 | 2 | 3 | 4 | 64.44% | 7 | 3 | 5 | 1 | 5 | 4 | 3 | 70% | 7 |  | 4522
379 | L2 | FACILITY | MECHANICAL |  | AIR COMP | Saskatoon | 2025-07-31 | 2025 | 78 | 2 | 2025-05-14 | med | high | med | med | high | 85000 | 85842 | 84351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25500 | 51000 | 8500 | 85000 | 790.6318 | CAPITAL | Yes | Unit outage | X |  | X | X | X | no | no | Yes | no | no | no | Yes | Yes | no | 3 | 2 | 3 | 2 | 5 | 1 | 2 | 2 | 4 | 53.33% | 6 | 1 | 2 | 1 | 4 | 1 | 5 | 46.67% | 5 |  | 9580.8769
380 | L2 | FACILITY | ELECTRICAL |  | IGNITION SYSTEM | Montreal | 2026-12-31 | 2026 | 174 | 3 | 2026-07-10 | high | med | high | med | low | 525000 | 629579 | 612080 | 0 | 157500 | 315000 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 81.6263 | CAPITAL | No | Station outage |  |  |  | X | X | Yes | no | no | Yes | no | Yes | no | no | Yes | 5 | 5 | 3 | 2 | 4 | 4 | 2 | 3 | 5 | 73.33% | 8 | 5 | 2 | 1 | 5 | 2 | 2 | 56.67% | 6 |  | 52
380 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Saskatoon | 2025-10-31 | 2025 | 150 | 8 | 2025-06-03 | low | high | high | low | low | 300000 | 303443 | 304754 | 30000 | 240000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 122.9237 | EXPENSE | No | Pipeline segment |  |  | X |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 5 | 1 | 1 | 3 | 4 | 4 | 1 | 3 | 51.11% | 6 | 3 | 4 | 1 | 5 | 3 | 1 | 56.67% | 6 |  | 8429.71
381 | L3 | FACILITY | ELECTRICAL |  | IGNITION SYSTEM | Calgary | 2027-07-31 | 2027 | 229 | 1 | 2026-12-14 | low | high | low | high | low | 525000 | 525741 | 525534 | 0 | 0 | 0 | 157500 | 315000 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 881.8043 | CAPITAL | Yes | Unit outage | X | X | X |  | X | no | no | Yes | no | no | no | Yes | no | Yes | 4 | 4 | 3 | 4 | 4 | 4 | 5 | 5 | 2 | 77.78% | 8 | 3 | 4 | 5 | 1 | 5 | 2 | 66.67% | 7 |  | 495.1227
381 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2025-05-31 | 2025 | 140 | 8 | 2025-01-11 | low | high | med | low | high | 1750000 | 1822372 | 1853987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 1050000 | 175000 | 1750000 | 87.2637 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X | X | X | no | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 4 | 5 | 4 | 2 | 1 | 5 | 4 | 3 | 2 | 66.67% | 7 | 3 | 4 | 5 | 4 | 1 | 1 | 60% | 6 |  | 8756
382 | L3 | PIPE INTEGRITY | Excavation | SCC | RECOAT | Winnipeg | 2025-03-31 | 2025 | 100 | 4 | 2024-12-21 | low | low | low | low | high | 350000 | 424886 | 436808 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 9.937 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | Yes | no | no | Yes | Yes | Yes | Yes | no | 3 | 4 | 3 | 2 | 4 | 5 | 3 | 4 | 4 | 71.11% | 8 | 1 | 4 | 1 | 4 | 4 | 4 | 60% | 6 |  | 52
384 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Edmonton | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | low | low | med | low | med | 300000 | 340748 | 344971 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 240000 | 30000 | 0 | 0 | 0 | 300000 | 7.9241 | EXPENSE | No | Pipeline segment |  | X | X |  | X | no | no | no | Yes | no | no | no | Yes | no | 1 | 5 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 42.22% | 5 | 5 | 2 | 1 | 4 | 1 | 2 | 50% | 5 |  | 258
385 | L3 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Edmonton | 2025-10-31 | 2025 | 159 | 8 | 2025-05-25 | high | high | high | med | med | 954752 | 1528786 | 1507834 | 0 | 0 | 0 | 0 | 286425.6 | 572851.2 | 95475.2 | 0 | 0 | 0 | 0 | 0 | 954752 | 157.9294 | EXPENSE | Yes | Unit outage | X |  |  | X | X | Yes | Yes | no | Yes | no | Yes | Yes | no | Yes | 3 | 4 | 2 | 1 | 5 | 1 | 1 | 3 | 3 | 51.11% | 6 | 4 | 5 | 5 | 2 | 5 | 3 | 80% | 8 |  | 4785
386 | L3 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Quebec City | 2025-12-31 | 2025 | 131 | 4 | 2025-08-22 | low | med | high | high | med | 750000 | 741959 | 741361 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 122.5762 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 5 | 4 | 2 | 5 | 2 | 2 | 1 | 2 | 5 | 62.22% | 7 | 2 | 3 | 1 | 4 | 1 | 5 | 53.33% | 6 |  | 4101.0339
387 | L2 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Regina | 2028-12-31 | 2028 | 61 | 8 | 2028-10-31 | low | high | high | high | low | 588848 | 535508 | 456687 | 0 | 0 | 0 | 176654.4 | 353308.8 | 58884.8 | 0 | 0 | 0 | 0 | 0 | 0 | 588848 | 77.556 | EXPENSE | Yes | Unit outage | X | X | X | X |  | Yes | Yes | no | no | no | Yes | no | no | no | 5 | 5 | 4 | 2 | 1 | 4 | 2 | 2 | 5 | 66.67% | 7 | 5 | 4 | 5 | 3 | 1 | 3 | 70% | 7 |  | 16059.7772
387 | L3 | FACILITY | MECHANICAL |  | INSTRUMENT AIR | WINNIPEG | 2025-10-31 | 2025 | 163 | 4 | 2025-05-21 | low | med | low | high | low | 320000 | 350475 | 374000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 256000 | 32000 | 0 | 320000 | 430.5675 | CAPITAL | Yes | Unit outage | [5 empty] | no | Yes | Yes | no | no | Yes | Yes | no | Yes | 2 | 4 | 1 | 2 | 5 | 3 | 2 | 2 | 4 | 55.56% | 6 | 3 | 5 | 5 | 5 | 3 | 4 | 83.33% | 9 |  | 778.6578
388 | L2 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | North Bay | 2027-12-31 | 2027 | 333 | 8 | 2027-02-01 | high | high | med | high | low | 371262 | 634614 | 653309 | 0 | 0 | 0 | 111378.6 | 222757.2 | 37126.2 | 0 | 0 | 0 | 0 | 0 | 0 | 371262 | 175.9698 | EXPENSE | Yes | Unit outage |  | X | X | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 2 | 1 | 3 | 1 | 1 | 4 | 2 | 2 | 3 | 42.22% | 5 | 5 | 2 | 1 | 4 | 1 | 4 | 56.67% | 6 |  | 425
388 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Regina | 2025-10-31 | 2025 | 209 | 7 | 2025-04-05 | low | med | low | med | high | 1912887 | 3258934 | 75898 | 0 | 0 | 0 | 0 | 573866.1 | 1147732.2 | 191288.7 | 0 | 0 | 0 | 0 | 0 | 1912887 | 3.9677 | CAPITAL | Yes | Unit outage | X | X | X | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 1 | 5 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 44.44% | 5 | 2 | 1 | 1 | 1 | 3 | 1 | 30% | 3 |  | 842.9817
389 | L3 | FACILITY | MECHANICAL |  | INSTRUMENT AIR | Ottawa | 2028-12-31 | 2028 | 60 | 4 | 2028-11-01 | high | low | high | med | med | 320000 | 166959 | 169214 | 96000 | 192000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 214.7122 | EXPENSE | Yes | Unit outage |  |  | X |  | X | Yes | Yes | no | no | Yes | no | no | no | Yes | 1 | 5 | 2 | 1 | 5 | 2 | 1 | 3 | 1 | 46.67% | 5 | 4 | 1 | 1 | 1 | 2 | 1 | 33.33% | 4 |  | 4391.6369
390 | L1 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Quebec City | 2027-12-31 | 2027 | 231 | 8 | 2027-05-14 | high | low | high | high | med | 616752 | 629177 | 648523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61675.2 | 493401.6 | 61675.2 | 0 | 616752 | 105.1513 | EXPENSE | Yes | Unit outage |  |  | X |  | X | Yes | Yes | no | no | no | no | no | Yes | Yes | 3 | 5 | 1 | 3 | 1 | 5 | 1 | 1 | 2 | 48.89% | 5 | 4 | 5 | 1 | 2 | 3 | 1 | 53.33% | 6 |  | 1475
389 | L2 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | North Bay | 2025-03-31 | 2025 | 204 | 4 | 2024-09-08 | high | med | high | med | med | 350000 | 377958 | 378402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 60.2487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | Yes | Yes | no | Yes | 4 | 4 | 2 | 2 | 3 | 5 | 4 | 2 | 4 | 66.67% | 7 | 1 | 2 | 1 | 5 | 1 | 3 | 43.33% | 5 |  | 842.9817
390 | L2 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Saskatoon | 2028-03-31 | 2028 | 148 | 7 | 2027-11-04 | med | med | low | low | med | 750000 | 844261 | 865990 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 55.7589 | EXPENSE | Yes | Unit outage |  |  | X |  |  | Yes | Yes | no | no | no | no | no | Yes | Yes | 4 | 5 | 3 | 2 | 5 | 2 | 2 | 1 | 3 | 60% | 6 | 2 | 2 | 1 | 4 | 2 | 4 | 50% | 5 |  | 347
390 | L3 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Saskatoon | 2025-07-31 | 2025 | 133 | 2 | 2025-03-20 | low | med | low | low | med | 520000 | 520076 | 517552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156000 | 260000 | 104000 | 520000 | 339.8771 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 2 | 4 | 2 | 3 | 1 | 2 | 4 | 2 | 4 | 53.33% | 6 | 1 | 2 | 1 | 1 | 2 | 4 | 36.67% | 4 |  | 13420.4072
391 | L3 | FACILITY | MAJOR EQUIP |  | VSV REPAIR | Regina | 2027-12-31 | 2027 | 150 | 7 | 2027-08-03 | high | high | low | high | med | 201736 | 315757 | 409549 | 0 | 0 | 0 | 0 | 20173.6 | 161388.8 | 20173.6 | 0 | 0 | 0 | 0 | 0 | 201736 | 946.5584 | EXPENSE | Yes | Unit outage |  | X | X |  | X | no | no | Yes | no | Yes | Yes | Yes | no | no | 5 | 5 | 1 | 2 | 2 | 1 | 1 | 5 | 4 | 57.78% | 6 | 1 | 4 | 1 | 3 | 3 | 4 | 53.33% | 6 |  | 278.7236
391 | L3 | FACILITY | MAJOR EQUIP |  | MAJOR OH | Ottawa | 2026-03-31 | 2026 | 216 | 7 | 2025-08-27 | med | med | high | low | low | 4100000 | 4162797 | 4274098 | 0 | 0 | 410000 | 3280000 | 410000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100000 | 63.7402 | CAPITAL | Yes | Unit outage | X | X |  | X | X | Yes | Yes | Yes | Yes | no | Yes | no | Yes | Yes | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 2 | 3 | 40% | 4 | 5 | 5 | 1 | 4 | 3 | 4 | 73.33% | 8 |  | 1727.2647
392 | L2 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Quebec City | 2028-12-31 | 2028 | 56 | 2 | 2028-11-05 | low | high | med | low | med | 450000 | 493301 | 555422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 146.1537 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | no | no | Yes | Yes | no | Yes | no | Yes | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 84.44% | 9 | 1 | 2 | 1 | 3 | 5 | 5 | 56.67% | 6 |  | 13659.19
392 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2025-07-31 | 2025 | 150 | 4 | 2025-03-03 | med | low | low | low | med | 750000 | 800359 | 808385 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 201.382 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | Yes | no | no | no | no | no | Yes | no | no | 3 | 2 | 2 | 3 | 1 | 2 | 4 | 1 | 5 | 51.11% | 6 | 5 | 1 | 1 | 5 | 2 | 2 | 53.33% | 6 |  | 1578
393 | L1 | FACILITY | CIVIL |  | WATERWELL REPLACE | Quebec City | 2028-10-31 | 2028 | 133 | 1 | 2028-06-20 | med | med | med | low | low | 85000 | 85685 | 82589 | 8500 | 34000 | 42500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 1753.282 | CAPITAL | No | NO |  | X |  |  | X | no | no | Yes | no | Yes | Yes | Yes | Yes | no | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 24.44% | 3 | 3 | 3 | 5 | 4 | 4 | 3 | 73.33% | 8 |  | 8501.4285
394 | L1 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Toronto | 2026-12-31 | 2026 | 280 | 4 | 2026-03-26 | high | high | low | high | low | 1000000 | 1024910 | 1058330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 800000 | 100000 | 0 | 1000000 | 61.0855 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 4 | 42.22% | 5 | 2 | 1 | 5 | 1 | 3 | 3 | 50% | 5 |  | 842.9817
393 | L2 | FACILITY | MAJOR EQUIP |  | MINOR OH | Ottawa | 2025-07-31 | 2025 | 334 | 4 | 2024-08-31 | med | low | low | high | low | 1305126 | 1760248 | 1777193 | 0 | 130512.6 | 1044100.8 | 130512.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1305126 | 136.1702 | CAPITAL | Yes | Unit outage |  |  | X |  | X | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 4 | 3 | 4 | 4 | 3 | 3 | 5 | 1 | 2 | 64.44% | 7 | 3 | 1 | 1 | 4 | 3 | 5 | 56.67% | 6 |  | 3506.8708
394 | L1 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Winnipeg | 2026-03-31 | 2026 | 74 | 4 | 2026-01-16 | low | low | high | low | low | 1000000 | 1295898 | 1247471 | 0 | 0 | 0 | 0 | 300000 | 600000 | 100000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 78.2163 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X | X | Yes | no | no | no | no | no | Yes | no | Yes | 1 | 3 | 1 | 1 | 4 | 3 | 2 | 3 | 1 | 42.22% | 5 | 2 | 4 | 1 | 1 | 2 | 3 | 43.33% | 5 |  | 1578
394 | L1 | FACILITY | AUTOMATION & CONTROLS |  | DVC CONTROLLER | Toronto | 2028-12-31 | 2028 | 187 | 1 | 2028-06-27 | high | high | med | med | low | 120282 | 138145 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36084.6 | 72169.2 | 12028.2 | 0 | 0 | 120282 | 618.0177 | EXPENSE | Yes | Unit outage | X | X | X | X | X | Yes | Yes | no | Yes | Yes | no | Yes | no | no | 3 | 3 | 2 | 3 | 2 | 4 | 4 | 3 | 2 | 57.78% | 6 | 2 | 4 | 1 | 5 | 2 | 3 | 56.67% | 6 |  | 18109.7232
395 | L2 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Saskatoon | 2029-07-31 | 2029 | 45 | 4 | 2029-06-16 | low | med | med | low | high | 1000000 | 1035786 | 1004048 | 0 | 0 | 0 | 100000 | 800000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 336.0415 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 4 | 1 | 3 | 1 | 5 | 5 | 3 | 3 | 62.22% | 7 | 1 | 1 | 1 | 4 | 1 | 1 | 30% | 3 |  | 278.7236
395 | L3 | FACILITY | MECHANICAL |  | GAS COOLER REPAIR | Winnipeg | 2025-03-31 | 2025 | 238 | 4 | 2024-08-05 | med | med | high | med | high | 650000 | 896761 | 975631 | 0 | 0 | 0 | 0 | 65000 | 520000 | 65000 | 0 | 0 | 0 | 0 | 0 | 650000 | 156.2747 | EXPENSE | No | Station outage |  | X |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 1 | 5 | 1 | 1 | 2 | 3 | 4 | 2 | 3 | 48.89% | 5 | 5 | 3 | 1 | 1 | 4 | 3 | 56.67% | 6 |  | 1685.9635
396 | L2 | PIPE INTEGRITY | ILI | DENT | MFL INSPECTION RUN | Calgary | 2027-12-31 | 2027 | 216 | 4 | 2027-05-29 | med | low | low | high | low | 1900000 | 2439945 | 2463759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 1520000 | 190000 | 0 | 1900000 | 28.0968 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 1 | 1 | 1 | 4 | 1 | 5 | 1 | 4 | 42.22% | 5 | 2 | 2 | 1 | 5 | 3 | 3 | 53.33% | 6 |  | 7007.9205
396 | L3 | FACILITY | ELECTRICAL |  | VFD REPLACE | Calgary | 2025-07-31 | 2025 | 229 | 1 | 2024-12-14 | low | high | low | high | low | 750000 | 751933 | 751534 | 0 | 0 | 0 | 0 | 0 | 75000 | 600000 | 75000 | 0 | 0 | 0 | 0 | 750000 | 881.8043 | CAPITAL | Yes | Unit outage | X | X | X |  | X | no | no | Yes | no | no | no | Yes | no | Yes | 4 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 3 | 44.44% | 5 | 1 | 1 | 1 | 5 | 3 | 3 | 46.67% | 5 |  | 20815.3255
397 | L1 | FACILITY | AUTOMATION & CONTROLS |  | GAS DETECTOR | Montreal | 2029-10-31 | 2029 | 319 | 4 | 2028-12-16 | med | low | low | med | low | 53873 | 54482 | 579305 | 0 | 0 | 0 | 0 | 53873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53873 | 70.4069 | EXPENSE | No | plant outage | X | X |  | X |  | no | no | no | no | no | Yes | no | no | Yes | 1 | 5 | 3 | 1 | 4 | 2 | 1 | 1 | 2 | 44.44% | 5 | 4 | 5 | 1 | 4 | 2 | 2 | 60% | 6 |  | 842.9817
398 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2028-03-31 | 2028 | 248 | 7 | 2027-07-27 | med | low | high | high | high | 1900000 | 1977581 | 1989278 | 0 | 0 | 0 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 94.5144 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | no | no | Yes | Yes | Yes | Yes | Yes | no | 2 | 4 | 2 | 3 | 4 | 2 | 5 | 3 | 3 | 62.22% | 7 | 4 | 1 | 1 | 3 | 3 | 4 | 53.33% | 6 |  | 2369.8282
397 | L2 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Quebec City | 2027-12-31 | 2027 | 200 | 4 | 2027-06-14 | high | low | med | med | low | 2555385 | 2536764 | 2531509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255538.5 | 2044308 | 255538.5 | 0 | 0 | 2555385 | 32.4619 | CAPITAL | Yes | Unit outage |  |  |  |  | X | no | Yes | no | Yes | Yes | no | no | no | no | 3 | 4 | 1 | 1 | 2 | 5 | 4 | 3 | 1 | 53.33% | 6 | 2 | 1 | 1 | 3 | 1 | 2 | 33.33% | 4 |  | 425
398 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2028-07-31 | 2028 | 17 | 4 | 2028-07-14 | high | low | low | low | med | 1500000 | 1410189 | 1490446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 600000 | 750000 | 1500000 | 61.5579 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  | X | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 5 | 3 | 2 | 1 | 5 | 3 | 1 | 4 | 3 | 60% | 6 | 4 | 3 | 1 | 5 | 5 | 2 | 66.67% | 7 |  | 425
399 | L3 | FACILITY | ELECTRICAL |  | VFD REPLACE | Quebec City | 2029-12-31 | 2028 | 79 | 2 | 2029-10-13 | high | low | low | low | low | 750000 | 754236 | 786497 | 0 | 0 | 0 | 0 | 75000 | 600000 | 75000 | 0 | 0 | 0 | 0 | 0 | 750000 | 198.3414 | CAPITAL | Yes | Unit outage |  |  | X |  | X | Yes | no | no | no | Yes | Yes | no | Yes | Yes | 2 | 5 | 3 | 1 | 3 | 3 | 2 | 2 | 2 | 51.11% | 6 | 1 | 4 | 5 | 5 | 4 | 5 | 80% | 8 |  | 5097.261
398 | L1 | FACILITY | ELECTRICAL |  | TEG | Quebec City | 2025-07-31 | 2025 | 319 | 1 | 2024-09-15 | low | low | med | high | med | 150000 | 155289 | 171994 | 0 | 0 | 0 | 15000 | 120000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 249.175 | CAPITAL | No | Station outage | X | X |  | X |  | no | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 3 | 5 | 1 | 5 | 2 | 2 | 1 | 2 | 5 | 57.78% | 6 | 1 | 1 | 1 | 2 | 4 | 1 | 33.33% | 4 |  | 278.7236
399 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2026-07-31 | 2026 | 223 | 7 | 2025-12-20 | med | low | high | med | high | 2000000 | 2451951 | 2464009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 1600000 | 200000 | 0 | 0 | 2000000 | 287.5273 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 4 | 1 | 3 | 4 | 3 | 2 | 1 | 1 | 44.44% | 5 | 3 | 2 | 1 | 1 | 4 | 2 | 43.33% | 5 |  | 45.3112
400 | L2 | FACILITY | ELECTRICAL |  | VFD REPLACE | Saskatoon | 2027-10-31 | 2027 | 137 | 5 | 2027-06-16 | med | high | med | low | low | 750000 | 736500 | 771402 | 0 | 0 | 0 | 0 | 75000 | 600000 | 75000 | 0 | 0 | 0 | 0 | 0 | 750000 | 32.9312 | CAPITAL | No | Station outage | [5 empty] | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 2 | 1 | 1 | 5 | 2 | 1 | 2 | 3 | 42.22% | 5 | 1 | 2 | 1 | 1 | 1 | 3 | 30% | 3 |  | 172.2548
399 | L2 | PIPE INTEGRITY | Excavation | SCC | RECOAT | Montreal | 2025-12-31 | 2025 | 200 | 5 | 2025-06-14 | high | med | low | high | med | 500000 | 580071 | 583077 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 400000 | 50000 | 0 | 0 | 500000 | 339.2298 | EXPENSE | No | pipeline segment outage |  | X | X |  |  | no | Yes | no | Yes | no | Yes | no | no | no | 3 | 1 | 3 | 1 | 4 | 1 | 2 | 1 | 3 | 42.22% | 5 | 2 | 2 | 1 | 4 | 2 | 3 | 46.67% | 5 |  | 278.7236
400 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2025-03-31 | 2025 | 360 | 4 | 2024-04-05 | low | high | med | low | high | 1750000 | 1822372 | 1853987 | 0 | 0 | 0 | 175000 | 1400000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 87.2637 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X | X | X | no | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 1 | 3 | 1 | 1 | 3 | 5 | 1 | 2 | 2 | 42.22% | 5 | 2 | 5 | 1 | 2 | 2 | 1 | 43.33% | 5 |  | 16.9273
401 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | North Bay | 2028-03-31 | 2028 | 160 | 2 | 2027-10-23 | high | med | high | med | med | 1000000 | 1015946 | 1061154 | 0 | 0 | 100000 | 800000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 60.2487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | Yes | Yes | no | Yes | 5 | 3 | 3 | 4 | 1 | 3 | 5 | 4 | 2 | 66.67% | 7 | 1 | 1 | 5 | 5 | 3 | 3 | 60% | 6 |  | 2369.8282
400 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Quebec City | 2025-07-31 | 2025 | 284 | 4 | 2024-10-20 | low | high | high | low | med | 125000 | 137635 | 149404 | 0 | 0 | 0 | 0 | 0 | 12500 | 100000 | 12500 | 0 | 0 | 0 | 0 | 125000 | 946.0832 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 5 | 3 | 3 | 1 | 5 | 3 | 2 | 5 | 5 | 71.11% | 8 | 1 | 2 | 1 | 2 | 2 | 2 | 33.33% | 4 |  | 278.7236
401 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Regina | 2025-12-31 | 2025 | 131 | 8 | 2025-08-22 | med | med | high | med | low | 450000 | 522096 | 523817 | 0 | 0 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 450000 | 101.141 | CAPITAL | No | Pipeline segment |  | X |  | X |  | no | Yes | no | no | Yes | Yes | Yes | no | no | 5 | 2 | 1 | 2 | 5 | 4 | 4 | 5 | 5 | 73.33% | 8 | 5 | 4 | 1 | 5 | 3 | 1 | 63.33% | 7 |  | 203.1281
402 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2028-03-31 | 2028 | 200 | 4 | 2027-09-13 | med | low | med | med | med | 1000000 | 1021505 | 1092551 | 75000 | 75000 | 75000 | 662000 | 662000 | 400000 | 100000 | 0 | 0 | 0 | 0 | 0 | 2049000 | 56.5076 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | no | no | no | no | no | no | no | no | Yes | 5 | 2 | 1 | 3 | 2 | 4 | 1 | 3 | 3 | 53.33% | 6 | 2 | 5 | 1 | 3 | 4 | 1 | 53.33% | 6 |  | 2973.4021
402 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Toronto | 2025-03-31 | 2025 | 100 | 4 | 2024-12-21 | low | low | high | low | med | 550000 | 957635 | 1018992 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 105.7103 | EXPENSE | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 5 | 1 | 1 | 5 | 1 | 4 | 2 | 1 | 2 | 48.89% | 5 | 4 | 2 | 1 | 1 | 3 | 5 | 53.33% | 6 |  | 203.1281
403 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2029-07-31 | 2029 | 150 | 2 | 2029-03-03 | high | med | low | med | high | 275000 | 279845 | 309640 | 0 | 0 | 0 | 0 | 0 | 27500 | 110000 | 137500 | 0 | 0 | 0 | 0 | 275000 | 500.6594 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 3 | 4 | 46.67% | 5 | 3 | 5 | 5 | 2 | 4 | 5 | 80% | 8 |  | 5522
403 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2026-03-31 | 2026 | 180 | 8 | 2025-10-02 | high | low | low | low | low | 450000 | 407875 | 435270 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 80.7138 | CAPITAL | No | pipeline segment outage | X | X |  | X |  | no | Yes | no | Yes | no | Yes | no | Yes | no | 3 | 2 | 3 | 1 | 5 | 4 | 3 | 1 | 2 | 53.33% | 6 | 3 | 3 | 5 | 4 | 1 | 3 | 63.33% | 7 |  | 203.1281
404 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2026-03-31 | 2026 | 200 | 4 | 2025-09-12 | low | high | low | low | high | 1900000 | 1900004 | 1920751 | 0 | 0 | 0 | 0 | 0 | 1520000 | 380000 | 0 | 0 | 0 | 0 | 0 | 1900000 | 44.5632 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  | X |  | Yes | Yes | no | no | no | no | no | no | Yes | 4 | 5 | 4 | 2 | 2 | 2 | 2 | 1 | 4 | 57.78% | 6 | 1 | 1 | 1 | 5 | 5 | 3 | 53.33% | 6 |  | 13420.4072
404 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Winnipeg | 2025-03-31 | 2025 | 120 | 4 | 2024-12-01 | med | low | med | med | med | 1000000 | 1021505 | 1092551 | 0 | 100000 | 0 | 0 | 0 | 800000 | 100000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 56.5076 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | no | no | no | no | no | no | no | no | Yes | 5 | 4 | 3 | 2 | 1 | 4 | 2 | 4 | 4 | 64.44% | 7 | 3 | 4 | 5 | 3 | 5 | 4 | 80% | 8 |  | 853.1382
405 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2026-12-31 | 2026 | 150 | 2 | 2026-08-03 | high | med | med | med | high | 350000 | 441828 | 446179 | 35000 | 280000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 16.1628 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X | X | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 5 | 1 | 4 | 3 | 3 | 4 | 2 | 5 | 3 | 66.67% | 7 | 2 | 5 | 1 | 4 | 2 | 5 | 63.33% | 7 |  | 121.8769
405 | L1 | FACILITY | MAJOR EQUIP |  | MINOR OH | Toronto | 2025-10-31 | 2025 | 81 | 8 | 2025-08-11 | low | low | low | high | med | 2316843 | 2149065 | 2251331 | 231684.3 | 0 | 1853474.4 | 231684.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2316843 | 11.492 | CAPITAL | Yes | Unit outage | X | X | X | X |  | no | no | no | Yes | no | no | Yes | no | Yes | 4 | 5 | 2 | 4 | 2 | 3 | 5 | 5 | 3 | 73.33% | 8 | 4 | 3 | 5 | 4 | 1 | 3 | 66.67% | 7 |  | 23717.2367
406 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2028-10-31 | 2028 | 250 | 4 | 2028-02-24 | med | med | low | high | low | 1500000 | 1871375 | 1900437 | 0 | 0 | 0 | 0 | 150000 | 1200000 | 150000 | 0 | 0 | 0 | 0 | 0 | 1500000 | 20.7353 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X | X | Yes | no | Yes | Yes | no | Yes | Yes | no | Yes | 5 | 2 | 3 | 3 | 5 | 2 | 3 | 3 | 5 | 68.89% | 7 | 5 | 5 | 1 | 2 | 2 | 5 | 66.67% | 7 |  | 267.7598
407 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2026-07-31 | 2026 | 120 | 2 | 2026-04-02 | med | med | med | high | med | 650000 | 835557 | 838033 | 195000 | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 224.9398 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | Yes | no | 5 | 5 | 1 | 2 | 4 | 2 | 2 | 2 | 1 | 53.33% | 6 | 1 | 5 | 1 | 5 | 1 | 1 | 46.67% | 5 |  | 5732.891
406 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | high | high | high | high | high | 350000 | 404631 | 406242 | 0 | 0 | 0 | 0 | 0 | 35000 | 280000 | 35000 | 0 | 0 | 0 | 0 | 350000 | 26.1799 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | Yes | no | no | no | Yes | no | Yes | Yes | 4 | 3 | 4 | 3 | 3 | 3 | 1 | 1 | 2 | 53.33% | 6 | 3 | 2 | 1 | 1 | 2 | 1 | 33.33% | 4 |  | 746.1723
407 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Montreal | 2025-10-31 | 2025 | 250 | 4 | 2025-02-23 | med | med | med | low | low | 500000 | 571069 | 578420 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 20.7067 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | no | no | no | no | Yes | Yes | Yes | 4 | 1 | 1 | 3 | 1 | 1 | 2 | 5 | 2 | 44.44% | 5 | 2 | 4 | 1 | 1 | 2 | 4 | 46.67% | 5 |  | 1174.9707
408 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | North Bay | 2029-07-31 | 2029 | 120 | 2 | 2029-04-02 | low | med | high | high | med | 950000 | 989229 | 980770 | 0 | 0 | 0 | 95000 | 760000 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 128.235 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | Yes | no | Yes | Yes | Yes | 1 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 1 | 40% | 4 | 1 | 3 | 1 | 4 | 3 | 1 | 43.33% | 5 |  | 3077.963
408 | L3 | FACILITY | MEASUREMENT |  | FUEL GAS UPGRADE | Calgary | 2028-12-31 | 2028 | 262 | 5 | 2028-04-13 | med | med | high | high | high | 1000000 | 1066612 | 1017199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 800000 | 100000 | 0 | 0 | 1000000 | 120.2789 | CAPITAL | No | Derate/low flow Pipe segment |  |  |  |  | X | no | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 3 | 2 | 5 | 5 | 2 | 2 | 1 | 3 | 57.78% | 6 | 5 | 2 | 1 | 5 | 5 | 1 | 63.33% | 7 |  | 13677.1818
409 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2026-10-31 | 2026 | 355 | 4 | 2025-11-10 | high | high | low | low | high | 1500000 | 1708182 | 1716547 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 1050000 | 0 | 0 | 0 | 0 | 1500000 | 45.4478 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 3 | 3 | 3 | 2 | 5 | 4 | 3 | 1 | 2 | 57.78% | 6 | 1 | 5 | 1 | 4 | 4 | 4 | 63.33% | 7 |  | 2610.39
409 | L1 | PIPE INTEGRITY | Excavation | SCC | RECOAT | Ottawa | 2025-07-31 | 2025 | 150 | 4 | 2025-03-03 | low | high | low | high | low | 400000 | 574072 | 556987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 400000 | 133.3009 | EXPENSE | No | Station outage | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | Yes | no | Yes | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 35.56% | 4 | 5 | 1 | 1 | 2 | 4 | 2 | 50% | 5 |  | 16021.8416
410 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Quebec City | 2027-10-31 | 2027 | 200 | 2 | 2027-04-14 | med | med | high | med | high | 450000 | 486253 | 471492 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 34.7089 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 1 | 4 | 5 | 4 | 4 | 5 | 5 | 4 | 82.22% | 9 | 4 | 1 | 1 | 2 | 2 | 5 | 50% | 5 |  | 289
410 | L1 | FACILITY | MECHANICAL |  | AIR INTAKE | Regina | 2027-12-31 | 2027 | 205 | 4 | 2027-06-09 | med | med | high | med | med | 1950000 | 1854716 | 1855447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 1560000 | 195000 | 0 | 0 | 1950000 | 19.4031 | CAPITAL | No | Station outage | X | X | X | X |  | no | no | no | Yes | no | Yes | Yes | no | no | 2 | 5 | 2 | 1 | 3 | 4 | 3 | 1 | 2 | 51.11% | 6 | 2 | 2 | 1 | 2 | 1 | 2 | 33.33% | 4 |  | 425
411 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2028-07-31 | 2028 | 200 | 4 | 2028-01-13 | med | med | high | med | high | 1000000 | 1649706 | 1663088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 800000 | 100000 | 0 | 0 | 1000000 | 96.0767 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X | X | no | Yes | no | no | Yes | Yes | no | no | no | 5 | 5 | 3 | 2 | 5 | 2 | 2 | 5 | 3 | 71.11% | 8 | 3 | 5 | 1 | 4 | 1 | 4 | 60% | 6 |  | 347
411 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2025-03-31 | 2025 | 180 | 15 | 2024-10-02 | high | med | med | low | low | 450000 | 836197 | 864086 | 0 | 45000 | 45000 | 315000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 65.7764 | CAPITAL | No | Pipeline segment | X | X | X |  | X | Yes | Yes | no | no | no | no | Yes | Yes | Yes | 2 | 2 | 1 | 1 | 2 | 2 | 5 | 3 | 5 | 51.11% | 6 | 4 | 5 | 5 | 1 | 3 | 4 | 73.33% | 8 |  | 7007.9205
412 | L3 | FACILITY | MECHANICAL |  | AIR INTAKE | Winnipeg | 2028-03-31 | 2028 | 238 | 4 | 2027-08-06 | med | med | high | med | high | 650000 | 896761 | 975631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 520000 | 65000 | 0 | 650000 | 156.2747 | EXPENSE | No | Station outage |  | X |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 4 | 3 | 5 | 4 | 2 | 5 | 5 | 4 | 2 | 75.56% | 8 | 3 | 1 | 1 | 3 | 1 | 1 | 33.33% | 4 |  | 4858.8867
413 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2026-03-31 | 2026 | 150 | 4 | 2025-11-01 | med | high | med | med | low | 1800000 | 1817708 | 1819840 | 0 | 0 | 180000 | 1440000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 73.0943 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 2 | 1 | 1 | 4 | 4 | 1 | 2 | 1 | 40% | 4 | 2 | 5 | 1 | 4 | 3 | 4 | 63.33% | 7 |  | 900.2043
412 | L2 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | WINNIPEG | 2025-10-31 | 2025 | 269 | 8 | 2025-02-04 | high | med | low | high | med | 1860140 | 1917540 | 1909145 | 0 | 0 | 0 | 0 | 186014 | 744056 | 930070 | 0 | 0 | 0 | 0 | 0 | 1860140 | 54.251 | EXPENSE | Yes | Unit outage |  | X | X |  |  | no | Yes | no | Yes | no | no | Yes | Yes | Yes | 4 | 2 | 2 | 2 | 5 | 3 | 3 | 5 | 4 | 66.67% | 7 | 1 | 2 | 1 | 4 | 5 | 1 | 46.67% | 5 |  | 18.4662
413 | L1 | FACILITY | MECHANICAL |  | AIR INTAKE | Ottawa | 2027-12-31 | 2027 | 230 | 4 | 2027-05-15 | high | med | med | low | low | 800000 | 715612 | 769294 | 0 | 0 | 80000 | 640000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 158.7999 | CAPITAL | Yes | Unit outage |  |  |  | X |  | no | Yes | no | no | no | no | Yes | Yes | no | 2 | 5 | 1 | 1 | 4 | 1 | 5 | 2 | 5 | 57.78% | 6 | 1 | 3 | 1 | 2 | 4 | 2 | 43.33% | 5 |  | 13582.28
414 | L2 | FACILITY | MEASUREMENT |  | AMTECK | Quebec City | 2026-12-31 | 2026 | 152 | 4 | 2026-08-01 | high | high | med | high | med | 450000 | 341162 | 487137 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 108.4626 | CAPITAL | No | Derate/low flow Pipe segment | X |  |  | X | X | no | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 24.44% | 3 | 4 | 2 | 5 | 1 | 1 | 4 | 56.67% | 6 |  | 5732.891
413 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2025-12-31 | 2025 | 100 | 2 | 2025-09-22 | med | med | high | med | low | 350000 | 331626 | 366466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 280000 | 35000 | 0 | 0 | 350000 | 618.2189 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | Yes | no | Yes | Yes | Yes | no | no | no | Yes | 2 | 4 | 2 | 2 | 2 | 5 | 1 | 2 | 5 | 55.56% | 6 | 5 | 5 | 5 | 1 | 4 | 2 | 73.33% | 8 |  | 1685.9635
414 | L2 | FACILITY | MEASUREMENT |  | AMTECK | North Bay | 2027-12-31 | 2027 | 36 | 4 | 2027-11-25 | med | high | low | low | med | 250000 | 250350 | 254714 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 200000 | 25000 | 0 | 0 | 0 | 250000 | 118.532 | CAPITAL | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | no | Yes | no | no | no | Yes | Yes | 4 | 2 | 1 | 2 | 5 | 4 | 2 | 3 | 4 | 60% | 6 | 1 | 2 | 1 | 3 | 4 | 5 | 53.33% | 6 |  | 121.8769
414 | L1 | FACILITY | MEASUREMENT |  | CALIBRATION | North Bay | 2025-05-31 | 2025 | 152 | 1 | 2024-12-30 | low | low | high | high | med | 200000 | 296294 | 291217 | 20000 | 160000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 246.3806 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | no | Yes | no | no | Yes | Yes | no | Yes | 1 | 5 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 37.78% | 4 | 4 | 5 | 5 | 1 | 4 | 5 | 80% | 8 |  | 1685.9635
415 | L2 | FACILITY | ELECTRICAL |  | APU | North Bay | 2030-12-31 | 2030 | 136 | 0 | 2030-08-17 | low | med | low | low | high | 160000 | 182879 | 188703 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 64000 | 80000 | 0 | 0 | 0 | 160000 | 417.9806 | EXPENSE | No | NO |  |  | X | X | X | no | Yes | Yes | no | Yes | Yes | Yes | no | no | 1 | 5 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 40% | 4 | 3 | 2 | 1 | 3 | 2 | 1 | 40% | 4 |  | 5732.8906
415 | L3 | FACILITY | MECHANICAL |  | LUBE OIL | Winnipeg | 2026-03-31 | 2026 | 96 | 5 | 2025-12-25 | med | low | high | med | low | 250000 | 484837 | 471784 | 0 | 0 | 0 | 25000 | 200000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 440.9277 | CAPITAL | No | Unit outage |  | X |  | X | X | no | no | no | no | Yes | Yes | Yes | no | no | 3 | 5 | 1 | 5 | 5 | 3 | 2 | 4 | 3 | 68.89% | 7 | 3 | 1 | 1 | 5 | 4 | 1 | 50% | 5 |  | 32.5005
416 | L3 | FACILITY | MEASUREMENT |  | CALIBRATION | Ottawa | 2026-10-31 | 2026 | 61 | 2 | 2026-08-31 | low | high | high | med | high | 200000 | 172690 | 183162 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 160000 | 20000 | 0 | 0 | 0 | 200000 | 373.8206 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X |  | X | Yes | no | no | Yes | Yes | Yes | no | Yes | no | 5 | 3 | 4 | 5 | 1 | 2 | 2 | 1 | 2 | 55.56% | 6 | 1 | 5 | 1 | 4 | 3 | 3 | 56.67% | 6 |  | 746.1723
417 | L3 | FACILITY | ELECTRICAL |  | APU | Winnipeg | 2028-10-31 | 2028 | 80 | 1 | 2028-08-12 | low | med | low | med | med | 160000 | 150735 | 155396 | 0 | 0 | 0 | 0 | 0 | 48000 | 80000 | 32000 | 0 | 0 | 0 | 0 | 160000 | 77.6998 | EXPENSE | No | Unit outage |  | X |  |  | X | Yes | Yes | no | no | Yes | Yes | no | Yes | no | 1 | 4 | 2 | 2 | 3 | 5 | 3 | 3 | 2 | 55.56% | 6 | 3 | 3 | 1 | 2 | 1 | 3 | 43.33% | 5 |  | 1475
416 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | North Bay | 2025-07-31 | 2025 | 150 | 2 | 2025-03-03 | high | med | high | med | high | 125000 | 205456 | 208103 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 75000 | 12500 | 0 | 0 | 0 | 125000 | 713.9495 | EXPENSE | Yes | NO |  | X |  |  |  | Yes | Yes | no | no | Yes | Yes | no | Yes | no | 2 | 1 | 3 | 2 | 5 | 2 | 3 | 2 | 1 | 46.67% | 5 | 2 | 3 | 1 | 2 | 1 | 5 | 46.67% | 5 |  | 121.8769
417 | L3 | FACILITY | MEASUREMENT |  | CALIBRATION | Toronto | 2028-09-30 | 2028 | 270 | 3 | 2028-01-04 | high | high | low | high | med | 200000 | 197515 | 197279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 160000 | 20000 | 0 | 0 | 200000 | 128.3733 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X | X | X | Yes | Yes | no | Yes | no | Yes | no | no | no | 3 | 4 | 1 | 4 | 4 | 3 | 4 | 2 | 4 | 64.44% | 7 | 3 | 4 | 1 | 2 | 5 | 1 | 53.33% | 6 |  | 18.4662
418 | L3 | FACILITY | MEASUREMENT |  | CALIBRATION | Edmonton | 2026-12-31 | 2026 | 258 | 4 | 2026-04-17 | high | low | med | low | high | 200000 | 187154 | 182280 | 0 | 0 | 0 | 0 | 60000 | 120000 | 20000 | 0 | 0 | 0 | 0 | 0 | 200000 | 124.1453 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | no | no | no | Yes | Yes | 4 | 4 | 4 | 4 | 5 | 1 | 5 | 3 | 1 | 68.89% | 7 | 5 | 2 | 1 | 3 | 3 | 5 | 63.33% | 7 |  | 5878
417 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | North Bay | 2027-12-31 | 2027 | 43 | 4 | 2027-11-18 | low | high | med | low | high | 1171635 | 1299309 | 1278867 | 0 | 0 | 0 | 0 | 0 | 117163.5 | 468654 | 585817.5 | 0 | 0 | 0 | 0 | 1171635 | 109.1523 | CAPITAL | Yes | Unit outage | X |  |  | X | X | no | Yes | no | Yes | no | no | Yes | Yes | no | 2 | 1 | 3 | 2 | 4 | 2 | 5 | 1 | 3 | 51.11% | 6 | 2 | 4 | 1 | 2 | 5 | 1 | 50% | 5 |  | 643.2391
418 | L3 | FACILITY | MECHANICAL |  | LUBE OIL | Winnipeg | 2027-03-31 | 2027 | 96 | 5 | 2026-12-25 | med | low | high | med | low | 450000 | 254745 | 252784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 450000 | 440.9277 | CAPITAL | No | Unit outage |  | X |  | X | X | no | no | no | no | Yes | Yes | Yes | no | no | 1 | 3 | 3 | 1 | 1 | 5 | 2 | 1 | 2 | 42.22% | 5 | 1 | 1 | 5 | 3 | 2 | 5 | 56.67% | 6 |  | 48885
419 | L2 | FACILITY | MEASUREMENT |  | CALIBRATION | Toronto | 2028-10-31 | 2028 | 60 | 2 | 2028-09-01 | med | low | high | low | low | 450000 | 427047 | 435720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 450000 | 149.6713 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X |  | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | 4 | 4 | 2 | 2 | 2 | 5 | 1 | 4 | 5 | 64.44% | 7 | 3 | 1 | 5 | 2 | 1 | 3 | 50% | 5 |  | 3333.1342
418 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2028-12-31 | 2028 | 180 | 7 | 2028-07-04 | low | med | med | high | high | 1500000 | 1460980 | 1558652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 600000 | 750000 | 0 | 0 | 1500000 | 152.9836 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | Yes | no | Yes | Yes | Yes | no | 5 | 5 | 3 | 1 | 3 | 4 | 1 | 1 | 1 | 53.33% | 6 | 2 | 2 | 1 | 5 | 5 | 1 | 53.33% | 6 |  | 267.7598
419 | L2 | FACILITY | MEASUREMENT |  | CALIBRATION | North Bay | 2029-12-31 | 2029 | 223 | 2 | 2029-05-22 | low | high | low | med | high | 200000 | 254000 | 258562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 80000 | 100000 | 200000 | 240.276 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | Yes | no | no | no | no | Yes | 1 | 1 | 3 | 1 | 3 | 4 | 4 | 2 | 2 | 46.67% | 5 | 2 | 1 | 1 | 4 | 4 | 2 | 46.67% | 5 |  | 1300.7103
419 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2025-07-31 | 2025 | 85 | 2 | 2025-05-07 | high | med | low | med | high | 520000 | 590076 | 591552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 208000 | 260000 | 0 | 0 | 520000 | 500.6594 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 24.44% | 3 | 2 | 2 | 1 | 5 | 4 | 5 | 63.33% | 7 |  | 267.7598
420 | L1 | FACILITY | MEASUREMENT |  | CALIBRATION | Winnipeg | 2027-03-31 | 2027 | 60 | 2 | 2027-01-30 | low | low | high | high | med | 200000 | 139629 | 131217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 120000 | 20000 | 0 | 0 | 200000 | 246.3806 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | no | Yes | no | no | Yes | Yes | no | Yes | 2 | 4 | 2 | 1 | 1 | 5 | 3 | 3 | 3 | 53.33% | 6 | 2 | 3 | 1 | 2 | 2 | 4 | 46.67% | 5 |  | 8429.71
420 | L2 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Winnipeg | 2025-07-31 | 2025 | 200 | 5 | 2025-01-12 | low | high | med | low | low | 800000 | 817249 | 857404 | 0 | 0 | 0 | 0 | 80000 | 320000 | 400000 | 0 | 0 | 0 | 0 | 0 | 800000 | 116.0893 | EXPENSE | Yes | NO outage |  | X |  | X | X | no | no | no | no | Yes | Yes | no | Yes | Yes | 3 | 1 | 4 | 3 | 5 | 3 | 5 | 4 | 1 | 64.44% | 7 | 5 | 2 | 1 | 2 | 1 | 1 | 40% | 4 |  | 267.7598
421 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2026-12-31 | 2026 | 170 | 5 | 2026-07-14 | med | low | low | med | med | 400000 | 406220 | 406135 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 33.5343 | CAPITAL | Yes | Pipeline segment | X | X | X | X |  | no | no | Yes | no | Yes | no | Yes | no | Yes | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 24.44% | 3 | 3 | 3 | 1 | 1 | 4 | 1 | 43.33% | 5 |  | 17599.3754
422 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Winnipeg | 2025-03-31 | 2025 | 160 | 15 | 2024-10-22 | med | low | low | high | med | 500000 | 513676 | 518168 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 0 | 0 | 0 | 0 | 500000 | 511.7996 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 5 | 5 | 4 | 3 | 5 | 2 | 3 | 4 | 1 | 71.11% | 8 | 1 | 3 | 1 | 1 | 3 | 1 | 33.33% | 4 |  | 7024.2246
423 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2025-10-31 | 2025 | 200 | 8 | 2025-04-14 | low | low | med | med | med | 500000 | 501921 | 501943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 500000 | 47.5442 | EXPENSE | No | Pipeline segment | X |  |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 5 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 68.89% | 7 | 1 | 4 | 1 | 4 | 2 | 4 | 53.33% | 6 |  | 1591.1704
424 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2025-03-31 | 2025 | 150 | 7 | 2024-11-01 | low | high | low | low | high | 1900000 | 1900004 | 1908751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 1140000 | 190000 | 1900000 | 44.5632 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  | X |  | Yes | Yes | no | no | no | no | no | no | Yes | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 5 | 44.44% | 5 | 3 | 1 | 1 | 4 | 3 | 3 | 50% | 5 |  | 6832.4917
425 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2025-12-31 | 2025 | 194 | 10 | 2025-06-20 | low | high | low | med | low | 350000 | 835683 | 830953 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 35000 | 280000 | 35000 | 0 | 700000 | 55.3744 | CAPITAL | No | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | Yes | no | Yes | no | 4 | 2 | 2 | 4 | 3 | 5 | 3 | 5 | 3 | 68.89% | 7 | 4 | 1 | 1 | 5 | 5 | 2 | 60% | 6 |  | 330
426 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2025-03-31 | 2025 | 180 | 8 | 2024-10-02 | high | med | high | high | low | 450000 | 479835 | 487417 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 0 | 0 | 0 | 450000 | 412.8922 | CAPITAL | No | pipeline segment outage | X |  |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 3 | 3 | 2 | 4 | 2 | 5 | 1 | 2 | 1 | 51.11% | 6 | 3 | 1 | 1 | 3 | 4 | 5 | 56.67% | 6 |  | 5845
427 | L1 | FACILITY | MEASUREMENT |  | METER REPLACEMENT | Ottawa | 2025-12-31 | 2025 | 329 | 5 | 2025-02-05 | high | high | low | high | med | 1000000 | 983774 | 985478 | 0 | 0 | 300000 | 600000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 90.8397 | CAPITAL | Yes | pipeline segment outage |  | X | X |  | X | Yes | Yes | no | no | no | Yes | Yes | no | no | 2 | 5 | 3 | 3 | 4 | 1 | 2 | 3 | 4 | 60% | 6 | 3 | 3 | 1 | 4 | 3 | 5 | 63.33% | 7 |  | 5732.8906
428 | L1 | FACILITY | MEASUREMENT |  | METER REPLACEMENT | Calgary | 2026-12-31 | 2026 | 128 | 3 | 2026-08-25 | high | med | med | low | low | 600000 | 648079 | 647388 | 0 | 60000 | 480000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 30.6378 | CAPITAL | No | pipeline segment outage |  |  |  | X | X | no | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 4 | 1 | 4 | 1 | 1 | 2 | 4 | 1 | 46.67% | 5 | 2 | 5 | 5 | 5 | 1 | 4 | 73.33% | 8 |  | 6062.6028
428 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Calgary | 2025-07-31 | 2025 | 174 | 5 | 2025-02-07 | low | med | low | high | med | 350000 | 406595 | 482491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 280000 | 35000 | 0 | 350000 | 284.7276 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 2 | 2 | 2 | 1 | 2 | 4 | 5 | 1 | 2 | 46.67% | 5 | 2 | 3 | 1 | 5 | 1 | 4 | 53.33% | 6 |  | 3077.9635
429 | L1 | FACILITY | MECHANICAL |  | FUEL GAS HEATING | Quebec City | 2025-10-31 | 2025 | 299 | 2 | 2025-01-05 | med | low | low | high | med | 750000 | 745237 | 701880 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 750000 | 158.2455 | CAPITAL | Yes | Station outage | X | X | X | X |  | Yes | no | Yes | Yes | Yes | Yes | no | no | no | 5 | 1 | 3 | 4 | 3 | 2 | 2 | 1 | 2 | 51.11% | 6 | 4 | 3 | 1 | 4 | 1 | 3 | 53.33% | 6 |  | 5097.2605
430 | L1 | FACILITY | MEASUREMENT |  | METER REPLACEMENT | Ottawa | 2026-12-31 | 2026 | 329 | 5 | 2026-02-05 | high | high | low | high | med | 600000 | 587747 | 586001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 360000 | 60000 | 600000 | 90.8397 | CAPITAL | Yes | pipeline segment outage |  | X | X |  | X | Yes | Yes | no | no | no | Yes | Yes | no | no | 1 | 2 | 2 | 3 | 3 | 4 | 3 | 1 | 2 | 46.67% | 5 | 2 | 5 | 1 | 2 | 5 | 3 | 60% | 6 |  | 3506.8708
430 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2025-07-31 | 2025 | 191 | 10 | 2025-01-21 | high | med | low | high | high | 350000 | 379453 | 378408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 350000 | 58.7845 | CAPITAL | No | Pipeline segment |  |  | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 1 | 4 | 3 | 1 | 5 | 2 | 5 | 3 | 60% | 6 | 2 | 4 | 1 | 5 | 5 | 2 | 63.33% | 7 |  | 13582.277
431 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2025-12-31 | 2025 | 211 | 8 | 2025-06-03 | low | low | low | high | high | 500000 | 682395 | 696748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 500000 | 22.5065 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | no | no | no | Yes | no | no | no | Yes | 5 | 5 | 3 | 2 | 4 | 5 | 4 | 4 | 4 | 80% | 8 | 2 | 1 | 1 | 1 | 5 | 5 | 50% | 5 |  | 7709.8457
432 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2025-07-31 | 2025 | 323 | 8 | 2024-09-11 | high | med | med | high | med | 350000 | 318965 | 339197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 350000 | 71.4985 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 2 | 2 | 2 | 3 | 2 | 3 | 5 | 1 | 2 | 48.89% | 5 | 3 | 2 | 1 | 5 | 2 | 2 | 50% | 5 |  | 7110.0938
433 | L3 | FACILITY | MAJOR EQUIP |  | REPAIR | Regina | 2027-12-31 | 2025 | 307 | 4 | 2027-02-27 | high | high | low | high | med | 201736 | 315757 | 409549 | 0 | 0 | 0 | 0 | 60520.8 | 121041.6 | 20173.6 | 0 | 0 | 0 | 0 | 0 | 201736 | 946.5584 | EXPENSE | Yes | Unit outage |  | X | X |  | X | no | no | Yes | no | Yes | Yes | Yes | no | no | 2 | 3 | 3 | 2 | 3 | 1 | 3 | 1 | 1 | 42.22% | 5 | 4 | 5 | 1 | 4 | 1 | 3 | 60% | 6 |  | 4391.6369
434 | L1 | FACILITY | MAJOR EQUIP |  | REPAIR | North Bay | 2026-03-31 | 2026 | 318 | 4 | 2025-05-17 | low | low | high | med | med | 1782115 | 1872852 | 1850714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178211.5 | 712846 | 891057.5 | 0 | 1782115 | 40.9465 | EXPENSE | Yes | Unit outage |  |  | X | X | X | no | Yes | no | no | no | Yes | no | Yes | Yes | 4 | 4 | 2 | 1 | 1 | 2 | 5 | 5 | 5 | 64.44% | 7 | 2 | 3 | 1 | 2 | 5 | 5 | 60% | 6 |  | 5521.3731
434 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Saskatoon | 2028-12-31 | 2028 | 100 | 8 | 2028-09-22 | high | low | med | med | high | 300000 | 805802 | 891083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 300000 | 36.3611 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | no | Yes | no | no | Yes | no | no | Yes | no | 1 | 1 | 2 | 2 | 2 | 5 | 3 | 1 | 1 | 40% | 4 | 5 | 4 | 5 | 3 | 2 | 1 | 66.67% | 7 |  | 4314.1949
435 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2025-07-31 | 2025 | 165 | 2 | 2025-02-16 | low | low | low | high | low | 350000 | 482300 | 486971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 350000 | 593.4244 | EXPENSE | No | Pipeline segment | X | X | X |  | X | no | no | Yes | no | no | no | Yes | Yes | Yes | 3 | 2 | 1 | 1 | 2 | 1 | 4 | 3 | 4 | 46.67% | 5 | 4 | 2 | 1 | 2 | 4 | 1 | 46.67% | 5 |  | 4858.8867
436 | L3 | FACILITY | MAJOR EQUIP |  | REPAIR | Regina | 2028-12-31 | 2028 | 247 | 7 | 2028-04-28 | high | low | low | low | low | 900542 | 960268 | 1273533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90054.2 | 360216.8 | 450271 | 0 | 0 | 900542 | 141.4185 | EXPENSE | Yes | Unit outage |  | X | X | X | X | no | Yes | Yes | no | no | no | no | no | Yes | 1 | 5 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 35.56% | 4 | 5 | 5 | 5 | 4 | 3 | 2 | 80% | 8 |  | 278.7236
436 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2026-12-31 | 2026 | 272 | 8 | 2026-04-03 | med | med | med | low | med | 350000 | 444414 | 440670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 350000 | 101.6158 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 3 | 3 | 4 | 1 | 2 | 2 | 3 | 1 | 1 | 44.44% | 5 | 5 | 5 | 1 | 1 | 3 | 5 | 66.67% | 7 |  | 2178.0735
437 | L1 | FACILITY | MAJOR EQUIP |  | REPAIR | Winnipeg | 2026-12-31 | 2026 | 108 | 4 | 2026-09-14 | high | med | low | low | high | 797261 | 334282 | 1027178 | 0 | 0 | 0 | 79726.1 | 318904.4 | 398630.5 | 0 | 0 | 0 | 0 | 0 | 0 | 797261 | 128.8384 | EXPENSE | No | Unit outage | X |  | X | X | X | no | Yes | Yes | Yes | Yes | no | no | no | Yes | 4 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 40% | 4 | 5 | 2 | 1 | 3 | 3 | 3 | 56.67% | 6 |  | 3358
437 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2025-10-31 | 2025 | 200 | 7 | 2025-04-14 | high | low | high | low | high | 750000 | 875896 | 878514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 300000 | 375000 | 0 | 0 | 750000 | 24.8857 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  |  | no | Yes | no | Yes | no | no | no | no | Yes | 2 | 4 | 2 | 5 | 2 | 1 | 2 | 2 | 2 | 48.89% | 5 | 4 | 2 | 5 | 1 | 3 | 3 | 60% | 6 |  | 1090.5382
438 | L3 | FACILITY | MAJOR EQUIP |  | REPAIR | Saskatoon | 2028-03-31 | 2028 | 255 | 8 | 2027-07-20 | med | high | high | low | med | 255000 | 299343 | 290897 | 76500 | 153000 | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 627.0632 | EXPENSE | Yes | Unit outage | X |  |  | X |  | Yes | no | no | no | Yes | no | no | Yes | no | 3 | 5 | 2 | 2 | 4 | 4 | 5 | 5 | 4 | 75.56% | 8 | 1 | 4 | 1 | 1 | 5 | 4 | 53.33% | 6 |  | 646
438 | L2 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Quebec City | 2029-12-31 | 2029 | 267 | 4 | 2029-04-08 | low | med | med | high | high | 1820507 | 1988450 | 1950473 | 182050.7 | 182050.7 | 1456405.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1820507 | 45.6177 | CAPITAL | Yes | Unit outage |  |  |  | X | X | Yes | no | no | no | Yes | no | no | no | Yes | 5 | 4 | 2 | 1 | 5 | 4 | 4 | 5 | 3 | 73.33% | 8 | 5 | 5 | 5 | 2 | 5 | 3 | 83.33% | 9 |  | 8501.4285
439 | L3 | FACILITY | MAJOR EQUIP |  | REPAIR | Saskatoon | 2028-07-31 | 2028 | 280 | 2 | 2027-10-25 | high | med | high | high | low | 95000 | 85000 | 87000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 38000 | 47500 | 0 | 95000 | 62.0325 | EXPENSE | Yes | Unit outage | X |  |  | X | X | Yes | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 4 | 2 | 4 | 3 | 2 | 1 | 4 | 2 | 55.56% | 6 | 4 | 4 | 1 | 4 | 2 | 4 | 63.33% | 7 |  | 3220.812
439 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2025-10-31 | 2025 | 160 | 15 | 2025-05-24 | high | high | med | high | high | 450000 | 428046 | 421693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 450000 | 82.8772 | CAPITAL | No | Pipeline segment |  | X |  | X | X | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 2 | 3 | 1 | 3 | 5 | 5 | 63.33% | 7 |  | 4052.0846
440 | L3 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Ottawa | 2026-10-31 | 2026 | 254 | 4 | 2026-02-19 | med | low | med | med | med | 1109165 | 1300190 | 1349541 | 0 | 0 | 0 | 0 | 0 | 110916.5 | 443666 | 554582.5 | 0 | 0 | 0 | 0 | 1109165 | 31.5139 | CAPITAL | Yes | Unit outage |  |  | X | X | X | Yes | Yes | no | Yes | no | no | no | no | no | 1 | 5 | 2 | 1 | 2 | 2 | 5 | 2 | 2 | 48.89% | 5 | 4 | 1 | 1 | 1 | 4 | 4 | 50% | 5 |  | 4526
440 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Montreal | 2025-03-31 | 2025 | 130 | 4 | 2024-11-21 | med | high | high | med | med | 3559855 | 3658888 | 3370070 | 355985.5 | 1423942 | 1779927.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3559855 | 87.8332 | CAPITAL | Yes | Unit outage | X |  |  |  | X | no | no | Yes | no | no | Yes | no | no | no | 2 | 1 | 2 | 1 | 4 | 2 | 3 | 1 | 5 | 46.67% | 5 | 3 | 1 | 1 | 3 | 4 | 1 | 43.33% | 5 |  | 6062.6028
441 | L2 | FACILITY | MAJOR EQUIP |  | REPAIR | Toronto | 2026-12-31 | 2026 | 49 | 4 | 2026-11-12 | med | low | low | med | low | 430601 | 714721 | 1089646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43060.1 | 172240.4 | 215300.5 | 0 | 430601 | 253.0524 | EXPENSE | Yes | Unit outage |  | X | X | X | X | no | no | no | no | no | no | no | Yes | no | 5 | 5 | 3 | 1 | 4 | 1 | 3 | 2 | 3 | 60% | 6 | 4 | 4 | 1 | 5 | 2 | 2 | 60% | 6 |  | 6039.002
442 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Toronto | 2029-12-31 | 2029 | 58 | 8 | 2029-11-03 | med | low | high | med | low | 732345 | 820669 | 850502 | 0 | 0 | 0 | 0 | 73234.5 | 292938 | 366172.5 | 0 | 0 | 0 | 0 | 0 | 732345 | 252.6817 | CAPITAL | Yes | Unit outage | [5 empty] | no | no | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 3 | 2 | 1 | 5 | 3 | 1 | 1 | 5 | 51.11% | 6 | 4 | 4 | 1 | 5 | 5 | 3 | 73.33% | 8 |  | 267.7598
441 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2025-12-31 | 2025 | 85 | 7 | 2025-10-07 | med | med | med | low | low | 2000000 | 2054742 | 2048761 | 0 | 0 | 0 | 0 | 200000 | 1600000 | 200000 | 0 | 0 | 0 | 0 | 0 | 2000000 | 57.9714 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 3 | 2 | 4 | 4 | 1 | 1 | 2 | 5 | 2 | 53.33% | 6 | 4 | 5 | 5 | 1 | 4 | 1 | 66.67% | 7 |  | 2610.3898
442 | L1 | FACILITY | MAJOR EQUIP |  | REPAIR | Saskatoon | 2027-10-31 | 2028 | 25 | 7 | 2027-10-06 | med | low | low | high | med | 350000 | 535575 | 525049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 350000 | 38.5967 | EXPENSE | Yes | Unit outage | X | X | X |  |  | Yes | Yes | no | no | no | no | Yes | no | Yes | 5 | 3 | 3 | 3 | 1 | 5 | 4 | 4 | 3 | 68.89% | 7 | 1 | 1 | 1 | 1 | 2 | 3 | 30% | 3 |  | 1846.619
443 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | North Bay | 2029-07-31 | 2029 | 157 | 4 | 2029-02-24 | low | low | med | high | med | 2481256 | 2167672 | 2503476 | 0 | 0 | 0 | 248125.6 | 1985004.8 | 248125.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2481256 | 33.9898 | CAPITAL | Yes | Unit outage |  | X | X | X | X | Yes | no | Yes | no | Yes | no | Yes | no | Yes | 2 | 2 | 2 | 3 | 1 | 3 | 4 | 1 | 4 | 48.89% | 5 | 2 | 4 | 1 | 5 | 2 | 5 | 63.33% | 7 |  | 6062.603
442 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2025-10-31 | 2025 | 154 | 10 | 2025-05-30 | high | med | low | low | low | 350000 | 379854 | 356546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 350000 | 25.9626 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 3 | 1 | 2 | 1 | 5 | 2 | 1 | 2 | 2 | 42.22% | 5 | 2 | 4 | 1 | 3 | 3 | 3 | 53.33% | 6 |  | 241.5599
443 | L2 | FACILITY | MAJOR EQUIP |  | REPAIR | Montreal | 2029-12-31 | 2029 | 148 | 7 | 2029-08-05 | low | high | high | med | med | 674006 | 553524 | 137499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67400.6 | 269602.4 | 337003 | 0 | 0 | 674006 | 20.4003 | EXPENSE | Yes | Unit outage |  | X |  | X | X | Yes | Yes | no | Yes | Yes | no | Yes | no | Yes | 4 | 2 | 4 | 1 | 3 | 2 | 2 | 5 | 4 | 60% | 6 | 3 | 2 | 1 | 2 | 1 | 2 | 36.67% | 4 |  | 9580.8769
444 | L1 | FACILITY | MAJOR EQUIP |  | REPAIR | Quebec City | 2029-12-31 | 2029 | 49 | 7 | 2029-11-12 | low | low | low | med | med | 850000 | 886000 | 910000 | 0 | 0 | 170000 | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 112.7399 | EXPENSE | Yes | Unit outage |  | X |  | X | X | no | no | Yes | Yes | no | no | no | no | Yes | 5 | 3 | 3 | 3 | 3 | 5 | 2 | 4 | 3 | 68.89% | 7 | 5 | 3 | 1 | 3 | 3 | 1 | 53.33% | 6 |  | 4785
443 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Calgary | 2025-12-31 | 2025 | 105 | 8 | 2025-09-17 | med | med | low | med | med | 350000 | 410000 | 410045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 350000 | 183.6307 | EXPENSE | Yes | Pipeline segment |  |  | X |  |  | no | no | Yes | Yes | no | Yes | no | Yes | no | 3 | 4 | 4 | 1 | 2 | 4 | 4 | 2 | 1 | 55.56% | 6 | 2 | 1 | 1 | 1 | 1 | 5 | 36.67% | 4 |  | 4995.3897
444 | L2 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Winnipeg | 2029-10-31 | 2029 | 100 | 4 | 2029-07-23 | low | med | med | low | low | 1708501 | 1963873 | 1943106 | 0 | 0 | 0 | 0 | 170850.1 | 1366800.8 | 170850.1 | 0 | 0 | 0 | 0 | 0 | 1708501 | 31.7885 | CAPITAL | Yes | Unit outage |  |  |  | X |  | no | Yes | Yes | no | Yes | Yes | Yes | Yes | no | 3 | 1 | 1 | 1 | 3 | 1 | 5 | 4 | 1 | 44.44% | 5 | 4 | 4 | 1 | 5 | 2 | 2 | 60% | 6 |  | 191.3942
445 | L1 | FACILITY | MAJOR EQUIP |  | GG MINOR OH | Montreal | 2026-07-31 | 2026 | 150 | 8 | 2026-03-03 | low | high | low | low | med | 1301814 | 1645284 | 1656042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130181.4 | 520725.6 | 650907 | 1301814 | 104.1656 | CAPITAL | Yes | Unit outage |  |  | X | X | X | no | Yes | no | Yes | Yes | no | no | no | Yes | 1 | 4 | 3 | 1 | 1 | 4 | 2 | 3 | 2 | 46.67% | 5 | 2 | 5 | 1 | 4 | 5 | 5 | 73.33% | 8 |  | 32.5005
446 | L3 | FACILITY | MAJOR EQUIP |  | REPAIR | Winnipeg | 2027-12-31 | 2027 | 187 | 4 | 2027-06-27 | high | med | low | high | low | 524525 | 270026 | 443557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52452.5 | 419620 | 52452.5 | 0 | 0 | 524525 | 84.5636 | EXPENSE | Yes | Unit outage | X | X | X | X | X | Yes | Yes | no | no | no | no | no | Yes | Yes | 5 | 5 | 2 | 4 | 1 | 3 | 2 | 2 | 3 | 60% | 6 | 1 | 4 | 5 | 1 | 1 | 3 | 50% | 5 |  | 267.7598
444 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | WINNIPEG | 2027-12-31 | 2027 | 141 | 8 | 2027-08-12 | low | med | high | med | low | 350000 | 818560 | 807036 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 31.5417 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 4 | 3 | 2 | 4 | 5 | 2 | 1 | 2 | 5 | 62.22% | 7 | 5 | 2 | 1 | 1 | 4 | 2 | 50% | 5 |  | 6993.5456
445 | L2 | FACILITY | MAJOR EQUIP |  | REPAIR | Calgary | 2028-07-31 | 2028 | 138 | 7 | 2028-03-15 | med | med | low | high | low | 279976 | 354614 | 246324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27997.6 | 111990.4 | 139988 | 0 | 0 | 279976 | 87.9804 | EXPENSE | Yes | Unit outage | X |  |  | X | X | no | Yes | Yes | Yes | no | Yes | no | no | Yes | 4 | 1 | 3 | 1 | 5 | 3 | 3 | 2 | 1 | 51.11% | 6 | 1 | 4 | 1 | 4 | 1 | 1 | 40% | 4 |  | 4447
445 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | North Bay | 2025-12-31 | 2025 | 150 | 2 | 2025-08-03 | high | high | low | med | low | 275000 | 364668 | 363142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 110000 | 137500 | 275000 | 898.364 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | Yes | no | no | no | Yes | Yes | Yes | Yes | no | 4 | 5 | 2 | 2 | 2 | 2 | 1 | 1 | 4 | 51.11% | 6 | 1 | 1 | 1 | 3 | 1 | 5 | 40% | 4 |  | 222.8052
446 | L1 | FACILITY | MAJOR EQUIP |  | REPAIR | Quebec City | 2027-12-31 | 2027 | 329 | 4 | 2027-02-05 | low | low | low | high | high | 717268 | 447194 | 557595 | 0 | 0 | 0 | 0 | 215180.4 | 430360.8 | 71726.8 | 0 | 0 | 0 | 0 | 0 | 717268 | 159.9953 | EXPENSE | Yes | Unit outage | X | X |  | X |  | no | Yes | no | Yes | Yes | Yes | no | no | Yes | 3 | 1 | 4 | 2 | 5 | 2 | 1 | 5 | 5 | 62.22% | 7 | 5 | 5 | 1 | 3 | 5 | 2 | 70% | 7 |  | 2078
446 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Regina | 2025-07-31 | 2025 | 200 | 10 | 2025-01-12 | high | high | med | low | high | 750000 | 745189 | 786550 | 75000 | 300000 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 57.545 | EXPENSE | No | NO outage | X |  | X |  | X | Yes | Yes | Yes | no | no | no | no | no | no | 2 | 1 | 2 | 2 | 5 | 4 | 4 | 3 | 4 | 60% | 6 | 5 | 3 | 1 | 2 | 1 | 5 | 56.67% | 6 |  | 840.2082
447 | L3 | FACILITY | MECHANICAL |  | REPAIR | Montreal | 2025-10-31 | 2025 | 120 | 1 | 2025-07-03 | high | high | low | med | low | 35220 | 30060 | 31745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3522 | 21132 | 10566 | 0 | 35220 | 327.759 | EXPENSE | Yes | Unit outage |  |  |  | X | X | Yes | Yes | Yes | no | no | no | no | no | no | 2 | 3 | 3 | 2 | 4 | 4 | 3 | 3 | 2 | 57.78% | 6 | 3 | 3 | 1 | 4 | 2 | 1 | 46.67% | 5 |  | 1184.9141
447 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Winnipeg | 2026-12-31 | 2026 | 85 | 7 | 2026-10-07 | low | med | high | med | med | 2000000 | 1758655 | 1869566 | 200000 | 800000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 383.6846 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | no | no | Yes | Yes | Yes | no | 3 | 2 | 2 | 3 | 5 | 3 | 2 | 4 | 5 | 64.44% | 7 | 2 | 2 | 1 | 3 | 5 | 3 | 53.33% | 6 |  | 5000
448 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2025-12-31 | 2025 | 120 | 2 | 2025-09-02 | high | med | med | med | high | 350000 | 441828 | 446179 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 16.1628 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X | X | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 4 | 5 | 1 | 4 | 5 | 4 | 5 | 1 | 2 | 68.89% | 7 | 2 | 3 | 1 | 4 | 1 | 5 | 53.33% | 6 |  | 646
449 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2025-12-31 | 2025 | 200 | 4 | 2025-06-14 | med | high | high | med | low | 1800000 | 1909884 | 1937687 | 0 | 180000 | 1440000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 97.7988 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | no | no | Yes | no | no | no | no | no | Yes | 2 | 2 | 3 | 1 | 4 | 3 | 4 | 1 | 2 | 48.89% | 5 | 4 | 5 | 1 | 4 | 3 | 1 | 60% | 6 |  | 289
450 | L1 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Quebec City | 2025-12-31 | 2025 | 245 | 20 | 2025-04-30 | med | low | low | med | med | 28550000 | 28506803 | 28740397 | 2855000 | 11420000 | 14275000 | 0 | 0 | 0 | 0 | 0 | 2855000 | 11420000 | 14275000 | 0 | 57100000 | 96.8203 | CAPITAL | No | pipeline segment outage | X |  | X | X | X | Yes | no | no | no | Yes | Yes | Yes | Yes | no | 3 | 5 | 3 | 1 | 4 | 1 | 5 | 4 | 5 | 68.89% | 7 | 5 | 5 | 1 | 2 | 5 | 5 | 76.67% | 8 |  | 347
451 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2025-10-31 | 2025 | 150 | 4 | 2025-06-03 | med | med | low | high | low | 1500000 | 1871375 | 1900437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 600000 | 750000 | 0 | 1500000 | 20.7353 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X | X | Yes | no | Yes | Yes | no | Yes | Yes | no | Yes | 4 | 3 | 4 | 2 | 3 | 3 | 4 | 2 | 1 | 57.78% | 6 | 4 | 4 | 1 | 2 | 2 | 2 | 50% | 5 |  | 158885
452 | L3 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Saskatoon | 2025-10-31 | 2025 | 180 | 4 | 2025-05-04 | med | high | low | high | med | 1980019 | 1980030 | 1987975 | 0 | 0 | 0 | 198001.9 | 792007.6 | 990009.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1980019 | 68.0789 | EXPENSE | Yes | Unit outage | X | X | X |  | X | Yes | Yes | Yes | no | no | no | Yes | no | Yes | 3 | 2 | 1 | 2 | 5 | 5 | 3 | 1 | 4 | 57.78% | 6 | 3 | 5 | 1 | 5 | 4 | 1 | 63.33% | 7 |  | 1207.7993
453 | L2 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | North Bay | 2025-07-31 | 2025 | 254 | 25 | 2024-11-19 | med | high | med | high | med | 1405000 | 15158244 | 15509480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140500 | 562000 | 702500 | 0 | 1405000 | 80.1164 | CAPITAL | Yes | pipeline segment outage | X |  |  | X | X | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 1 | 2 | 2 | 3 | 2 | 3 | 5 | 1 | 1 | 44.44% | 5 | 4 | 2 | 1 | 5 | 5 | 5 | 73.33% | 8 |  | 1785
454 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Montreal | 2025-03-31 | 2025 | 200 | 15 | 2024-09-12 | med | low | low | high | high | 750000 | 1164753 | 1662254 | 0 | 0 | 0 | 0 | 75000 | 300000 | 375000 | 0 | 0 | 0 | 0 | 0 | 750000 | 91.2063 | EXPENSE | No | Pipeline segment |  |  | X |  |  | no | Yes | Yes | no | Yes | no | Yes | no | no | 4 | 1 | 3 | 3 | 4 | 3 | 4 | 3 | 3 | 62.22% | 7 | 3 | 5 | 1 | 2 | 1 | 3 | 50% | 5 |  | 898
455 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Edmonton | 2025-12-31 | 2025 | 60 | 15 | 2025-11-01 | high | high | low | med | med | 850000 | 827077 | 841856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 340000 | 425000 | 0 | 0 | 850000 | 80.7922 | EXPENSE | Yes | pipeline segment outage |  |  | X |  | X | no | Yes | Yes | no | Yes | Yes | Yes | no | Yes | 3 | 2 | 1 | 5 | 3 | 3 | 1 | 1 | 1 | 44.44% | 5 | 3 | 5 | 1 | 5 | 1 | 1 | 53.33% | 6 |  | 172.2548
456 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | North Bay | 2026-10-31 | 2026 | 200 | 8 | 2026-04-14 | low | high | med | high | med | 750000 | 611769 | 669250 | 0 | 0 | 0 | 0 | 75000 | 300000 | 375000 | 0 | 0 | 0 | 0 | 0 | 750000 | 85.7283 | EXPENSE | Yes | Pipeline segment | x | x | x | x | x | Yes | x | NR | NR | NR | NR | NR | No | Yes | 3 | 5 | 2 | 4 | 2 | 2 | 3 | 3 | 2 | 57.78% | 6 | 4 | 5 | 5 | 4 | 3 | 5 | 86.67% | 9 |  | 16.9273
456 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Montreal | 2025-10-31 | 2025 | 120 | 8 | 2025-07-03 | med | med | high | low | med | 1000000 | 1022203 | 1280954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 400000 | 500000 | 0 | 1000000 | 44.865 | EXPENSE | No | NO outage |  | X | X | X |  | Yes | Yes | no | no | Yes | no | no | no | no | 5 | 2 | 1 | 4 | 4 | 2 | 1 | 3 | 5 | 60% | 6 | 2 | 5 | 1 | 2 | 3 | 4 | 56.67% | 6 |  | 172.2548
457 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Quebec City | 2028-12-31 | 2028 | 150 | 15 | 2028-08-03 | low | med | low | low | low | 550000 | 499129 | 513827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 550000 | 77.5311 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | no | Yes | no | Yes | 4 | 3 | 1 | 4 | 3 | 3 | 3 | 5 | 1 | 60% | 6 | 2 | 2 | 1 | 2 | 3 | 4 | 46.67% | 5 |  | 23717.24
457 | L1 | FACILITY | AUTOMATION & CONTROLS |  | UNIT CONTROLS OBS | Calgary | 2025-12-31 | 2025 | 291 | 5 | 2025-03-15 | med | low | high | high | med | 1366920 | 1345102 | 1333738 | 0 | 0 | 0 | 136692 | 546768 | 683460 | 0 | 0 | 0 | 0 | 0 | 0 | 1366920 | 6.8576 | CAPITAL | Yes | Station outage |  | X | X |  | X | no | no | Yes | no | no | no | no | Yes | Yes | 5 | 1 | 4 | 2 | 2 | 4 | 5 | 4 | 2 | 64.44% | 7 | 1 | 3 | 1 | 5 | 5 | 1 | 53.33% | 6 |  | 191.3942
458 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Toronto | 2026-07-31 | 2026 | 150 | 12 | 2026-03-03 | med | high | high | low | high | 300000 | 362980 | 335201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 120000 | 150000 | 0 | 0 | 300000 | 1124.6434 | EXPENSE | No | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 2 | 2 | 1 | 1 | 1 | 2 | 5 | 2 | 3 | 42.22% | 5 | 4 | 4 | 1 | 1 | 5 | 3 | 60% | 6 |  | 560.1412
458 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2025-10-31 | 2025 | 150 | 5 | 2025-06-03 | med | high | high | high | high | 400000 | 434790 | 444911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 160000 | 200000 | 400000 | 114.2737 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 5 | 2 | 2 | 5 | 5 | 2 | 5 | 2 | 2 | 66.67% | 7 | 2 | 3 | 1 | 2 | 1 | 2 | 36.67% | 4 |  | 382.7885
459 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | North Bay | 2028-12-31 | 2028 | 150 | 8 | 2028-08-03 | high | med | high | high | low | 550000 | 529833 | 522678 | 55000 | 0 | 55000 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 78.3491 | EXPENSE | Yes | Pipeline segment |  |  |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 5 | 4 | 4 | 5 | 1 | 5 | 1 | 3 | 2 | 66.67% | 7 | 1 | 5 | 1 | 2 | 1 | 2 | 40% | 4 |  | 16593.69
459 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Regina | 2025-07-31 | 2025 | 150 | 2 | 2025-03-03 | med | med | med | high | med | 650000 | 655557 | 668033 | 0 | 0 | 0 | 0 | 65000 | 260000 | 325000 | 0 | 0 | 0 | 0 | 0 | 650000 | 224.9398 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | Yes | no | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 2 | 35.56% | 4 | 1 | 1 | 1 | 3 | 2 | 1 | 30% | 3 |  | 173.2929
460 | L1 | FACILITY | AUTOMATION & CONTROLS |  | UNIT CONTROLS OBS | Montreal | 2026-03-31 | 2026 | 158 | 3 | 2025-10-24 | med | med | low | med | high | 1941215 | 1986313 | 1927545 | 0 | 0 | 0 | 0 | 0 | 0 | 194121.5 | 776486 | 970607.5 | 0 | 0 | 0 | 1941215 | 98.5476 | CAPITAL | No | Station outage | X |  | X | X | X | no | Yes | Yes | no | no | no | no | no | no | 1 | 3 | 1 | 1 | 4 | 2 | 5 | 2 | 2 | 46.67% | 5 | 3 | 5 | 1 | 4 | 1 | 3 | 56.67% | 6 |  | 3077.9635
461 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Toronto | 2026-12-31 | 2026 | 150 | 10 | 2026-08-03 | low | med | med | low | low | 550000 | 870821 | 874947 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 250.7139 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | no | no | no | Yes | 5 | 5 | 3 | 1 | 5 | 2 | 1 | 5 | 5 | 71.11% | 8 | 1 | 5 | 1 | 2 | 1 | 3 | 43.33% | 5 |  | 1083.35
460 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | North Bay | 2025-07-31 | 2025 | 100 | 2 | 2025-04-22 | low | med | high | high | med | 950000 | 1089229 | 1080770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 | 380000 | 475000 | 0 | 950000 | 128.235 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | Yes | no | Yes | Yes | Yes | 4 | 4 | 3 | 5 | 4 | 2 | 1 | 4 | 4 | 68.89% | 7 | 3 | 2 | 1 | 1 | 3 | 1 | 36.67% | 4 |  | 900.2043
461 | L3 | FACILITY | AUTOMATION & CONTROLS |  | UNIT CONTROLS OBS | Montreal | 2026-12-31 | 2026 | 303 | 5 | 2026-03-03 | med | high | med | high | low | 1377445 | 1433590 | 1490827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137744.5 | 1101956 | 137744.5 | 0 | 0 | 1377445 | 14.4786 | CAPITAL | No | Station outage |  | X | X | X |  | no | no | Yes | Yes | no | Yes | Yes | no | no | 2 | 5 | 2 | 2 | 5 | 4 | 5 | 3 | 3 | 68.89% | 7 | 5 | 4 | 1 | 5 | 1 | 2 | 60% | 6 |  | 5875
462 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | North Bay | 2027-10-31 | 2027 | 180 | 10 | 2027-05-04 | med | low | high | med | high | 300000 | 314592 | 316431 | 0 | 0 | 0 | 0 | 30000 | 120000 | 150000 | 0 | 0 | 0 | 0 | 0 | 300000 | 134.8065 | EXPENSE | No | Pipeline segment | X | X |  |  | X | Yes | no | Yes | Yes | no | no | no | no | no | 4 | 4 | 4 | 1 | 1 | 5 | 4 | 3 | 5 | 68.89% | 7 | 4 | 4 | 1 | 2 | 2 | 1 | 46.67% | 5 |  | 1846.619
461 | L1 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Winnipeg | 2027-03-31 | 2027 | 300 | 15 | 2026-06-04 | low | med | high | med | high | 6870000 | 6877100 | 7401079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687000 | 2748000 | 3435000 | 6870000 | 369.6154 | CAPITAL | Yes | pipeline segment outage | X | X |  |  | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 5 | 5 | 3 | 4 | 4 | 5 | 5 | 3 | 5 | 86.67% | 9 | 2 | 4 | 1 | 1 | 5 | 2 | 50% | 5 |  | 749.7244
462 | L1 | FACILITY | AUTOMATION & CONTROLS |  | UNIT CONTROLS OBS | Edmonton | 2028-12-31 | 2028 | 279 | 5 | 2028-03-27 | high | med | med | high | med | 1625081 | 1659514 | 1659910 | 0 | 162508.1 | 650032.4 | 812540.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1625081 | 227.1562 | CAPITAL | No | Station outage | X | X | X |  | X | Yes | no | no | no | Yes | no | no | no | Yes | 5 | 5 | 3 | 2 | 5 | 4 | 4 | 4 | 5 | 82.22% | 9 | 1 | 2 | 1 | 4 | 4 | 4 | 53.33% | 6 |  | 2789
463 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Montreal | 2030-03-31 | 2030 | 200 | 8 | 2029-09-12 | med | high | med | med | high | 550000 | 467194 | 477060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 0 | 550000 | 49.109 | EXPENSE | No | Pipeline segment | X | X |  |  |  | Yes | Yes | no | no | Yes | no | no | Yes | Yes | 4 | 5 | 2 | 2 | 3 | 2 | 4 | 2 | 4 | 62.22% | 7 | 3 | 4 | 1 | 5 | 5 | 2 | 66.67% | 7 |  | 203.1281
462 | L1 | FACILITY | MECHANICAL |  | AERIAL COOLER FAN | Ottawa | 2025-12-31 | 2025 | 200 | 4 | 2025-06-14 | high | med | med | low | low | 200000 | 215612 | 269294 | 0 | 0 | 0 | 20000 | 80000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 158.7999 | CAPITAL | Yes | Unit outage |  |  |  | X |  | no | Yes | no | no | no | no | Yes | Yes | no | 5 | 3 | 4 | 1 | 1 | 4 | 4 | 3 | 1 | 57.78% | 6 | 5 | 2 | 1 | 5 | 4 | 3 | 66.67% | 7 |  | 41798.5165
463 | L1 | FACILITY | AUTOMATION & CONTROLS |  | UNIT CONTROLS OBS | Ottawa | 2028-12-31 | 2028 | 313 | 5 | 2028-02-22 | med | low | low | high | high | 2560778 | 2330462 | 3258048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256077.8 | 1024311.2 | 1280389 | 0 | 0 | 2560778 | 675.1875 | CAPITAL | No | Station outage |  |  | X |  |  | Yes | Yes | Yes | no | no | no | no | no | Yes | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 37.78% | 4 | 3 | 4 | 1 | 2 | 5 | 5 | 66.67% | 7 |  | 643.2391
464 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Edmonton | 2028-12-31 | 2028 | 150 | 10 | 2028-08-03 | med | low | med | low | med | 550000 | 750527 | 763520 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 0 | 0 | 550000 | 21.7053 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | no | Yes | no | no | Yes | no | Yes | 4 | 1 | 4 | 4 | 1 | 4 | 3 | 3 | 3 | 60% | 6 | 2 | 4 | 1 | 3 | 5 | 3 | 60% | 6 |  | 746.1723
463 | L1 | FACILITY | MAJOR EQUIP |  | MAJOR OH | North Bay | 2025-03-31 | 2025 | 42 | 4 | 2025-02-17 | low | low | med | low | med | 1587007 | 1927112 | 1764093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158700.7 | 634802.8 | 793503.5 | 0 | 1587007 | 111.1585 | CAPITAL | Yes | Unit outage |  | X |  | X | X | no | Yes | no | Yes | Yes | Yes | no | no | Yes | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 4 | 3 | 53.33% | 6 | 1 | 5 | 1 | 2 | 3 | 3 | 50% | 5 |  | 32.5005
464 | L3 | FACILITY | MECHANICAL |  | AGB | Saskatoon | 2026-10-31 | 2026 | 180 | 1 | 2026-05-04 | med | low | low | high | low | 79175 | 78184 | 85441 | 0 | 0 | 0 | 0 | 0 | 7917.5 | 31670 | 39587.5 | 0 | 0 | 0 | 0 | 79175 | 1206.7458 | EXPENSE | Yes | Unit outage | X |  |  |  |  | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 4 | 1 | 1 | 2 | 3 | 4 | 5 | 3 | 3 | 57.78% | 6 | 5 | 2 | 1 | 4 | 2 | 4 | 60% | 6 |  | 2078
465 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | North Bay | 2027-12-31 | 2027 | 150 | 1 | 2027-08-03 | med | med | high | med | low | 550000 | 531626 | 566466 | 55000 | 220000 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 618.2189 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | Yes | no | Yes | Yes | Yes | no | no | no | Yes | 3 | 3 | 3 | 3 | 4 | 2 | 4 | 3 | 3 | 62.22% | 7 | 1 | 1 | 1 | 4 | 5 | 1 | 43.33% | 5 |  | 9580.8769
464 | L2 | FACILITY | ELECTRICAL |  | TEG | Quebec City | 2025-12-31 | 2025 | 213 | 1 | 2025-06-01 | low | high | high | high | high | 150000 | 162725 | 168152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 60000 | 75000 | 0 | 0 | 150000 | 678.633 | EXPENSE | Yes | Unit outage | [5 empty] | no | no | no | Yes | Yes | Yes | no | no | Yes | 3 | 1 | 3 | 2 | 5 | 5 | 5 | 4 | 5 | 73.33% | 8 | 4 | 3 | 1 | 1 | 2 | 2 | 43.33% | 5 |  | 1022.4116
465 | L3 | FACILITY | MECHANICAL |  | AGB | Saskatoon | 2029-10-31 | 2029 | 180 | 1 | 2029-05-04 | med | low | low | high | low | 79175 | 78184 | 85441 | 0 | 0 | 0 | 0 | 7917.5 | 31670 | 39587.5 | 0 | 0 | 0 | 0 | 0 | 79175 | 1206.7458 | EXPENSE | Yes | Unit outage | X |  |  |  |  | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 3 | 2 | 3 | 3 | 4 | 4 | 4 | 1 | 5 | 64.44% | 7 | 4 | 2 | 1 | 4 | 1 | 4 | 53.33% | 6 |  | 2679.519
466 | L1 | FACILITY | MAJOR EQUIP |  | MAJOR OH | North Bay | 2026-03-31 | 2026 | 116 | 4 | 2025-12-05 | med | high | med | high | med | 3179675 | 3341721 | 3333892 | 0 | 0 | 0 | 0 | 0 | 0 | 317967.5 | 1271870 | 1589837.5 | 0 | 0 | 0 | 3179675 | 3.1976 | CAPITAL | Yes | Unit outage | X |  | X | X |  | no | Yes | Yes | no | no | no | no | Yes | no | 4 | 5 | 4 | 1 | 5 | 3 | 4 | 2 | 4 | 71.11% | 8 | 1 | 4 | 1 | 4 | 1 | 2 | 43.33% | 5 |  | 1300.71
465 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2027-12-31 | 2027 | 85 | 4 | 2027-10-07 | med | high | high | low | high | 400000 | 458461 | 454334 | 0 | 0 | 40000 | 160000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 125.3264 | EXPENSE | No | Pipeline segment | X |  | X |  | X | no | Yes | no | Yes | no | Yes | no | Yes | no | 5 | 4 | 3 | 3 | 4 | 4 | 2 | 3 | 3 | 68.89% | 7 | 5 | 3 | 1 | 5 | 4 | 4 | 73.33% | 8 |  | 1022.4116
466 | L3 | FACILITY | MAJOR EQUIP |  | MAJOR OH | Saskatoon | 2026-12-31 | 2026 | 156 | 4 | 2026-07-28 | low | high | low | low | med | 1186829 | 1367226 | 1320125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356048.7 | 712097.4 | 118682.9 | 0 | 0 | 1186829 | 111.2313 | CAPITAL | Yes | Unit outage |  |  | X | X | X | Yes | no | Yes | Yes | no | no | Yes | no | no | 4 | 1 | 4 | 3 | 1 | 4 | 4 | 4 | 4 | 64.44% | 7 | 2 | 2 | 5 | 3 | 5 | 2 | 63.33% | 7 |  | 172.2548
467 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Edmonton | 2026-12-31 | 2026 | 150 | 4 | 2026-08-03 | med | low | high | low | med | 550000 | 600984 | 601355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 550000 | 83.4126 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | no | no | no | Yes | Yes | Yes | Yes | no | Yes | 3 | 5 | 2 | 3 | 5 | 5 | 4 | 1 | 3 | 68.89% | 7 | 4 | 1 | 1 | 4 | 4 | 2 | 53.33% | 6 |  | 222.8052
466 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | Montreal | 2028-12-31 | 2028 | 226 | 4 | 2028-05-19 | med | high | high | high | high | 250000 | 285616 | 285266 | 25000 | 0 | 25000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 68.1605 | EXPENSE | No | NO |  |  | X |  | X | no | no | no | Yes | no | Yes | Yes | no | no | 2 | 1 | 1 | 1 | 3 | 5 | 2 | 1 | 3 | 42.22% | 5 | 5 | 4 | 5 | 4 | 2 | 1 | 70% | 7 |  | 458
467 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Saskatoon | 2028-12-31 | 2028 | 170 | 4 | 2028-07-14 | med | low | low | med | med | 550000 | 586220 | 590135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 550000 | 33.5343 | EXPENSE | Yes | Pipeline segment | X | X | X | X |  | no | no | Yes | no | Yes | no | Yes | no | Yes | 2 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 3 | 42.22% | 5 | 1 | 5 | 1 | 4 | 1 | 3 | 50% | 5 |  | 22170.3266
468 | L1 | FACILITY | MAJOR EQUIP |  | MAJOR OH | Saskatoon | 2028-12-31 | 2028 | 23 | 4 | 2028-12-08 | med | low | high | low | med | 2823542 | 2769725 | 2750123 | 0 | 0 | 0 | 0 | 564708.4 | 282354.2 | 1976479.4 | 0 | 0 | 0 | 0 | 0 | 2823542 | 9.3293 | CAPITAL | Yes | unit outage |  | X | X |  |  | no | no | Yes | no | no | no | Yes | Yes | no | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 35.56% | 4 | 1 | 3 | 1 | 1 | 4 | 3 | 43.33% | 5 |  | 2369.828
467 | L1 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Ottawa | 2025-03-31 | 2025 | 226 | 15 | 2024-08-17 | low | low | high | med | low | 9400000 | 19427475 | 9354713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940000 | 3760000 | 4700000 | 0 | 9400000 | 89.0006 | CAPITAL | No | pipeline segment outage | X |  | X | X |  | Yes | Yes | Yes | no | Yes | no | no | no | no | 3 | 5 | 2 | 5 | 1 | 2 | 4 | 2 | 1 | 55.56% | 6 | 3 | 4 | 1 | 1 | 2 | 5 | 53.33% | 6 |  | 425
468 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | North Bay | 2029-07-31 | 2029 | 160 | 10 | 2029-02-21 | low | low | low | low | high | 550000 | 781048 | 788414 | 55000 | 55000 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 41.8408 | EXPENSE | No | Pipeline segment | X |  | X | X | X | no | Yes | Yes | Yes | Yes | no | no | no | no | 1 | 5 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 44.44% | 5 | 3 | 1 | 1 | 4 | 3 | 2 | 46.67% | 5 |  | 749.7244
469 | L3 | FACILITY | MAJOR EQUIP |  | MAJOR OH | Ottawa | 2028-10-31 | 2028 | 304 | 4 | 2028-01-01 | med | high | high | high | med | 3878690 | 3880067 | 3887753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163607 | 2327214 | 387869 | 0 | 0 | 3878690 | 4.671 | CAPITAL | Yes | Unit outage |  |  | X | X | X | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 2 | 5 | 2 | 3 | 5 | 4 | 4 | 1 | 5 | 68.89% | 7 | 4 | 3 | 1 | 2 | 5 | 3 | 60% | 6 |  | 4522
468 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Quebec City | 2025-10-31 | 2025 | 30 | 4 | 2025-10-01 | med | med | med | high | low | 600000 | 757099 | 785103 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 360000 | 60000 | 0 | 0 | 0 | 600000 | 484.7808 | CAPITAL | No | Derate/low flow Pipe segment |  |  |  | X |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 2 | 5 | 2 | 2 | 2 | 1 | 4 | 1 | 5 | 53.33% | 6 | 4 | 2 | 1 | 1 | 2 | 2 | 40% | 4 |  | 4447
469 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Montreal | 2027-07-31 | 2027 | 201 | 2 | 2027-01-11 | med | high | high | med | high | 190000 | 196187 | 197468 | 0 | 0 | 0 | 0 | 57000 | 114000 | 19000 | 0 | 0 | 0 | 0 | 0 | 190000 | 40.7081 | EXPENSE | No | NO |  |  | x | x | x |  | x | x | x | [5 empty] | 3 | 5 | 4 | 2 | 1 | 3 | 5 | 4 | 1 | 62.22% | 7 | 4 | 2 | 1 | 3 | 3 | 4 | 56.67% | 6 |  | 16.9273
470 | L1 | FACILITY | MAJOR EQUIP |  | MAJOR OH | Saskatoon | 2025-07-31 | 2025 | 243 | 4 | 2024-11-30 | high | low | high | high | high | 3536540 | 3511282 | 3586508 | 0 | 0 | 0 | 0 | 353654 | 1414616 | 1768270 | 0 | 0 | 0 | 0 | 0 | 3536540 | 202.5027 | CAPITAL | Yes | Unit outage | X |  | X |  | X | Yes | Yes | Yes | no | no | no | Yes | no | Yes | 5 | 3 | 3 | 3 | 3 | 2 | 5 | 3 | 4 | 68.89% | 7 | 4 | 3 | 1 | 1 | 5 | 4 | 60% | 6 |  | 6832.4917
469 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2025-07-31 | 2025 | 120 | 6 | 2025-04-02 | high | high | med | high | low | 1750000 | 1770877 | 1780700 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 700000 | 875000 | 0 | 0 | 0 | 1750000 | 91.2089 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | no | 3 | 1 | 4 | 4 | 3 | 5 | 4 | 2 | 4 | 66.67% | 7 | 4 | 5 | 5 | 4 | 5 | 2 | 83.33% | 9 |  | 20000
470 | L1 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Quebec City | 2028-12-31 | 2028 | 320 | 20 | 2028-02-15 | med | low | low | med | med | 8550000 | 8506803 | 8740397 | 0 | 0 | 0 | 0 | 2565000 | 5130000 | 855000 | 0 | 0 | 0 | 0 | 0 | 8550000 | 96.8203 | CAPITAL | No | pipeline segment outage | X |  | X | X | X | Yes | no | no | no | Yes | Yes | Yes | Yes | no | 3 | 3 | 1 | 2 | 3 | 2 | 5 | 3 | 3 | 55.56% | 6 | 4 | 5 | 1 | 5 | 4 | 1 | 66.67% | 7 |  | 267.7598
471 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | Calgary | 2027-10-31 | 2027 | 190 | 2 | 2027-04-24 | med | high | high | low | high | 125000 | 110410 | 117380 | 0 | 0 | 0 | 0 | 0 | 37500 | 75000 | 12500 | 0 | 0 | 0 | 0 | 125000 | 565.0045 | EXPENSE | Yes | NO | X |  |  |  | X | no | Yes | Yes | no | Yes | no | Yes | no | Yes | 4 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 37.78% | 4 | 4 | 3 | 1 | 3 | 3 | 5 | 63.33% | 7 |  | 18109.7232
472 | L1 | FACILITY | MAJOR EQUIP |  | MAJOR OH | Saskatoon | 2026-10-31 | 2026 | 214 | 4 | 2026-03-31 | low | low | med | high | high | 4617354 | 4365331 | 4340535 | 0 | 0 | 0 | 0 | 461735.4 | 3693883.2 | 461735.4 | 0 | 0 | 0 | 0 | 0 | 4617354 | 70.5186 | CAPITAL | Yes | Unit outage |  |  | X |  |  | no | Yes | no | Yes | no | Yes | Yes | no | no | 2 | 3 | 2 | 2 | 5 | 1 | 5 | 1 | 5 | 57.78% | 6 | 1 | 2 | 1 | 2 | 2 | 5 | 43.33% | 5 |  | 7110.0938
470 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Quebec City | 2026-03-31 | 2026 | 85 | 4 | 2026-01-05 | med | high | med | high | high | 1500000 | 1500982 | 1500604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 1200000 | 150000 | 0 | 1500000 | 7.9794 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | Yes | Yes | no | no | Yes | no | 2 | 4 | 2 | 1 | 4 | 2 | 5 | 1 | 5 | 57.78% | 6 | 3 | 1 | 1 | 3 | 5 | 4 | 56.67% | 6 |  | 2078
471 | L2 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | North Bay | 2027-07-31 | 2027 | 300 | 25 | 2026-10-04 | med | high | med | high | med | 14050000 | 15158244 | 15509480 | 0 | 0 | 0 | 0 | 0 | 4215000 | 8430000 | 1405000 | 0 | 0 | 0 | 0 | 14050000 | 80.1164 | CAPITAL | Yes | pipeline segment outage | X |  |  | X | X | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 42.22% | 5 | 2 | 5 | 1 | 1 | 4 | 5 | 60% | 6 |  | 17599.38
472 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | Calgary | 2028-10-31 | 2028 | 155 | 4 | 2028-05-29 | high | high | high | med | med | 190000 | 173510 | 194286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 152000 | 19000 | 0 | 0 | 190000 | 670.6684 | EXPENSE | No | NO | X |  | X |  |  | Yes | no | Yes | no | Yes | Yes | no | no | Yes | 1 | 3 | 2 | 2 | 1 | 5 | 5 | 1 | 1 | 46.67% | 5 | 1 | 1 | 1 | 2 | 3 | 3 | 36.67% | 4 |  | 1174.971
473 | L1 | FACILITY | MAJOR EQUIP |  | MAJOR OH | Edmonton | 2026-12-31 | 2026 | 21 | 4 | 2026-12-10 | high | med | low | low | high | 1533520 | 1146998 | 1139804 | 0 | 0 | 0 | 0 | 0 | 460056 | 920112 | 153352 | 0 | 0 | 0 | 0 | 1533520 | 74.326 | CAPITAL | Yes | Unit outage |  |  |  | X |  | no | Yes | Yes | no | Yes | no | Yes | no | Yes | 5 | 3 | 1 | 4 | 1 | 1 | 5 | 1 | 3 | 53.33% | 6 | 3 | 3 | 1 | 4 | 5 | 5 | 70% | 7 |  | 382.7885
471 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2026-07-31 | 2026 | 105 | 10 | 2026-04-17 | med | low | med | low | med | 350000 | 363583 | 359590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 350000 | 32.0854 | CAPITAL | No | Pipeline segment |  |  | X | X |  | no | Yes | no | no | Yes | no | Yes | no | no | 3 | 2 | 4 | 3 | 1 | 3 | 3 | 2 | 4 | 55.56% | 6 | 3 | 5 | 1 | 3 | 1 | 1 | 46.67% | 5 |  | 1875
472 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Regina | 2027-07-31 | 2027 | 120 | 8 | 2027-04-02 | med | med | low | low | high | 700000 | 437705 | 443302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 560000 | 70000 | 0 | 700000 | 228.8332 | CAPITAL | Yes | Pipeline segment | X | X |  | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | no | 1 | 5 | 1 | 1 | 5 | 1 | 1 | 3 | 3 | 46.67% | 5 | 4 | 4 | 1 | 1 | 5 | 4 | 63.33% | 7 |  | 4447
473 | L1 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Winnipeg | 2029-03-31 | 2029 | 340 | 12 | 2028-04-25 | low | med | high | med | high | 3420000 | 3477100 | 3401079 | 0 | 0 | 0 | 0 | 1026000 | 2052000 | 342000 | 0 | 0 | 0 | 0 | 0 | 3420000 | 369.6154 | CAPITAL | Yes | pipeline segment outage | X | X |  |  | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 5 | 5 | 1 | 4 | 3 | 3 | 3 | 1 | 1 | 57.78% | 6 | 1 | 5 | 1 | 3 | 4 | 5 | 63.33% | 7 |  | 5097.261
474 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Calgary | 2026-12-31 | 2026 | 184 | 8 | 2026-06-30 | high | high | high | med | high | 250000 | 298807 | 298469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 250000 | 14.7788 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X |  | no | no | Yes | Yes | no | no | Yes | no | Yes | 1 | 2 | 2 | 1 | 2 | 4 | 4 | 1 | 3 | 44.44% | 5 | 4 | 1 | 1 | 2 | 1 | 5 | 46.67% | 5 |  | 2491.953
475 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Calgary | 2026-10-31 | 2026 | 184 | 1 | 2026-04-30 | low | med | high | low | med | 250000 | 203595 | 211700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 250000 | 218.414 | EXPENSE | No | Station outage |  |  |  |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 3 | 2 | 3 | 3 | 4 | 5 | 1 | 2 | 55.56% | 6 | 3 | 5 | 1 | 3 | 1 | 1 | 46.67% | 5 |  | 18109.7232
472 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2028-07-31 | 2028 | 160 | 8 | 2028-02-22 | low | med | high | high | high | 450000 | 483200 | 482753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 123.3918 | CAPITAL | No | Pipeline segment |  | X |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 3 | 5 | 2 | 5 | 4 | 4 | 1 | 2 | 5 | 68.89% | 7 | 3 | 5 | 1 | 4 | 5 | 5 | 76.67% | 8 |  | 7718.869
473 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Quebec City | 2027-12-31 | 2027 | 200 | 8 | 2027-06-14 | high | high | high | low | med | 700000 | 770309 | 770000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 420000 | 70000 | 0 | 0 | 700000 | 28.6028 | CAPITAL | No | pipeline segment outage |  |  | X |  | X | Yes | no | no | no | no | Yes | no | Yes | Yes | 2 | 5 | 1 | 2 | 2 | 3 | 2 | 1 | 4 | 48.89% | 5 | 4 | 5 | 1 | 1 | 1 | 3 | 50% | 5 |  | 8429.71
474 | L1 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Ottawa | 2026-09-30 | 2026 | 300 | 15 | 2025-12-04 | low | low | high | med | low | 5400000 | 5427475 | 5354713 | 0 | 0 | 0 | 0 | 1620000 | 3240000 | 540000 | 0 | 0 | 0 | 0 | 0 | 5400000 | 89.0006 | CAPITAL | No | pipeline segment outage | X |  | X | X |  | Yes | Yes | Yes | no | Yes | no | no | no | no | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 35.56% | 4 | 2 | 5 | 5 | 2 | 1 | 4 | 63.33% | 7 |  | 4858.887
475 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Quebec City | 2027-10-31 | 2026 | 180 | 4 | 2027-05-04 | med | med | med | high | low | 700000 | 657099 | 685103 | 0 | 0 | 0 | 210000 | 420000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 484.7808 | CAPITAL | No | Derate/low flow Pipe segment |  |  |  | X |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 1 | 2 | 2 | 1 | 1 | 4 | 2 | 3 | 3 | 42.22% | 5 | 3 | 2 | 5 | 4 | 4 | 4 | 73.33% | 8 |  | 2178.073
476 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | North Bay | 2027-12-31 | 2027 | 108 | 4 | 2027-09-14 | med | med | high | low | med | 250000 | 200338 | 207290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 0 | 250000 | 167.215 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 3 | 4 | 2 | 5 | 4 | 1 | 3 | 2 | 5 | 64.44% | 7 | 5 | 5 | 1 | 3 | 5 | 3 | 73.33% | 8 |  | 1022.4116
473 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2026-10-31 | 2026 | 150 | 4 | 2026-06-03 | high | high | low | low | high | 1750000 | 1708182 | 1716547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 1050000 | 175000 | 0 | 1750000 | 45.4478 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 2 | 2 | 1 | 1 | 4 | 4 | 3 | 2 | 1 | 44.44% | 5 | 5 | 1 | 1 | 2 | 2 | 2 | 43.33% | 5 |  | 7718.869
474 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Edmonton | 2026-03-31 | 2026 | 150 | 2 | 2025-11-01 | high | low | low | low | high | 700000 | 598833 | 611085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 490000 | 70000 | 0 | 0 | 700000 | 218.6029 | CAPITAL | No | pipeline segment outage | X |  | X | X |  | no | no | no | Yes | no | Yes | Yes | Yes | no | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 2 | 35.56% | 4 | 1 | 1 | 1 | 1 | 1 | 3 | 26.67% | 3 |  | 7709.8457
475 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Saskatoon | 2027-10-31 | 2027 | 100 | 8 | 2027-07-23 | high | low | high | low | high | 700000 | 855692 | 885145 | 0 | 210000 | 420000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 139.156 | CAPITAL | Yes | Derate/low flow Pipe segment |  | X | X |  | X | Yes | Yes | no | no | no | Yes | no | no | Yes | 5 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 4 | 44.44% | 5 | 2 | 1 | 1 | 3 | 1 | 3 | 36.67% | 4 |  | 6993.546
476 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | North Bay | 2028-12-31 | 2028 | 200 | 8 | 2028-06-14 | med | high | low | low | med | 250000 | 252651 | 284871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 0 | 250000 | 56.4922 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | no | Yes | no | Yes | no | no | Yes | no | no | 2 | 2 | 1 | 2 | 2 | 5 | 5 | 3 | 3 | 55.56% | 6 | 3 | 5 | 1 | 2 | 4 | 1 | 53.33% | 6 |  | 2369.8282
474 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2025-12-31 | 2025 | 85 | 2 | 2025-10-07 | high | high | high | low | high | 300000 | 378545 | 398478 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 300000 | 311.1133 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X | X | X | no | no | no | Yes | Yes | no | no | Yes | no | 5 | 5 | 2 | 1 | 5 | 2 | 5 | 2 | 4 | 68.89% | 7 | 4 | 4 | 5 | 5 | 5 | 1 | 80% | 8 |  | 6993.5456
475 | L1 | FACILITY | MAJOR EQUIP |  | MAJOR OH | North Bay | 2027-03-31 | 2027 | 150 | 4 | 2026-11-01 | low | low | med | low | med | 1587007 | 1927112 | 1764093 | 0 | 0 | 0 | 476102.1 | 952204.2 | 158700.7 | 0 | 0 | 0 | 0 | 0 | 0 | 1587007 | 111.1585 | CAPITAL | Yes | Unit outage |  | X |  | X | X | no | Yes | no | Yes | Yes | Yes | no | no | Yes | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 35.56% | 4 | 3 | 3 | 1 | 1 | 3 | 2 | 43.33% | 5 |  | 7709.846
476 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2028-03-31 | 2028 | 180 | 8 | 2027-10-03 | high | med | high | low | low | 550000 | 555744 | 590000 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 550000 | 32.772 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | Yes | no | no | no | Yes | Yes | no | 5 | 4 | 1 | 3 | 5 | 5 | 4 | 2 | 2 | 68.89% | 7 | 1 | 5 | 1 | 5 | 3 | 1 | 53.33% | 6 |  | 2491.953
477 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Montreal | 2029-12-31 | 2029 | 200 | 8 | 2029-06-14 | low | low | med | med | med | 650000 | 634470 | 663637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 650000 | 147.3292 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | no | Yes | no | no | Yes | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 33.33% | 4 | 5 | 3 | 1 | 4 | 3 | 3 | 63.33% | 7 |  | 16593.6851
478 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | Winnipeg | 2026-12-31 | 2026 | 224 | 8 | 2026-05-21 | med | med | med | low | low | 250000 | 236609 | 246072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 250000 | 96.9233 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | Yes | no | Yes | Yes | Yes | no | no | Yes | no | 2 | 2 | 1 | 2 | 1 | 3 | 3 | 3 | 5 | 48.89% | 5 | 2 | 4 | 1 | 1 | 1 | 4 | 43.33% | 5 |  | 2679.5194
475 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Ottawa | 2027-03-31 | 2027 | 268 | 4 | 2026-07-06 | low | med | med | med | med | 1059613 | 1004902 | 1042600 | 0 | 0 | 0 | 0 | 0 | 0 | 317883.9 | 635767.8 | 105961.3 | 0 | 0 | 0 | 1059613 | 32.3326 | CAPITAL | Yes | Unit outage | X |  | X | X |  | Yes | no | Yes | Yes | no | no | Yes | Yes | no | 1 | 5 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 48.89% | 5 | 1 | 2 | 1 | 5 | 4 | 5 | 60% | 6 |  | 1475
476 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2027-10-31 | 2027 | 175 | 15 | 2027-05-09 | med | high | high | low | med | 500000 | 478589 | 470244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 500000 | 180.0007 | CAPITAL | Yes | Pipeline segment | X |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 1 | 3 | 1 | 5 | 1 | 3 | 1 | 3 | 42.22% | 5 | 2 | 4 | 1 | 4 | 5 | 2 | 60% | 6 |  | 2480.6254
477 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | Quebec City | 2030-07-31 | 2030 | 100 | 4 | 2030-04-22 | low | high | high | low | med | 125000 | 137635 | 149404 | 0 | 0 | 0 | 0 | 37500 | 75000 | 12500 | 0 | 0 | 0 | 0 | 0 | 125000 | 946.0832 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 2 | 2 | 3 | 2 | 3 | 3 | 3 | 2 | 5 | 55.56% | 6 | 1 | 4 | 1 | 2 | 2 | 1 | 36.67% | 4 |  | 13659.1884
476 | L1 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Saskatoon | 2025-10-31 | 2025 | 180 | 8 | 2025-05-04 | high | low | high | low | high | 750000 | 855692 | 855145 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 139.156 | EXPENSE | Yes | NO outage |  | X | X |  | X | Yes | Yes | no | no | no | Yes | no | no | Yes | 3 | 5 | 3 | 3 | 2 | 4 | 2 | 3 | 2 | 60% | 6 | 4 | 1 | 1 | 1 | 5 | 5 | 56.67% | 6 |  | 636.4681
477 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2028-10-31 | 2028 | 150 | 15 | 2028-06-03 | low | low | low | low | med | 550000 | 615279 | 618240 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 550000 | 184.0435 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | Yes | no | no | no | no | no | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 31.11% | 4 | 2 | 2 | 1 | 1 | 2 | 5 | 43.33% | 5 |  | 2973.4021
477 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Edmonton | 2028-12-31 | 2028 | 85 | 4 | 2028-10-07 | med | low | high | low | med | 400000 | 560984 | 561355 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 83.4126 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | no | no | no | Yes | Yes | Yes | Yes | no | Yes | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 28.89% | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 36.67% | 4 |  | 25393.3666
478 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | North Bay | 2027-07-31 | 2027 | 200 | 1 | 2027-01-12 | high | med | high | med | high | 125000 | 105456 | 105103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 75000 | 12500 | 125000 | 713.9495 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  |  |  | Yes | Yes | no | no | Yes | Yes | no | Yes | no | 5 | 3 | 2 | 1 | 2 | 1 | 4 | 5 | 4 | 60% | 6 | 2 | 5 | 1 | 5 | 4 | 5 | 73.33% | 8 |  | 5875
479 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Montreal | 2030-12-31 | 2030 | 120 | 5 | 2030-09-02 | med | high | high | high | high | 250000 | 282472 | 312000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 250000 | 68.1605 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | no | no | no | Yes | no | Yes | Yes | no | no | 2 | 1 | 3 | 3 | 1 | 4 | 5 | 2 | 5 | 57.78% | 6 | 5 | 2 | 5 | 2 | 1 | 2 | 56.67% | 6 |  | 4314.195
478 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Regina | 2025-12-31 | 2025 | 206 | 15 | 2025-06-08 | med | low | low | low | med | 1800000 | 1825733 | 1857547 | 0 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 76.4961 | EXPENSE | No | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 2 | 4 | 3 | 2 | 3 | 4 | 5 | 1 | 5 | 64.44% | 7 | 3 | 2 | 1 | 2 | 5 | 4 | 56.67% | 6 |  | 2369.8282
479 | L2 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Montreal | 2029-10-31 | 2029 | 180 | 5 | 2029-05-04 | high | med | med | med | low | 1000000 | 1550026 | 1443747 | 300000 | 600000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 76.5526 | EXPENSE | No | NO outage | X | X |  |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 1 | 5 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 35.56% | 4 | 2 | 5 | 1 | 5 | 5 | 3 | 70% | 7 |  | 13420.4072
480 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Quebec City | 2027-03-31 | 2027 | 180 | 8 | 2026-10-02 | high | med | low | high | low | 1000000 | 1514932 | 1512774 | 0 | 0 | 0 | 0 | 300000 | 100000 | 100000 | 300000 | 200000 | 0 | 0 | 0 | 1000000 | 7.2499 | EXPENSE | No | NO outage | X | X | X |  | X | no | no | no | no | no | no | no | Yes | Yes | 1 | 1 | 2 | 2 | 4 | 4 | 3 | 2 | 3 | 48.89% | 5 | 1 | 1 | 1 | 2 | 1 | 2 | 26.67% | 3 |  | 4785
481 | L1 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Edmonton | 2029-12-31 | 2029 | 180 | 8 | 2029-07-04 | low | high | high | low | high | 750000 | 861410 | 860656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 750000 | 15.3529 | EXPENSE | No | NO outage |  | X | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | no | 3 | 1 | 1 | 1 | 4 | 4 | 4 | 3 | 2 | 51.11% | 6 | 5 | 2 | 5 | 1 | 2 | 3 | 60% | 6 |  | 241.5599
479 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Saskatoon | 2028-12-31 | 2025 | 12 | 4 | 2028-12-19 | high | high | med | med | high | 425000 | 662668 | 637944 | 0 | 127500 | 255000 | 42500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425000 | 32.9243 | EXPENSE | Yes | pipeline segment outage | X | X | X |  | X | no | Yes | Yes | no | Yes | no | no | no | no | 2 | 4 | 3 | 1 | 4 | 5 | 5 | 2 | 4 | 66.67% | 7 | 5 | 4 | 1 | 5 | 1 | 3 | 63.33% | 7 |  | 2369.8282
480 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Montreal | 2027-07-31 | 2027 | 230 | 10 | 2026-12-13 | high | high | low | low | high | 550000 | 620373 | 628500 | 0 | 0 | 0 | 0 | 0 | 55000 | 55000 | 55000 | 330000 | 55000 | 0 | 0 | 550000 | 16.0911 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 3 | 1 | 66.67% | 7 | 2 | 2 | 1 | 1 | 2 | 1 | 30% | 3 |  | 5776.4313
481 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2028-12-31 | 2028 | 230 | 10 | 2028-05-15 | low | high | high | low | low | 550000 | 897555 | 933585 | 55000 | 70000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370000 | 23.9593 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | Yes | no | no | Yes | Yes | no | Yes | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 4 | 4 | 46.67% | 5 | 4 | 1 | 1 | 4 | 1 | 2 | 43.33% | 5 |  | 6487.5816
482 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Saskatoon | 2027-12-31 | 2027 | 185 | 10 | 2027-06-29 | high | low | high | med | med | 500000 | 582971 | 589878 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 270.4653 | CAPITAL | No | Pipeline segment |  | X |  |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 4 | 37.78% | 4 | 4 | 4 | 5 | 5 | 2 | 5 | 83.33% | 9 |  | 1083.35
483 | L1 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Calgary | 2027-12-31 | 2027 | 180 | 10 | 2027-07-04 | high | low | low | low | med | 750000 | 751968 | 754634 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 750000 | 41.9164 | EXPENSE | Yes | NO outage |  | X | X | X |  | Yes | no | Yes | Yes | no | Yes | Yes | Yes | no | 5 | 1 | 3 | 5 | 3 | 1 | 5 | 3 | 1 | 60% | 6 | 2 | 3 | 1 | 2 | 3 | 5 | 53.33% | 6 |  | 173.2929
480 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Saskatoon | 2025-07-31 | 2025 | 64 | 8 | 2025-05-28 | low | low | med | high | med | 1800000 | 1875000 | 1830883 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 49.4725 | EXPENSE | No | pipeline segment outage |  |  |  | X |  | no | no | no | Yes | Yes | Yes | Yes | no | no | 5 | 4 | 2 | 4 | 3 | 2 | 5 | 4 | 3 | 71.11% | 8 | 1 | 2 | 1 | 3 | 4 | 5 | 53.33% | 6 |  | 3138.8656
481 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2029-12-31 | 2029 | 170 | 1 | 2029-07-14 | med | high | high | med | high | 550000 | 852979 | 857775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 35.5286 | CAPITAL | No | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | Yes | Yes | Yes | Yes | no | 2 | 5 | 3 | 1 | 4 | 4 | 5 | 2 | 2 | 62.22% | 7 | 5 | 2 | 5 | 3 | 4 | 3 | 73.33% | 8 |  | 5875
482 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Saskatoon | 2027-10-31 | 2027 | 180 | 10 | 2027-05-04 | med | low | high | low | med | 750000 | 752055 | 721982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 750000 | 100.5902 | EXPENSE | No | NO outage |  | X | X |  | X | no | Yes | no | no | no | Yes | no | no | Yes | 2 | 5 | 3 | 2 | 4 | 4 | 5 | 1 | 1 | 60% | 6 | 5 | 3 | 1 | 1 | 2 | 4 | 53.33% | 6 |  | 45.3112
481 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Quebec City | 2025-10-31 | 2025 | 150 | 2 | 2025-06-03 | med | med | high | med | high | 520000 | 686253 | 671492 | 0 | 0 | 156000 | 312000 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 34.7089 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 3 | 3 | 3 | 4 | 5 | 3 | 3 | 1 | 66.67% | 7 | 2 | 4 | 1 | 1 | 2 | 2 | 40% | 4 |  | 3138.8656
482 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2030-07-31 | 2030 | 185 | 15 | 2030-01-27 | med | high | med | high | med | 550000 | 542014 | 546441 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 550000 | 26.015 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | Yes | Yes | 4 | 5 | 2 | 3 | 2 | 4 | 5 | 3 | 4 | 71.11% | 8 | 3 | 5 | 1 | 3 | 5 | 2 | 63.33% | 7 |  | 25777
483 | L1 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Winnipeg | 2030-12-31 | 2030 | 227 | 10 | 2030-05-18 | low | low | high | high | high | 750000 | 701590 | 708037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 750000 | 118.806 | EXPENSE | No | NO outage | X | X |  |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 5 | 3 | 3 | 4 | 2 | 2 | 2 | 4 | 3 | 62.22% | 7 | 5 | 4 | 5 | 1 | 2 | 1 | 60% | 6 |  | 258
482 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2025-07-31 | 2025 | 150 | 4 | 2025-03-03 | med | med | high | med | high | 1000000 | 1649706 | 1663088 | 300000 | 600000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 96.0767 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X | X | no | Yes | no | no | Yes | Yes | no | no | no | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 35.56% | 4 | 2 | 4 | 1 | 5 | 2 | 2 | 53.33% | 6 |  | 14928.9944
483 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Ottawa | 2028-12-31 | 2028 | 185 | 15 | 2028-06-29 | low | high | low | low | low | 550000 | 986403 | 1000025 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 103.1048 | CAPITAL | No | Pipeline segment | X |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 4 | 4 | 2 | 4 | 4 | 3 | 3 | 5 | 3 | 71.11% | 8 | 5 | 5 | 1 | 1 | 1 | 2 | 50% | 5 |  | 20815.3255
484 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Winnipeg | 2028-12-31 | 2028 | 180 | 10 | 2028-07-04 | low | low | med | high | low | 800000 | 962796 | 971191 | 240000 | 480000 | 80000 | 0 | 0 | 0 | 0 | 0 | 240000 | 480000 | 80000 | 0 | 1600000 | 107.4224 | EXPENSE | No | NO outage |  | X | X |  | X | no | Yes | Yes | no | no | no | no | Yes | Yes | 5 | 5 | 3 | 5 | 3 | 5 | 2 | 5 | 3 | 80% | 8 | 3 | 5 | 1 | 5 | 4 | 5 | 76.67% | 8 |  | 173.2929
483 | L1 | FACILITY | MAJOR EQUIP |  | MINOR OH | Montreal | 2025-12-31 | 2025 | 137 | 4 | 2025-08-16 | high | high | low | low | med | 857925 | 846017 | 847000 | 0 | 0 | 0 | 0 | 0 | 257377.5 | 514755 | 85792.5 | 0 | 0 | 0 | 0 | 857925 | 818.9288 | CAPITAL | Yes | Unit outage |  | X |  | X | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 2 | 1 | 3 | 1 | 4 | 2 | 3 | 2 | 5 | 51.11% | 6 | 5 | 3 | 1 | 3 | 5 | 1 | 60% | 6 |  | 4785
484 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | WINNIPEG | 2028-12-31 | 2028 | 150 | 10 | 2028-08-03 | low | med | low | high | high | 550000 | 528864 | 528750 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 550000 | 56.9979 | CAPITAL | Yes | Pipeline segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | no | no | no | 1 | 2 | 1 | 1 | 1 | 4 | 3 | 3 | 3 | 42.22% | 5 | 3 | 3 | 1 | 2 | 1 | 4 | 46.67% | 5 |  | 203.1281
485 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Regina | 2026-09-30 | 2026 | 180 | 10 | 2026-04-03 | high | high | med | low | high | 750000 | 754518 | 786550 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 57.545 | EXPENSE | No | NO outage | X |  | X |  | X | Yes | Yes | Yes | no | no | no | no | no | no | 4 | 5 | 2 | 3 | 1 | 4 | 2 | 3 | 3 | 60% | 6 | 3 | 1 | 1 | 1 | 5 | 4 | 50% | 5 |  | 1685.963
484 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2026-07-31 | 2026 | 180 | 5 | 2026-02-01 | med | low | med | med | low | 400000 | 850000 | 895000 | 120000 | 120000 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 24.5147 | EXPENSE | No | Pipeline segment |  | X |  | X |  | no | no | no | no | no | no | Yes | Yes | no | 1 | 2 | 3 | 3 | 5 | 3 | 1 | 2 | 2 | 48.89% | 5 | 2 | 4 | 1 | 2 | 5 | 5 | 63.33% | 7 |  | 4487
485 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | North Bay | 2029-12-31 | 2029 | 150 | 8 | 2029-08-03 | high | high | low | high | high | 550000 | 680678 | 686152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 22.4512 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | no | Yes | no | no | 3 | 5 | 1 | 4 | 3 | 2 | 2 | 1 | 2 | 51.11% | 6 | 1 | 5 | 1 | 1 | 5 | 2 | 50% | 5 |  | 1685.9635
486 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Montreal | 2027-10-31 | 2027 | 180 | 8 | 2027-05-04 | med | med | high | low | med | 1000000 | 1022203 | 1280954 | 0 | 0 | 0 | 300000 | 300000 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 44.865 | EXPENSE | No | NO outage |  | X | X | X |  | Yes | Yes | no | no | Yes | no | no | no | no | 4 | 1 | 4 | 4 | 3 | 2 | 5 | 2 | 3 | 62.22% | 7 | 2 | 1 | 5 | 1 | 4 | 4 | 56.67% | 6 |  | 6832.492
485 | L3 | FACILITY | ELECTRICAL |  | MCC | Edmonton | 2025-03-31 | 2025 | 13 | 2 | 2025-03-18 | high | med | high | med | med | 275436 | 238926 | 230244 | 0 | 0 | 0 | 0 | 82630.8 | 165261.6 | 27543.6 | 0 | 0 | 0 | 0 | 0 | 275436 | 519.2655 | CAPITAL | Yes | Unit outage | X | X | X | X | X | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 3 | 3 | 1 | 4 | 2 | 5 | 1 | 4 | 4 | 60% | 6 | 2 | 3 | 1 | 5 | 1 | 1 | 43.33% | 5 |  | 211.3988
486 | L3 | FACILITY | MAJOR EQUIP |  | MINOR OH | Edmonton | 2027-07-31 | 2027 | 140 | 4 | 2027-03-13 | med | low | low | high | high | 2926827 | 2801872 | 2905463 | 878048.1 | 1756096.2 | 292682.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2926827 | 35.5747 | CAPITAL | Yes | Unit outage | X |  |  |  |  | no | Yes | no | no | no | no | Yes | Yes | no | 2 | 2 | 1 | 3 | 2 | 4 | 3 | 2 | 5 | 53.33% | 6 | 5 | 5 | 1 | 3 | 3 | 3 | 66.67% | 7 |  | 2166.5828
487 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2028-12-31 | 2028 | 150 | 15 | 2028-08-03 | low | low | med | high | med | 550000 | 583975 | 578458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 550000 | 29.298 | CAPITAL | No | Pipeline segment | X |  |  | X | X | no | Yes | no | Yes | no | no | no | no | Yes | 5 | 4 | 1 | 5 | 1 | 5 | 2 | 5 | 2 | 66.67% | 7 | 4 | 5 | 1 | 4 | 3 | 1 | 60% | 6 |  | 1591.1704
488 | L1 | FACILITY | MAJOR EQUIP |  | MINOR OH | North Bay | 2026-12-31 | 2026 | 181 | 4 | 2026-07-03 | low | high | high | high | med | 2494653 | 2370566 | 2526101 | 748395.9 | 1496791.8 | 249465.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2494653 | 35.1989 | CAPITAL | Yes | Unit outage | X | X | X | X |  | no | no | no | Yes | Yes | no | no | no | Yes | 1 | 4 | 1 | 3 | 2 | 4 | 4 | 1 | 3 | 51.11% | 6 | 1 | 1 | 1 | 1 | 2 | 2 | 26.67% | 3 |  | 48755
486 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Edmonton | 2025-07-31 | 2025 | 120 | 8 | 2025-04-02 | low | high | med | high | low | 3200000 | 3281295 | 3570817 | 0 | 0 | 0 | 0 | 0 | 0 | 960000 | 1920000 | 320000 | 0 | 0 | 0 | 3200000 | 714.4143 | EXPENSE | No | pipeline segment outage | X |  | X |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 1 | 1 | 1 | 1 | 4 | 1 | 4 | 2 | 1 | 35.56% | 4 | 1 | 4 | 1 | 5 | 5 | 2 | 60% | 6 |  | 477.3811
487 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2028-03-31 | 2028 | 100 | 15 | 2027-12-22 | low | med | low | high | med | 550000 | 575844 | 575478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 28.5018 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | no | Yes | no | no | Yes | 3 | 2 | 2 | 1 | 1 | 5 | 1 | 4 | 2 | 46.67% | 5 | 1 | 1 | 1 | 5 | 4 | 3 | 50% | 5 |  | 5097.2605
488 | L2 | FACILITY | ELECTRICAL |  | MCC | Calgary | 2028-03-31 | 2028 | 127 | 2 | 2027-11-25 | low | med | med | low | low | 288982 | 222067 | 990619 | 0 | 0 | 0 | 86694.6 | 173389.2 | 28898.2 | 86694.6 | 173389.2 | 28898.2 | 0 | 0 | 0 | 577964 | 342.7961 | CAPITAL | Yes | Unit outage |  |  | X |  |  | Yes | no | Yes | no | Yes | no | Yes | Yes | no | 4 | 1 | 1 | 5 | 4 | 5 | 3 | 2 | 4 | 64.44% | 7 | 1 | 5 | 1 | 1 | 2 | 5 | 50% | 5 |  | 1846.6194
487 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2025-03-31 | 2025 | 85 | 2 | 2025-01-05 | high | low | low | low | med | 350000 | 378827 | 442990 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 700000 | 523.2809 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | no | 5 | 4 | 2 | 5 | 3 | 3 | 3 | 3 | 2 | 66.67% | 7 | 2 | 2 | 1 | 4 | 2 | 5 | 53.33% | 6 |  | 5347.325
488 | L1 | FACILITY | MAJOR EQUIP |  | MINOR OH | Ottawa | 2028-10-31 | 2028 | 280 | 4 | 2028-01-25 | high | med | high | high | high | 1924395 | 1930813 | 1914572 | 0 | 0 | 0 | 0 | 0 | 0 | 577318.5 | 1154637 | 192439.5 | 0 | 0 | 0 | 1924395 | 99.4896 | CAPITAL | Yes | Unit outage |  | X |  | X | X | Yes | Yes | no | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 3 | 46.67% | 5 | 2 | 2 | 1 | 5 | 1 | 2 | 43.33% | 5 |  | 7709.8457
489 | L3 | FACILITY | MAJOR EQUIP |  | MINOR OH | Toronto | 2029-10-31 | 2029 | 56 | 4 | 2029-09-05 | low | high | low | low | high | 1594549 | 1595132 | 1599106 | 0 | 0 | 0 | 0 | 0 | 0 | 478364.7 | 956729.4 | 159454.9 | 0 | 0 | 0 | 1594549 | 37.5721 | CAPITAL | Yes | Unit outage |  | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | no | no | 4 | 5 | 3 | 4 | 3 | 2 | 1 | 2 | 5 | 64.44% | 7 | 5 | 3 | 5 | 4 | 5 | 1 | 76.67% | 8 |  | 2610.3898
488 | L2 | FACILITY | MEASUREMENT |  | FLOW CONTROL | Winnipeg | 2025-07-31 | 2025 | 297 | 1 | 2024-10-07 | high | high | low | high | low | 500000 | 545110 | 587320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 200.2629 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 4 | 5 | 3 | 1 | 1 | 3 | 5 | 5 | 1 | 62.22% | 7 | 1 | 5 | 1 | 5 | 2 | 3 | 56.67% | 6 |  | 4542.743
489 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Saskatoon | 2028-03-31 | 2028 | 100 | 10 | 2027-12-22 | high | low | med | med | high | 550000 | 1480343 | 1480758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 550000 | 89.4674 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 4 | 5 | 3 | 1 | 1 | 5 | 3 | 2 | 5 | 64.44% | 7 | 4 | 1 | 1 | 5 | 3 | 1 | 50% | 5 |  | 7110.0938
490 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2028-12-31 | 2028 | 200 | 8 | 2028-06-14 | med | med | low | med | high | 650000 | 662027 | 682144 | 65000 | 65000 | 65000 | 0 | 0 | 0 | 0 | 390000 | 65000 | 0 | 0 | 0 | 650000 | 108.8597 | CAPITAL | No | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | no | Yes | Yes | 4 | 2 | 1 | 5 | 2 | 5 | 3 | 5 | 4 | 68.89% | 7 | 4 | 4 | 1 | 5 | 4 | 4 | 73.33% | 8 |  | 2178.0735
491 | L1 | FACILITY | ELECTRICAL |  | MCC | Ottawa | 2026-12-31 | 2026 | 172 | 1 | 2026-07-12 | med | low | high | med | high | 85969 | 146638 | 146725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25790.7 | 51581.4 | 8596.9 | 0 | 85969 | 670.8523 | EXPENSE | Yes | Station outage |  | X | X | X |  | Yes | no | no | Yes | Yes | Yes | no | no | no | 4 | 4 | 2 | 2 | 5 | 5 | 4 | 3 | 1 | 66.67% | 7 | 5 | 5 | 1 | 1 | 5 | 3 | 66.67% | 7 |  | 1117.2047
489 | L2 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Winnipeg | 2025-12-31 | 2025 | 104 | 8 | 2025-09-18 | low | med | med | low | low | 1708501 | 1963873 | 1943106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512550.3 | 1025100.6 | 170850.1 | 1708501 | 31.7885 | EXPENSE | Yes | Unit outage |  |  |  | X |  | no | Yes | Yes | no | Yes | Yes | Yes | Yes | no | 4 | 1 | 1 | 4 | 3 | 3 | 4 | 1 | 2 | 51.11% | 6 | 5 | 2 | 1 | 5 | 3 | 1 | 56.67% | 6 |  | 1486.7011
490 | L1 | FACILITY | ELECTRICAL |  | MCC | North Bay | 2026-12-31 | 2026 | 235 | 2 | 2026-05-10 | med | med | high | med | high | 432975 | 436911 | 379627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129892.5 | 259785 | 43297.5 | 432975 | 41.4867 | EXPENSE | Yes | Station outage |  | X |  |  |  | Yes | no | Yes | no | no | Yes | Yes | Yes | no | 5 | 1 | 1 | 1 | 3 | 4 | 1 | 3 | 1 | 44.44% | 5 | 4 | 1 | 1 | 1 | 3 | 3 | 43.33% | 5 |  | 1591.17
491 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2028-12-31 | 2028 | 342 | 2 | 2028-01-24 | high | low | med | low | low | 650000 | 609531 | 605189 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 0 | 0 | 650000 | 242.8512 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X | X | no | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 5 | 3 | 1 | 5 | 5 | 5 | 5 | 4 | 80% | 8 | 5 | 3 | 1 | 3 | 4 | 2 | 60% | 6 |  | 495.1227
492 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | North Bay | 2026-12-31 | 2026 | 200 | 8 | 2026-06-14 | med | low | med | low | med | 500000 | 786958 | 789562 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 500000 | 64.1787 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 4 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 42.22% | 5 | 3 | 2 | 5 | 3 | 5 | 3 | 70% | 7 |  | 4052.0846
490 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2025-07-31 | 2025 | 100 | 6 | 2025-04-22 | med | low | high | high | high | 1000000 | 1200000 | 1281639 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 400000 | 500000 | 0 | 0 | 0 | 1000000 | 8.2654 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  |  | X | no | no | no | Yes | no | Yes | Yes | no | Yes | 5 | 3 | 3 | 1 | 3 | 4 | 1 | 4 | 2 | 57.78% | 6 | 4 | 4 | 1 | 1 | 1 | 5 | 53.33% | 6 |  | 2679.5194
491 | L3 | FACILITY | MAJOR EQUIP |  | MINOR OH | Saskatoon | 2026-10-31 | 2026 | 240 | 4 | 2026-03-05 | low | high | high | high | med | 1982860 | 1977099 | 1931924 | 594858 | 1189716 | 198286 | 0 | 0 | 0 | 0 | 0 | 594858 | 1189716 | 198286 | 0 | 3965720 | 41.9558 | CAPITAL | Yes | Unit outage | X |  | X | X |  | no | no | no | no | no | no | no | no | Yes | 4 | 5 | 2 | 3 | 4 | 1 | 4 | 3 | 2 | 62.22% | 7 | 3 | 1 | 1 | 4 | 2 | 5 | 53.33% | 6 |  | 7024.225
492 | L3 | FACILITY | MEASUREMENT |  | FLOW CONTROL | Calgary | 2026-12-31 | 2026 | 177 | 3 | 2026-07-07 | high | med | med | high | high | 450000 | 457337 | 462837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 180000 | 225000 | 0 | 0 | 450000 | 193.479 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | Yes | no | no | no | no | no | Yes | no | no | 5 | 3 | 3 | 1 | 2 | 2 | 1 | 5 | 5 | 60% | 6 | 1 | 2 | 1 | 2 | 2 | 3 | 36.67% | 4 |  | 1072.766
493 | L1 | FACILITY | MEASUREMENT |  | FLOW CONTROL | Saskatoon | 2028-07-31 | 2028 | 122 | 1 | 2028-03-31 | low | low | high | med | med | 500000 | 528341 | 531697 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 500000 | 8.6875 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  | X | X | Yes | Yes | no | no | no | Yes | no | Yes | Yes | 3 | 1 | 1 | 2 | 4 | 3 | 2 | 4 | 1 | 46.67% | 5 | 4 | 1 | 1 | 2 | 2 | 4 | 46.67% | 5 |  | 1785
491 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Winnipeg | 2025-07-31 | 2025 | 250 | 8 | 2024-11-23 | high | high | med | med | low | 1300000 | 1324785 | 1350260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 780000 | 130000 | 0 | 0 | 1300000 | 2123.4281 | EXPENSE | Yes | pipeline segment outage | X |  |  |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | no | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 24.44% | 3 | 1 | 1 | 1 | 1 | 1 | 4 | 30% | 3 |  | 2679.5194
492 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2026-03-31 | 2026 | 248 | 4 | 2025-07-26 | med | high | high | high | high | 2000000 | 2373474 | 2320004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 800000 | 1000000 | 0 | 0 | 2000000 | 25.7224 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | no | Yes | no | no | no | Yes | Yes | 1 | 3 | 1 | 3 | 3 | 2 | 5 | 2 | 1 | 46.67% | 5 | 1 | 5 | 1 | 4 | 2 | 5 | 60% | 6 |  | 6039.0018
493 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2028-07-31 | 2028 | 285 | 4 | 2027-10-20 | med | low | high | med | low | 300000 | 295522 | 290724 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 0 | 300000 | 87.5976 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | no | no | 1 | 1 | 2 | 2 | 1 | 1 | 4 | 1 | 1 | 31.11% | 4 | 1 | 1 | 3 | 1 | 1 | 5 | 40% | 4 |  | 267.7598
494 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2027-03-31 | 2027 | 170 | 4 | 2026-10-12 | high | high | high | high | med | 1500000 | 1557641 | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 1500000 | 27.6329 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 2 | 4 | 1 | 1 | 1 | 5 | 4 | 1 | 4 | 51.11% | 6 | 3 | 2 | 5 | 1 | 1 | 5 | 56.67% | 6 |  | 267.7598
492 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Regina | 2025-03-31 | 2025 | 120 | 6 | 2024-12-01 | med | high | med | med | low | 1800000 | 1817708 | 1891840 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 73.0943 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 4 | 1 | 3 | 2 | 1 | 4 | 2 | 3 | 48.89% | 5 | 1 | 4 | 1 | 5 | 3 | 3 | 56.67% | 6 |  | 1072.7658
493 | L3 | FACILITY | MAJOR EQUIP |  | MINOR OH | North Bay | 2028-10-31 | 2028 | 205 | 4 | 2028-04-09 | low | low | low | med | med | 1556876 | 1569750 | 1524237 | 467062.8 | 467062.8 | 311375.2 | 311375.2 | 0 | 0 | 0 | 0 | 0 | 467062.8 | 934125.6 | 155687.6 | 3113752 | 163.9144 | CAPITAL | Yes | Unit outage |  | X | X |  | X | no | Yes | no | Yes | no | no | no | no | Yes | 5 | 2 | 4 | 3 | 3 | 4 | 4 | 1 | 1 | 60% | 6 | 2 | 1 | 1 | 2 | 5 | 2 | 43.33% | 5 |  | 289
494 | L3 | FACILITY | MAJOR EQUIP |  | MINOR OH | Toronto | 2026-12-31 | 2026 | 63 | 4 | 2026-10-29 | low | high | low | med | high | 1034944 | 1055596 | 1050204 | 0 | 0 | 0 | 103494.4 | 413977.6 | 517472 | 0 | 0 | 0 | 0 | 0 | 0 | 1034944 | 19.5223 | CAPITAL | Yes | Unit outage | X |  |  |  | X | no | Yes | no | no | Yes | Yes | no | no | no | 3 | 5 | 2 | 1 | 2 | 5 | 2 | 3 | 5 | 62.22% | 7 | 4 | 2 | 5 | 3 | 3 | 4 | 70% | 7 |  | 898
495 | L1 | FACILITY | MAJOR EQUIP |  | MINOR OH | Quebec City | 2027-10-31 | 2027 | 98 | 4 | 2027-07-25 | high | low | high | low | med | 1585134 | 2069708 | 2046698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475540.2 | 951080.4 | 158513.4 | 0 | 1585134 | 40.7977 | CAPITAL | Yes | unit outage | X | X |  | X | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 5 | 2 | 4 | 1 | 5 | 2 | 5 | 5 | 2 | 68.89% | 7 | 3 | 3 | 1 | 2 | 2 | 3 | 46.67% | 5 |  | 1022.412
496 | L3 | FACILITY | MECHANICAL |  | FUEL GAS HEAT EXCHANGER | Winnipeg | 2025-12-31 | 2025 | 43 | 3 | 2025-11-18 | low | low | med | high | med | 370079 | 376658 | 376508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111023.7 | 222047.4 | 37007.9 | 0 | 370079 | 540.6712 | CAPITAL | Yes | Unit outage |  | X | X | X | X | Yes | no | no | no | Yes | Yes | no | no | no | 3 | 4 | 1 | 3 | 4 | 1 | 3 | 3 | 2 | 53.33% | 6 | 5 | 3 | 5 | 2 | 1 | 2 | 60% | 6 |  | 17906.94
493 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | North Bay | 2026-07-31 | 2026 | 180 | 8 | 2026-02-01 | low | low | low | low | high | 350000 | 371048 | 377414 | 0 | 0 | 0 | 0 | 0 | 105000 | 105000 | 70000 | 70000 | 0 | 0 | 0 | 350000 | 41.8408 | CAPITAL | No | Pipeline segment | X |  | X | X | X | no | Yes | Yes | Yes | Yes | no | no | no | no | 3 | 3 | 2 | 3 | 3 | 1 | 1 | 2 | 2 | 44.44% | 5 | 2 | 2 | 1 | 5 | 3 | 3 | 53.33% | 6 |  | 3333.1342
494 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Regina | 2027-12-31 | 2027 | 198 | 4 | 2027-06-16 | low | med | low | low | low | 1555220 | 1812532 | 1821625 | 0 | 0 | 0 | 466566 | 466566 | 311044 | 311044 | 0 | 0 | 0 | 0 | 0 | 1555220 | 52.8301 | EXPENSE | Yes | Unit outage |  | X |  |  |  | Yes | no | no | no | Yes | no | no | Yes | Yes | 5 | 1 | 4 | 4 | 4 | 5 | 4 | 3 | 5 | 77.78% | 8 | 4 | 1 | 1 | 1 | 1 | 2 | 33.33% | 4 |  | 10535.7532
495 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Regina | 2026-03-31 | 2026 | 136 | 4 | 2025-11-15 | low | med | med | low | med | 1850000 | 1837033 | 1893775 | 0 | 0 | 0 | 555000 | 1110000 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 1850000 | 38.7086 | EXPENSE | Yes | Unit outage |  | X |  | X |  | no | Yes | no | no | Yes | Yes | Yes | no | no | 3 | 4 | 2 | 2 | 2 | 2 | 4 | 3 | 2 | 53.33% | 6 | 1 | 5 | 1 | 3 | 3 | 5 | 60% | 6 |  | 3220.812
496 | L3 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Toronto | 2028-12-31 | 2028 | 143 | 4 | 2028-08-10 | high | med | low | high | med | 1661943 | 1679277 | 1613482 | 0 | 0 | 0 | 0 | 0 | 498582.9 | 997165.8 | 166194.3 | 0 | 0 | 0 | 0 | 1661943 | 12.8453 | EXPENSE | Yes | Unit outage | X |  |  |  | X | no | no | no | no | no | no | no | Yes | no | 2 | 1 | 3 | 2 | 1 | 4 | 5 | 2 | 2 | 48.89% | 5 | 5 | 4 | 1 | 5 | 1 | 2 | 60% | 6 |  | 48955
497 | L2 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Regina | 2027-07-31 | 2027 | 93 | 8 | 2027-04-29 | high | high | high | high | low | 1800000 | 1807733 | 1857547 | 0 | 0 | 0 | 540000 | 540000 | 360000 | 360000 | 0 | 0 | 0 | 0 | 0 | 1800000 | 102.2668 | EXPENSE | No | Pipeline segment | X |  | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 3 | 3 | 1 | 3 | 4 | 1 | 1 | 1 | 1 | 40% | 4 | 2 | 5 | 5 | 2 | 1 | 3 | 60% | 6 |  | 4995.39
498 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Calgary | 2026-12-31 | 2026 | 118 | 4 | 2026-09-04 | high | med | low | med | med | 1032128 | 1501619 | 1608733 | 309638.4 | 619276.8 | 103212.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032128 | 58.9784 | EXPENSE | Yes | Unit outage | X |  |  | X |  | no | no | Yes | no | Yes | no | Yes | Yes | Yes | 3 | 1 | 4 | 2 | 1 | 2 | 2 | 5 | 5 | 55.56% | 6 | 3 | 1 | 1 | 4 | 5 | 5 | 63.33% | 7 |  | 425
494 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2025-10-31 | 2025 | 150 | 4 | 2025-06-03 | med | med | high | med | high | 2348327 | 2332370 | 2833738 | 704498.1 | 1408996.2 | 234832.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2348327 | 47.6878 | CAPITAL | Yes | Unit outage | X |  | X | X | X | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 4 | 3 | 3 | 3 | 2 | 5 | 2 | 5 | 1 | 62.22% | 7 | 1 | 4 | 1 | 5 | 4 | 2 | 56.67% | 6 |  | 1117.2047
495 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Regina | 2026-03-31 | 2026 | 150 | 8 | 2025-11-01 | low | med | med | high | high | 500000 | 666455 | 685432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 500000 | 12.1249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 33.33% | 4 | 1 | 2 | 1 | 4 | 5 | 1 | 46.67% | 5 |  | 8756
496 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Toronto | 2027-12-31 | 2027 | 100 | 8 | 2027-09-22 | low | low | med | high | high | 500000 | 483098 | 491931 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 1000000 | 94.2513 | CAPITAL | Yes | Pipeline segment |  |  | X |  | X | Yes | no | no | Yes | Yes | Yes | Yes | Yes | no | 4 | 3 | 1 | 2 | 4 | 1 | 5 | 4 | 3 | 60% | 6 | 5 | 2 | 5 | 4 | 5 | 2 | 76.67% | 8 |  | 4785
497 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2029-12-31 | 2029 | 150 | 8 | 2029-08-03 | low | med | med | low | high | 550000 | 531429 | 533699 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 69.7306 | CAPITAL | No | Pipeline segment | X | X |  | X | X | Yes | Yes | Yes | no | Yes | Yes | Yes | no | no | 4 | 1 | 1 | 4 | 3 | 2 | 4 | 4 | 4 | 60% | 6 | 3 | 1 | 1 | 3 | 4 | 3 | 50% | 5 |  | 778.6578
498 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2028-12-31 | 2028 | 200 | 4 | 2028-06-14 | high | low | low | med | med | 1800000 | 1964493 | 1902540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 0 | 1800000 | 55.4393 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 1 | 5 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 37.78% | 4 | 1 | 1 | 5 | 5 | 5 | 5 | 73.33% | 8 |  | 1090.5382
499 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Winnipeg | 2026-12-31 | 2026 | 120 | 8 | 2026-09-02 | low | med | med | med | low | 500000 | 780384 | 780364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 500000 | 36.7014 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 5 | 4 | 4 | 5 | 1 | 2 | 4 | 1 | 1 | 60% | 6 | 2 | 5 | 1 | 5 | 2 | 2 | 56.67% | 6 |  | 267.7598
500 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Edmonton | 2026-07-31 | 2026 | 60 | 10 | 2026-06-01 | high | high | low | med | med | 1300000 | 1227077 | 1411856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 780000 | 130000 | 0 | 0 | 1300000 | 80.7922 | EXPENSE | Yes | pipeline segment outage |  |  | X |  | X | no | Yes | Yes | no | Yes | Yes | Yes | no | Yes | 4 | 4 | 4 | 5 | 1 | 1 | 3 | 2 | 5 | 64.44% | 7 | 2 | 1 | 1 | 4 | 3 | 1 | 40% | 4 |  | 1591.17
495 | L1 | FACILITY | MAJOR EQUIP |  | PT MAJOR OH | Montreal | 2025-07-31 | 2025 | 265 | 4 | 2024-11-08 | low | high | low | low | med | 1301814 | 1645284 | 1656042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390544.2 | 781088.4 | 130181.4 | 0 | 1301814 | 104.1656 | CAPITAL | Yes | Unit outage |  |  | X | X | X | no | Yes | no | Yes | Yes | no | no | no | Yes | 4 | 4 | 2 | 5 | 2 | 3 | 4 | 2 | 2 | 62.22% | 7 | 1 | 3 | 1 | 2 | 4 | 3 | 46.67% | 5 |  | 1117.2047
496 | L2 | FACILITY | MEASUREMENT |  | FLOW CONTROL | Toronto | 2028-03-31 | 2028 | 120 | 4 | 2027-12-02 | med | low | high | med | med | 500000 | 436083 | 437918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 39.4615 | CAPITAL | No | Derate/low flow Pipe segment |  | X |  |  |  | no | no | no | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 42.22% | 5 | 4 | 5 | 1 | 1 | 2 | 3 | 53.33% | 6 |  | 1022.412
497 | L3 | FACILITY | MAJOR EQUIP |  | MINOR OH | Quebec City | 2026-10-31 | 2026 | 334 | 4 | 2025-12-01 | low | med | high | low | high | 726541 | 798772 | 810709 | 217962.3 | 435924.6 | 72654.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726541 | 97.8209 | CAPITAL | Yes | Unit outage |  | X |  |  |  | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 3 | 5 | 3 | 2 | 2 | 2 | 4 | 1 | 3 | 55.56% | 6 | 2 | 5 | 1 | 2 | 5 | 1 | 53.33% | 6 |  | 3138.866
498 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2027-12-31 | 2027 | 315 | 4 | 2027-02-19 | high | med | med | high | low | 650000 | 888878 | 879764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 650000 | 65.902 | EXPENSE | Yes | Derate/low flow Pipe segment | x | x | x | x | x | Yes | x | x | Yes | Yes | Yes |  | No | No | 5 | 5 | 3 | 2 | 4 | 3 | 4 | 1 | 3 | 66.67% | 7 | 2 | 1 | 1 | 5 | 4 | 3 | 53.33% | 6 |  | 560.1412
499 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2026-12-31 | 2026 | 100 | 4 | 2026-09-22 | high | med | low | high | med | 1500000 | 1580829 | 1584305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 1500000 | 143.1102 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 3 | 5 | 2 | 2 | 4 | 2 | 4 | 2 | 3 | 60% | 6 | 3 | 1 | 1 | 5 | 2 | 5 | 56.67% | 6 |  | 636.4681
496 | L2 | FACILITY | MEASUREMENT |  | BARTON | Toronto | 2025-03-31 | 2025 | 232 | 4 | 2024-08-11 | med | low | high | med | med | 400000 | 536083 | 497918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 39.4615 | CAPITAL | No | Derate/low flow Pipe segment |  | X |  |  |  | no | no | no | Yes | no | Yes | Yes | Yes | no | 2 | 2 | 1 | 1 | 4 | 1 | 2 | 3 | 5 | 46.67% | 5 | 1 | 1 | 1 | 2 | 1 | 2 | 26.67% | 3 |  | 45.3112
497 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Montreal | 2029-12-31 | 2029 | 232 | 7 | 2029-05-13 | med | med | low | high | high | 1083938 | 1109932 | 1042157 | 325181.4 | 650362.8 | 108393.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1083938 | 96.1454 | EXPENSE | Yes | Unit outage | X | X |  |  | X | no | no | Yes | no | no | Yes | Yes | no | Yes | 5 | 3 | 1 | 2 | 3 | 2 | 1 | 4 | 1 | 48.89% | 5 | 2 | 1 | 1 | 1 | 5 | 3 | 43.33% | 5 |  | 853.1382
498 | L2 | FACILITY | MAJOR EQUIP |  | MINOR OH | WINNIPEG | 2028-10-31 | 2028 | 180 | 4 | 2028-05-04 | high | med | low | high | med | 1860140 | 1917540 | 1909145 | 0 | 0 | 0 | 0 | 558042 | 1116084 | 186014 | 0 | 0 | 0 | 0 | 0 | 1860140 | 54.251 | CAPITAL | Yes | Unit outage |  | X | X |  |  | no | Yes | no | Yes | no | no | Yes | Yes | Yes | 5 | 3 | 3 | 3 | 1 | 4 | 4 | 1 | 4 | 62.22% | 7 | 1 | 4 | 1 | 2 | 4 | 1 | 43.33% | 5 |  | 1846.6194
499 | L2 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Ottawa | 2025-12-31 | 2025 | 364 | 4 | 2025-01-01 | high | high | low | low | low | 741595 | 765559 | 799216 | 0 | 0 | 222478.5 | 444957 | 74159.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741595 | 13.3787 | EXPENSE | Yes | Unit outage |  |  | X | X |  | no | Yes | Yes | no | no | no | no | Yes | no | 4 | 1 | 4 | 3 | 5 | 3 | 1 | 4 | 3 | 62.22% | 7 | 5 | 3 | 1 | 3 | 5 | 2 | 63.33% | 7 |  | 25393.37
497 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2027-12-31 | 2027 | 130 | 4 | 2027-08-23 | high | low | low | high | low | 350000 | 901807 | 925115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 243.4001 | EXPENSE | No | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 5 | 2 | 5 | 5 | 2 | 5 | 2 | 1 | 66.67% | 7 | 5 | 3 | 1 | 4 | 4 | 2 | 63.33% | 7 |  | 1300.7103
498 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Ottawa | 2028-12-31 | 2028 | 150 | 8 | 2028-08-03 | low | med | low | high | high | 550000 | 565673 | 562884 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 550000 | 110.153 | CAPITAL | No | Pipeline segment | X | X | X |  | X | no | no | Yes | Yes | Yes | no | no | no | no | 5 | 4 | 4 | 1 | 1 | 1 | 3 | 1 | 3 | 51.11% | 6 | 2 | 3 | 1 | 2 | 1 | 5 | 46.67% | 5 |  | 267.7598
499 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Winnipeg | 2027-03-31 | 2027 | 163 | 4 | 2026-10-19 | high | low | high | med | high | 3691558 | 3641880 | 3680790 | 0 | 0 | 0 | 0 | 1107467.4 | 2214934.8 | 369155.8 | 0 | 0 | 0 | 0 | 0 | 3691558 | 87.54 | EXPENSE | Yes | Unit outage | [5 empty] | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 1 | 5 | 1 | 3 | 1 | 1 | 4 | 1 | 1 | 40% | 4 | 3 | 1 | 1 | 3 | 1 | 2 | 36.67% | 4 |  | 16021.84
500 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | North Bay | 2026-10-31 | 2026 | 180 | 4 | 2026-05-04 | low | med | med | med | low | 500000 | 595726 | 599706 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 500000 | 19.694 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 3 | 2 | 3 | 1 | 1 | 4 | 4 | 4 | 2 | 53.33% | 6 | 2 | 5 | 5 | 4 | 2 | 5 | 76.67% | 8 |  | 13582.28
501 | L2 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Saskatoon | 2026-07-31 | 2026 | 90 | 8 | 2026-05-02 | low | high | med | med | med | 1606464 | 1926241 | 1980196 | 0 | 0 | 0 | 0 | 481939.2 | 963878.4 | 160646.4 | 0 | 0 | 0 | 0 | 0 | 1606464 | 48.566 | EXPENSE | Yes | Unit outage | X |  | X | X | X | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 1 | 1 | 1 | 2 | 5 | 2 | 2 | 3 | 2 | 42.22% | 5 | 1 | 5 | 5 | 2 | 1 | 1 | 50% | 5 |  | 13420.4072
502 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Saskatoon | 2027-10-31 | 2027 | 85 | 8 | 2027-08-07 | med | high | low | low | low | 2000000 | 2534662 | 2571775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 2000000 | 87.159 | EXPENSE | Yes | Derate/low flow Pipe segment | x | x | x | x | x | NR | x | x | x | x | x |  | No | Yes | 2 | 2 | 3 | 2 | 1 | 1 | 5 | 2 | 5 | 51.11% | 6 | 3 | 4 | 1 | 3 | 1 | 1 | 43.33% | 5 |  | 76225.6763
503 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Saskatoon | 2028-07-31 | 2028 | 120 | 15 | 2028-04-02 | med | low | high | high | high | 550000 | 864397 | 866898 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 61.6448 | CAPITAL | Yes | Pipeline segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | no | Yes | Yes | 3 | 3 | 3 | 2 | 2 | 1 | 4 | 4 | 5 | 60% | 6 | 4 | 5 | 1 | 3 | 2 | 3 | 60% | 6 |  | 5845
504 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2027-03-31 | 2027 | 260 | 8 | 2026-07-14 | low | low | low | low | low | 2100000 | 2120000 | 2154250 | 0 | 0 | 0 | 0 | 630000 | 1260000 | 210000 | 0 | 0 | 0 | 0 | 0 | 2100000 | 40.3349 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | no | no | no | no | no | Yes | no | 2 | 2 | 1 | 2 | 4 | 2 | 2 | 2 | 2 | 42.22% | 5 | 2 | 5 | 1 | 2 | 2 | 4 | 53.33% | 6 |  | 728.1385
505 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Calgary | 2026-07-31 | 2026 | 150 | 10 | 2026-03-03 | low | low | med | med | high | 500000 | 490412 | 496874 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 19.5924 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | no | no | no | no | no | no | Yes | 5 | 2 | 1 | 2 | 3 | 3 | 4 | 5 | 5 | 66.67% | 7 | 5 | 1 | 1 | 2 | 5 | 1 | 50% | 5 |  | 4858.887
506 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Winnipeg | 2029-03-31 | 2029 | 84 | 10 | 2029-01-06 | high | high | low | med | med | 1300000 | 1324785 | 1350260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 780000 | 130000 | 0 | 1300000 | 119.9716 | EXPENSE | No | Pipeline segment | X |  |  |  | X | Yes | no | no | Yes | Yes | no | no | Yes | no | 3 | 4 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 42.22% | 5 | 2 | 5 | 1 | 2 | 5 | 3 | 60% | 6 |  | 17906.94
507 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2026-12-31 | 2026 | 183 | 8 | 2026-07-01 | low | high | high | high | low | 2000000 | 2058655 | 2014691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 2000000 | 488.9487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | no | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 31.11% | 4 | 4 | 2 | 1 | 3 | 1 | 4 | 50% | 5 |  | 2480.6254
508 | L1 | FACILITY | Major EQUIP |  | GG MAJOR OH | Regina | 2028-12-31 | 2028 | 150 | 4 | 2028-08-03 | low | med | med | high | med | 2275112 | 2782481 | 2834679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682533.6 | 1365067.2 | 227511.2 | 0 | 2275112 | 1776.9185 | CAPITAL | Yes | Unit outage | X | X |  |  |  | no | Yes | Yes | Yes | no | Yes | no | Yes | no | 4 | 5 | 1 | 1 | 1 | 5 | 3 | 4 | 5 | 64.44% | 7 | 5 | 4 | 1 | 2 | 3 | 4 | 63.33% | 7 |  | 17906.9371
509 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2027-03-31 | 2027 | 100 | 2 | 2026-12-21 | high | low | high | high | med | 1500000 | 2469351 | 704714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 1500000 | 48.6768 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | no | Yes | no | Yes | Yes | Yes | Yes | no | 2 | 5 | 1 | 1 | 4 | 4 | 4 | 2 | 2 | 55.56% | 6 | 1 | 2 | 1 | 2 | 4 | 3 | 43.33% | 5 |  | 1846.6194
510 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2029-12-31 | 2029 | 120 | 8 | 2029-09-02 | low | low | med | low | med | 2100000 | 2089588 | 2100050 | 0 | 0 | 0 | 0 | 630000 | 1260000 | 210000 | 0 | 0 | 0 | 0 | 0 | 2100000 | 1745.308 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | Yes | no | no | no | no | no | Yes | 1 | 4 | 3 | 3 | 2 | 5 | 2 | 1 | 2 | 51.11% | 6 | 5 | 3 | 1 | 5 | 5 | 5 | 80% | 8 |  | 7110.094
511 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Toronto | 2026-10-31 | 2026 | 139 | 4 | 2026-06-14 | low | med | high | med | high | 2446435 | 2171872 | 2212990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733930.5 | 1467861 | 244643.5 | 0 | 0 | 2446435 | 271.7058 | CAPITAL | Yes | Unit outage | x | x | x | x | x | x | x | NR | x | x | x | x | no | x | 5 | 5 | 3 | 1 | 5 | 5 | 4 | 5 | 5 | 84.44% | 9 | 4 | 2 | 1 | 5 | 3 | 5 | 66.67% | 7 |  | 14995.8254
512 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Saskatoon | 2026-12-31 | 2026 | 180 | 4 | 2026-07-04 | high | high | med | med | high | 425000 | 662668 | 637944 | 0 | 0 | 0 | 0 | 127500 | 255000 | 42500 | 0 | 0 | 0 | 0 | 0 | 425000 | 32.9243 | EXPENSE | Yes | pipeline segment outage | X | X | X |  | X | no | Yes | Yes | no | Yes | no | no | no | no | 4 | 2 | 4 | 3 | 2 | 2 | 4 | 2 | 2 | 55.56% | 6 | 5 | 1 | 1 | 4 | 1 | 4 | 53.33% | 6 |  | 5000
513 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Regina | 2026-03-31 | 2026 | 52 | 4 | 2026-02-07 | high | low | med | high | high | 3188591 | 3052434 | 3104640 | 0 | 0 | 0 | 0 | 956577.3 | 1913154.6 | 318859.1 | 0 | 0 | 0 | 0 | 0 | 3188591 | 81.1583 | CAPITAL | Yes | Unit outage |  |  |  | X |  | Yes | Yes | no | Yes | no | no | Yes | no | Yes | 3 | 2 | 3 | 1 | 5 | 4 | 2 | 4 | 3 | 60% | 6 | 4 | 2 | 1 | 2 | 2 | 1 | 40% | 4 |  | 7007.9205
514 | L2 | FACILITY | MAJOR EQUIP |  | MINOR OH | Ottawa | 2026-07-31 | 2026 | 334 | 4 | 2025-08-31 | med | low | low | high | low | 1305126 | 1760248 | 1777193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391537.8 | 783075.6 | 130512.6 | 0 | 0 | 1305126 | 136.1702 | CAPITAL | Yes | Unit outage |  |  | X |  | X | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 1 | 2 | 3 | 3 | 5 | 5 | 2 | 3 | 4 | 62.22% | 7 | 5 | 4 | 5 | 3 | 1 | 2 | 66.67% | 7 |  | 2480.6254
515 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Regina | 2027-12-31 | 2027 | 180 | 10 | 2027-07-04 | med | low | low | low | med | 1800000 | 1807733 | 1857547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 0 | 0 | 1800000 | 76.4961 | EXPENSE | No | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 5 | 1 | 1 | 5 | 4 | 4 | 4 | 5 | 1 | 66.67% | 7 | 4 | 3 | 1 | 4 | 5 | 5 | 73.33% | 8 |  | 840.2082
516 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2028-07-31 | 2028 | 217 | 8 | 2027-12-27 | med | high | low | high | high | 2000000 | 1920848 | 1689578 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 0 | 2000000 | 304.5368 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X | X | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 1 | 1 | 5 | 5 | 4 | 1 | 5 | 1 | 57.78% | 6 | 3 | 2 | 1 | 4 | 5 | 2 | 56.67% | 6 |  | 5347.325
517 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Edmonton | 2026-07-31 | 2026 | 150 | 10 | 2026-03-03 | low | high | med | high | low | 1300000 | 1281295 | 1270817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 780000 | 390000 | 1300000 | 714.4143 | EXPENSE | No | pipeline segment outage | X |  | X |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 4 | 1 | 4 | 5 | 2 | 4 | 4 | 1 | 62.22% | 7 | 2 | 1 | 1 | 1 | 5 | 5 | 50% | 5 |  | 898
518 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2027-10-31 | 2027 | 185 | 4 | 2027-04-29 | high | low | low | low | med | 1800000 | 1789522 | 1832500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 720000 | 900000 | 1800000 | 2.6813 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 5 | 5 | 3 | 1 | 2 | 2 | 4 | 5 | 4 | 68.89% | 7 | 1 | 5 | 1 | 3 | 1 | 3 | 46.67% | 5 |  | 477.3811
519 | L2 | FACILITY | AUTOMATION & CONTROLS |  | PLC | North Bay | 2027-12-31 | 2027 | 204 | 2 | 2027-06-10 | high | low | med | low | high | 285000 | 439078 | 450000 | 85500 | 171000 | 28500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285000 | 426.8693 | EXPENSE | Yes | Unit outage |  | X | X | X | X | Yes | no | no | no | Yes | no | no | no | no | 4 | 4 | 4 | 4 | 2 | 1 | 2 | 4 | 4 | 64.44% | 7 | 2 | 5 | 1 | 2 | 1 | 4 | 50% | 5 |  | 16.9273
520 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2027-07-31 | 2027 | 100 | 4 | 2027-04-22 | low | high | high | high | high | 1500000 | 1804556 | 1813074 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 83.977 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  | X | Yes | Yes | no | no | Yes | no | no | no | no | 5 | 4 | 1 | 1 | 3 | 5 | 5 | 2 | 2 | 62.22% | 7 | 3 | 1 | 1 | 3 | 4 | 2 | 46.67% | 5 |  | 8501.4285
521 | L1 | FACILITY | MAJOR EQUIP |  | MINOR OH | Ottawa | 2029-03-31 | 2029 | 160 | 4 | 2028-10-22 | low | med | med | med | med | 1059613 | 1004902 | 1042600 | 0 | 0 | 0 | 317883.9 | 635767.8 | 105961.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1059613 | 32.3326 | CAPITAL | Yes | Unit outage | X |  | X | X |  | Yes | no | Yes | Yes | no | no | Yes | Yes | no | 3 | 1 | 3 | 4 | 2 | 3 | 2 | 1 | 4 | 51.11% | 6 | 4 | 2 | 1 | 1 | 5 | 3 | 53.33% | 6 |  | 4995.39
522 | L2 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Quebec City | 2028-03-31 | 2028 | 170 | 4 | 2027-10-13 | high | high | low | med | high | 928800 | 1327497 | 1407658 | 278640 | 557280 | 92880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 928800 | 43.8908 | EXPENSE | Yes | Unit outage | X | X |  | X |  | no | no | no | Yes | no | no | Yes | no | no | 2 | 4 | 2 | 2 | 1 | 4 | 4 | 2 | 1 | 48.89% | 5 | 2 | 5 | 1 | 2 | 1 | 4 | 50% | 5 |  | 14995.83
523 | L2 | FACILITY | AUTOMATION & CONTROLS |  | PLC | Toronto | 2027-12-31 | 2027 | 288 | 1 | 2027-03-18 | high | low | low | high | med | 120000 | 87500 | 127000 | 0 | 0 | 0 | 0 | 36000 | 72000 | 12000 | 0 | 0 | 0 | 0 | 0 | 120000 | 183.8574 | CAPITAL | No | Unit outage |  |  |  | X |  | no | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 4 | 3 | 4 | 1 | 5 | 4 | 4 | 3 | 3 | 68.89% | 7 | 4 | 3 | 1 | 4 | 1 | 4 | 56.67% | 6 |  | 4526
524 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Ottawa | 2028-10-31 | 2028 | 180 | 10 | 2028-05-04 | high | high | low | low | low | 550000 | 464113 | 471206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 51.5723 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 1 | 1 | 1 | 1 | 1 | 2 | 5 | 2 | 1 | 33.33% | 4 | 5 | 1 | 1 | 3 | 1 | 5 | 53.33% | 6 |  | 4314.195
525 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2026-03-31 | 2026 | 130 | 8 | 2025-11-21 | low | high | high | low | low | 350000 | 332894 | 386745 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 350000 | 27.2404 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | Yes | Yes | 3 | 2 | 2 | 3 | 5 | 3 | 1 | 3 | 1 | 51.11% | 6 | 2 | 5 | 1 | 5 | 4 | 1 | 60% | 6 |  | 560.1412
526 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2027-10-31 | 2027 | 275 | 4 | 2027-01-29 | low | med | low | high | low | 2000000 | 2242580 | 2285780 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 104.3547 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 3 | 4 | 2 | 2 | 4 | 3 | 4 | 3 | 2 | 60% | 6 | 3 | 1 | 1 | 1 | 4 | 1 | 36.67% | 4 |  | 1184.9141
527 | L3 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Edmonton | 2025-10-31 | 2025 | 159 | 7 | 2025-05-25 | high | high | high | med | med | 954752 | 1528786 | 1507834 | 0 | 190950.4 | 95475.2 | 0 | 0 | 95475.2 | 572851.2 | 0 | 0 | 0 | 0 | 0 | 954752 | 157.9294 | EXPENSE | Yes | Unit outage | X |  |  | X | X | Yes | Yes | no | Yes | no | Yes | Yes | no | Yes | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 37.78% | 4 | 5 | 5 | 1 | 3 | 3 | 4 | 70% | 7 |  | 10535.7532
528 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2029-03-31 | 2029 | 318 | 4 | 2028-05-17 | med | med | med | med | low | 2601688 | 2675222 | 2315263 | 0 | 0 | 0 | 780506.4 | 1561012.8 | 260168.8 | 0 | 0 | 0 | 0 | 0 | 0 | 2601688 | 218.5955 | CAPITAL | Yes | Unit outage |  | X | X |  | X | no | Yes | Yes | Yes | no | no | Yes | Yes | Yes | 3 | 2 | 4 | 4 | 4 | 4 | 1 | 1 | 2 | 55.56% | 6 | 4 | 4 | 1 | 4 | 4 | 1 | 60% | 6 |  | 1174.9707
529 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Saskatoon | 2029-07-31 | 2029 | 125 | 10 | 2029-03-28 | high | high | low | med | med | 550000 | 489598 | 483329 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 550000 | 57.38 | CAPITAL | Yes | Pipeline segment | X | X |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 4 | 2 | 3 | 1 | 2 | 5 | 1 | 4 | 55.56% | 6 | 5 | 4 | 1 | 4 | 2 | 3 | 63.33% | 7 |  | 1090.538
530 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Saskatoon | 2030-07-31 | 2030 | 180 | 10 | 2030-02-01 | low | low | med | high | med | 1800000 | 1875000 | 1830883 | 180000 | 1440000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 49.4725 | EXPENSE | No | pipeline segment outage |  |  |  | X |  | no | no | no | Yes | Yes | Yes | Yes | no | no | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 28.89% | 3 | 5 | 2 | 1 | 3 | 3 | 5 | 63.33% | 7 |  | 646
531 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2028-12-31 | 2028 | 200 | 2 | 2028-06-14 | low | low | low | low | low | 850000 | 852000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 510000 | 85000 | 0 | 850000 | 26.0956 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 5 | 5 | 2 | 5 | 3 | 2 | 4 | 4 | 1 | 68.89% | 7 | 1 | 2 | 5 | 2 | 4 | 2 | 53.33% | 6 |  | 8429.71
532 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2030-12-31 | 2030 | 200 | 4 | 2030-06-14 | low | low | low | high | med | 950000 | 951400 | 1073713 | 0 | 0 | 285000 | 570000 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 165.7118 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | no | no | no | Yes | 2 | 3 | 2 | 1 | 4 | 5 | 4 | 1 | 3 | 55.56% | 6 | 4 | 2 | 1 | 2 | 3 | 5 | 56.67% | 6 |  | 495.1227
533 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Calgary | 2029-12-31 | 2029 | 169 | 4 | 2029-07-15 | high | low | med | high | med | 1880538 | 2506702 | 2514549 | 0 | 0 | 0 | 0 | 0 | 0 | 564161.4 | 1128322.8 | 188053.8 | 0 | 0 | 0 | 1880538 | 53.9499 | CAPITAL | Yes | Unit outage |  |  | X | X | X | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 4 | 3 | 3 | 1 | 3 | 3 | 3 | 4 | 4 | 62.22% | 7 | 1 | 5 | 5 | 5 | 5 | 5 | 86.67% | 9 |  | 6062.6028
534 | L3 | FACILITY | AUTOMATION & CONTROLS |  | PLC | Edmonton | 2026-03-31 | 2026 | 64 | 1 | 2026-01-26 | med | low | high | high | med | 225500 | 287177 | 299089 | 0 | 0 | 0 | 0 | 67650 | 135300 | 22550 | 0 | 0 | 0 | 0 | 0 | 225500 | 399.787 | EXPENSE | No | Unit outage | X |  |  |  | X | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 2 | 5 | 2 | 3 | 4 | 5 | 5 | 1 | 5 | 71.11% | 8 | 1 | 2 | 1 | 3 | 1 | 1 | 30% | 3 |  | 2166.583
535 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Winnipeg | 2026-07-31 | 2026 | 250 | 10 | 2025-11-23 | high | high | med | med | low | 1300000 | 1424785 | 1450260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 780000 | 130000 | 0 | 0 | 1300000 | 2123.4281 | EXPENSE | Yes | pipeline segment outage | X |  |  |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | no | 1 | 4 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 37.78% | 4 | 2 | 3 | 5 | 5 | 4 | 5 | 80% | 8 |  | 173.2929
536 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2030-03-31 | 2030 | 100 | 4 | 2029-12-21 | med | high | low | high | med | 520000 | 582895 | 685540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156000 | 312000 | 52000 | 0 | 0 | 520000 | 199.4572 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 2 | 1 | 3 | 3 | 5 | 2 | 5 | 57.78% | 6 | 4 | 4 | 1 | 1 | 1 | 4 | 50% | 5 |  | 4995.3897
537 | L1 | FACILITY | AUTOMATION & CONTROLS |  | PLC | Toronto | 2027-12-31 | 2027 | 187 | 1 | 2027-06-27 | high | high | med | med | low | 120282 | 78145 | 743364 | 0 | 12028.2 | 96225.6 | 12028.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120282 | 618.0177 | EXPENSE | Yes | Unit outage | X | X | X | X | X | Yes | Yes | no | Yes | Yes | no | Yes | no | no | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 3 | 2 | 55.56% | 6 | 1 | 2 | 1 | 5 | 2 | 4 | 50% | 5 |  | 31873.2921
538 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2027-10-31 | 2027 | 130 | 8 | 2027-06-23 | med | med | low | low | med | 420000 | 465754 | 449856 | 126000 | 252000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 159.1014 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | Yes | Yes | no | Yes | no | Yes | Yes | no | 3 | 4 | 5 | 2 | 3 | 1 | 1 | 3 | 5 | 60% | 6 | 4 | 2 | 1 | 5 | 5 | 1 | 60% | 6 |  | 2310.5725
539 | L1 | FACILITY | MAJOR EQUIP |  | COMPRESOR REPAIR | Montreal | 2026-12-31 | 2026 | 180 | 8 | 2026-07-04 | high | high | low | low | med | 857925 | 846017 | 847000 | 257377.5 | 514755 | 85792.5 | 0 | 0 | 0 | 0 | 0 | 0 | 257377.5 | 514755 | 85792.5 | 1715850 | 818.9288 | EXPENSE | Yes | Unit outage |  | X |  | X | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 5 | 3 | 4 | 1 | 4 | 4 | 4 | 4 | 75.56% | 8 | 5 | 5 | 1 | 2 | 2 | 4 | 63.33% | 7 |  | 158885
540 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Saskatoon | 2027-12-31 | 2027 | 125 | 10 | 2027-08-28 | low | med | med | high | low | 500000 | 487877 | 486522 | 0 | 50000 | 50000 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 121.3811 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | no | no | Yes | no | no | Yes | no | no | Yes | 4 | 1 | 1 | 1 | 5 | 1 | 4 | 4 | 3 | 53.33% | 6 | 5 | 4 | 1 | 1 | 3 | 4 | 60% | 6 |  | 8501.429
541 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | North Bay | 2028-03-31 | 2028 | 150 | 2 | 2027-11-02 | med | high | low | high | med | 1250000 | 1381952 | 1385422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 750000 | 125000 | 0 | 1250000 | 72.2212 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  | X | no | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 4 | 5 | 4 | 5 | 5 | 4 | 3 | 1 | 1 | 71.11% | 8 | 5 | 2 | 1 | 5 | 1 | 1 | 50% | 5 |  | 3981.0002
542 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2030-07-31 | 2030 | 80 | 4 | 2030-05-12 | med | low | high | high | low | 3872272 | 3820379 | 3865247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1161681.6 | 2323363.2 | 387227.2 | 0 | 3872272 | 213.8378 | CAPITAL | Yes | Unit outage | X |  |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 2 | 4 | 3 | 2 | 1 | 2 | 2 | 3 | 2 | 46.67% | 5 | 5 | 5 | 1 | 3 | 5 | 5 | 80% | 8 |  | 2898
543 | L3 | FACILITY | AUTOMATION & CONTROLS |  | PLC | Edmonton | 2027-03-31 | 2027 | 200 | 2 | 2026-09-12 | high | med | high | med | med | 275436 | 238926 | 230244 | 0 | 0 | 0 | 0 | 82630.8 | 165261.6 | 27543.6 | 0 | 0 | 0 | 0 | 0 | 275436 | 519.2655 | EXPENSE | Yes | Unit outage | X | X | X | X | X | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 2 | 2 | 2 | 3 | 3 | 4 | 5 | 3 | 4 | 62.22% | 7 | 1 | 5 | 1 | 4 | 4 | 3 | 60% | 6 |  | 1785
544 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2026-03-31 | 2026 | 130 | 8 | 2025-11-21 | high | med | med | high | low | 350000 | 358642 | 375845 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 83.0189 | CAPITAL | No | Pipeline segment |  | X |  | X |  | Yes | Yes | no | Yes | Yes | no | no | Yes | Yes | 5 | 5 | 3 | 3 | 4 | 5 | 1 | 4 | 3 | 73.33% | 8 | 2 | 4 | 1 | 1 | 5 | 2 | 50% | 5 |  | 2369.8282
545 | L1 | FACILITY | AUTOMATION & CONTROLS |  | CONTROLS UPGRADE | Calgary | 2026-12-31 | 2026 | 320 | 3 | 2026-02-14 | med | low | high | high | med | 2366920 | 1345102 | 1333738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710076 | 1183460 | 473384 | 2366920 | 6.8576 | CAPITAL | Yes | Station outage |  | X | X |  | X | no | no | Yes | no | no | no | no | Yes | Yes | 1 | 1 | 1 | 1 | 5 | 5 | 3 | 2 | 3 | 48.89% | 5 | 5 | 1 | 5 | 4 | 4 | 5 | 80% | 8 |  | 25885
546 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Ottawa | 2026-03-31 | 2026 | 200 | 8 | 2025-09-12 | high | med | high | low | med | 500000 | 827580 | 888541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 500000 | 53.7439 | CAPITAL | No | Pipeline segment | X |  |  |  |  | Yes | Yes | no | no | no | Yes | Yes | no | Yes | 2 | 2 | 1 | 1 | 5 | 3 | 2 | 2 | 3 | 46.67% | 5 | 1 | 1 | 1 | 2 | 5 | 4 | 46.67% | 5 |  | 347
547 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2028-12-31 | 2028 | 150 | 4 | 2028-08-03 | low | high | high | high | med | 1500000 | 1583805 | 1580197 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 3000000 | 110.9054 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | no | no | Yes | no | no | Yes | Yes | Yes | 5 | 2 | 2 | 1 | 3 | 2 | 5 | 2 | 3 | 55.56% | 6 | 5 | 5 | 5 | 3 | 1 | 5 | 80% | 8 |  | 17599.3754
548 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2026-07-31 | 2026 | 304 | 4 | 2025-09-30 | med | med | low | high | low | 3275751 | 3384117 | 3338163 | 0 | 0 | 0 | 0 | 0 | 0 | 982725.3 | 1965450.6 | 327575.1 | 0 | 0 | 0 | 3275751 | 57.8611 | CAPITAL | Yes | Unit outage | X |  | X | X | X | Yes | no | no | Yes | no | no | Yes | Yes | no | 5 | 4 | 1 | 3 | 3 | 5 | 2 | 2 | 3 | 62.22% | 7 | 5 | 1 | 1 | 3 | 2 | 3 | 50% | 5 |  | 9580.877
549 | L3 | FACILITY | ELECTRICAL |  | PPU | Toronto | 2026-10-31 | 2026 | 177 | 1 | 2026-05-07 | high | med | med | high | med | 160000 | 198500 | 192500 | 0 | 0 | 0 | 0 | 0 | 48000 | 96000 | 16000 | 0 | 0 | 0 | 0 | 160000 | 94.0727 | CAPITAL | No | Unit outage | X |  | X | X | X | no | Yes | Yes | no | Yes | Yes | no | Yes | no | 4 | 3 | 2 | 3 | 2 | 3 | 3 | 4 | 1 | 55.56% | 6 | 1 | 1 | 1 | 1 | 3 | 4 | 36.67% | 4 |  | 10182.17
550 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2026-07-31 | 2026 | 130 | 5 | 2026-03-23 | low | high | low | med | low | 400000 | 450563 | 459107 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 135.4595 | EXPENSE | No | Pipeline segment |  | X |  |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 2 | 4 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 40% | 4 | 2 | 1 | 1 | 3 | 4 | 4 | 50% | 5 |  | 13659.1884
551 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Quebec City | 2027-03-31 | 2027 | 200 | 8 | 2026-09-12 | high | high | low | high | low | 550000 | 1575306 | 1571669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 68.6381 | CAPITAL | Yes | Pipeline segment | X |  | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 1 | 2 | 3 | 2 | 4 | 5 | 3 | 1 | 1 | 48.89% | 5 | 4 | 4 | 1 | 1 | 1 | 4 | 50% | 5 |  | 1207.799
552 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2029-10-31 | 2029 | 175 | 4 | 2029-05-09 | low | high | med | med | low | 1250000 | 1350000 | 1450000 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 750000 | 125000 | 0 | 0 | 0 | 1250000 | 96.934 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 2 | 1 | 3 | 3 | 5 | 1 | 3 | 53.33% | 6 | 1 | 5 | 5 | 1 | 5 | 1 | 60% | 6 |  | 7024.2246
553 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2027-03-31 | 2027 | 169 | 4 | 2026-10-13 | low | high | high | low | high | 4185667 | 4675386 | 4686248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255700.1 | 2511400.2 | 418566.7 | 0 | 0 | 4185667 | 7.2742 | CAPITAL | Yes | Unit outage |  | X | X | X |  | no | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 3 | 1 | 2 | 5 | 2 | 1 | 2 | 4 | 51.11% | 6 | 5 | 1 | 1 | 3 | 2 | 1 | 43.33% | 5 |  | 1685.963
554 | L2 | FACILITY | ELECTRICAL |  | PPU | North Bay | 2028-12-31 | 2028 | 136 | 0 | 2028-08-17 | low | med | low | low | high | 160000 | 178525 | 198703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | 96000 | 16000 | 160000 | 417.9806 | EXPENSE | No | NO |  |  | X | X | X | no | Yes | Yes | no | Yes | Yes | Yes | no | no | 4 | 3 | 3 | 4 | 2 | 2 | 3 | 4 | 1 | 57.78% | 6 | 4 | 2 | 1 | 2 | 5 | 4 | 60% | 6 |  | 13582.277
555 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2027-10-31 | 2027 | 130 | 5 | 2027-06-23 | low | high | low | med | high | 420000 | 850041 | 889250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 252000 | 42000 | 420000 | 122.5032 | EXPENSE | Yes | Pipeline segment | X |  |  | X |  | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 4 | 1 | 1 | 2 | 2 | 2 | 2 | 5 | 46.67% | 5 | 5 | 1 | 1 | 5 | 3 | 1 | 53.33% | 6 |  | 13659.1884
556 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Winnipeg | 2027-07-31 | 2027 | 120 | 10 | 2027-04-02 | high | high | low | low | low | 500000 | 488609 | 483956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 84.9423 | CAPITAL | No | pipeline segment | X | X | X | X |  | no | no | Yes | Yes | no | no | no | Yes | Yes | 2 | 1 | 1 | 1 | 4 | 3 | 5 | 3 | 2 | 48.89% | 5 | 1 | 3 | 5 | 2 | 5 | 5 | 70% | 7 |  | 172.2548
557 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2030-12-31 | 2030 | 100 | 4 | 2030-09-22 | med | low | low | high | low | 1750000 | 1789882 | 1779817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 1050000 | 175000 | 0 | 0 | 1750000 | 4.1819 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | no | no | no | no | no | Yes | Yes | no | no | 2 | 5 | 1 | 3 | 3 | 2 | 3 | 1 | 4 | 53.33% | 6 | 2 | 3 | 1 | 5 | 2 | 3 | 53.33% | 6 |  | 5732.8906
558 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Quebec City | 2028-12-31 | 2028 | 222 | 4 | 2028-05-23 | med | med | med | high | med | 1540000 | 1677575 | 1687601 | 462000 | 924000 | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540000 | 63.4775 | CAPITAL | Yes | Unit outage | X |  | X |  | X | no | Yes | Yes | no | no | no | Yes | no | no | 4 | 3 | 2 | 2 | 1 | 3 | 4 | 1 | 1 | 46.67% | 5 | 3 | 3 | 1 | 3 | 4 | 3 | 56.67% | 6 |  | 3077.963
559 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2026-07-31 | 2026 | 100 | 5 | 2026-04-22 | high | med | high | med | med | 420000 | 419283 | 410602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 252000 | 42000 | 0 | 0 | 420000 | 148.1189 | EXPENSE | Yes | Pipeline segment | X |  | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 3 | 5 | 4 | 1 | 2 | 2 | 3 | 2 | 5 | 60% | 6 | 4 | 5 | 5 | 3 | 4 | 1 | 73.33% | 8 |  | 21537.8368
560 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Regina | 2026-10-31 | 2026 | 120 | 10 | 2026-07-03 | med | med | low | low | low | 500000 | 624655 | 652754 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 95.8703 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | no | no | Yes | no | no | no | no | Yes | 3 | 1 | 1 | 1 | 5 | 1 | 4 | 2 | 3 | 46.67% | 5 | 2 | 2 | 1 | 4 | 3 | 1 | 43.33% | 5 |  | 41798.52
561 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2027-10-31 | 2027 | 120 | 8 | 2027-07-03 | low | med | high | high | low | 2000000 | 2063711 | 2060699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 2000000 | 35.0188 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | no | no | no | 1 | 3 | 2 | 1 | 1 | 3 | 4 | 2 | 2 | 42.22% | 5 | 3 | 4 | 5 | 5 | 1 | 5 | 76.67% | 8 |  | 7709.846
562 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | WINNIPEG | 2027-10-31 | 2027 | 190 | 4 | 2027-04-24 | med | med | high | low | low | 1807464 | 1640026 | 1584985 | 0 | 542239.2 | 1084478.4 | 180746.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1807464 | 163.8288 | CAPITAL | Yes | Unit outage |  |  | X | X |  | Yes | no | Yes | no | no | no | Yes | Yes | no | 2 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 4 | 44.44% | 5 | 1 | 5 | 5 | 5 | 1 | 2 | 63.33% | 7 |  | 222.8052
563 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2027-10-31 | 2027 | 101 | 10 | 2027-07-22 | high | low | low | med | med | 400000 | 500000 | 489415 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 194.4749 | EXPENSE | Yes | Pipeline segment |  |  |  | X | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 1 | 2 | 3 | 1 | 5 | 3 | 5 | 1 | 2 | 51.11% | 6 | 3 | 3 | 5 | 2 | 3 | 5 | 70% | 7 |  | 9580.8769
564 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2029-12-31 | 2029 | 180 | 8 | 2029-07-04 | high | med | med | low | low | 550000 | 931419 | 934750 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 550000 | 76.4614 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | no | no | 2 | 4 | 1 | 2 | 2 | 2 | 5 | 1 | 1 | 44.44% | 5 | 5 | 3 | 1 | 5 | 3 | 2 | 63.33% | 7 |  | 1022.412
565 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Regina | 2029-07-31 | 2029 | 120 | 8 | 2029-04-02 | high | low | med | med | med | 2000000 | 1987275 | 1896800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1000000 | 400000 | 2000000 | 526.2579 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 5 | 2 | 3 | 4 | 1 | 4 | 3 | 4 | 2 | 62.22% | 7 | 4 | 1 | 1 | 3 | 3 | 2 | 46.67% | 5 |  | 4052.085
566 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Toronto | 2028-10-31 | 2028 | 230 | 4 | 2028-03-15 | med | low | high | high | med | 3926870 | 3987955 | 3963500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178061 | 1963435 | 785374 | 0 | 3926870 | 132.3115 | CAPITAL | Yes | Unit outage | X | X | X | X |  | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 4 | 1 | 2 | 3 | 1 | 3 | 1 | 2 | 40% | 4 | 3 | 3 | 1 | 1 | 2 | 1 | 36.67% | 4 |  | 1486.701
567 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2027-10-31 | 2027 | 150 | 10 | 2027-06-03 | high | med | low | med | low | 500000 | 385254 | 395452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 500000 | 156.8587 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 2 | 1 | 1 | 3 | 5 | 3 | 1 | 1 | 4 | 46.67% | 5 | 1 | 1 | 5 | 2 | 2 | 4 | 50% | 5 |  | 425
568 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2028-12-31 | 2028 | 180 | 8 | 2028-07-04 | low | low | high | med | low | 550000 | 558450 | 559906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 134.4344 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | no | no | Yes | Yes | Yes | no | no | Yes | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 2 | 3 | 44.44% | 5 | 3 | 2 | 1 | 5 | 4 | 3 | 60% | 6 |  | 7718.869
569 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Winnipeg | 2026-12-31 | 2026 | 130 | 4 | 2026-08-23 | med | low | high | high | low | 1500000 | 1506928 | 1495675 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 33.796 | CAPITAL | Yes | Derate/low flow Pipe segment | X |  | X |  | X | Yes | no | no | Yes | no | no | Yes | no | no | 2 | 1 | 1 | 1 | 2 | 4 | 5 | 2 | 2 | 44.44% | 5 | 5 | 3 | 1 | 1 | 3 | 4 | 56.67% | 6 |  | 191.3942
570 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2029-12-31 | 2029 | 350 | 4 | 2029-01-15 | low | high | high | low | low | 1823036 | 1792775 | 1824513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546910.8 | 1093821.6 | 182303.6 | 0 | 1823036 | 137.9035 | CAPITAL | Yes | Unit outage |  | X |  | X |  | Yes | no | Yes | no | Yes | Yes | Yes | Yes | Yes | 1 | 1 | 2 | 1 | 5 | 3 | 2 | 1 | 2 | 40% | 4 | 4 | 3 | 1 | 1 | 4 | 2 | 50% | 5 |  | 3333.134
571 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2029-12-31 | 2029 | 150 | 4 | 2029-08-03 | high | high | high | high | med | 420000 | 449044 | 455180 | 42000 | 168000 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 18.1227 | CAPITAL | No | Pipeline segment | X | X |  |  |  | no | Yes | no | Yes | no | no | no | Yes | no | 4 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 4 | 44.44% | 5 | 3 | 1 | 1 | 5 | 1 | 5 | 53.33% | 6 |  | 5522
572 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2029-12-31 | 2029 | 120 | 10 | 2029-09-02 | high | high | high | low | high | 550000 | 792798 | 734137 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 890.1864 | CAPITAL | No | Pipeline segment |  | X | X | X | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 3 | 2 | 1 | 5 | 5 | 5 | 4 | 4 | 5 | 75.56% | 8 | 1 | 3 | 5 | 4 | 4 | 4 | 70% | 7 |  | 6993.546
573 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2028-07-31 | 2028 | 185 | 4 | 2028-01-28 | high | low | low | low | high | 1250000 | 1201124 | 1215797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 750000 | 125000 | 0 | 1250000 | 732.8044 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  |  | no | Yes | Yes | Yes | Yes | no | no | no | no | 3 | 4 | 1 | 2 | 3 | 1 | 4 | 2 | 1 | 46.67% | 5 | 5 | 5 | 1 | 4 | 3 | 3 | 70% | 7 |  | 5521.373
574 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Montreal | 2028-03-31 | 2028 | 51 | 4 | 2028-02-09 | med | high | low | high | med | 4635660 | 4788708 | 4799585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1390698 | 2781396 | 463566 | 4635660 | 12.2021 | CAPITAL | Yes | Unit outage |  |  | X | X | X | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 2 | 3 | 2 | 5 | 3 | 4 | 5 | 3 | 68.89% | 7 | 4 | 4 | 5 | 5 | 1 | 1 | 66.67% | 7 |  | 728.1385
575 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2027-12-31 | 2027 | 150 | 4 | 2027-08-03 | low | high | high | high | low | 350000 | 534618 | 575616 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 502.8679 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | no | Yes | no | no | no | no | Yes | no | no | 5 | 1 | 4 | 5 | 2 | 2 | 3 | 1 | 4 | 60% | 6 | 1 | 3 | 1 | 5 | 3 | 2 | 50% | 5 |  | 4101.0339
576 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2027-07-31 | 2027 | 120 | 15 | 2027-04-02 | high | high | high | med | med | 500000 | 897582 | 890760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 56.3678 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | Yes | no | no | no | no | no | no | no | no | 3 | 5 | 1 | 5 | 3 | 2 | 2 | 3 | 4 | 62.22% | 7 | 1 | 5 | 1 | 1 | 1 | 2 | 36.67% | 4 |  | 3138.866
577 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2027-07-31 | 2027 | 100 | 7 | 2027-04-22 | low | high | low | low | med | 2000000 | 2222026 | 2251913 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 4000000 | 12.9047 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | no | no | no | no | Yes | no | 5 | 3 | 2 | 2 | 1 | 2 | 5 | 4 | 1 | 55.56% | 6 | 4 | 5 | 1 | 3 | 5 | 2 | 66.67% | 7 |  | 13659.19
578 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Winnipeg | 2027-12-31 | 2027 | 118 | 4 | 2027-09-04 | high | high | med | med | med | 2252939 | 2587340 | 2606499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675881.7 | 1351763.4 | 225293.9 | 0 | 2252939 | 39.0549 | CAPITAL | Yes | unit outage | X | X |  |  | X | no | Yes | Yes | Yes | no | Yes | Yes | no | no | 5 | 5 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 51.11% | 6 | 3 | 5 | 1 | 5 | 3 | 4 | 70% | 7 |  | 2973.402
579 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2028-03-31 | 2028 | 85 | 5 | 2028-01-06 | med | low | high | low | low | 400000 | 495918 | 472825 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 800000 | 414.8802 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | Yes | 1 | 3 | 3 | 2 | 2 | 3 | 5 | 1 | 3 | 51.11% | 6 | 1 | 1 | 1 | 5 | 2 | 1 | 36.67% | 4 |  | 1727.2647
580 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Quebec City | 2028-12-31 | 2028 | 200 | 10 | 2028-06-14 | high | med | high | low | low | 650000 | 769127 | 763937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 650000 | 53.022 | CAPITAL | No | Pipeline segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 3 | 1 | 3 | 3 | 5 | 1 | 5 | 3 | 5 | 64.44% | 7 | 3 | 2 | 1 | 4 | 5 | 5 | 66.67% | 7 |  | 4487
581 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | WINNIPEG | 2030-07-31 | 2030 | 85 | 4 | 2030-05-07 | med | low | low | med | high | 850000 | 795426 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 510000 | 85000 | 0 | 0 | 850000 | 287.411 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 3 | 4 | 3 | 1 | 4 | 2 | 5 | 1 | 1 | 53.33% | 6 | 2 | 2 | 5 | 5 | 1 | 1 | 53.33% | 6 |  | 425
582 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Calgary | 2028-10-31 | 2028 | 241 | 4 | 2028-03-04 | low | high | med | low | high | 2982904 | 2699996 | 2955454 | 0 | 0 | 0 | 894871.2 | 1789742.4 | 298290.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2982904 | 23.1267 | CAPITAL | Yes | Unit outage | X |  |  | X |  | Yes | Yes | Yes | Yes | no | Yes | no | Yes | Yes | 2 | 5 | 1 | 2 | 2 | 4 | 2 | 1 | 5 | 53.33% | 6 | 2 | 5 | 1 | 2 | 1 | 5 | 53.33% | 6 |  | 7007.9205
583 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2027-12-31 | 2027 | 85 | 5 | 2027-10-07 | low | low | med | high | low | 420000 | 491000 | 485000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 252000 | 42000 | 0 | 0 | 420000 | 1266.3815 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 3 | 5 | 2 | 3 | 2 | 2 | 2 | 4 | 2 | 55.56% | 6 | 1 | 5 | 1 | 3 | 4 | 3 | 56.67% | 6 |  | 2588
584 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Winnipeg | 2026-12-31 | 2026 | 140 | 10 | 2026-08-13 | med | low | low | low | high | 500000 | 496475 | 495002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 500000 | 13.0596 | CAPITAL | No | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 1 | 2 | 2 | 3 | 5 | 2 | 5 | 3 | 1 | 53.33% | 6 | 2 | 3 | 1 | 5 | 5 | 4 | 66.67% | 7 |  | 18394.3
585 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2028-12-31 | 2029 | 85 | 2 | 2028-10-07 | med | med | high | high | low | 300000 | 351489 | 352567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 300000 | 256.8876 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  | X | X | Yes | Yes | no | Yes | Yes | no | no | no | no | 1 | 2 | 3 | 3 | 1 | 1 | 4 | 1 | 3 | 42.22% | 5 | 4 | 5 | 5 | 3 | 4 | 3 | 80% | 8 |  | 23717.2367
586 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Quebec City | 2026-07-31 | 2026 | 158 | 4 | 2026-02-23 | high | med | low | low | low | 2262383 | 2018438 | 2390176 | 678714.9 | 1357429.8 | 226238.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2262383 | 110.1232 | CAPITAL | Yes | Unit outage |  | X | X | X |  | no | no | no | no | no | Yes | no | Yes | no | 2 | 3 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 42.22% | 5 | 4 | 3 | 1 | 2 | 5 | 5 | 66.67% | 7 |  | 289
587 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2026-07-31 | 2026 | 200 | 4 | 2026-01-12 | low | high | high | med | low | 500000 | 514135 | 576815 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 91.6522 | CAPITAL | Yes | PIpeline segment | X |  |  | X |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 4 | 1 | 2 | 3 | 3 | 2 | 3 | 2 | 4 | 53.33% | 6 | 3 | 4 | 1 | 4 | 4 | 3 | 63.33% | 7 |  | 278.7236
588 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2026-03-31 | 2026 | 150 | 10 | 2025-11-01 | high | low | med | med | low | 550000 | 875950 | 888752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 59.654 | CAPITAL | No | Pipeline segment |  | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 5 | 1 | 3 | 3 | 2 | 1 | 4 | 3 | 3 | 55.56% | 6 | 4 | 1 | 1 | 2 | 2 | 5 | 50% | 5 |  | 6487.582
589 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2027-03-31 | 2027 | 85 | 4 | 2027-01-05 | high | high | med | high | med | 1500000 | 1812742 | 1842116 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 34.0888 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 5 | 1 | 2 | 5 | 4 | 1 | 2 | 2 | 4 | 57.78% | 6 | 5 | 4 | 1 | 1 | 4 | 4 | 63.33% | 7 |  | 5845
590 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2028-03-31 | 2028 | 70 | 8 | 2028-01-21 | low | med | med | high | high | 2850000 | 2954019 | 2922819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855000 | 1710000 | 285000 | 0 | 2850000 | 148.0887 | CAPITAL | Yes | Unit outage |  | X | X | X | X | Yes | Yes | no | Yes | Yes | Yes | no | no | no | 5 | 3 | 3 | 5 | 2 | 4 | 2 | 5 | 4 | 73.33% | 8 | 1 | 4 | 1 | 4 | 4 | 2 | 53.33% | 6 |  | 158885
591 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2027-12-31 | 2027 | 150 | 8 | 2027-08-03 | high | high | low | high | high | 500000 | 1505538 | 1480254 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 1000000 | 98.783 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 4 | 2 | 1 | 2 | 2 | 5 | 5 | 2 | 2 | 55.56% | 6 | 2 | 3 | 1 | 3 | 1 | 4 | 46.67% | 5 |  | 278.7236
592 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Calgary | 2028-10-31 | 2028 | 180 | 5 | 2028-05-04 | low | low | low | med | low | 550000 | 544446 | 575417 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 145.3755 | CAPITAL | No | Pipeline segment |  |  | X | X | X | Yes | no | Yes | Yes | Yes | no | Yes | Yes | Yes | 1 | 4 | 1 | 2 | 2 | 2 | 5 | 1 | 2 | 44.44% | 5 | 5 | 4 | 1 | 5 | 3 | 3 | 70% | 7 |  | 3981.0002
593 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2028-07-31 | 2028 | 343 | 4 | 2027-08-23 | low | high | low | med | high | 1500000 | 1853330 | 1827797 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 200.4576 | EXPENSE | No | Derate/low flow Pipe segment | [5 empty] | no | no | no | no | Yes | Yes | no | no | Yes | 5 | 3 | 2 | 3 | 1 | 5 | 4 | 1 | 3 | 60% | 6 | 3 | 3 | 1 | 3 | 1 | 5 | 53.33% | 6 |  | 4052.0846
594 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Edmonton | 2027-07-31 | 2027 | 266 | 8 | 2026-11-07 | high | med | high | high | high | 1638449 | 1676663 | 1652332 | 0 | 491534.7 | 983069.4 | 163844.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1638449 | 39.814 | CAPITAL | Yes | Unit outage | [5 empty] | no | no | Yes | no | no | no | no | Yes | Yes | 5 | 5 | 1 | 1 | 1 | 1 | 2 | 2 | 5 | 51.11% | 6 | 4 | 4 | 1 | 5 | 3 | 5 | 73.33% | 8 |  | 898
595 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2026-03-31 | 2026 | 100 | 8 | 2025-12-21 | med | high | high | high | med | 350000 | 438059 | 432793 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 279.986 | CAPITAL | No | Pipeline segment |  | X | X |  |  | no | Yes | no | Yes | Yes | no | Yes | no | no | 3 | 3 | 2 | 5 | 2 | 4 | 1 | 5 | 5 | 66.67% | 7 | 3 | 1 | 1 | 5 | 5 | 3 | 60% | 6 |  | 203.1281
596 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Calgary | 2027-12-31 | 2027 | 180 | 8 | 2027-07-04 | high | low | med | high | high | 500000 | 458949 | 459364 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 44.4078 | CAPITAL | Yes | pipeline segment | X | X |  |  | X | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 4 | 4 | 3 | 1 | 4 | 4 | 1 | 2 | 3 | 57.78% | 6 | 3 | 1 | 1 | 1 | 5 | 2 | 43.33% | 5 |  | 20815.3255
597 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2027-10-31 | 2027 | 150 | 2 | 2027-06-03 | high | low | med | high | high | 450000 | 442587 | 452847 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 450000 | 172.7549 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 3 | 3 | 3 | 5 | 2 | 1 | 4 | 4 | 64.44% | 7 | 4 | 3 | 1 | 2 | 5 | 3 | 60% | 6 |  | 6993.5456
598 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Regina | 2027-03-31 | 2027 | 150 | 4 | 2026-11-01 | high | med | low | high | low | 1587641 | 1549493 | 1648557 | 0 | 476292.3 | 952584.6 | 158764.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1587641 | 78.6423 | CAPITAL | Yes | Unit outage |  |  |  |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | no | 4 | 3 | 1 | 4 | 5 | 4 | 2 | 4 | 2 | 64.44% | 7 | 5 | 3 | 1 | 5 | 1 | 1 | 53.33% | 6 |  | 636.4681
599 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Edmonton | 2027-03-31 | 2027 | 100 | 10 | 2026-12-21 | high | low | high | med | med | 400000 | 410639 | 410032 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 400000 | 4.3752 | CAPITAL | No | Pipeline segment | X | X | X |  | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 5 | 4 | 2 | 1 | 1 | 1 | 1 | 5 | 3 | 51.11% | 6 | 1 | 2 | 1 | 3 | 4 | 5 | 53.33% | 6 |  | 23717.2367
600 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2028-03-31 | 2028 | 150 | 8 | 2027-11-02 | low | high | med | low | med | 550000 | 1496322 | 1504238 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 104.2124 | CAPITAL | No | Pipeline segment | X | X | X |  | X | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 2 | 3 | 2 | 2 | 3 | 5 | 2 | 5 | 62.22% | 7 | 5 | 1 | 1 | 3 | 4 | 3 | 56.67% | 6 |  | 853.1382
601 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2026-12-31 | 2026 | 150 | 4 | 2026-08-03 | high | high | med | med | med | 1500000 | 1517309 | 1527293 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 1500000 | 56.1178 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  |  | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | no | 4 | 5 | 3 | 3 | 4 | 1 | 3 | 1 | 1 | 55.56% | 6 | 1 | 5 | 5 | 1 | 3 | 4 | 63.33% | 7 |  | 5000
602 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | North Bay | 2026-07-31 | 2026 | 175 | 8 | 2026-02-06 | low | high | low | high | high | 350000 | 307934 | 302673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 350000 | 32.9463 | CAPITAL | No | pipeline segment outage | X | X |  |  |  | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 5 | 1 | 1 | 5 | 2 | 2 | 2 | 3 | 4 | 55.56% | 6 | 1 | 5 | 1 | 5 | 2 | 2 | 53.33% | 6 |  | 25393.3666
603 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2028-07-31 | 2028 | 180 | 10 | 2028-02-02 | med | med | low | high | low | 400000 | 451173 | 453222 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 400000 | 22.175 | EXPENSE | Yes | Pipeline segment | X | X | X |  |  | Yes | no | no | no | Yes | no | no | Yes | no | 3 | 2 | 2 | 4 | 1 | 1 | 5 | 4 | 5 | 60% | 6 | 3 | 4 | 1 | 4 | 1 | 2 | 50% | 5 |  | 16021.8416
604 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Edmonton | 2026-12-31 | 2026 | 200 | 15 | 2026-06-14 | med | low | low | low | low | 500000 | 495184 | 495568 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 500000 | 15.392 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | no | no | Yes | 5 | 5 | 3 | 4 | 1 | 3 | 1 | 2 | 2 | 57.78% | 6 | 4 | 5 | 1 | 2 | 3 | 3 | 60% | 6 |  | 643.2391
605 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2027-12-31 | 2027 | 100 | 4 | 2027-09-22 | high | low | high | med | high | 1500000 | 1450980 | 1458652 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 118.0594 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 2 | 4 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 44.44% | 5 | 5 | 5 | 1 | 2 | 3 | 4 | 66.67% | 7 |  | 1022.4116
606 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2027-12-31 | 2027 | 91 | 4 | 2027-10-01 | high | low | high | high | high | 1321805 | 1359803 | 1610853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396541.5 | 793083 | 132180.5 | 1321805 | 121.8677 | CAPITAL | Yes | Unit outage |  |  |  |  | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 1 | 1 | 1 | 3 | 1 | 4 | 3 | 1 | 2 | 37.78% | 4 | 4 | 5 | 1 | 2 | 1 | 4 | 56.67% | 6 |  | 3138.8656
607 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2027-03-31 | 2027 | 200 | 2 | 2026-09-12 | med | med | high | med | low | 500000 | 608924 | 630832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 500000 | 93.0837 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | Yes | Yes | no | no | 5 | 3 | 2 | 2 | 3 | 1 | 5 | 5 | 2 | 62.22% | 7 | 3 | 1 | 1 | 1 | 4 | 3 | 43.33% | 5 |  | 121.8769
608 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2026-07-31 | 2026 | 150 | 8 | 2026-03-03 | med | med | med | low | low | 500000 | 544088 | 549248 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 152.364 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | no | Yes | no | Yes | Yes | no | Yes | Yes | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 31.11% | 4 | 5 | 5 | 1 | 1 | 4 | 4 | 66.67% | 7 |  | 7024.2246
609 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2025-12-31 | 2025 | 85 | 4 | 2025-10-07 | high | high | med | med | med | 850000 | 850944 | 820000 | 0 | 0 | 0 | 0 | 0 | 255000 | 510000 | 85000 | 0 | 0 | 0 | 0 | 850000 | 24.4354 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X |  | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 2 | 4 | 75.56% | 8 | 4 | 2 | 5 | 1 | 1 | 1 | 46.67% | 5 |  | 4785
610 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Winnipeg | 2027-12-31 | 2027 | 249 | 4 | 2027-04-26 | high | high | high | low | high | 1191808 | 1997991 | 1907322 | 0 | 0 | 0 | 0 | 0 | 357542.4 | 715084.8 | 119180.8 | 0 | 0 | 0 | 0 | 1191808 | 134.8642 | CAPITAL | Yes | Unit outage | X | X |  |  |  | no | Yes | Yes | Yes | no | no | no | Yes | no | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 35.56% | 4 | 1 | 1 | 5 | 5 | 4 | 5 | 70% | 7 |  | 211.3988
611 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2026-12-31 | 2026 | 192 | 4 | 2026-06-22 | low | high | low | low | low | 350000 | 539330 | 577636 | 0 | 0 | 105000 | 210000 | 35000 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 700000 | 415.9262 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | no | no | no | Yes | Yes | Yes | no | Yes | 5 | 5 | 2 | 2 | 5 | 4 | 4 | 1 | 3 | 68.89% | 7 | 2 | 2 | 1 | 4 | 2 | 5 | 53.33% | 6 |  | 643.2391
612 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2027-12-31 | 2027 | 150 | 8 | 2027-08-03 | low | med | med | med | low | 500000 | 990834 | 987555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 500000 | 177.3607 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | Yes | no | no | Yes | no | Yes | no | no | 5 | 1 | 4 | 1 | 3 | 5 | 4 | 5 | 3 | 68.89% | 7 | 4 | 3 | 1 | 2 | 3 | 3 | 53.33% | 6 |  | 1591.1704
613 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2029-10-31 | 2029 | 202 | 4 | 2029-04-12 | high | med | high | med | high | 300000 | 496541 | 474310 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 86.2445 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | Yes | no | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 33.33% | 4 | 4 | 4 | 1 | 2 | 5 | 1 | 56.67% | 6 |  | 1117.2047
614 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Toronto | 2026-03-31 | 2026 | 180 | 15 | 2025-10-02 | low | high | med | high | high | 450000 | 530563 | 545236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 450000 | 60.5912 | CAPITAL | No | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 1 | 2 | 3 | 1 | 3 | 5 | 3 | 1 | 2 | 46.67% | 5 | 1 | 2 | 1 | 1 | 3 | 2 | 33.33% | 4 |  | 477.3811
615 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2026-10-31 | 2026 | 196 | 10 | 2026-04-18 | high | low | low | med | med | 350000 | 370016 | 378399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 96.1798 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | no | no | no | Yes | Yes | 4 | 5 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 86.67% | 9 | 1 | 1 | 1 | 1 | 1 | 5 | 33.33% | 4 |  | 13582.277
616 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2028-12-31 | 2028 | 180 | 4 | 2028-07-04 | low | high | med | med | high | 550000 | 526296 | 558571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 550000 | 163.365 | CAPITAL | No | Pipeline segment |  | X | X | X | X | no | no | Yes | no | no | no | Yes | no | no | 1 | 4 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 33.33% | 4 | 2 | 2 | 1 | 1 | 1 | 3 | 33.33% | 4 |  | 4858.8867
617 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2026-07-31 | 2026 | 100 | 2 | 2026-04-22 | med | med | low | med | med | 350000 | 387958 | 348402 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 338.5852 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 4 | 37.78% | 4 | 2 | 5 | 1 | 4 | 4 | 5 | 70% | 7 |  | 18394.3019
618 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Regina | 2027-10-31 | 2027 | 160 | 4 | 2027-05-24 | low | med | low | med | high | 3912887 | 3258934 | 3758983 | 0 | 0 | 0 | 0 | 0 | 1173866.1 | 2347732.2 | 391288.7 | 0 | 0 | 0 | 0 | 3912887 | 3.9677 | CAPITAL | Yes | Unit outage | X | X | X | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 5 | 3 | 4 | 4 | 3 | 5 | 4 | 5 | 2 | 77.78% | 8 | 5 | 3 | 1 | 3 | 2 | 5 | 63.33% | 7 |  | 2310.5725
619 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2029-12-31 | 2029 | 156 | 10 | 2029-07-28 | med | med | low | med | high | 400000 | 477837 | 478567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 68.0307 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 5 | 4 | 3 | 1 | 5 | 1 | 3 | 4 | 4 | 66.67% | 7 | 2 | 1 | 1 | 5 | 4 | 5 | 60% | 6 |  | 4858.8867
620 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Montreal | 2026-12-31 | 2026 | 200 | 10 | 2026-06-14 | high | low | med | high | high | 550000 | 549928 | 591050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 550000 | 59.9299 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | Yes | Yes | no | no | no | Yes | no | Yes | 1 | 2 | 2 | 1 | 1 | 2 | 4 | 2 | 1 | 35.56% | 4 | 4 | 1 | 1 | 2 | 1 | 2 | 36.67% | 4 |  | 222.8052
621 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Quebec City | 2029-12-31 | 2029 | 120 | 4 | 2029-09-02 | low | med | high | high | med | 1500000 | 1411959 | 1411361 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 1500000 | 122.5762 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 4 | 2 | 2 | 2 | 2 | 4 | 2 | 5 | 2 | 55.56% | 6 | 5 | 3 | 1 | 2 | 2 | 3 | 53.33% | 6 |  | 16059.7772
622 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Ottawa | 2026-03-31 | 2026 | 180 | 4 | 2025-10-02 | med | med | high | low | low | 4100000 | 4162797 | 4274098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230000 | 2050000 | 820000 | 0 | 4100000 | 63.7402 | CAPITAL | Yes | Unit outage | X | X |  | X | X | Yes | Yes | Yes | Yes | no | Yes | no | Yes | Yes | 3 | 1 | 2 | 2 | 2 | 4 | 2 | 5 | 2 | 51.11% | 6 | 1 | 5 | 1 | 4 | 3 | 5 | 63.33% | 7 |  | 16593.6851
623 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2027-12-31 | 2027 | 244 | 4 | 2027-05-01 | high | low | low | high | high | 400000 | 545632 | 516927 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 93.8623 | EXPENSE | No | Pipeline segment |  | X |  | X | X | no | no | no | no | Yes | no | Yes | no | no | 3 | 4 | 2 | 3 | 1 | 1 | 2 | 5 | 2 | 51.11% | 6 | 5 | 4 | 1 | 5 | 5 | 3 | 76.67% | 8 |  | 4522
624 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Ottawa | 2027-03-31 | 2027 | 200 | 10 | 2026-09-12 | med | high | med | high | high | 500000 | 987000 | 954825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 24.4952 | CAPITAL | No | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 1 | 4 | 2 | 1 | 2 | 2 | 4 | 2 | 3 | 46.67% | 5 | 3 | 5 | 5 | 2 | 5 | 3 | 76.67% | 8 |  | 840.2082
625 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Saskatoon | 2030-07-31 | 2030 | 120 | 2 | 2030-04-02 | low | med | low | low | med | 520000 | 520076 | 521552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156000 | 312000 | 52000 | 0 | 520000 | 339.8771 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 2 | 3 | 1 | 1 | 4 | 2 | 2 | 3 | 2 | 44.44% | 5 | 5 | 5 | 1 | 1 | 2 | 2 | 53.33% | 6 |  | 2491.953
626 | L2 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Quebec City | 2029-12-31 | 2029 | 200 | 4 | 2029-06-14 | high | low | med | med | low | 2555385 | 2536764 | 2531509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766615.5 | 1533231 | 255538.5 | 0 | 2555385 | 32.4619 | CAPITAL | Yes | Unit outage |  |  |  |  | X | no | Yes | no | Yes | Yes | no | no | no | no | 5 | 2 | 2 | 4 | 2 | 5 | 4 | 4 | 4 | 71.11% | 8 | 3 | 5 | 1 | 1 | 1 | 1 | 40% | 4 |  | 5521.3731
627 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2029-12-31 | 2029 | 291 | 10 | 2029-03-15 | low | high | low | med | low | 400000 | 669911 | 715057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 54.5821 | EXPENSE | No | Pipeline segment | X |  |  |  | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 4 | 2 | 2 | 3 | 3 | 5 | 2 | 5 | 1 | 60% | 6 | 2 | 3 | 5 | 5 | 2 | 5 | 73.33% | 8 |  | 13420.41
628 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Quebec City | 2027-12-31 | 2027 | 200 | 15 | 2027-06-14 | low | med | low | low | high | 550000 | 554230 | 580197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 550000 | 6.3304 | CAPITAL | No | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | no | no | no | 2 | 1 | 3 | 1 | 2 | 2 | 4 | 2 | 2 | 42.22% | 5 | 4 | 4 | 1 | 1 | 1 | 3 | 46.67% | 5 |  | 191.3942
629 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2027-07-31 | 2027 | 150 | 4 | 2027-03-03 | med | low | low | low | med | 1750000 | 1800359 | 1858385 | 0 | 525000 | 1050000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 201.382 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | Yes | no | no | no | no | no | Yes | no | no | 4 | 3 | 1 | 3 | 4 | 1 | 4 | 2 | 3 | 55.56% | 6 | 5 | 5 | 1 | 3 | 3 | 5 | 73.33% | 8 |  | 2480.6254
630 | L1 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Toronto | 2028-10-31 | 2028 | 150 | 4 | 2028-06-03 | low | low | low | high | med | 2316843 | 2149065 | 2251331 | 0 | 0 | 0 | 0 | 695052.9 | 1390105.8 | 231684.3 | 0 | 0 | 0 | 0 | 0 | 2316843 | 11.492 | CAPITAL | Yes | Unit outage | X | X | X | X |  | no | no | no | Yes | no | no | Yes | no | Yes | 1 | 3 | 2 | 2 | 4 | 5 | 2 | 1 | 4 | 53.33% | 6 | 2 | 5 | 1 | 4 | 1 | 3 | 53.33% | 6 |  | 19639.8665
631 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2030-12-31 | 2030 | 85 | 10 | 2030-10-07 | med | high | high | low | med | 400000 | 344031 | 340632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 122.8607 | CAPITAL | No | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | no | Yes | no | Yes | Yes | 3 | 2 | 1 | 3 | 3 | 3 | 3 | 5 | 4 | 60% | 6 | 4 | 3 | 1 | 5 | 5 | 5 | 76.67% | 8 |  | 1727.265
632 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | WINNIPEG | 2026-07-31 | 2026 | 120 | 15 | 2026-04-02 | med | med | high | med | low | 450000 | 416535 | 407647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 90.3714 | CAPITAL | No | Pipeline segment | X | X | X |  |  | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 3 | 5 | 2 | 4 | 3 | 5 | 4 | 2 | 3 | 68.89% | 7 | 1 | 2 | 1 | 5 | 3 | 1 | 43.33% | 5 |  | 41798.5165
633 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2030-12-31 | 2030 | 250 | 7 | 2030-04-25 | low | med | med | high | high | 1500000 | 1307852 | 1350870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 750000 | 300000 | 0 | 1500000 | 152.9836 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 1 | 1 | 3 | 1 | 1 | 5 | 2 | 2 | 42.22% | 5 | 5 | 1 | 1 | 5 | 5 | 1 | 60% | 6 |  | 25777
634 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Montreal | 2026-03-31 | 2026 | 130 | 8 | 2025-11-21 | med | high | high | med | med | 3559855 | 3658888 | 3370070 | 0 | 0 | 0 | 0 | 1067956.5 | 2135913 | 355985.5 | 0 | 0 | 0 | 0 | 0 | 3559855 | 87.8332 | CAPITAL | Yes | Unit outage | X |  |  |  | X | no | no | Yes | no | no | Yes | no | no | no | 5 | 5 | 4 | 3 | 1 | 3 | 4 | 4 | 1 | 66.67% | 7 | 3 | 2 | 1 | 2 | 5 | 3 | 53.33% | 6 |  | 746.1723
635 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2026-12-31 | 2026 | 85 | 10 | 2026-10-07 | med | med | low | high | med | 350000 | 439702 | 481874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 350000 | 109.8564 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | no | no | no | no | no | no | no | Yes | Yes | 1 | 5 | 1 | 3 | 3 | 5 | 2 | 1 | 1 | 48.89% | 5 | 2 | 5 | 1 | 3 | 1 | 1 | 43.33% | 5 |  | 1578
636 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2027-12-31 | 2027 | 160 | 10 | 2027-07-24 | med | med | high | med | low | 500000 | 758562 | 785895 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 101.141 | CAPITAL | No | Pipeline segment |  | X |  | X |  | no | Yes | no | no | Yes | Yes | Yes | no | no | 3 | 3 | 3 | 3 | 5 | 1 | 5 | 5 | 4 | 71.11% | 8 | 4 | 2 | 1 | 2 | 5 | 3 | 56.67% | 6 |  | 13659.1884
637 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2027-10-31 | 2027 | 85 | 4 | 2027-08-07 | high | low | high | low | high | 1750000 | 1875896 | 1478514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 1050000 | 175000 | 0 | 0 | 1750000 | 24.8857 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  |  | no | Yes | no | Yes | no | no | no | no | Yes | 5 | 5 | 4 | 3 | 5 | 1 | 5 | 5 | 1 | 75.56% | 8 | 3 | 5 | 1 | 3 | 5 | 3 | 66.67% | 7 |  | 203.1281
638 | L3 | FACILITY | MAJOR EQUIP |  | GG MAJOR OH | Saskatoon | 2027-10-31 | 2027 | 150 | 4 | 2027-06-03 | med | med | high | med | high | 2348327 | 2332370 | 2833738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704498.1 | 1408996.2 | 234832.7 | 0 | 0 | 2348327 | 47.6878 | CAPITAL | Yes | Unit outage | X |  | X | X | X | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 2 | 3 | 3 | 3 | 4 | 1 | 4 | 1 | 53.33% | 6 | 1 | 5 | 5 | 2 | 2 | 5 | 66.67% | 7 |  | 41798.52
639 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2026-12-31 | 2026 | 150 | 10 | 2026-08-03 | high | low | high | low | high | 350000 | 661009 | 682588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 111.3269 | EXPENSE | Yes | Pipeline segment | X |  | X | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 3 | 2 | 3 | 2 | 5 | 5 | 2 | 5 | 5 | 71.11% | 8 | 5 | 2 | 1 | 5 | 3 | 2 | 60% | 6 |  | 3506.871
640 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | North Bay | 2026-03-31 | 2026 | 200 | 4 | 2025-09-12 | high | low | low | low | low | 450000 | 878955 | 905888 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 80.7138 | CAPITAL | No | pipeline segment outage | X | X |  | X |  | no | Yes | no | Yes | no | Yes | no | Yes | no | 2 | 1 | 3 | 1 | 1 | 1 | 5 | 3 | 1 | 40% | 4 | 2 | 2 | 1 | 5 | 1 | 2 | 43.33% | 5 |  | 21537.8368
641 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | North Bay | 2026-12-31 | 2026 | 160 | 2 | 2026-07-24 | high | high | low | med | low | 275000 | 258668 | 258420 | 0 | 0 | 0 | 0 | 82500 | 165000 | 27500 | 0 | 0 | 0 | 0 | 0 | 275000 | 898.364 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | Yes | no | no | no | Yes | Yes | Yes | Yes | no | 5 | 5 | 3 | 4 | 3 | 3 | 2 | 5 | 1 | 68.89% | 7 | 1 | 2 | 1 | 1 | 5 | 2 | 40% | 4 |  | 7007.9205
642 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2026-12-31 | 2026 | 150 | 10 | 2026-08-03 | high | high | high | low | low | 350000 | 323179 | 320094 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 59.7386 | CAPITAL | No | Pipeline segment |  | X |  | X | X | Yes | no | no | no | no | no | no | no | Yes | 3 | 2 | 1 | 5 | 5 | 3 | 3 | 2 | 3 | 60% | 6 | 2 | 2 | 1 | 4 | 3 | 3 | 50% | 5 |  | 18109.72
643 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Montreal | 2026-10-31 | 2026 | 180 | 8 | 2026-05-04 | med | med | med | low | low | 500000 | 501069 | 508000 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 20.7067 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | no | no | no | no | Yes | Yes | Yes | 3 | 3 | 3 | 3 | 4 | 1 | 5 | 5 | 5 | 71.11% | 8 | 5 | 2 | 1 | 2 | 2 | 3 | 50% | 5 |  | 2166.5828
644 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Winnipeg | 2029-12-31 | 2029 | 150 | 4 | 2029-08-03 | low | med | high | med | med | 2500000 | 2758655 | 2869566 | 0 | 0 | 750000 | 1500000 | 250000 | 0 | 0 | 0 | 0 | 750000 | 1500000 | 250000 | 5000000 | 383.6846 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | no | no | Yes | Yes | Yes | no | 4 | 5 | 4 | 3 | 2 | 1 | 1 | 3 | 1 | 53.33% | 6 | 5 | 5 | 1 | 1 | 1 | 3 | 53.33% | 6 |  | 778.6578
645 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2028-07-31 | 2028 | 170 | 10 | 2028-02-12 | low | med | low | low | high | 500000 | 590681 | 590005 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 24.542 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | Yes | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 26.67% | 3 | 1 | 5 | 1 | 1 | 1 | 5 | 46.67% | 5 |  | 20815.33
646 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Toronto | 2026-03-31 | 2026 | 250 | 15 | 2025-07-24 | high | med | med | low | low | 450000 | 1236197 | 1274450 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 450000 | 65.7764 | CAPITAL | No | Pipeline segment | X | X | X |  | X | Yes | Yes | no | no | no | no | Yes | Yes | Yes | 5 | 4 | 1 | 3 | 3 | 3 | 1 | 5 | 1 | 57.78% | 6 | 3 | 4 | 1 | 1 | 3 | 3 | 50% | 5 |  | 1846.6194
647 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2027-12-31 | 2027 | 150 | 4 | 2027-08-03 | med | high | high | med | low | 1800000 | 1909884 | 1937687 | 0 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 97.7988 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | no | no | Yes | no | no | no | no | no | Yes | 5 | 4 | 2 | 5 | 1 | 3 | 3 | 4 | 2 | 64.44% | 7 | 1 | 3 | 1 | 2 | 2 | 3 | 40% | 4 |  | 643.2391
648 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2025-12-31 | 2025 | 120 | 8 | 2025-09-02 | high | low | low | high | low | 400000 | 801992 | 806981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 279.7384 | EXPENSE | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 2 | 4 | 2 | 1 | 4 | 4 | 3 | 1 | 5 | 57.78% | 6 | 5 | 4 | 1 | 1 | 5 | 2 | 60% | 6 |  | 2789
649 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Winnipeg | 2027-03-31 | 2027 | 185 | 15 | 2026-09-27 | med | low | low | high | med | 500000 | 513676 | 518168 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 500000 | 511.7996 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 2 | 5 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 46.67% | 5 | 4 | 3 | 1 | 2 | 1 | 3 | 46.67% | 5 |  | 842.9817
650 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2028-07-31 | 2028 | 200 | 4 | 2028-01-13 | high | high | med | high | low | 1750000 | 1770877 | 1780700 | 0 | 0 | 0 | 525000 | 1050000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 91.2089 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | no | 3 | 2 | 1 | 5 | 1 | 3 | 1 | 3 | 4 | 51.11% | 6 | 5 | 3 | 1 | 3 | 4 | 1 | 56.67% | 6 |  | 1090.538
651 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2027-10-31 | 2027 | 150 | 8 | 2027-06-03 | med | low | high | high | med | 500000 | 550475 | 595557 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 500000 | 117.2576 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 4 | 5 | 2 | 4 | 4 | 3 | 5 | 3 | 3 | 73.33% | 8 | 5 | 3 | 1 | 4 | 2 | 5 | 66.67% | 7 |  | 5666
652 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | North Bay | 2028-03-31 | 2028 | 200 | 10 | 2027-09-13 | high | med | high | high | low | 550000 | 689835 | 687417 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 412.8922 | CAPITAL | No | pipeline segment outage | X |  |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 5 | 3 | 4 | 3 | 1 | 5 | 1 | 5 | 5 | 71.11% | 8 | 5 | 3 | 1 | 1 | 2 | 2 | 46.67% | 5 |  | 2588
653 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2026-12-31 | 2026 | 85 | 2 | 2026-10-07 | high | high | high | low | high | 300000 | 378545 | 398478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 300000 | 311.1133 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X | X | X | no | no | no | Yes | Yes | no | no | Yes | no | 3 | 5 | 3 | 3 | 3 | 4 | 2 | 1 | 5 | 64.44% | 7 | 3 | 1 | 1 | 5 | 4 | 1 | 50% | 5 |  | 241.5599
654 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2026-10-31 | 2026 | 122 | 10 | 2026-07-01 | med | low | med | low | low | 350000 | 540105 | 540380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 350000 | 81.2986 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | no | no | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 35.56% | 4 | 1 | 2 | 1 | 5 | 2 | 4 | 50% | 5 |  | 2789
655 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2026-10-31 | 2026 | 150 | 15 | 2026-06-03 | high | high | med | high | high | 450000 | 868046 | 874514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 82.8772 | CAPITAL | No | Pipeline segment |  | X |  | X | X | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 1 | 5 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 40% | 4 | 2 | 3 | 1 | 1 | 1 | 4 | 40% | 4 |  | 23717.2367
656 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Regina | 2028-03-31 | 2028 | 150 | 2 | 2027-11-02 | high | low | low | low | med | 350000 | 378827 | 442990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 350000 | 523.2809 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | no | 5 | 4 | 2 | 2 | 2 | 2 | 5 | 2 | 1 | 55.56% | 6 | 2 | 2 | 5 | 3 | 1 | 1 | 46.67% | 5 |  | 172.2548
657 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2029-12-31 | 2029 | 250 | 10 | 2029-04-25 | med | high | high | high | high | 500000 | 724601 | 723464 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 500000 | 98.531 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | no | no | no | Yes | 1 | 3 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 42.22% | 5 | 5 | 2 | 1 | 2 | 4 | 2 | 53.33% | 6 |  | 2588
658 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2028-07-31 | 2028 | 120 | 8 | 2028-04-02 | low | med | high | high | high | 550000 | 553200 | 542753 | 0 | 0 | 0 | 55000 | 440000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 123.3918 | CAPITAL | No | Pipeline segment |  | X |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 1 | 1 | 2 | 1 | 4 | 3 | 2 | 3 | 1 | 40% | 4 | 1 | 1 | 1 | 1 | 1 | 3 | 26.67% | 3 |  | 6062.603
659 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2026-12-31 | 2026 | 120 | 10 | 2026-09-02 | low | high | med | med | low | 350000 | 352474 | 355000 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 37.7222 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | Yes | 2 | 2 | 1 | 1 | 4 | 1 | 3 | 2 | 1 | 37.78% | 4 | 4 | 2 | 1 | 3 | 1 | 1 | 40% | 4 |  | 8792
660 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2029-07-31 | 2029 | 250 | 4 | 2028-11-23 | med | low | high | low | high | 400000 | 350785 | 393433 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 109.3207 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 3 | 2 | 1 | 1 | 3 | 5 | 2 | 1 | 4 | 48.89% | 5 | 1 | 2 | 1 | 3 | 5 | 2 | 46.67% | 5 |  | 746.1723
661 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | WINNIPEG | 2029-12-31 | 2029 | 100 | 8 | 2029-09-22 | high | high | high | low | med | 400000 | 422998 | 420888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 74.8121 | CAPITAL | No | Pipeline segment | X | X |  | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 4 | 2 | 3 | 4 | 3 | 5 | 4 | 4 | 71.11% | 8 | 5 | 4 | 1 | 1 | 2 | 3 | 53.33% | 6 |  | 13677.18
662 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2030-03-31 | 2030 | 100 | 8 | 2029-12-21 | high | med | med | med | high | 400000 | 381473 | 383108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 142.0502 | CAPITAL | No | Pipeline segment | X | X | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 1 | 4 | 2 | 5 | 4 | 5 | 2 | 2 | 66.67% | 7 | 3 | 3 | 1 | 4 | 4 | 1 | 53.33% | 6 |  | 7007.921
663 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | med | med | low | med | low | 350000 | 362424 | 362097 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 350000 | 82.7364 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 4 | 42.22% | 5 | 4 | 4 | 1 | 1 | 3 | 5 | 60% | 6 |  | 1685.963
664 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Winnipeg | 2029-03-31 | 2029 | 90 | 8 | 2028-12-31 | high | low | low | med | low | 400000 | 474413 | 474247 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 400000 | 13.6895 | CAPITAL | No | Pipeline segment | X | X |  | X | X | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 4 | 3 | 1 | 3 | 2 | 5 | 1 | 5 | 2 | 57.78% | 6 | 5 | 5 | 1 | 4 | 2 | 1 | 60% | 6 |  | 6832.492
665 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2027-03-31 | 2027 | 80 | 4 | 2027-01-10 | med | low | high | low | med | 400000 | 487955 | 487622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 81.7758 | EXPENSE | No | Pipeline segment | X | X | X |  |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 5 | 5 | 3 | 4 | 5 | 2 | 5 | 2 | 1 | 71.11% | 8 | 5 | 5 | 1 | 4 | 3 | 1 | 63.33% | 7 |  | 25885
666 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Winnipeg | 2026-12-31 | 2026 | 100 | 10 | 2026-09-22 | high | high | high | high | med | 400000 | 443423 | 420247 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 167.1303 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 5 | 40% | 4 | 1 | 5 | 1 | 5 | 5 | 4 | 70% | 7 |  | 4391.637
667 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2025-12-31 | 2025 | 100 | 8 | 2025-09-22 | high | med | low | high | low | 400000 | 827809 | 927128 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 245.1045 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | no | no | 2 | 3 | 1 | 2 | 3 | 5 | 2 | 2 | 3 | 51.11% | 6 | 1 | 3 | 1 | 2 | 5 | 4 | 53.33% | 6 |  | 2178.073
668 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2026-03-31 | 2029 | 150 | 10 | 2025-11-01 | low | med | med | high | med | 350000 | 474581 | 482853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 166.8084 | CAPITAL | Yes | Pipeline segment |  | X |  | X |  | no | no | no | Yes | Yes | Yes | no | no | no | 2 | 5 | 2 | 2 | 1 | 1 | 2 | 3 | 5 | 51.11% | 6 | 1 | 4 | 5 | 1 | 3 | 1 | 50% | 5 |  | 2610.39
669 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2026-03-31 | 2026 | 150 | 8 | 2025-11-01 | high | low | high | low | high | 400000 | 555442 | 543668 | 0 | 0 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 71.2228 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | no | Yes | Yes | Yes | no | 5 | 2 | 4 | 1 | 3 | 2 | 3 | 3 | 1 | 53.33% | 6 | 3 | 2 | 1 | 2 | 1 | 1 | 33.33% | 4 |  | 5000
670 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2026-07-31 | 2026 | 150 | 8 | 2026-03-03 | med | high | low | low | low | 350000 | 380645 | 388809 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 117.9206 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | no | 5 | 3 | 1 | 2 | 1 | 1 | 5 | 4 | 2 | 53.33% | 6 | 2 | 4 | 1 | 2 | 3 | 5 | 56.67% | 6 |  | 158885
671 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2029-12-31 | 2029 | 142 | 10 | 2029-08-11 | med | low | med | low | med | 500000 | 509915 | 513929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 72.3249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | no | no | no | no | Yes | no | no | 1 | 3 | 3 | 2 | 1 | 2 | 5 | 1 | 1 | 42.22% | 5 | 5 | 3 | 1 | 3 | 4 | 1 | 56.67% | 6 |  | 1785
672 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2026-12-31 | 2026 | 85 | 5 | 2026-10-07 | low | med | high | high | low | 350000 | 320570 | 415873 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 700000 | 375.5287 | EXPENSE | No | Pipeline segment |  |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | Yes | 1 | 3 | 2 | 1 | 4 | 5 | 2 | 3 | 3 | 53.33% | 6 | 4 | 1 | 1 | 5 | 5 | 3 | 63.33% | 7 |  | 900.2043
673 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2028-07-31 | 2028 | 150 | 10 | 2028-03-03 | high | med | high | low | med | 400000 | 709452 | 706903 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 34.9002 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 1 | 4 | 1 | 1 | 5 | 2 | 2 | 2 | 3 | 46.67% | 5 | 2 | 3 | 1 | 2 | 5 | 4 | 56.67% | 6 |  | 749.7244
674 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2026-10-31 | 2026 | 85 | 4 | 2026-08-07 | med | high | med | low | med | 400000 | 454302 | 487376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 71.1665 | EXPENSE | No | Pipeline segment |  | X |  |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | 3 | 3 | 4 | 2 | 2 | 3 | 1 | 2 | 2 | 48.89% | 5 | 3 | 3 | 1 | 5 | 5 | 4 | 70% | 7 |  | 32.5005
675 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Winnipeg | 2026-10-31 | 2026 | 85 | 8 | 2026-08-07 | med | low | med | med | high | 400000 | 485478 | 480917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 28.2991 | EXPENSE | No | Pipeline segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 2 | 2 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 35.56% | 4 | 3 | 4 | 1 | 4 | 2 | 4 | 60% | 6 |  | 7718.869
676 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2025-12-31 | 2025 | 125 | 10 | 2025-08-28 | med | high | high | high | low | 500000 | 351865 | 354621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 500000 | 86.0466 | CAPITAL | Yes | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 1 | 3 | 1 | 1 | 4 | 3 | 2 | 1 | 1 | 37.78% | 4 | 1 | 5 | 1 | 4 | 4 | 5 | 66.67% | 7 |  | 2369.828
677 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2026-07-31 | 2026 | 180 | 10 | 2026-02-01 | low | med | low | med | low | 500000 | 985848 | 988631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 71.0178 | EXPENSE | Yes | Pipeline segment |  |  |  | X |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 28.89% | 3 | 4 | 5 | 1 | 5 | 3 | 5 | 76.67% | 8 |  | 2369.828
678 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2028-12-31 | 2028 | 120 | 15 | 2028-09-02 | low | high | high | low | high | 400000 | 623417 | 635508 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 400000 | 204.7502 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 5 | 44.44% | 5 | 3 | 4 | 1 | 2 | 4 | 2 | 53.33% | 6 |  | 14928.99
679 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2029-12-31 | 2029 | 120 | 5 | 2029-09-02 | high | high | med | med | med | 420000 | 384800 | 395163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 210000 | 84000 | 0 | 0 | 420000 | 193.3484 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | no | Yes | Yes | no | no | Yes | Yes | Yes | 1 | 4 | 3 | 2 | 4 | 3 | 5 | 1 | 1 | 53.33% | 6 | 2 | 2 | 1 | 2 | 2 | 5 | 46.67% | 5 |  | 4785
680 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2028-07-31 | 2028 | 120 | 10 | 2028-04-02 | med | med | low | high | high | 400000 | 499341 | 496308 | 0 | 0 | 0 | 40000 | 160000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 44.7596 | CAPITAL | No | Pipeline segment | X | X |  | X | X | no | no | Yes | Yes | Yes | Yes | no | Yes | no | 1 | 4 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 35.56% | 4 | 2 | 1 | 1 | 1 | 1 | 2 | 26.67% | 3 |  | 4542.743
681 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2028-07-31 | 2028 | 120 | 8 | 2028-04-02 | med | med | low | low | low | 400000 | 423560 | 460010 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 400000 | 86.1551 | EXPENSE | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | Yes | Yes | Yes | no | no | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 2 | 35.56% | 4 | 1 | 1 | 1 | 1 | 5 | 2 | 36.67% | 4 |  | 2679.519
682 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2027-12-31 | 2027 | 200 | 8 | 2027-06-14 | high | high | med | high | high | 500000 | 725080 | 725529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 0 | 500000 | 32.563 | EXPENSE | No | Pipeline segment |  |  | X | X | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 5 | 44.44% | 5 | 2 | 5 | 1 | 1 | 3 | 2 | 46.67% | 5 |  | 263.7275
683 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2028-12-31 | 2028 | 200 | 8 | 2028-06-14 | low | med | low | high | med | 500000 | 478617 | 519000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 500000 | 3.8339 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 5 | 2 | 2 | 3 | 5 | 3 | 1 | 2 | 53.33% | 6 | 4 | 3 | 1 | 3 | 4 | 1 | 53.33% | 6 |  | 76225.68
684 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2027-12-31 | 2027 | 200 | 8 | 2027-06-14 | med | high | low | med | high | 520000 | 986111 | 1100500 | 0 | 0 | 0 | 0 | 0 | 0 | 156000 | 312000 | 52000 | 0 | 0 | 0 | 520000 | 89.8531 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 5 | 5 | 2 | 1 | 5 | 2 | 5 | 5 | 3 | 73.33% | 8 | 3 | 3 | 1 | 5 | 1 | 5 | 60% | 6 |  | 16.9273
685 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Winnipeg | 2027-10-31 | 2027 | 200 | 8 | 2027-04-14 | med | high | high | high | high | 400000 | 371481 | 367796 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 400000 | 137.4312 | CAPITAL | No | Pipeline segment |  |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 4 | 1 | 3 | 1 | 3 | 3 | 4 | 5 | 5 | 64.44% | 7 | 4 | 2 | 1 | 4 | 2 | 2 | 50% | 5 |  | 10535.75
686 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2029-07-31 | 2029 | 120 | 8 | 2029-04-02 | med | high | high | med | low | 400000 | 636064 | 696142 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 188.6819 | EXPENSE | Yes | Pipeline segment |  | X |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 5 | 5 | 1 | 1 | 1 | 4 | 5 | 1 | 3 | 57.78% | 6 | 1 | 2 | 5 | 5 | 3 | 2 | 60% | 6 |  | 31873.29
687 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2026-12-31 | 2026 | 120 | 5 | 2026-09-02 | high | med | med | high | med | 400000 | 393878 | 395581 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 318.2127 | EXPENSE | No | Pipeline segment | X |  |  | X | X | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 4 | 4 | 2 | 4 | 5 | 5 | 3 | 1 | 1 | 64.44% | 7 | 5 | 4 | 1 | 1 | 1 | 3 | 50% | 5 |  | 19639.87
688 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2028-10-31 | 2028 | 85 | 8 | 2028-08-07 | low | low | high | med | med | 400000 | 617515 | 618701 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 129.2729 | EXPENSE | No | Pipeline segment | X | X |  | X |  | no | Yes | Yes | Yes | no | no | no | Yes | no | 1 | 1 | 3 | 3 | 4 | 1 | 4 | 1 | 1 | 42.22% | 5 | 4 | 1 | 1 | 1 | 5 | 4 | 53.33% | 6 |  | 1184.914
689 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2027-07-31 | 2027 | 150 | 10 | 2027-03-03 | low | low | low | low | low | 500000 | 677573 | 672660 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 500000 | 11.9354 | EXPENSE | No | Pipeline segment |  |  | X |  |  | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 3 | 1 | 1 | 1 | 4 | 2 | 1 | 2 | 3 | 40% | 4 | 5 | 5 | 5 | 4 | 4 | 3 | 86.67% | 9 |  | 842.9817
690 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2027-07-31 | 2027 | 139 | 8 | 2027-03-14 | med | med | med | med | low | 400000 | 425230 | 434107 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 383.2311 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | no | Yes | no | Yes | no | no | Yes | no | 3 | 3 | 2 | 4 | 4 | 3 | 4 | 2 | 2 | 60% | 6 | 5 | 3 | 1 | 2 | 5 | 1 | 56.67% | 6 |  | 1727.2647
691 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Winnipeg | 2028-03-31 | 2028 | 85 | 8 | 2028-01-06 | high | high | high | low | high | 400000 | 493729 | 468570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 162.7571 | EXPENSE | No | Pipeline segment | X | X |  |  | X | no | Yes | Yes | Yes | no | no | Yes | no | Yes | 5 | 3 | 2 | 4 | 2 | 5 | 5 | 3 | 3 | 71.11% | 8 | 4 | 1 | 5 | 5 | 4 | 1 | 66.67% | 7 |  | 3506.8708
692 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Edmonton | 2026-07-31 | 2026 | 85 | 8 | 2026-05-07 | med | med | med | high | med | 350000 | 356367 | 314154 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 56.2148 | CAPITAL | Yes | Pipeline segment |  | X | X |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 2 | 4 | 2 | 3 | 5 | 2 | 4 | 1 | 4 | 60% | 6 | 2 | 4 | 1 | 2 | 4 | 5 | 60% | 6 |  | 203.1281
693 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2026-12-31 | 2026 | 100 | 8 | 2026-09-22 | high | low | med | med | high | 400000 | 567316 | 563023 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 42.7227 | CAPITAL | No | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 1 | 4 | 5 | 4 | 2 | 4 | 2 | 5 | 66.67% | 7 | 2 | 2 | 1 | 2 | 1 | 4 | 40% | 4 |  | 1174.9707
694 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2027-03-31 | 2027 | 100 | 10 | 2026-12-21 | low | med | low | low | low | 400000 | 380028 | 388094 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 90.2519 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | no | 2 | 2 | 1 | 1 | 2 | 2 | 4 | 2 | 2 | 40% | 4 | 1 | 4 | 1 | 2 | 1 | 4 | 43.33% | 5 |  | 13677.1818
695 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2027-12-31 | 2027 | 100 | 10 | 2027-09-22 | low | high | med | low | low | 400000 | 424238 | 427119 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 61.5753 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 4 | 44.44% | 5 | 4 | 4 | 1 | 2 | 2 | 4 | 56.67% | 6 |  | 16021.8416
696 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2028-03-31 | 2028 | 100 | 10 | 2027-12-22 | low | low | high | high | low | 400000 | 400160 | 405476 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 7.1499 | CAPITAL | No | Pipeline segment | X |  |  | X |  | no | no | Yes | no | no | no | Yes | no | Yes | 1 | 3 | 1 | 1 | 4 | 1 | 4 | 3 | 3 | 46.67% | 5 | 3 | 3 | 1 | 3 | 1 | 3 | 46.67% | 5 |  | 1685.9635
697 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2025-12-31 | 2025 | 100 | 10 | 2025-09-22 | low | med | low | med | med | 350000 | 400542 | 406801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 350000 | 120.5022 | CAPITAL | Yes | Pipeline segment | X | X | X |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 2 | 4 | 1 | 2 | 3 | 5 | 1 | 2 | 2 | 48.89% | 5 | 5 | 4 | 5 | 3 | 4 | 4 | 83.33% | 9 |  | 267.7598
698 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2029-12-31 | 2029 | 200 | 8 | 2029-06-14 | high | low | high | med | med | 500000 | 598707 | 598210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 152.9866 | EXPENSE | No | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | Yes | no | no | no | no | 5 | 1 | 1 | 2 | 5 | 3 | 1 | 5 | 2 | 55.56% | 6 | 4 | 3 | 1 | 3 | 1 | 1 | 43.33% | 5 |  | 330
699 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2028-12-31 | 2028 | 180 | 4 | 2028-07-04 | high | low | high | high | low | 400000 | 587205 | 589911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 242.1342 | CAPITAL | No | Pipeline segment |  |  |  | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 3 | 1 | 4 | 2 | 2 | 4 | 2 | 2 | 51.11% | 6 | 3 | 3 | 1 | 2 | 1 | 1 | 36.67% | 4 |  | 4391.6369
700 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2026-10-31 | 2026 | 160 | 4 | 2026-05-24 | med | high | low | med | low | 400000 | 408000 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 218.7171 | EXPENSE | Yes | pipeline segment |  |  | X | X | X | no | no | no | no | no | Yes | Yes | Yes | no | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 35.56% | 4 | 1 | 1 | 1 | 5 | 3 | 5 | 53.33% | 6 |  | 4314.1949
701 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2026-12-31 | 2026 | 160 | 8 | 2026-07-24 | high | high | med | high | high | 500000 | 481652 | 445736 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 41.1751 | EXPENSE | No | Pipeline segment |  | X | X |  |  | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 2 | 2 | 2 | 2 | 5 | 3 | 4 | 1 | 1 | 48.89% | 5 | 3 | 1 | 1 | 5 | 1 | 4 | 50% | 5 |  | 2178.0735
702 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2029-12-31 | 2029 | 200 | 8 | 2029-06-14 | low | med | med | med | low | 520000 | 523241 | 529365 | 0 | 156000 | 312000 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 5.9556 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | no | 5 | 4 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | 53.33% | 6 | 1 | 5 | 1 | 1 | 4 | 2 | 46.67% | 5 |  | 1090.5382
703 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2027-03-31 | 2027 | 150 | 4 | 2026-11-01 | med | med | low | high | med | 500000 | 583881 | 573876 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 11.6418 | EXPENSE | No | Pipeline segment |  | X |  | X | X | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 5 | 4 | 2 | 2 | 1 | 2 | 3 | 3 | 5 | 60% | 6 | 4 | 2 | 1 | 4 | 1 | 5 | 56.67% | 6 |  | 1207.7993
704 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Edmonton | 2029-07-31 | 2029 | 150 | 10 | 2029-03-03 | med | med | low | med | low | 400000 | 422034 | 425419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 101.2735 | EXPENSE | Yes | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 33.33% | 4 | 2 | 2 | 5 | 2 | 4 | 5 | 66.67% | 7 |  | 900.2043
705 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2026-03-31 | 2026 | 170 | 8 | 2025-10-12 | high | low | high | med | high | 420000 | 488222 | 478271 | 0 | 126000 | 252000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 202.8834 | CAPITAL | Yes | Pipeline segment |  | X |  | X | X | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 1 | 2 | 5 | 3 | 1 | 3 | 3 | 5 | 57.78% | 6 | 1 | 1 | 1 | 4 | 3 | 3 | 43.33% | 5 |  | 749.7244
706 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | North Bay | 2028-03-31 | 2028 | 150 | 8 | 2027-11-02 | med | med | med | low | high | 400000 | 892844 | 905260 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 190.1713 | CAPITAL | No | Pipeline segment |  |  |  | X | X | Yes | no | no | no | no | Yes | no | no | no | 1 | 2 | 3 | 1 | 3 | 3 | 4 | 2 | 1 | 44.44% | 5 | 1 | 4 | 1 | 3 | 2 | 2 | 43.33% | 5 |  | 7718.869
707 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2026-07-31 | 2026 | 150 | 8 | 2026-03-03 | med | high | low | low | high | 420000 | 405834 | 402505 | 126000 | 252000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 98.3964 | EXPENSE | No | pipeline segment outage |  |  |  |  | X | no | Yes | Yes | Yes | no | no | no | Yes | no | 2 | 3 | 2 | 2 | 5 | 3 | 1 | 2 | 4 | 53.33% | 6 | 2 | 4 | 1 | 4 | 5 | 1 | 56.67% | 6 |  | 6993.5456
708 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Winnipeg | 2027-03-31 | 2027 | 120 | 8 | 2026-12-01 | high | low | high | med | med | 400000 | 469283 | 472670 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 400000 | 143.1483 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 2 | 4 | 3 | 1 | 1 | 4 | 3 | 2 | 2 | 48.89% | 5 | 5 | 3 | 1 | 5 | 5 | 1 | 66.67% | 7 |  | 1072.7658
709 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2029-10-31 | 2029 | 120 | 8 | 2029-07-03 | low | high | high | low | low | 420000 | 480344 | 486953 | 0 | 126000 | 252000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 122.9237 | CAPITAL | No | Pipeline segment |  |  | X |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 1 | 1 | 1 | 2 | 5 | 3 | 3 | 3 | 46.67% | 5 | 2 | 5 | 1 | 2 | 3 | 1 | 46.67% | 5 |  | 76225.6763
710 | L3 | PIPE INTEGRITY | Excavation | DENT | RECOAT | Winnipeg | 2028-03-31 | 2028 | 135 | 5 | 2027-11-17 | low | low | low | low | high | 400000 | 424886 | 436808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 9.937 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | Yes | no | no | Yes | Yes | Yes | Yes | no | 4 | 2 | 3 | 3 | 2 | 1 | 4 | 5 | 5 | 64.44% | 7 | 4 | 1 | 1 | 3 | 3 | 2 | 46.67% | 5 |  | 16.9273
711 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2029-03-31 | 2029 | 100 | 10 | 2028-12-21 | low | low | med | low | med | 400000 | 340748 | 84971 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 800000 | 7.9241 | CAPITAL | No | Pipeline segment |  | X | X |  | X | no | no | no | Yes | no | no | no | Yes | no | 3 | 4 | 3 | 2 | 4 | 4 | 1 | 5 | 5 | 68.89% | 7 | 5 | 3 | 1 | 4 | 4 | 1 | 60% | 6 |  | 560.1412
712 | L2 | PIPE INTEGRITY | Excavation | CORROSION | RECOAT | Montreal | 2027-03-31 | 2026 | 200 | 5 | 2026-09-12 | high | med | low | high | med | 500000 | 580071 | 863077 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 339.2298 | CAPITAL | No | pipeline segment outage |  | X | X |  |  | no | Yes | no | Yes | no | Yes | no | no | no | 2 | 4 | 2 | 1 | 5 | 3 | 5 | 1 | 4 | 60% | 6 | 2 | 5 | 1 | 1 | 4 | 1 | 46.67% | 5 |  | 6039.0018
713 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2030-03-31 | 2030 | 150 | 8 | 2029-11-01 | low | low | high | low | med | 400000 | 1157635 | 1189920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 105.7103 | CAPITAL | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 4 | 2 | 2 | 3 | 3 | 1 | 3 | 2 | 2 | 48.89% | 5 | 3 | 5 | 1 | 5 | 2 | 4 | 66.67% | 7 |  | 17906.9371
714 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2026-12-31 | 2026 | 120 | 4 | 2026-09-02 | high | high | high | high | high | 350000 | 304631 | 304242 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 350000 | 26.1799 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | Yes | no | no | no | Yes | no | Yes | Yes | 2 | 4 | 2 | 2 | 5 | 2 | 2 | 1 | 4 | 53.33% | 6 | 3 | 4 | 1 | 5 | 2 | 1 | 53.33% | 6 |  | 5776.4313
715 | L1 | PIPE INTEGRITY | Excavation | SCC | RECOAT | Ottawa | 2028-07-31 | 2028 | 120 | 2 | 2028-04-02 | low | high | low | high | low | 400000 | 674072 | 656987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 133.3009 | EXPENSE | No | Station outage | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | Yes | no | Yes | 3 | 2 | 4 | 3 | 3 | 5 | 1 | 3 | 4 | 62.22% | 7 | 2 | 5 | 1 | 1 | 2 | 5 | 53.33% | 6 |  | 1083.35
716 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2030-10-31 | 2030 | 150 | 10 | 2030-06-03 | low | low | med | med | med | 500000 | 491921 | 499436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 500000 | 47.5442 | EXPENSE | No | Pipeline segment | X |  |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 4 | 3 | 2 | 5 | 1 | 5 | 5 | 4 | 1 | 66.67% | 7 | 4 | 4 | 1 | 3 | 4 | 2 | 60% | 6 |  | 842.9817
717 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2027-12-31 | 2027 | 150 | 10 | 2027-08-03 | low | high | low | med | low | 400000 | 555683 | 550953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 55.3744 | CAPITAL | No | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | Yes | no | Yes | no | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 40% | 4 | 1 | 2 | 5 | 2 | 5 | 3 | 60% | 6 |  | 1727.2647
718 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2026-07-31 | 2026 | 150 | 4 | 2026-03-03 | low | med | low | high | med | 350000 | 406595 | 482491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 350000 | 284.7276 | CAPITAL | No | Pipeline segment | X | X |  | X | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 2 | 1 | 1 | 1 | 4 | 4 | 3 | 2 | 4 | 48.89% | 5 | 2 | 4 | 1 | 2 | 2 | 5 | 53.33% | 6 |  | 18109.7232
719 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2026-07-31 | 2026 | 150 | 12 | 2026-03-03 | high | med | low | high | high | 350000 | 479453 | 498408 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 700000 | 58.7845 | CAPITAL | No | Pipeline segment |  |  | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 4 | 2 | 3 | 2 | 5 | 5 | 4 | 3 | 5 | 73.33% | 8 | 2 | 5 | 1 | 4 | 5 | 4 | 70% | 7 |  | 20815.3255
720 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2026-12-31 | 2026 | 200 | 10 | 2026-06-14 | low | low | low | high | high | 500000 | 852395 | 896748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 500000 | 22.5065 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | no | no | no | Yes | no | no | no | Yes | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 3 | 35.56% | 4 | 3 | 2 | 1 | 5 | 4 | 3 | 60% | 6 |  | 48955
721 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2027-07-31 | 2027 | 150 | 10 | 2027-03-03 | high | med | med | high | med | 400000 | 398965 | 399197 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 71.4985 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 1 | 5 | 1 | 2 | 2 | 3 | 3 | 2 | 4 | 51.11% | 6 | 4 | 3 | 1 | 4 | 1 | 1 | 46.67% | 5 |  | 278.7236
722 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2028-12-31 | 2028 | 85 | 10 | 2028-10-07 | high | low | med | med | high | 400000 | 805802 | 391083 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 400000 | 36.3611 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | no | Yes | no | no | Yes | no | no | Yes | no | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 31.11% | 4 | 4 | 2 | 5 | 4 | 5 | 3 | 76.67% | 8 |  | 278.7236
723 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2028-07-31 | 2028 | 165 | 1 | 2028-02-17 | low | low | low | high | low | 350000 | 374582 | 376971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 350000 | 593.4244 | EXPENSE | No | Pipeline segment | X | X | X |  | X | no | no | Yes | no | no | no | Yes | Yes | Yes | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 26.67% | 3 | 5 | 4 | 1 | 4 | 4 | 1 | 63.33% | 7 |  | 203.1281
724 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2027-12-31 | 2027 | 272 | 10 | 2027-04-03 | med | med | med | low | med | 400000 | 644214 | 640670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 101.6158 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 5 | 5 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 48.89% | 5 | 4 | 3 | 5 | 1 | 2 | 3 | 60% | 6 |  | 203.1281
725 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2026-10-31 | 2026 | 185 | 8 | 2026-04-29 | high | med | low | low | low | 350000 | 379854 | 376546 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 350000 | 25.9626 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 5 | 2 | 1 | 1 | 4 | 3 | 4 | 3 | 2 | 55.56% | 6 | 3 | 2 | 1 | 5 | 1 | 1 | 43.33% | 5 |  | 13677.1818
726 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2027-12-31 | 2027 | 85 | 8 | 2027-10-07 | med | med | low | med | med | 400000 | 380000 | 358470 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 183.6307 | EXPENSE | Yes | Pipeline segment |  |  | X |  |  | no | no | Yes | Yes | no | Yes | no | Yes | no | 5 | 5 | 1 | 2 | 1 | 1 | 4 | 1 | 5 | 55.56% | 6 | 2 | 5 | 1 | 4 | 4 | 3 | 63.33% | 7 |  | 16021.8416
727 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | WINNIPEG | 2028-12-31 | 2028 | 100 | 10 | 2028-09-22 | low | med | high | med | low | 400000 | 388560 | 387036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 31.5417 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 1 | 4 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 40% | 4 | 3 | 3 | 1 | 5 | 5 | 1 | 60% | 6 |  | 7007.9205
728 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2028-03-31 | 2028 | 150 | 10 | 2027-11-02 | med | low | low | high | high | 500000 | 564753 | 562254 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 91.2063 | CAPITAL | No | Pipeline segment |  |  | X |  |  | no | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 5 | 4 | 1 | 4 | 1 | 2 | 5 | 5 | 66.67% | 7 | 4 | 2 | 1 | 1 | 1 | 5 | 46.67% | 5 |  | 7024.225
729 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2028-10-31 | 2028 | 120 | 5 | 2028-07-03 | med | high | high | high | high | 420000 | 434790 | 444911 | 0 | 0 | 0 | 0 | 126000 | 252000 | 42000 | 0 | 0 | 0 | 0 | 0 | 420000 | 114.2737 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 2 | 5 | 1 | 3 | 2 | 2 | 3 | 3 | 2 | 51.11% | 6 | 3 | 4 | 5 | 1 | 5 | 3 | 70% | 7 |  | 5845
730 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2029-12-31 | 2029 | 120 | 5 | 2029-09-02 | med | high | high | low | high | 400000 | 408461 | 404334 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 400000 | 125.3264 | EXPENSE | No | Pipeline segment | X |  | X |  | X | no | Yes | no | Yes | no | Yes | no | Yes | no | 3 | 1 | 2 | 1 | 5 | 3 | 2 | 1 | 5 | 51.11% | 6 | 1 | 1 | 1 | 4 | 2 | 5 | 46.67% | 5 |  | 4391.637
731 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2029-07-31 | 2029 | 288 | 8 | 2028-10-16 | med | low | med | low | med | 400000 | 366358 | 369590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 32.0854 | CAPITAL | No | Pipeline segment |  |  | X | X |  | no | Yes | no | no | Yes | no | Yes | no | no | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 31.11% | 4 | 1 | 1 | 1 | 1 | 3 | 4 | 36.67% | 4 |  | 4052.085
732 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2027-07-31 | 2027 | 213 | 4 | 2026-12-30 | med | low | med | med | low | 400000 | 450000 | 495000 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 24.5147 | EXPENSE | No | Pipeline segment |  | X |  | X |  | no | no | no | no | no | no | Yes | Yes | no | 3 | 1 | 1 | 3 | 5 | 5 | 3 | 1 | 1 | 51.11% | 6 | 5 | 2 | 1 | 2 | 3 | 3 | 53.33% | 6 |  | 1207.799
733 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2027-12-31 | 2027 | 150 | 4 | 2027-08-03 | high | low | low | high | low | 400000 | 301807 | 325115 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 243.4001 | EXPENSE | No | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 5 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 33.33% | 4 | 1 | 1 | 1 | 1 | 3 | 3 | 33.33% | 4 |  | 1022.412
997 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2028-04-30 | 2028 | 200 | 4 | 2027-10-13 | med | high | low | low | low | 1800000 | 1864493 | 1802540 | 0 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 87.159 | EXPENSE | Yes | Derate/low flow Pipe segment | x | x | x | x | x | NR | x | x | x | x | x |  | No | Yes | 5 | 1 | 1 | 4 | 2 | 5 | 1 | 4 |  | 57.5% | 6 | 4 | 4 | 1 | 3 | 3 |  | 60% | 6 |  | 8429.71
998 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | Montreal | 2026-09-30 | 2026 | 120 | 2 | 2026-06-02 | med | high | high | med | high | 190000 | 175087 | 174680 | 0 | 0 | 0 | 19000 | 152000 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 40.7081 | EXPENSE | No | Derate/low flow Pipe segment |  |  | x | x | x | no | x | x | x | [5 empty] | 3 | 1 | 4 | 3 | 1 | 4 | 1 | 4 |  | 52.5% | 6 | 1 | 3 | 1 | 4 | 4 |  | 52% | 6 |  | 8756
999 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2030-09-30 | 2030 | 150 | 5 | 2030-05-03 | low | high | med | high | med | 400000 | 611769 | 669250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 85.7283 | EXPENSE | Yes | Pipeline segment | x | x | x | x | x | Yes | x | NR | NR | NR | NR | NR | No | Yes | 4 | 5 | 2 | 3 | 1 | 4 | 5 | 3 |  | 67.5% | 6 | 5 | 5 | 1 | 5 | 1 |  | 68% | 7 |  | 52
1000 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2026-12-31 | 2026 | 120 | 4 | 2026-09-02 | high | med | med | high | low | 650000 | 778878 | 779764 | 25184 | 100736 | 125920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251840 | 65.902 | EXPENSE | Yes | Derate/low flow Pipe segment | x | x | x | x | x | Yes | x | x | Yes | Yes | Yes |  | No | No | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 |  | 85% | 9 | 3 | 1 | 1 | 1 | 1 |  | 28% | 3 |  | 4526
1001 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Ottawa | 2030-12-31 | 2030 | 250 | 5 | 2030-04-25 | low | high | high | low | low | 300000 | 306500 | 310745 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 27.2404 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | Yes | Yes | 2 | 3 | 2 | 5 | 3 | 1 | 5 | 3 |  | 60% | 6 | 4 | 5 | 1 | 4 | 2 |  | 64% | 7 |  | 258
1002 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2029-11-30 | 2029 | 85 | 5 | 2029-09-06 | med | med | low | low | med | 400000 | 465754 | 469856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 159.1014 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | Yes | Yes | no | Yes | no | Yes | Yes | no | 4 | 5 | 3 | 4 | 5 | 3 | 4 | 4 |  | 80% | 8 | 2 | 5 | 1 | 2 | 1 |  | 44% | 5 |  | 842.9817
1003 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Calgary | 2029-09-30 | 2029 | 180 | 8 | 2029-04-03 | high | med | med | high | low | 450000 | 958642 | 975845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 450000 | 83.0189 | CAPITAL | No | Pipeline segment |  | X |  | X |  | Yes | Yes | no | Yes | Yes | no | no | Yes | Yes | 2 | 3 | 2 | 3 | 4 | 3 | 4 | 2 |  | 57.5% | 6 | 1 | 4 | 1 | 3 | 2 |  | 44% | 5 |  | 842.9817
1004 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2030-03-31 | 2030 | 200 | 5 | 2029-09-12 | high | med | high | low | low | 450000 | 505744 | 505000 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 450000 | 32.772 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | Yes | no | no | no | Yes | Yes | no | 1 | 5 | 3 | 2 | 1 | 1 | 1 | 1 |  | 37.5% | 4 | 3 | 4 | 1 | 1 | 3 |  | 48% | 5 |  | 13420.4072
1005 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Montreal | 2026-09-30 | 2026 | 200 | 5 | 2026-03-14 | low | low | med | med | med | 500000 | 534470 | 533637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 147.3292 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | no | Yes | no | no | Yes | 5 | 1 | 1 | 4 | 4 | 4 | 1 | 2 |  | 55% | 6 | 1 | 1 | 1 | 5 | 5 |  | 52% | 6 |  | 1727.2647
1006 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Toronto | 2028-04-30 | 2028 | 150 | 8 | 2027-12-02 | med | high | high | low | med | 300000 | 387000 | 435200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 300000 | 180.0007 | CAPITAL | Yes | Pipeline segment | X |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 37.5% | 4 | 2 | 4 | 1 | 5 | 2 |  | 56% | 6 |  | 1578
1007 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2029-11-30 | 2029 | 100 | 4 | 2029-08-22 | low | high | high | high | low | 2000000 | 2085890 | 2014691 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 488.9487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | no | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 1 |  | 35% | 4 | 1 | 4 | 1 | 1 | 3 |  | 40% | 4 |  | 3506.8708
1008 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2030-12-31 | 2030 | 180 | 4 | 2030-07-04 | low | low | low | low | low | 2100000 | 2520000 | 2454250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630000 | 1260000 | 210000 | 2100000 | 40.3349 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | no | no | no | no | no | Yes | no | 3 | 5 | 2 | 4 | 4 | 4 | 4 | 3 |  | 72.5% | 8 | 2 | 5 | 1 | 2 | 3 |  | 52% | 6 |  | 3981.0002
1009 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2026-05-31 | 2026 | 180 | 2 | 2025-12-02 | high | low | med | low | low | 650000 | 689531 | 725189 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 242.8512 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X | X | no | no | no | Yes | no | Yes | Yes | Yes | no | 2 | 2 | 1 | 3 | 1 | 4 | 2 | 2 |  | 42.5% | 5 | 3 | 1 | 1 | 2 | 2 |  | 36% | 4 |  | 20815.3255
1010 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2026-03-31 | 2026 | 150 | 4 | 2025-11-01 | med | high | high | high | high | 2000000 | 2473474 | 2450004 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 0 | 2000000 | 25.7224 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | no | Yes | no | no | no | Yes | Yes | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 5 |  | 70% | 6 | 2 | 5 | 5 | 1 | 2 |  | 60% | 6 |  | 278.7236
1011 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2029-08-31 | 2029 | 85 | 3 | 2029-06-07 | low | high | low | med | low | 400000 | 450563 | 409107 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 400000 | 135.4595 | EXPENSE | No | Pipeline segment |  | X |  |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 4 | 4 | 4 | 1 | 3 | 4 | 1 | 3 |  | 60% | 6 | 1 | 5 | 5 | 4 | 1 |  | 64% | 7 |  | 278.7236
1012 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2027-11-30 | 2027 | 150 | 3 | 2027-07-03 | low | high | low | med | high | 400000 | 450041 | 489250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 122.5032 | EXPENSE | Yes | Pipeline segment | X |  |  | X |  | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 3 | 2 | 4 | 4 | 3 | 5 | 5 |  | 70% | 6 | 5 | 4 | 5 | 4 | 4 |  | 88% | 9 |  | 203.1281
1013 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2028-12-31 | 2028 | 150 | 3 | 2028-08-03 | high | med | high | med | med | 500000 | 509283 | 509602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 250000 | 0 | 0 | 500000 | 148.1189 | EXPENSE | Yes | Pipeline segment | X |  | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 5 | 5 | 1 | 5 | 4 | 5 | 5 | 4 |  | 85% | 9 | 5 | 3 | 5 | 3 | 2 |  | 72% | 8 |  | 203.1281
1014 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Regina | 2025-09-30 | 2025 | 200 | 15 | 2025-03-14 | low | low | low | low | med | 450000 | 715279 | 728240 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 184.0435 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | Yes | no | no | no | no | no | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 2 |  | 35% | 4 | 4 | 5 | 1 | 2 | 3 |  | 60% | 6 |  | 853.1382
1015 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Saskatoon | 2027-03-31 | 2026 | 100 | 4 | 2026-12-21 | med | med | med | high | high | 450000 | 419931 | 446058 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 34.5922 | CAPITAL | No | derate/low flow Pipe segment | X | X |  |  | X | Yes | no | no | no | Yes | no | no | Yes | Yes | 3 | 1 | 2 | 4 | 3 | 2 | 4 | 2 |  | 52.5% | 6 | 4 | 5 | 1 | 1 | 5 |  | 64% | 7 |  | 23717.2367
1016 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Montreal | 2029-11-30 | 2029 | 250 | 8 | 2029-03-25 | high | high | low | low | high | 500000 | 520373 | 521000 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 1000000 | 16.0911 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 4 | 2 | 5 | 1 | 3 | 3 | 1 | 2 |  | 52.5% | 6 | 2 | 3 | 1 | 3 | 3 |  | 48% | 5 |  | 746.1723
1017 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2026-03-31 | 2026 | 250 | 5 | 2025-07-24 | low | high | high | low | low | 450000 | 515075 | 534568 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 23.9593 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | Yes | no | no | Yes | Yes | no | Yes | 3 | 3 | 2 | 1 | 4 | 3 | 5 | 1 |  | 55% | 6 | 1 | 2 | 1 | 2 | 3 |  | 36% | 4 |  | 13677.1818
1018 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Saskatoon | 2028-04-30 | 2028 | 120 | 15 | 2028-01-01 | high | low | high | med | med | 450000 | 529718 | 528784 | 0 | 0 | 0 | 45000 | 270000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 270.4653 | CAPITAL | No | Pipeline segment |  | X |  |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 2 |  | 45% | 5 | 1 | 4 | 1 | 4 | 3 |  | 52% | 6 |  | 16021.8416
1019 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2025-11-30 | 2025 | 85 | 7 | 2025-09-06 | low | med | low | high | low | 450000 | 542580 | 545780 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 104.3547 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 4 | 2 | 4 | 2 | 4 | 5 | 2 | 4 |  | 67.5% | 6 | 1 | 5 | 1 | 2 | 4 |  | 52% | 6 |  | 7007.9205
1020 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2030-12-31 | 2030 | 120 | 4 | 2030-09-02 | high | low | high | high | med | 650000 | 789531 | 768189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 650000 | 48.6768 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | no | Yes | no | Yes | Yes | Yes | Yes | no | 4 | 2 | 4 | 3 | 2 | 3 | 4 | 5 |  | 67.5% | 6 | 2 | 1 | 1 | 5 | 2 |  | 44% | 5 |  | 7007.9205
1021 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2029-04-30 | 2029 | 150 | 5 | 2028-12-01 | high | low | low | med | med | 400000 | 550000 | 559415 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 400000 | 194.4749 | EXPENSE | Yes | Pipeline segment |  |  |  | X | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 1 | 2 | 3 | 2 | 1 | 5 | 4 | 4 |  | 55% | 6 | 1 | 1 | 1 | 4 | 3 |  | 40% | 4 |  | 1685.9635
1022 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2028-12-31 | 2028 | 180 | 3 | 2028-07-04 | low | low | low | low | low | 650000 | 620531 | 625189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 650000 | 26.0956 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 1 | 5 | 5 | 5 | 4 | 2 | 3 |  | 67.5% | 6 | 2 | 1 | 1 | 1 | 3 |  | 32% | 4 |  | 1685.9635
1023 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Quebec City | 2029-04-30 | 2029 | 100 | 2 | 2029-01-20 | high | med | low | med | low | 75000 | 85254 | 95452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 45000 | 7500 | 0 | 0 | 75000 | 156.8587 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 1 | 1 | 5 | 5 | 2 | 1 | 2 | 4 |  | 52.5% | 6 | 1 | 1 | 1 | 1 | 2 |  | 24% | 3 |  | 778.6578
1024 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | North Bay | 2029-11-30 | 2029 | 200 | 4 | 2029-05-14 | med | high | high | med | high | 450000 | 852538 | 857775 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 450000 | 35.5286 | CAPITAL | No | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | Yes | Yes | Yes | Yes | no | 2 | 4 | 2 | 2 | 4 | 1 | 2 | 2 |  | 47.5% | 5 | 1 | 4 | 1 | 5 | 2 |  | 52% | 6 |  | 121.8769
1025 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Edmonton | 2026-03-31 | 2026 | 120 | 8 | 2025-12-01 | med | high | med | high | med | 450000 | 452014 | 454644 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 26.015 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | Yes | Yes | 1 | 4 | 2 | 4 | 2 | 1 | 4 | 2 |  | 50% | 5 | 3 | 5 | 5 | 3 | 5 |  | 84% | 9 |  | 267.7598
1026 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2027-11-30 | 2027 | 85 | 4 | 2027-09-06 | high | high | high | high | med | 400000 | 449044 | 455180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 18.1227 | CAPITAL | No | Pipeline segment | X | X |  |  |  | no | Yes | no | Yes | no | no | no | Yes | no | 1 | 5 | 1 | 4 | 5 | 3 | 3 | 1 |  | 57.5% | 6 | 2 | 1 | 5 | 3 | 1 |  | 48% | 5 |  | 267.7598
1027 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2025-09-30 | 2025 | 150 | 2 | 2025-05-03 | low | high | high | high | low | 350000 | 534618 | 575616 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 502.8679 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | no | Yes | no | no | no | no | Yes | no | no | 3 | 4 | 2 | 5 | 5 | 3 | 1 | 1 |  | 60% | 6 | 2 | 2 | 5 | 3 | 1 |  | 52% | 6 |  | 267.7598
1028 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANNUAL SURVEY | Calgary | 2027-04-30 | 2029 | 120 | 5 | 2026-12-31 | high | med | high | high | low | 780000 | 1376437 | 1313514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234000 | 468000 | 78000 | 0 | 0 | 780000 | 98.0993 | EXPENSE | Yes | NO outage | X | X | X | X | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 3 | 4 | 1 | 5 | 4 | 5 | 4 | 1 |  | 67.5% | 6 | 1 | 3 | 5 | 5 | 3 |  | 68% | 7 |  | 17599.3754
1029 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-REMEDITION | Winnipeg | 2028-09-30 | 2028 | 250 | 5 | 2028-01-24 | high | med | med | med | low | 850000 | 850026 | 8543747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 510000 | 85000 | 0 | 0 | 850000 | 76.5526 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 3 | 2 | 1 | 5 | 3 | 4 | 3 | 3 |  | 60% | 6 | 4 | 2 | 1 | 4 | 2 |  | 52% | 6 |  | 6832.4917
1030 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | North Bay | 2030-09-30 | 2030 | 150 | 5 | 2030-05-03 | med | low | high | low | low | 400000 | 495918 | 472825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 414.8802 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | Yes | 3 | 3 | 1 | 5 | 2 | 1 | 1 | 5 |  | 52.5% | 6 | 1 | 5 | 1 | 4 | 5 |  | 64% | 7 |  | 330
1031 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | North Bay | 2026-03-31 | 2026 | 150 | 4 | 2025-11-01 | low | low | med | high | low | 400000 | 491000 | 485000 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 1266.3815 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 2 | 4 | 1 | 2 | 1 | 3 | 4 | 1 |  | 45% | 5 | 4 | 2 | 1 | 2 | 4 |  | 52% | 6 |  | 5845
1032 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | Calgary | 2029-08-31 | 2029 | 100 | 4 | 2029-05-23 | med | high | high | low | high | 125000 | 110410 | 107380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 75000 | 12500 | 0 | 0 | 125000 | 565.0045 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | Yes | no | Yes | no | Yes | 1 | 4 | 2 | 5 | 4 | 5 | 1 | 3 |  | 62.5% | 6 | 1 | 1 | 1 | 2 | 4 |  | 36% | 4 |  | 3077.9635
1033 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | North Bay | 2026-03-31 | 2026 | 250 | 4 | 2025-07-24 | med | high | low | high | med | 1250000 | 1281952 | 1285422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 750000 | 125000 | 0 | 0 | 1250000 | 72.2212 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  | X | no | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 3 | 1 | 2 | 3 | 5 | 2 | 1 | 1 |  | 45% | 5 | 5 | 3 | 1 | 2 | 4 |  | 60% | 6 |  | 5097.2605
1034 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Ottawa | 2030-09-30 | 2030 | 250 | 15 | 2030-01-23 | low | high | low | low | low | 450000 | 986403 | 1000404 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 103.1048 | CAPITAL | No | Pipeline segment | X |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 5 | 5 | 1 | 3 | 5 | 5 | 5 | 4 |  | 82.5% | 9 | 4 | 5 | 5 | 2 | 2 |  | 72% | 8 |  | 13582.277
1035 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2028-04-30 | 2028 | 180 | 3 | 2027-11-02 | low | high | high | med | low | 500000 | 534135 | 576815 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 91.6522 | CAPITAL | Yes | PIpeline segment | X |  |  | X |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 5 | 1 | 2 | 4 | 3 | 1 | 5 | 5 |  | 65% | 6 | 3 | 4 | 5 | 5 | 2 |  | 76% | 8 |  | 4391.6369
1036 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Montreal | 2026-12-31 | 2026 | 180 | 4 | 2026-07-04 | high | high | low | high | high | 300000 | 505538 | 508025 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 0 | 0 | 300000 | 98.783 | EXPENSE | Yes | Pipeline segment | X |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 2 | 5 | 1 | 2 | 1 | 4 | 2 | 3 |  | 50% | 5 | 1 | 1 | 5 | 5 | 2 |  | 56% | 6 |  | 4314.1949
1037 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Ottawa | 2028-09-30 | 2028 | 180 | 8 | 2028-04-03 | med | high | high | high | med | 750000 | 838059 | 852793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 750000 | 279.986 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | Yes | no | Yes | Yes | no | Yes | no | no | 2 | 5 | 4 | 2 | 4 | 2 | 2 | 4 |  | 62.5% | 6 | 5 | 4 | 5 | 5 | 1 |  | 80% | 8 |  | 4858.8867
1038 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | WINNIPEG | 2027-04-30 | 2027 | 150 | 8 | 2026-12-01 | low | med | low | high | high | 450000 | 428864 | 428750 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 56.9979 | CAPITAL | Yes | Pipeline segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | no | no | no | 2 | 1 | 2 | 2 | 2 | 4 | 1 | 2 |  | 40% | 4 | 1 | 5 | 5 | 2 | 5 |  | 72% | 8 |  | 2178.0735
1039 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | WINNIPEG | 2029-04-30 | 2029 | 100 | 8 | 2029-01-20 | med | low | med | med | med | 450000 | 816716 | 810460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 30.4676 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | Yes | Yes | Yes | no | Yes | no | Yes | no | Yes | 5 | 5 | 1 | 3 | 3 | 5 | 5 | 3 |  | 75% | 8 | 1 | 4 | 1 | 4 | 3 |  | 52% | 6 |  | 1090.5382
1040 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2028-04-30 | 2028 | 52 | 8 | 2028-03-09 | high | low | high | med | med | 350000 | 310639 | 310032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 350000 | 4.3752 | CAPITAL | No | Pipeline segment | X | X | X |  | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 4 |  | 47.5% | 5 | 2 | 1 | 1 | 3 | 4 |  | 44% | 5 |  | 4052.0846
1041 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2027-04-30 | 2027 | 120 | 5 | 2026-12-31 | med | med | low | high | low | 350000 | 451173 | 453222 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 350000 | 22.175 | EXPENSE | Yes | Pipeline segment | X | X | X |  |  | Yes | no | no | no | Yes | no | no | Yes | no | 4 | 1 | 5 | 4 | 4 | 5 | 1 | 2 |  | 65% | 6 | 3 | 4 | 1 | 4 | 5 |  | 68% | 7 |  | 4995.3897
1042 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2027-04-30 | 2027 | 200 | 15 | 2026-10-12 | low | low | low | high | high | 450000 | 680678 | 686152 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 450000 | 22.4512 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | no | Yes | no | no | 3 | 5 | 4 | 2 | 2 | 1 | 5 | 5 |  | 67.5% | 6 | 5 | 3 | 1 | 2 | 5 |  | 64% | 7 |  | 646
1043 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2028-09-30 | 2028 | 200 | 4 | 2028-03-14 | med | med | high | med | low | 500000 | 608924 | 630832 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 500000 | 93.0837 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | Yes | Yes | no | no | 4 | 4 | 3 | 4 | 1 | 2 | 4 | 1 |  | 57.5% | 6 | 2 | 3 | 1 | 3 | 1 |  | 40% | 4 |  | 347
1044 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2027-04-30 | 2027 | 150 | 4 | 2026-12-01 | low | high | low | low | low | 350000 | 379330 | 377636 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 415.9262 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | no | no | no | Yes | Yes | Yes | no | Yes | 4 | 2 | 4 | 3 | 3 | 5 | 2 | 5 |  | 70% | 6 | 4 | 3 | 1 | 5 | 5 |  | 72% | 8 |  | 158885
1045 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2030-09-30 | 2030 | 180 | 5 | 2030-04-03 | med | low | high | med | low | 1800000 | 1855522 | 1845724 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 87.5976 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 5 | 5 | 2 | 3 | 1 | 3 | 4 |  | 65% | 6 | 3 | 5 | 1 | 2 | 2 |  | 52% | 6 |  | 1207.7993
1046 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2028-09-30 | 2028 | 120 | 5 | 2028-06-02 | high | high | high | high | med | 650000 | 788878 | 779764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 650000 | 27.6329 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 5 | 4 | 3 | 2 | 1 | 1 | 5 | 4 |  | 62.5% | 6 | 1 | 3 | 1 | 1 | 5 |  | 44% | 5 |  | 1785
1047 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2027-04-30 | 2027 | 150 | 5 | 2026-12-01 | low | high | high | high | med | 300000 | 295522 | 295724 | 0 | 90000 | 60000 | 0 | 0 | 0 | 0 | 120000 | 30000 | 0 | 0 | 0 | 300000 | 110.9054 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | no | no | Yes | no | no | Yes | Yes | Yes | 4 | 1 | 3 | 4 | 4 | 2 | 3 | 4 |  | 62.5% | 6 | 1 | 1 | 1 | 2 | 3 |  | 32% | 4 |  | 172.2548
1048 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2026-09-30 | 2026 | 117 | 5 | 2026-06-05 | low | high | med | med | low | 1250000 | 1350000 | 1450000 | 0 | 0 | 0 | 0 | 375000 | 625000 | 250000 | 0 | 0 | 0 | 0 | 0 | 1250000 | 96.934 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 2 | 3 | 5 | 1 | 3 | 1 | 2 | 5 |  | 55% | 6 | 2 | 1 | 1 | 5 | 4 |  | 52% | 6 |  | 172.2548
1049 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2027-08-31 | 2027 | 150 | 15 | 2027-04-03 | low | low | med | high | med | 450000 | 453975 | 454237 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 29.298 | CAPITAL | No | Pipeline segment | X |  |  | X | X | no | Yes | no | Yes | no | no | no | no | Yes | 1 | 4 | 2 | 2 | 2 | 2 | 3 | 5 |  | 52.5% | 6 | 2 | 3 | 1 | 4 | 4 |  | 56% | 6 |  | 191.3942
1050 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Quebec City | 2028-09-30 | 2028 | 100 | 7 | 2028-06-22 | high | med | low | high | low | 450000 | 1514932 | 1512774 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 900000 | 7.2499 | CAPITAL | No | pipeline segment | X | X | X |  | X | no | no | no | no | no | no | no | Yes | Yes | 5 | 4 | 2 | 1 | 5 | 2 | 1 | 1 |  | 52.5% | 6 | 2 | 1 | 1 | 4 | 4 |  | 48% | 5 |  | 173.2929
1051 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2029-08-31 | 2029 | 150 | 4 | 2029-04-03 | med | low | low | high | low | 750000 | 789882 | 779817 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 750000 | 4.1819 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | no | no | no | no | no | Yes | Yes | no | no | 2 | 1 | 5 | 4 | 2 | 3 | 4 | 5 |  | 65% | 6 | 2 | 1 | 1 | 1 | 3 |  | 32% | 4 |  | 749.7244
1052 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Edmonton | 2028-12-31 | 2028 | 150 | 7 | 2028-08-03 | low | med | low | high | med | 650000 | 698448 | 697296 | 0 | 195000 | 0 | 65000 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 28.5018 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | no | Yes | no | no | Yes | 1 | 1 | 3 | 5 | 5 | 2 | 2 | 4 |  | 57.5% | 6 | 1 | 2 | 1 | 1 | 1 |  | 24% | 3 |  | 32.5005
1053 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | North Bay | 2025-09-30 | 2025 | 180 | 7 | 2025-04-03 | high | low | low | med | med | 350000 | 370016 | 378399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 350000 | 96.1798 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | no | no | no | Yes | Yes | 5 | 2 | 2 | 2 | 3 | 1 | 3 | 1 |  | 47.5% | 5 | 2 | 3 | 1 | 5 | 4 |  | 60% | 6 |  | 1022.4116
1054 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Saskatoon | 2026-03-31 | 2026 | 150 | 8 | 2025-11-01 | high | low | med | med | high | 450000 | 480343 | 480758 | 0 | 0 | 0 | 0 | 135000 | 0 | 45000 | 270000 | 0 | 0 | 0 | 0 | 450000 | 89.4674 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 5 | 4 | 5 | 5 | 1 | 3 | 2 | 3 |  | 70% | 6 | 4 | 1 | 1 | 2 | 3 |  | 44% | 5 |  | 458
1055 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2027-08-31 | 2027 | 156 | 6 | 2027-03-28 | med | med | low | med | high | 350000 | 677837 | 682856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 68.0307 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 2 | 1 | 2 | 4 | 5 | 4 | 4 | 1 |  | 57.5% | 6 | 1 | 1 | 1 | 2 | 2 |  | 28% | 3 |  | 20000
1056 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2030-09-30 | 2030 | 200 | 8 | 2030-03-14 | med | med | low | med | high | 650000 | 686027 | 682144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 650000 | 108.8597 | CAPITAL | No | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | no | Yes | Yes | 1 | 4 | 5 | 4 | 2 | 4 | 3 | 3 |  | 65% | 6 | 1 | 1 | 1 | 3 | 1 |  | 28% | 3 |  | 2078
1057 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2026-03-31 | 2026 | 200 | 7 | 2025-09-12 | high | low | low | med | med | 1800000 | 1964493 | 1902540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 0 | 1800000 | 55.4393 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 5 | 4 | 4 | 2 | 1 | 2 | 4 | 4 |  | 65% | 6 | 5 | 1 | 1 | 1 | 4 |  | 48% | 5 |  | 1875
1058 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2030-09-30 | 2030 | 120 | 4 | 2030-06-02 | med | low | med | low | med | 450000 | 856958 | 888680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 64.1787 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 3 | 2 | 1 | 3 | 4 | 5 | 4 | 2 |  | 60% | 6 | 2 | 5 | 5 | 1 | 3 |  | 64% | 7 |  | 7718.869
1059 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2026-05-31 | 2026 | 120 | 4 | 2026-01-31 | high | low | low | high | high | 400000 | 445632 | 446927 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 93.8623 | EXPENSE | No | Pipeline segment |  | X |  | X | X | no | no | no | no | Yes | no | Yes | no | no | 1 | 2 | 2 | 5 | 2 | 4 | 4 | 5 |  | 62.5% | 6 | 4 | 5 | 5 | 3 | 1 |  | 72% | 8 |  | 25393.3666
1060 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2030-12-31 | 2030 | 150 | 4 | 2030-08-03 | low | med | med | high | high | 650000 | 666455 | 695432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 650000 | 12.1249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 4 | 2 | 1 | 2 | 3 | 5 | 4 | 4 |  | 62.5% | 6 | 5 | 3 | 1 | 5 | 4 |  | 72% | 8 |  | 3138.8656
1061 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2025-06-30 | 2025 | 150 | 4 | 2025-01-31 | low | low | med | high | high | 450000 | 743098 | 791931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 94.2513 | CAPITAL | Yes | Pipeline segment |  |  | X |  | X | Yes | no | no | Yes | Yes | Yes | Yes | Yes | no | 5 | 1 | 1 | 2 | 2 | 3 | 1 | 3 |  | 45% | 5 | 1 | 4 | 1 | 4 | 4 |  | 56% | 6 |  | 4487
1062 | L! | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Toronto | 2025-11-30 | 2025 | 180 | 8 | 2025-06-03 | med | high | high | med | high | 1000000 | 1821878 | 1824096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 600000 | 100000 | 1000000 | 99.9422 | EXPENSE | Yes | NO outage |  | X | X | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | Yes | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 |  | 30% | 3 | 1 | 3 | 1 | 4 | 2 |  | 44% | 5 |  | 211.3988
1063 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2028-12-31 | 2028 | 150 | 8 | 2028-08-03 | low | high | low | med | low | 350000 | 669911 | 695057 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 54.5821 | EXPENSE | No | Pipeline segment | X |  |  |  | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 5 | 5 | 1 | 5 | 1 | 5 | 1 | 4 |  | 67.5% | 6 | 3 | 4 | 5 | 1 | 3 |  | 64% | 7 |  | 1486.7011
1064 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2026-09-30 | 2026 | 85 | 8 | 2026-07-07 | med | high | high | low | med | 350000 | 344031 | 340632 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 350000 | 122.8607 | CAPITAL | No | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | no | Yes | no | Yes | Yes | 2 | 2 | 4 | 3 | 1 | 2 | 5 | 4 |  | 57.5% | 6 | 3 | 4 | 1 | 1 | 1 |  | 40% | 4 |  | 2679.5194
1065 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2027-11-30 | 2027 | 150 | 8 | 2027-07-03 | med | med | low | high | med | 350000 | 339702 | 391874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 350000 | 109.8564 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | no | no | no | no | no | no | no | Yes | Yes | 4 | 4 | 5 | 2 | 5 | 3 | 5 | 3 |  | 77.5% | 8 | 5 | 4 | 5 | 2 | 1 |  | 68% | 7 |  | 2679.5194
1066 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Toronto | 2029-04-30 | 2029 | 180 | 8 | 2028-11-01 | high | low | high | low | high | 550000 | 661009 | 682588 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 111.3269 | EXPENSE | Yes | Pipeline segment | X |  | X | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 1 | 1 | 2 | 1 | 3 | 2 | 4 | 3 |  | 42.5% | 5 | 5 | 4 | 5 | 4 | 2 |  | 80% | 8 |  | 1072.7658
1067 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Saskatoon | 2029-11-30 | 2029 | 150 | 8 | 2029-07-03 | high | high | high | low | low | 550000 | 623179 | 603094 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 59.7386 | EXPENSE | No | Pipeline segment |  | X |  | X | X | Yes | no | no | no | no | no | no | no | Yes | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 |  | 35% | 4 | 3 | 2 | 1 | 1 | 2 |  | 36% | 4 |  | 3333.1342
1068 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Montreal | 2029-11-30 | 2029 | 180 | 8 | 2029-06-03 | low | med | low | low | high | 550000 | 590681 | 591056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 280 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | Yes | 3 | 1 | 3 | 2 | 4 | 4 | 4 | 4 |  | 62.5% | 6 | 5 | 2 | 1 | 2 | 1 |  | 44% | 5 |  | 1117.2047
1069 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2030-12-31 | 2030 | 120 | 5 | 2030-09-02 | high | low | low | high | low | 400000 | 391992 | 396981 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 400000 | 279.7384 | EXPENSE | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 4 | 5 | 5 | 2 | 3 | 3 | 1 | 3 |  | 65% | 6 | 3 | 3 | 1 | 1 | 1 |  | 36% | 4 |  | 1300.7103
1070 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2030-12-31 | 2030 | 120 | 2 | 2030-09-02 | med | low | high | high | med | 500000 | 550475 | 595557 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 500000 | 117.2576 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 4 | 1 | 5 | 3 | 1 | 2 | 5 | 4 |  | 62.5% | 6 | 5 | 4 | 5 | 5 | 3 |  | 88% | 9 |  | 14995.8254
1071 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2025-11-30 | 2025 | 120 | 5 | 2025-08-02 | med | low | med | low | low | 350000 | 340105 | 340380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 81.2986 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | no | no | 3 | 4 | 4 | 5 | 1 | 2 | 3 | 1 |  | 57.5% | 6 | 1 | 1 | 5 | 4 | 2 |  | 52% | 6 |  | 76225.6763
1072 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2030-03-31 | 2030 | 200 | 5 | 2029-09-12 | med | high | high | high | high | 500000 | 724601 | 722346 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 500000 | 98.531 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | no | no | no | Yes | 4 | 5 | 1 | 1 | 1 | 1 | 1 | 5 |  | 47.5% | 5 | 3 | 5 | 5 | 1 | 5 |  | 76% | 8 |  | 16.9273
1073 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2029-08-31 | 2029 | 150 | 8 | 2029-04-03 | low | high | med | med | low | 350000 | 332474 | 335000 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 350000 | 37.7222 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | Yes | 5 | 3 | 5 | 5 | 5 | 2 | 4 | 2 |  | 77.5% | 8 | 2 | 2 | 1 | 4 | 3 |  | 48% | 5 |  | 16.9273
1074 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2028-12-31 | 2028 | 200 | 15 | 2028-06-14 | low | med | low | low | low | 350000 | 499124 | 498275 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 77.5311 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | no | Yes | no | Yes | 3 | 3 | 5 | 3 | 4 | 5 | 2 | 5 |  | 75% | 8 | 5 | 3 | 1 | 1 | 2 |  | 48% | 5 |  | 560.1412
1075 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2025-11-30 | 2025 | 200 | 4 | 2025-05-14 | med | low | high | low | high | 400000 | 350785 | 393433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 109.3207 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 3 | 1 | 3 | 2 | 2 | 1 | 5 | 4 |  | 52.5% | 6 | 5 | 4 | 1 | 4 | 1 |  | 60% | 6 |  | 560.1412
1076 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | WINNIPEG | 2027-11-30 | 2027 | 150 | 8 | 2027-07-03 | high | high | high | low | med | 350000 | 522998 | 520888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 350000 | 74.8121 | CAPITAL | No | Pipeline segment | X | X |  | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 2 | 2 | 3 | 5 | 4 | 2 | 3 |  | 60% | 6 | 4 | 4 | 1 | 3 | 5 |  | 68% | 7 |  | 16059.7772
1077 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2029-08-31 | 2029 | 120 | 8 | 2029-05-03 | high | med | med | med | high | 350000 | 411473 | 413108 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 350000 | 142.0502 | CAPITAL | No | Pipeline segment | X | X | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 1 | 1 | 5 | 5 | 5 | 4 | 5 | 1 |  | 67.5% | 6 | 1 | 1 | 1 | 1 | 1 |  | 20% | 2 |  | 2310.5725
1078 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2025-11-30 | 2025 | 120 | 8 | 2025-08-02 | med | med | low | med | low | 350000 | 466242 | 460097 | 0 | 0 | 0 | 0 | 35000 | 210000 | 105000 | 0 | 0 | 0 | 0 | 0 | 350000 | 82.7364 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 5 | 1 | 1 | 4 | 3 | 3 | 3 | 2 |  | 55% | 6 | 1 | 3 | 1 | 3 | 5 |  | 52% | 6 |  | 2480.6254
1079 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2029-04-30 | 2029 | 200 | 7 | 2028-10-12 | low | med | med | low | high | 450000 | 531429 | 533699 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 450000 | 69.7306 | CAPITAL | No | Pipeline segment | X | X |  | X | X | Yes | Yes | Yes | no | Yes | Yes | Yes | no | no | 4 | 4 | 2 | 2 | 5 | 3 | 2 | 3 |  | 62.5% | 6 | 4 | 4 | 1 | 1 | 5 |  | 60% | 6 |  | 2480.6254
1080 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Ottawa | 2028-09-30 | 2028 | 250 | 8 | 2028-01-24 | low | med | low | high | high | 450000 | 465673 | 462884 | 0 | 0 | 0 | 0 | 0 | 45000 | 360000 | 45000 | 0 | 0 | 0 | 0 | 450000 | 110.153 | CAPITAL | No | Pipeline segment | X | X | X |  | X | no | no | Yes | Yes | Yes | no | no | no | no | 5 | 5 | 1 | 4 | 5 | 5 | 4 | 4 |  | 82.5% | 9 | 3 | 1 | 1 | 4 | 3 |  | 48% | 5 |  | 495.1227
1081 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Winnipeg | 2026-12-31 | 2026 | 120 | 8 | 2026-09-02 | low | med | med | med | low | 450000 | 400384 | 400364 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 450000 | 36.7014 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 4 | 5 | 1 | 4 | 2 | 1 | 1 | 5 |  | 57.5% | 6 | 4 | 3 | 1 | 1 | 5 |  | 56% | 6 |  | 3220.812
1082 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Winnipeg | 2025-11-30 | 2025 | 120 | 5 | 2025-08-02 | high | low | low | med | low | 400000 | 424413 | 424247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 400000 | 13.6895 | CAPITAL | No | Pipeline segment | X | X |  | X | X | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 5 | 1 | 5 | 3 | 4 | 2 | 4 | 4 |  | 70% | 6 | 5 | 3 | 1 | 5 | 2 |  | 64% | 7 |  | 17906.9371
1083 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2030-03-31 | 2030 | 120 | 4 | 2029-12-01 | med | low | high | low | med | 400000 | 487955 | 487622 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 400000 | 81.7758 | EXPENSE | No | Pipeline segment | X | X | X |  |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 3 | 5 | 5 | 4 | 2 | 3 | 3 | 2 |  | 67.5% | 6 | 2 | 3 | 1 | 4 | 1 |  | 44% | 5 |  | 21537.8368
1084 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Saskatoon | 2027-08-31 | 2027 | 185 | 15 | 2027-02-27 | med | low | high | high | high | 450000 | 994397 | 956898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 450000 | 61.6448 | CAPITAL | Yes | Pipeline segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | no | Yes | Yes | 2 | 2 | 4 | 3 | 1 | 3 | 3 | 5 |  | 57.5% | 6 | 4 | 2 | 1 | 5 | 3 |  | 60% | 6 |  | 2973.4021
1085 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | North Bay | 2026-05-31 | 2026 | 200 | 8 | 2025-11-12 | low | med | med | med | low | 450000 | 495726 | 469706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 450000 | 19.694 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 2 | 4 | 2 | 2 | 3 | 1 | 5 | 4 |  | 57.5% | 6 | 5 | 1 | 1 | 1 | 1 |  | 36% | 4 |  | 6487.5816
1086 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2026-03-31 | 2026 | 150 | 7 | 2025-11-01 | low | med | high | high | low | 1800000 | 2095522 | 2095724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 0 | 1800000 | 35.0188 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | no | no | no | 3 | 3 | 2 | 2 | 2 | 1 | 5 | 4 |  | 55% | 6 | 5 | 4 | 1 | 4 | 5 |  | 76% | 8 |  | 1083.35
1087 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2026-05-31 | 2026 | 150 | 7 | 2026-01-01 | low | low | med | low | med | 2100000 | 2089588 | 2100050 | 630000 | 1260000 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 1745.308 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | Yes | no | no | no | no | no | Yes | 5 | 3 | 4 | 5 | 2 | 3 | 5 | 1 |  | 70% | 6 | 4 | 3 | 1 | 4 | 1 |  | 52% | 6 |  | 1184.9141
1088 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Winnipeg | 2027-08-31 | 2027 | 120 | 4 | 2027-05-03 | high | high | high | high | med | 400000 | 453423 | 450247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 167.1303 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 5 | 2 | 5 | 1 | 4 | 3 | 1 |  | 60% | 6 | 5 | 2 | 1 | 4 | 2 |  | 56% | 6 |  | 1846.6194
1089 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Ottawa | 2028-04-30 | 2028 | 200 | 8 | 2027-10-13 | high | high | low | low | low | 450000 | 434113 | 437206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 51.5723 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 4 | 5 | 2 | 2 | 3 | 3 | 5 | 3 |  | 67.5% | 6 | 2 | 4 | 1 | 5 | 4 |  | 64% | 7 |  | 1846.6194
1090 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Calgary | 2026-12-31 | 2026 | 185 | 8 | 2026-06-29 | low | low | med | med | high | 450000 | 510412 | 516874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 450000 | 19.5924 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | no | no | no | no | no | no | Yes | 4 | 2 | 4 | 2 | 5 | 1 | 2 | 1 |  | 52.5% | 6 | 4 | 4 | 1 | 1 | 2 |  | 48% | 5 |  | 9580.8769
1091 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2029-08-31 | 2029 | 120 | 8 | 2029-05-03 | high | med | low | high | low | 400000 | 827809 | 927128 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 245.1045 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | no | no | 4 | 3 | 3 | 5 | 4 | 4 | 4 | 3 |  | 75% | 8 | 2 | 5 | 1 | 3 | 2 |  | 52% | 6 |  | 8429.71
1092 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Saskatoon | 2025-06-30 | 2025 | 150 | 8 | 2025-01-31 | high | high | low | med | med | 650000 | 808987 | 803329 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 0 | 650000 | 57.38 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 2 | 2 | 5 | 3 | 3 | 4 | 3 |  | 62.5% | 6 | 1 | 1 | 1 | 3 | 1 |  | 28% | 3 |  | 425
1093 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Saskatoon | 2028-04-30 | 2028 | 150 | 8 | 2027-12-02 | low | med | med | high | low | 450000 | 857877 | 866522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 121.3811 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | no | no | Yes | no | no | Yes | no | no | Yes | 5 | 4 | 3 | 3 | 4 | 5 | 5 | 4 |  | 82.5% | 9 | 1 | 3 | 1 | 3 | 3 |  | 44% | 5 |  | 5875
1094 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2025-09-30 | 2025 | 120 | 7 | 2025-06-02 | high | low | med | med | med | 450000 | 428727 | 466800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 526.2579 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 4 | 2 | 4 | 1 | 1 | 5 | 5 | 5 |  | 67.5% | 6 | 4 | 1 | 1 | 5 | 4 |  | 60% | 6 |  | 48755
1095 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2026-12-31 | 2026 | 120 | 8 | 2026-09-02 | low | med | med | high | med | 350000 | 374581 | 382853 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 166.8084 | CAPITAL | Yes | Pipeline segment |  | X |  | X |  | no | no | no | Yes | Yes | Yes | no | no | no | 1 | 2 | 1 | 3 | 2 | 3 | 4 | 3 |  | 47.5% | 5 | 5 | 4 | 1 | 3 | 5 |  | 72% | 8 |  | 5522
1096 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Edmonton | 2030-03-31 | 2030 | 180 | 8 | 2029-10-02 | low | high | high | low | high | 750000 | 861410 | 860656 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 15.3529 | EXPENSE | No | NO outage |  | X | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | no | 5 | 5 | 2 | 5 | 4 | 5 | 4 | 4 |  | 85% | 9 | 5 | 5 | 5 | 1 | 3 |  | 76% | 8 |  | 4101.0339
1097 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Regina | 2027-11-30 | 2027 | 100 | 4 | 2027-08-22 | high | high | high | high | low | 1800000 | 1807733 | 1857547 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 102.2668 | EXPENSE | No | Pipeline segment | X |  | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 4 |  | 47.5% | 5 | 3 | 4 | 1 | 5 | 1 |  | 56% | 6 |  | 22170.3266
1098 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2025-06-30 | 2025 | 150 | 7 | 2025-01-31 | high | low | high | low | high | 400000 | 555442 | 55668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 71.2228 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | no | Yes | Yes | Yes | no | 2 | 2 | 1 | 5 | 1 | 5 | 1 | 4 |  | 52.5% | 6 | 5 | 2 | 1 | 3 | 3 |  | 56% | 6 |  | 1727.2647
1099 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Ottawa | 2025-06-30 | 2025 | 200 | 7 | 2024-12-12 | high | med | high | low | med | 450000 | 525700 | 525468 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 450000 | 53.7439 | CAPITAL | No | Pipeline segment | X |  |  |  |  | Yes | Yes | no | no | no | Yes | Yes | no | Yes | 1 | 3 | 1 | 2 | 3 | 5 | 5 | 5 |  | 62.5% | 6 | 2 | 2 | 1 | 5 | 2 |  | 48% | 5 |  | 18109.7232
1100 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2030-03-31 | 2030 | 150 | 8 | 2029-11-01 | med | high | low | low | low | 350000 | 780645 | 788090 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 117.9206 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | no | 5 | 5 | 2 | 5 | 5 | 2 | 1 | 4 |  | 72.5% | 8 | 1 | 1 | 1 | 4 | 1 |  | 32% | 4 |  | 3981.0002
1101 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2028-04-30 | 2028 | 200 | 8 | 2027-10-13 | high | high | low | high | low | 500000 | 685306 | 681669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 68.6381 | CAPITAL | Yes | Pipeline segment | X |  | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 2 | 3 | 4 | 1 | 1 | 3 | 2 | 5 |  | 52.5% | 6 | 1 | 2 | 1 | 2 | 1 |  | 28% | 3 |  | 20815.3255
1102 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2025-11-30 | 2025 | 200 | 4 | 2025-05-14 | med | low | med | low | med | 500000 | 509915 | 513929 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 72.3249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | no | no | no | no | Yes | no | no | 2 | 5 | 3 | 1 | 1 | 1 | 2 | 3 |  | 45% | 5 | 2 | 2 | 1 | 5 | 5 |  | 60% | 6 |  | 48955
1103 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Winnipeg | 2030-09-30 | 2030 | 150 | 8 | 2030-05-03 | high | high | low | low | low | 450000 | 806609 | 803956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 450000 | 84.9423 | CAPITAL | No | pipeline segment | X | X | X | X |  | no | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 5 | 3 | 4 | 4 | 1 | 4 | 4 |  | 70% | 6 | 4 | 2 | 1 | 1 | 3 |  | 44% | 5 |  | 278.7236
1104 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Winnipeg | 2029-08-31 | 2029 | 120 | 7 | 2029-05-03 | med | low | high | high | low | 1500000 | 1506928 | 1495675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 1500000 | 33.796 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | Yes | no | no | Yes | no | no | Yes | no | no | 5 | 1 | 1 | 1 | 5 | 5 | 2 | 5 |  | 62.5% | 6 | 4 | 4 | 1 | 3 | 2 |  | 56% | 6 |  | 203.1281
1105 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-REMEDITION | Toronto | 2025-09-30 | 2025 | 150 | 8 | 2025-05-03 | high | low | low | low | med | 850000 | 951968 | 9054634 | 0 | 0 | 0 | 0 | 0 | 255000 | 510000 | 85000 | 0 | 0 | 0 | 0 | 850000 | 41.9164 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | Yes | no | Yes | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 1 | 4 | 1 | 2 | 2 | 3 |  | 47.5% | 5 | 1 | 5 | 1 | 2 | 5 |  | 56% | 6 |  | 203.1281
1106 | L3 | FACILITY | CIVIL |  | CRANE | Ottawa | 2026-10-31 | 2026 | 343 | 4 | 2025-11-22 | low | low | high | low | low | 250000 | 255433 | 258806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 250000 | 74.4943 | EXPENSE | No | Unit outage | X |  |  | X | X | no | no | no | Yes | Yes | no | no | Yes | no | 5 | 2 | 5 | 3 | 2 | 4 | 3 | 4 | 3 | 68.89% | 7 | 5 | 4 | 1 | 2 | 5 | 1 | 60% | 6 |  | 203.1281
1106 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2026-12-31 | 2026 | 180 | 5 | 2026-07-04 | low | med | high | high | low | 350000 | 320570 | 315873 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 375.5287 | EXPENSE | No | Pipeline segment |  |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | Yes | 4 | 1 | 2 | 1 | 5 | 3 | 4 | 5 |  | 62.5% | 6 | 1 | 1 | 1 | 3 | 2 |  | 32% | 4 |  | 853.1382
1107 | L2 | FACILITY | CIVIL |  | CRANE | Regina | 2027-12-31 | 2027 | 86 | 4 | 2027-10-06 | high | high | high | high | high | 300000 | 447851 | 430410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 300000 | 578.2064 | EXPENSE | Yes | Unit outage | X |  | X |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | no | no | 2 | 3 | 1 | 1 | 2 | 4 | 1 | 3 | 5 | 48.89% | 5 | 2 | 3 | 1 | 3 | 5 | 2 | 53.33% | 6 |  | 22170.3266
1107 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2026-05-31 | 2026 | 180 | 8 | 2025-12-02 | high | med | high | low | med | 350000 | 449452 | 496903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 34.9002 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 2 | 4 | 2 | 5 | 4 | 3 | 3 | 1 |  | 60% | 6 | 5 | 4 | 5 | 2 | 2 |  | 72% | 8 |  | 23717.2367
1108 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Regina | 2025-06-30 | 2025 | 200 | 8 | 2024-12-12 | med | med | low | low | low | 450000 | 424655 | 452754 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 0 | 0 | 0 | 0 | 450000 | 95.8703 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | no | no | Yes | no | no | no | no | Yes | 4 | 3 | 5 | 3 | 2 | 4 | 1 | 4 |  | 65% | 6 | 1 | 4 | 5 | 1 | 5 |  | 64% | 7 |  | 746.1723
1109 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2028-04-30 | 2028 | 150 | 8 | 2027-12-02 | med | high | med | low | med | 350000 | 354302 | 387376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 350000 | 71.1665 | EXPENSE | No | Pipeline segment |  | X |  |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | 3 | 2 | 1 | 5 | 3 | 4 | 3 | 5 |  | 65% | 6 | 4 | 5 | 5 | 1 | 1 |  | 64% | 7 |  | 1174.9707
1110 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2025-11-30 | 2025 | 150 | 8 | 2025-07-03 | high | med | med | low | low | 450000 | 531419 | 534750 | 0 | 0 | 0 | 0 | 0 | 45000 | 270000 | 135000 | 0 | 0 | 0 | 0 | 450000 | 76.4614 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | no | no | 5 | 1 | 5 | 5 | 4 | 3 | 5 | 4 |  | 80% | 8 | 1 | 2 | 1 | 4 | 5 |  | 52% | 6 |  | 16021.8416
1111 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANNUAL SURVEY | Regina | 2025-06-30 | 2025 | 100 | 8 | 2025-03-22 | med | med | low | low | high | 780000 | 737705 | 703302 | 0 | 234000 | 390000 | 156000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780000 | 228.8332 | EXPENSE | Yes | NO outage | X | X |  | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | no | 1 | 1 | 1 | 3 | 2 | 1 | 5 | 1 |  | 37.5% | 4 | 3 | 3 | 1 | 5 | 3 |  | 60% | 6 |  | 18.4662
1112 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Winnipeg | 2030-03-31 | 2030 | 180 | 8 | 2029-10-02 | med | low | med | med | high | 550000 | 585478 | 580917 | 0 | 0 | 55000 | 440000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 28.2991 | EXPENSE | No | Pipeline segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 2 | 3 | 3 | 5 | 1 | 5 | 1 | 3 |  | 57.5% | 6 | 2 | 5 | 1 | 3 | 5 |  | 64% | 7 |  | 121.8769
1113 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2028-12-31 | 2028 | 150 | 8 | 2028-08-03 | low | low | high | med | low | 450000 | 448450 | 489906 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 134.4344 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | no | no | Yes | Yes | Yes | no | no | Yes | 1 | 5 | 3 | 4 | 1 | 5 | 4 | 1 |  | 60% | 6 | 3 | 2 | 1 | 2 | 3 |  | 44% | 5 |  | 643.2391
1114 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2030-12-31 | 2030 | 100 | 15 | 2030-09-22 | high | high | high | low | high | 450000 | 692798 | 634137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 890.1864 | CAPITAL | No | Pipeline segment |  | X | X | X | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 2 | 4 | 1 | 3 | 4 | 4 | 4 | 5 |  | 67.5% | 6 | 1 | 4 | 1 | 2 | 4 |  | 48% | 5 |  | 267.7598
1115 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Regina | 2026-09-30 | 2026 | 100 | 4 | 2026-06-22 | high | med | low | high | med | 1500000 | 1550829 | 1550305 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 143.1102 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 3 | 2 | 1 | 2 | 2 | 2 | 5 | 2 |  | 47.5% | 5 | 4 | 3 | 1 | 1 | 3 |  | 48% | 5 |  | 267.7598
1116 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Montreal | 2030-12-31 | 2030 | 200 | 8 | 2030-06-14 | med | high | high | high | low | 550000 | 551865 | 564621 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 86.0466 | EXPENSE | Yes | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 4 | 2 | 2 | 2 | 1 | 3 | 5 | 3 |  | 55% | 6 | 4 | 3 | 1 | 4 | 4 |  | 64% | 7 |  | 7024.2246
1117 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Quebec City | 2025-09-30 | 2025 | 250 | 5 | 2025-01-23 | low | med | low | med | low | 300000 | 385848 | 388631 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 71.0178 | EXPENSE | Yes | Pipeline segment |  |  |  | X |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 5 | 2 | 4 | 2 | 1 | 1 | 4 |  | 50% | 5 | 4 | 4 | 1 | 4 | 4 |  | 68% | 7 |  | 1591.1704
1118 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2026-09-30 | 2026 | 200 | 15 | 2026-03-14 | high | high | high | med | med | 450000 | 489758 | 489076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 56.3678 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | Yes | no | no | no | no | no | no | no | no | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 5 |  | 55% | 6 | 5 | 3 | 1 | 4 | 4 |  | 68% | 7 |  | 4785
1119 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Edmonton | 2028-09-30 | 2028 | 150 | 10 | 2028-05-03 | low | high | high | low | high | 300000 | 373417 | 385508 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 120000 | 60000 | 0 | 0 | 0 | 300000 | 204.7502 | EXPENSE | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 5 | 3 | 1 | 3 | 5 | 2 | 3 | 1 |  | 57.5% | 6 | 2 | 3 | 1 | 1 | 2 |  | 36% | 4 |  | 3358
1120 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Saskatoon | 2025-11-30 | 2025 | 180 | 8 | 2025-06-03 | high | high | med | med | med | 300000 | 384800 | 409516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 150000 | 60000 | 0 | 0 | 300000 | 193.3484 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | no | Yes | Yes | no | no | Yes | Yes | Yes | 5 | 1 | 3 | 2 | 3 | 1 | 2 | 3 |  | 50% | 5 | 1 | 4 | 1 | 1 | 2 |  | 36% | 4 |  | 5732.8906
1121 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2026-12-31 | 2026 | 200 | 8 | 2026-06-14 | high | med | high | low | low | 650000 | 1109127 | 1023937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 650000 | 53.022 | CAPITAL | No | Pipeline segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 3 | 3 | 3 | 2 | 4 | 5 | 2 | 5 |  | 67.5% | 6 | 5 | 1 | 1 | 5 | 1 |  | 52% | 6 |  | 3077.9635
1122 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Winnipeg | 2025-06-30 | 2025 | 85 | 4 | 2025-04-06 | high | low | low | low | med | 1800000 | 1789522 | 1832500 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 2.6813 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 1 | 5 | 4 | 5 | 4 | 5 | 1 | 1 |  | 65% | 6 | 1 | 5 | 1 | 3 | 1 |  | 44% | 5 |  | 13582.277
1123 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2026-05-31 | 2026 | 217 | 7 | 2025-10-26 | med | high | low | high | high | 2000000 | 2020848 | 2089578 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 304.5368 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X | X | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 |  | 65% | 6 | 4 | 2 | 1 | 2 | 4 |  | 52% | 6 |  | 7709.8457
1124 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Toronto | 2030-12-31 | 2030 | 180 | 15 | 2030-07-04 | med | med | low | high | high | 550000 | 899341 | 906308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 44.7596 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | no | Yes | Yes | Yes | Yes | no | Yes | no | 5 | 5 | 3 | 5 | 5 | 5 | 4 | 5 |  | 92.5% | 10 | 3 | 5 | 5 | 1 | 2 |  | 64% | 7 |  | 7110.0938
1125 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Ottawa | 2027-08-31 | 2027 | 180 | 10 | 2027-03-04 | med | med | low | low | low | 300000 | 323560 | 360010 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 300000 | 86.1551 | EXPENSE | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | Yes | Yes | Yes | no | no | 2 | 1 | 4 | 4 | 1 | 2 | 5 | 1 |  | 50% | 5 | 2 | 1 | 1 | 3 | 4 |  | 44% | 5 |  | 4314.1949
1126 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Saskatoon | 2025-06-30 | 2025 | 120 | 10 | 2025-03-02 | med | low | high | low | med | 450000 | 452055 | 421982 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 100.5902 | CAPITAL | No | pipeline segment outage |  | X | X |  | X | no | Yes | no | no | no | Yes | no | no | Yes | 2 | 3 | 5 | 2 | 2 | 5 | 3 | 3 |  | 62.5% | 6 | 3 | 3 | 1 | 5 | 2 |  | 56% | 6 |  | 6062.6028
1127 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Montreal | 2028-04-30 | 2028 | 250 | 10 | 2027-08-24 | high | high | med | high | high | 300000 | 275080 | 295529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 300000 | 32.563 | EXPENSE | No | Pipeline segment |  |  | X | X | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 5 | 4 | 5 | 4 | 5 | 3 | 2 | 4 |  | 80% | 8 | 1 | 3 | 1 | 4 | 2 |  | 44% | 5 |  | 2898
1128 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Winnipeg | 2029-04-30 | 2029 | 180 | 15 | 2028-11-01 | med | low | low | low | high | 450000 | 466475 | 465002 | 0 | 90000 | 0 | 0 | 270000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 13.0596 | CAPITAL | No | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 5 | 4 | 1 | 3 | 5 | 5 | 5 | 5 |  | 82.5% | 9 | 1 | 3 | 1 | 3 | 3 |  | 44% | 5 |  | 4522
1129 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Quebec City | 2030-03-31 | 2030 | 250 | 8 | 2029-07-24 | low | med | low | high | med | 550000 | 478617 | 519000 | 165000 | 0 | 0 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 3.8339 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 1 | 3 | 4 | 4 | 2 | 4 | 3 |  | 60% | 6 | 3 | 5 | 5 | 3 | 3 |  | 76% | 8 |  | 8429.71
1130 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2027-04-30 | 2027 | 200 | 8 | 2026-10-12 | med | high | low | med | high | 500000 | 986111 | 989500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 500000 | 89.8531 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 5 |  | 40% | 4 | 3 | 1 | 1 | 2 | 1 |  | 32% | 4 |  | 5875
1131 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2027-04-30 | 2027 | 215 | 10 | 2026-09-27 | med | high | high | low | high | 350000 | 362980 | 373520 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 350000 | 1124.6434 | EXPENSE | No | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 3 | 2 | 3 | 4 | 4 | 4 | 1 | 1 |  | 55% | 6 | 3 | 2 | 1 | 1 | 1 |  | 32% | 4 |  | 258
1132 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Winnipeg | 2028-12-31 | 2028 | 180 | 8 | 2028-07-04 | med | high | high | high | high | 350000 | 1071481 | 1076796 | 0 | 0 | 0 | 105000 | 0 | 0 | 210000 | 35000 | 0 | 0 | 0 | 0 | 350000 | 137.4312 | CAPITAL | No | Pipeline segment |  |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 20% | 2 | 2 | 3 | 1 | 4 | 1 |  | 44% | 5 |  | 4785
1133 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Calgary | 2025-11-30 | 2025 | 120 | 8 | 2025-08-02 | high | high | high | med | high | 250000 | 257881 | 301469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 125000 | 50000 | 0 | 0 | 250000 | 14.7788 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X |  | no | no | Yes | Yes | no | no | Yes | no | Yes | 1 | 2 | 2 | 4 | 2 | 4 | 5 | 3 |  | 57.5% | 6 | 2 | 2 | 1 | 2 | 4 |  | 44% | 5 |  | 13420.41
1134 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | North Bay | 2027-08-31 | 2027 | 200 | 8 | 2027-02-12 | high | med | high | high | low | 350000 | 359833 | 352678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 350000 | 78.3491 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 2 | 4 | 1 | 5 | 4 | 3 | 3 | 2 |  | 60% | 6 | 3 | 1 | 1 | 3 | 3 |  | 44% | 5 |  | 1727.265
1135 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2025-09-30 | 2025 | 200 | 8 | 2025-03-14 | med | high | high | med | low | 400000 | 836064 | 996142 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 188.6819 | EXPENSE | Yes | Pipeline segment |  | X |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 4 | 2 | 4 | 3 | 4 | 2 | 4 | 4 |  | 67.5% | 6 | 3 | 2 | 1 | 3 | 1 |  | 40% | 4 |  | 18109.72
1136 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Regina | 2026-05-31 | 2026 | 85 | 4 | 2026-03-07 | low | low | low | high | med | 950000 | 951400 | 9573713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285000 | 475000 | 190000 | 950000 | 165.7118 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | no | no | no | Yes | 2 | 1 | 1 | 2 | 2 | 4 | 3 | 3 |  | 45% | 5 | 1 | 2 | 1 | 4 | 2 |  | 40% | 4 |  | 20815.33
1137 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2030-03-31 | 2030 | 180 | 4 | 2029-10-02 | high | low | low | low | high | 650000 | 720531 | 725189 | 0 | 0 | 0 | 195000 | 325000 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 732.8044 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  |  | no | Yes | Yes | Yes | Yes | no | no | no | no | 4 | 3 | 4 | 3 | 4 | 5 | 3 | 5 |  | 77.5% | 8 | 1 | 1 | 1 | 2 | 4 |  | 36% | 4 |  | 425
1138 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Quebec City | 2027-04-30 | 2027 | 100 | 4 | 2027-01-20 | low | high | med | low | med | 650000 | 680531 | 685189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 325000 | 130000 | 0 | 650000 | 146.1537 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | no | no | Yes | Yes | no | Yes | no | Yes | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 3 |  | 42.5% | 5 | 1 | 1 | 1 | 1 | 3 |  | 28% | 3 |  | 2789
1139 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2029-04-30 | 2029 | 120 | 7 | 2028-12-31 | low | high | low | low | med | 2100000 | 2124910 | 2128330 | 0 | 0 | 0 | 630000 | 1050000 | 420000 | 0 | 0 | 630000 | 1050000 | 420000 | 0 | 4200000 | 12.9047 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | no | no | no | no | Yes | no | 2 | 4 | 3 | 2 | 3 | 2 | 1 | 1 |  | 45% | 5 | 2 | 4 | 1 | 1 | 1 |  | 36% | 4 |  | 5666
1140 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Winnipeg | 2030-03-31 | 2030 | 120 | 4 | 2029-12-01 | high | high | low | med | med | 1300000 | 1324785 | 1350260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 650000 | 260000 | 0 | 0 | 1300000 | 119.9716 | EXPENSE | No | Pipeline segment | X |  |  |  | X | Yes | no | no | Yes | Yes | no | no | Yes | no | 5 | 1 | 2 | 5 | 2 | 2 | 4 | 2 |  | 57.5% | 6 | 4 | 5 | 5 | 3 | 3 |  | 80% | 8 |  | 2789
1141 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2029-04-30 | 2029 | 180 | 4 | 2028-11-01 | high | med | med | high | med | 400000 | 393878 | 395581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 318.2127 | EXPENSE | No | Pipeline segment | X |  |  | X | X | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 5 | 3 | 1 | 2 | 4 | 4 | 4 | 1 |  | 60% | 6 | 2 | 5 | 1 | 2 | 3 |  | 52% | 6 |  | 23717.24
1142 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2026-03-31 | 2026 | 250 | 8 | 2025-07-24 | high | low | med | med | low | 500000 | 879950 | 872100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 500000 | 59.654 | CAPITAL | No | Pipeline segment |  | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 4 | 1 | 4 | 2 | 3 | 3 | 1 | 3 |  | 52.5% | 6 | 2 | 4 | 1 | 3 | 1 |  | 44% | 5 |  | 13677.18
1143 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2027-11-30 | 2027 | 180 | 8 | 2027-06-03 | low | med | med | low | low | 350000 | 350821 | 350947 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 250.7139 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | no | no | no | Yes | 2 | 4 | 3 | 3 | 5 | 4 | 4 | 4 |  | 72.5% | 8 | 1 | 5 | 1 | 2 | 3 |  | 48% | 5 |  | 16021.84
1144 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | North Bay | 2025-06-30 | 2025 | 150 | 5 | 2025-01-31 | low | low | high | med | med | 400000 | 527515 | 518701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 129.2729 | EXPENSE | No | Pipeline segment | X | X |  | X |  | no | Yes | Yes | Yes | no | no | no | Yes | no | 1 | 5 | 1 | 3 | 2 | 1 | 4 | 3 |  | 50% | 5 | 3 | 3 | 1 | 1 | 1 |  | 36% | 4 |  | 7007.921
1145 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | North Bay | 2025-11-30 | 2025 | 150 | 8 | 2025-07-03 | med | low | high | med | high | 350000 | 364592 | 366431 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 0 | 350000 | 134.8065 | EXPENSE | No | Pipeline segment | X | X |  |  | X | Yes | no | Yes | Yes | no | no | no | no | no | 1 | 1 | 5 | 4 | 1 | 3 | 4 | 2 |  | 52.5% | 6 | 3 | 2 | 1 | 5 | 2 |  | 52% | 6 |  | 7007.921
1146 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Quebec City | 2030-12-31 | 2030 | 150 | 8 | 2030-08-03 | high | high | high | low | med | 600000 | 670309 | 670000 | 0 | 180000 | 300000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 28.6028 | CAPITAL | No | pipeline segment outage |  |  | X |  | X | Yes | no | no | no | no | Yes | no | Yes | Yes | 2 | 1 | 5 | 1 | 5 | 1 | 2 | 2 |  | 47.5% | 5 | 2 | 2 | 1 | 4 | 3 |  | 48% | 5 |  | 121.8769
1147 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Winnipeg | 2025-09-30 | 2025 | 130 | 8 | 2025-05-23 | low | low | high | high | high | 450000 | 401590 | 401803 | 0 | 135000 | 225000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 118.806 | CAPITAL | No | pipeline segment outage | X | X |  |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 2 | 2 | 1 | 1 | 2 | 2 | 4 | 5 |  | 47.5% | 5 | 3 | 3 | 1 | 4 | 1 |  | 48% | 5 |  | 267.7598
1148 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2029-11-30 | 2029 | 180 | 4 | 2029-06-03 | high | high | low | high | low | 2100000 | 2014910 | 2018330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630000 | 1050000 | 420000 | 0 | 2100000 | 61.0855 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 2 | 3 | 5 | 5 | 5 | 3 | 2 | 5 |  | 75% | 8 | 2 | 4 | 5 | 2 | 4 |  | 68% | 7 |  | 6832.492
1149 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2028-04-30 | 2028 | 200 | 8 | 2027-10-13 | low | low | low | low | low | 500000 | 677573 | 672660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 500000 | 11.9354 | EXPENSE | No | Pipeline segment |  |  | X |  |  | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 3 | 1 | 4 | 5 | 3 | 4 | 5 | 4 |  | 72.5% | 8 | 1 | 4 | 1 | 4 | 2 |  | 48% | 5 |  | 25885
1150 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2027-08-31 | 2027 | 180 | 5 | 2027-03-04 | med | med | med | med | low | 400000 | 425230 | 434107 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 383.2311 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | no | Yes | no | Yes | no | no | Yes | no | 4 | 5 | 3 | 4 | 3 | 5 | 4 | 5 |  | 82.5% | 9 | 4 | 3 | 1 | 1 | 2 |  | 44% | 5 |  | 5732.891
1151 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2026-03-31 | 2026 | 120 | 4 | 2025-12-01 | low | low | high | low | low | 1000000 | 995898 | 947471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 500000 | 200000 | 0 | 1000000 | 78.2163 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X | X | Yes | no | no | no | no | no | Yes | no | Yes | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 1 |  | 50% | 5 | 5 | 4 | 1 | 2 | 2 |  | 56% | 6 |  | 3077.963
1152 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Winnipeg | 2027-08-31 | 2026 | 150 | 5 | 2027-04-03 | high | high | high | low | high | 400000 | 493729 | 468570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 162.7571 | EXPENSE | No | Pipeline segment | X | X |  |  | X | no | Yes | Yes | Yes | no | no | Yes | no | Yes | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 2 |  | 47.5% | 5 | 2 | 5 | 5 | 1 | 3 |  | 64% | 7 |  | 5097.261
1153 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Calgary | 2026-03-31 | 2026 | 200 | 8 | 2025-09-12 | low | low | low | med | low | 450000 | 444446 | 445417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 0 | 450000 | 145.3755 | CAPITAL | No | Pipeline segment |  |  | X | X | X | Yes | no | Yes | Yes | Yes | no | Yes | Yes | Yes | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 2 |  | 90% | 9 | 3 | 3 | 1 | 2 | 1 |  | 40% | 4 |  | 7709.846
1154 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Calgary | 2025-06-30 | 2025 | 200 | 8 | 2024-12-12 | high | low | med | high | high | 450000 | 858949 | 899364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 0 | 450000 | 44.4078 | CAPITAL | Yes | pipeline segment | X | X |  |  | X | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 2 | 5 | 3 | 2 | 4 | 4 | 3 | 1 |  | 60% | 6 | 1 | 3 | 1 | 3 | 1 |  | 36% | 4 |  | 7110.094
1155 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Winnipeg | 2025-11-30 | 2025 | 265 | 2 | 2025-03-10 | med | low | low | med | high | 850000 | 795426 | 800000 | 0 | 255000 | 425000 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 287.411 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 3 | 2 | 1 | 2 | 3 | 3 | 2 |  | 42.5% | 5 | 2 | 5 | 1 | 5 | 2 |  | 60% | 6 |  | 4391.637
1156 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Saskatoon | 2028-09-30 | 2028 | 120 | 4 | 2028-06-02 | low | med | med | low | high | 1000000 | 1135786 | 1204048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 500000 | 200000 | 0 | 0 | 1000000 | 336.0415 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 1 | 1 | 1 | 4 | 4 | 1 | 2 |  | 42.5% | 5 | 3 | 1 | 1 | 4 | 2 |  | 44% | 5 |  | 4858.887
1157 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2029-08-31 | 2029 | 200 | 8 | 2029-02-12 | med | high | med | med | high | 500000 | 567194 | 567060 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 0 | 0 | 0 | 500000 | 49.109 | EXPENSE | No | Pipeline segment | X | X |  |  |  | Yes | Yes | no | no | Yes | no | no | Yes | Yes | 4 | 2 | 2 | 4 | 5 | 1 | 3 | 5 |  | 65% | 6 | 3 | 2 | 1 | 2 | 4 |  | 48% | 5 |  | 1090.538
1158 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Edmonton | 2030-12-31 | 2030 | 180 | 8 | 2030-07-04 | med | med | med | high | med | 350000 | 306367 | 304154 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 56.2148 | CAPITAL | Yes | Pipeline segment |  | X | X |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 2 | 2 | 5 | 3 | 2 | 2 | 2 | 5 |  | 57.5% | 6 | 5 | 5 | 5 | 2 | 4 |  | 84% | 9 |  | 4052.085
1159 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2025-11-30 | 2025 | 180 | 8 | 2025-06-03 | low | high | med | low | med | 350000 | 306322 | 304238 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 350000 | 104.2124 | CAPITAL | No | Pipeline segment | X | X | X |  | X | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 1 | 5 | 2 | 1 | 3 | 2 | 2 |  | 50% | 5 | 1 | 5 | 1 | 5 | 1 |  | 52% | 6 |  | 6062.603
1160 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2030-03-31 | 2030 | 120 | 2 | 2029-12-01 | med | med | high | high | low | 300000 | 351489 | 352567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 150000 | 60000 | 0 | 0 | 300000 | 256.8876 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  | X | X | Yes | Yes | no | Yes | Yes | no | no | no | no | 3 | 4 | 1 | 1 | 3 | 3 | 3 | 2 |  | 50% | 5 | 3 | 3 | 1 | 1 | 1 |  | 36% | 4 |  | 2610.39
1161 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Edmonton | 2030-12-31 | 2030 | 180 | 8 | 2030-07-04 | med | low | med | low | med | 350000 | 393527 | 393520 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 21.7053 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | no | Yes | no | no | Yes | no | Yes | 5 | 3 | 2 | 4 | 2 | 4 | 5 | 3 |  | 70% | 6 | 1 | 2 | 1 | 5 | 2 |  | 44% | 5 |  | 241.5599
1162 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2027-04-30 | 2027 | 150 | 8 | 2026-12-01 | high | low | med | med | high | 400000 | 857316 | 863023 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 42.7227 | CAPITAL | No | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 2 | 3 | 3 | 5 | 1 | 2 | 4 |  | 57.5% | 6 | 4 | 4 | 5 | 1 | 2 |  | 64% | 7 |  | 4995.39
1163 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2029-08-31 | 2029 | 150 | 8 | 2029-04-03 | low | med | low | low | low | 350000 | 420028 | 448094 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 0 | 0 | 350000 | 90.2519 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | no | 4 | 5 | 1 | 3 | 1 | 1 | 2 | 1 |  | 45% | 5 | 1 | 4 | 1 | 2 | 1 |  | 36% | 4 |  | 6993.546
1164 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2030-12-31 | 2030 | 150 | 8 | 2030-08-03 | low | high | med | low | low | 350000 | 354238 | 347119 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 350000 | 61.5753 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 4 | 3 | 4 | 5 | 1 | 2 | 4 | 4 |  | 67.5% | 6 | 3 | 1 | 1 | 5 | 5 |  | 60% | 6 |  | 222.8052
1165 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Calgary | 2029-11-30 | 2029 | 120 | 4 | 2029-08-02 | med | low | low | high | low | 1900000 | 1959945 | 1963759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 950000 | 380000 | 1900000 | 28.0968 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | Yes | 4 | 2 | 2 | 3 | 3 | 2 | 3 | 2 |  | 52.5% | 6 | 2 | 2 | 1 | 3 | 4 |  | 48% | 5 |  | 5000
1166 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2030-09-30 | 2030 | 180 | 8 | 2030-04-03 | low | low | high | high | low | 350000 | 401605 | 407547 | 35000 | 140000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 140000 | 175000 | 700000 | 7.1499 | CAPITAL | No | Pipeline segment | X |  |  | X |  | no | no | Yes | no | no | no | Yes | no | Yes | 1 | 4 | 4 | 3 | 4 | 1 | 2 | 1 |  | 50% | 5 | 5 | 5 | 1 | 3 | 1 |  | 60% | 6 |  | 347
1167 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2028-04-30 | 2028 | 120 | 15 | 2028-01-01 | med | low | low | low | low | 450000 | 505184 | 505568 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 0 | 0 | 0 | 0 | 450000 | 15.392 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | no | no | Yes | 2 | 5 | 3 | 4 | 3 | 1 | 5 | 3 |  | 65% | 6 | 2 | 3 | 1 | 3 | 3 |  | 48% | 5 |  | 1785
1168 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Calgary | 2026-05-31 | 2026 | 150 | 8 | 2026-01-01 | low | med | low | med | med | 750000 | 900542 | 936801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 300000 | 375000 | 0 | 0 | 750000 | 120.5022 | EXPENSE | Yes | Pipeline segment | X | X | X |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 5 | 3 | 2 | 2 | 5 | 3 | 4 | 3 |  | 67.5% | 6 | 2 | 3 | 1 | 2 | 2 |  | 40% | 4 |  | 172.2548
1169 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Ottawa | 2025-06-30 | 2025 | 85 | 5 | 2025-04-06 | high | low | high | med | high | 450000 | 679319 | 635544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 0 | 450000 | 35.2892 | CAPITAL | No | pipeline segment outage | X |  | X | X | X | Yes | Yes | Yes | no | no | Yes | no | no | no | 4 | 5 | 2 | 4 | 4 | 1 | 5 | 4 |  | 72.5% | 8 | 3 | 2 | 1 | 1 | 4 |  | 44% | 5 |  | 191.3942
1170 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Edmonton | 2025-06-30 | 2025 | 180 | 4 | 2025-01-01 | med | med | med | low | low | 500000 | 544088 | 579248 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 0 | 500000 | 152.364 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | no | Yes | no | Yes | Yes | no | Yes | Yes | 1 | 3 | 4 | 1 | 2 | 5 | 1 | 2 |  | 47.5% | 5 | 5 | 3 | 1 | 2 | 3 |  | 56% | 6 |  | 382.7885
1171 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Edmonton | 2027-11-30 | 2027 | 195 | 8 | 2027-05-19 | low | med | med | med | low | 450000 | 360834 | 399482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 0 | 450000 | 177.3607 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | Yes | no | no | Yes | no | Yes | no | no | 2 | 3 | 3 | 4 | 3 | 2 | 3 | 3 |  | 57.5% | 6 | 1 | 3 | 1 | 1 | 2 |  | 32% | 4 |  | 173.2929
1172 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2027-08-31 | 2027 | 200 | 8 | 2027-02-12 | high | low | high | med | med | 500000 | 498707 | 498210 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 152.9866 | EXPENSE | No | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | Yes | no | no | no | no | 4 | 2 | 2 | 2 | 3 | 5 | 5 | 5 |  | 70% | 6 | 3 | 1 | 1 | 3 | 5 |  | 52% | 6 |  | 749.7244
1173 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2025-11-30 | 2025 | 120 | 4 | 2025-08-02 | high | high | med | high | med | 1500000 | 1812742 | 1842116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 750000 | 300000 | 0 | 0 | 1500000 | 34.0888 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 2 | 2 | 4 | 5 | 5 | 5 | 2 | 3 |  | 70% | 6 | 1 | 5 | 1 | 4 | 5 |  | 64% | 7 |  | 41798.52
1174 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Edmonton | 2026-09-30 | 2026 | 120 | 2 | 2026-06-02 | high | low | low | low | high | 600000 | 598833 | 611085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 300000 | 120000 | 0 | 0 | 600000 | 218.6029 | CAPITAL | No | pipeline segment outage | X |  | X | X |  | no | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 1 | 2 | 3 | 2 | 4 | 5 | 2 |  | 55% | 6 | 4 | 5 | 5 | 4 | 4 |  | 88% | 9 |  | 425
1175 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2026-05-31 | 2026 | 150 | 5 | 2026-01-01 | high | low | high | high | low | 400000 | 522720 | 529911 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 242.1342 | CAPITAL | No | Pipeline segment |  |  |  | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 4 | 2 | 5 | 1 | 4 | 3 | 3 |  | 62.5% | 6 | 2 | 1 | 1 | 2 | 2 |  | 32% | 4 |  | 20000
1176 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2029-04-30 | 2029 | 200 | 5 | 2028-10-12 | med | high | low | med | low | 400000 | 408000 | 425000 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 218.7171 | EXPENSE | Yes | pipeline segment |  |  | X | X | X | no | no | no | no | no | Yes | Yes | Yes | no | 5 | 2 | 1 | 2 | 5 | 5 | 2 | 1 |  | 57.5% | 6 | 1 | 3 | 1 | 4 | 2 |  | 44% | 5 |  | 2078
1177 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Toronto | 2026-09-30 | 2026 | 200 | 5 | 2026-03-14 | low | high | med | med | high | 500000 | 586296 | 558571 | 0 | 50000 | 200000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 163.365 | CAPITAL | No | Pipeline segment |  | X | X | X | X | no | no | Yes | no | no | no | Yes | no | no | 2 | 5 | 3 | 4 | 4 | 2 | 4 | 1 |  | 62.5% | 6 | 1 | 1 | 1 | 2 | 4 |  | 36% | 4 |  | 1875
1178 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2025-11-30 | 2025 | 200 | 4 | 2025-05-14 | high | high | med | high | high | 500000 | 501652 | 545736 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 41.1751 | EXPENSE | No | Pipeline segment |  | X | X |  |  | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 5 | 5 | 1 | 3 | 2 | 3 | 1 | 3 |  | 57.5% | 6 | 5 | 4 | 1 | 3 | 3 |  | 64% | 7 |  | 7718.869
1179 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2029-04-30 | 2029 | 200 | 8 | 2028-10-12 | low | med | med | med | low | 500000 | 513241 | 519365 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 0 | 0 | 0 | 500000 | 5.9556 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | no | 5 | 3 | 1 | 2 | 3 | 3 | 3 | 4 |  | 60% | 6 | 2 | 1 | 1 | 1 | 4 |  | 36% | 4 |  | 7718.869
1180 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Regina | 2028-09-30 | 2028 | 100 | 4 | 2028-06-22 | low | high | high | high | high | 750000 | 1804556 | 813074 | 0 | 225000 | 375000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 83.977 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  | X | Yes | Yes | no | no | Yes | no | no | no | no | 3 | 1 | 4 | 2 | 2 | 2 | 3 | 3 |  | 50% | 5 | 3 | 1 | 1 | 3 | 2 |  | 40% | 4 |  | 6993.546
1181 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2029-11-30 | 2029 | 200 | 4 | 2029-05-14 | low | high | low | med | high | 750000 | 853330 | 827797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 375000 | 150000 | 0 | 750000 | 200.4576 | EXPENSE | No | Derate/low flow Pipe segment | [5 empty] | no | no | no | no | Yes | Yes | no | no | Yes | 1 | 2 | 4 | 5 | 4 | 4 | 3 | 3 |  | 65% | 6 | 2 | 1 | 1 | 1 | 1 |  | 24% | 3 |  | 1475
1182 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2026-12-31 | 2026 | 150 | 8 | 2026-08-03 | med | high | low | high | med | 400000 | 582895 | 585540 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 800000 | 199.4572 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 3 | 2 | 1 | 1 | 2 | 4 | 5 | 5 |  | 57.5% | 6 | 1 | 4 | 1 | 3 | 5 |  | 56% | 6 |  | 2369.828
1183 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2027-04-30 | 2027 | 85 | 2 | 2027-02-04 | high | low | med | high | high | 450000 | 422239 | 452847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 450000 | 172.7549 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 4 | 3 | 3 | 2 | 3 | 5 | 2 |  | 65% | 6 | 1 | 2 | 1 | 2 | 3 |  | 36% | 4 |  | 3138.866
1184 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Montreal | 2026-05-31 | 2026 | 250 | 8 | 2025-09-23 | high | low | med | high | high | 500000 | 949928 | 991050 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 59.9299 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | Yes | Yes | no | no | no | Yes | no | Yes | 1 | 2 | 3 | 5 | 4 | 3 | 1 | 3 |  | 55% | 6 | 3 | 1 | 1 | 2 | 5 |  | 48% | 5 |  | 3138.866
1185 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Ottawa | 2029-11-30 | 2029 | 200 | 8 | 2029-05-14 | med | high | med | high | high | 450000 | 929329 | 985745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 450000 | 24.4952 | CAPITAL | No | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 3 | 5 | 4 | 1 | 1 | 4 | 1 | 5 |  | 60% | 6 | 4 | 5 | 1 | 3 | 4 |  | 68% | 7 |  | 14928.99
1186 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2030-03-31 | 2030 | 85 | 4 | 2030-01-05 | high | high | med | med | med | 1500000 | 1517309 | 1577293 | 0 | 450000 | 750000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 56.1178 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  |  | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | no | 3 | 4 | 2 | 2 | 1 | 2 | 3 | 4 |  | 52.5% | 6 | 5 | 1 | 1 | 2 | 3 |  | 48% | 5 |  | 4785
1187 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Edmonton | 2026-12-31 | 2026 | 200 | 8 | 2026-06-14 | med | med | low | high | med | 550000 | 583881 | 573876 | 0 | 0 | 165000 | 275000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 11.6418 | EXPENSE | No | Pipeline segment |  | X |  | X | X | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 2 | 5 | 2 | 3 | 4 | 5 | 5 | 1 |  | 67.5% | 6 | 3 | 2 | 1 | 4 | 4 |  | 56% | 6 |  | 4542.743
1188 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Quebec City | 2029-08-31 | 2029 | 200 | 15 | 2029-02-12 | low | med | low | low | high | 500000 | 554230 | 580197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 500000 | 6.3304 | CAPITAL | No | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | no | no | no | 4 | 3 | 3 | 4 | 2 | 1 | 5 | 2 |  | 60% | 6 | 5 | 5 | 5 | 2 | 1 |  | 72% | 8 |  | 3333.134
1189 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Saskatoon | 2029-08-31 | 2029 | 100 | 10 | 2029-05-23 | low | low | med | high | low | 450000 | 562796 | 571191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 450000 | 107.4224 | CAPITAL | No | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | no | no | no | no | Yes | Yes | 4 | 3 | 1 | 4 | 2 | 1 | 1 | 5 |  | 52.5% | 6 | 3 | 3 | 1 | 2 | 1 |  | 40% | 4 |  | 1117.205
1190 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Edmonton | 2030-09-30 | 2030 | 150 | 10 | 2030-05-03 | med | med | low | med | low | 550000 | 480203 | 490541 | 0 | 0 | 165000 | 275000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 101.2735 | EXPENSE | Yes | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 2 | 4 | 1 | 4 | 1 | 5 | 3 | 5 |  | 62.5% | 6 | 2 | 5 | 1 | 1 | 3 |  | 48% | 5 |  | 45.3112
1191 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2029-08-31 | 2029 | 170 | 4 | 2029-03-14 | high | low | high | med | high | 400000 | 488222 | 477827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 202.8834 | CAPITAL | Yes | Pipeline segment |  | X |  | X | X | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 1 | 2 | 1 | 3 | 3 | 2 | 2 | 5 |  | 47.5% | 5 | 4 | 5 | 5 | 4 | 2 |  | 80% | 8 |  | 1300.71
1192 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | WINNIPEG | 2028-04-30 | 2028 | 120 | 15 | 2028-01-01 | med | med | high | med | low | 450000 | 481653 | 480764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 450000 | 90.3714 | CAPITAL | No | Pipeline segment | X | X | X |  |  | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 4 | 2 | 3 | 5 | 1 | 3 | 1 | 1 |  | 50% | 5 | 3 | 2 | 1 | 5 | 1 |  | 48% | 5 |  | 263.7275
1193 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | North Bay | 2026-03-31 | 2026 | 108 | 8 | 2025-12-13 | med | med | high | low | med | 250000 | 200338 | 234729 | 0 | 0 | 0 | 75000 | 125000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 167.215 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 4 |  | 92.5% | 10 | 1 | 5 | 5 | 5 | 4 |  | 80% | 8 |  | 14995.83
1194 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2026-12-31 | 2026 | 120 | 4 | 2026-09-02 | high | low | high | med | high | 1500000 | 1450980 | 1458652 | 0 | 450000 | 750000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 118.0594 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 5 | 4 | 4 | 4 | 2 | 5 | 5 | 5 |  | 85% | 9 | 5 | 1 | 1 | 3 | 3 |  | 52% | 6 |  | 76225.68
1195 | L1 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Quebec City | 2026-09-30 | 2026 | 268 | 8 | 2026-01-05 | med | low | med | high | high | 4585000 | 4680012 | 4700046 | 1375500 | 2292500 | 917000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4585000 | 91.5834 | CAPITAL | Yes | Station outage |  |  | X |  |  | no | Yes | Yes | no | Yes | no | no | no | Yes | 4 | 4 | 1 | 1 | 4 | 2 | 1 | 2 |  | 47.5% | 5 | 3 | 3 | 1 | 2 | 5 |  | 56% | 6 |  | 16.9273
1196 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2028-04-30 | 2028 | 120 | 4 | 2028-01-01 | high | low | low | low | med | 750000 | 710189 | 719044 | 0 | 0 | 225000 | 375000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 61.5579 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  | X | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 2 | 3 | 5 | 1 | 2 | 3 | 5 |  | 60% | 6 | 5 | 1 | 1 | 2 | 2 |  | 44% | 5 |  | 16.9273
1197 | L3 | PIPE INTEGRITY | L&R |  | TETHER | Winnipeg | 2029-04-30 | 2029 | 165 | 7 | 2028-11-16 | med | low | low | med | low | 850000 | 892844 | 905260 | 225000 | 375000 | 150000 | 0 | 0 | 0 | 0 | 255000 | 425000 | 170000 | 0 | 0 | 1600000 | 1023.831 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | Yes | no | Yes | no | Yes | no | 2 | 4 | 4 | 3 | 5 | 2 | 1 | 5 |  | 65% | 6 | 4 | 5 | 1 | 2 | 1 |  | 52% | 6 |  | 560.1412
1198 | L1 | PIPE INTEGRITY | L&R |  | TETHER | Quebec City | 2030-12-31 | 2030 | 200 | 4 | 2030-06-14 | low | low | low | high | high | 450000 | 447194 | 557595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 450000 | 159.9953 | EXPENSE | Yes | Unit outage | X | X |  | X |  | no | Yes | no | Yes | Yes | Yes | no | no | Yes | 2 | 4 | 1 | 5 | 3 | 3 | 3 | 4 |  | 62.5% | 6 | 5 | 1 | 1 | 1 | 4 |  | 48% | 5 |  | 10535.75
1199 | L3 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Saskatoon | 2026-05-31 | 2026 | 258 | 4 | 2025-09-15 | med | high | low | high | high | 6620000 | 6515868 | 6632189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1986000 | 3310000 | 1324000 | 0 | 0 | 6620000 | 33.0673 | CAPITAL | No | Station outage |  | X |  | X |  | no | no | Yes | Yes | no | Yes | no | Yes | Yes | 2 | 1 | 1 | 5 | 2 | 5 | 3 | 5 |  | 60% | 6 | 4 | 1 | 1 | 3 | 4 |  | 52% | 6 |  | 16059.78
1200 | L2 | PIPE INTEGRITY | L&R |  | TETHER | North Bay | 2029-11-30 | 2029 | 165 | 8 | 2029-06-18 | med | med | med | low | high | 850000 | 792844 | 805260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 425000 | 170000 | 0 | 0 | 850000 | 190.1713 | EXPENSE | No | Pipeline segment |  |  |  | X | X | Yes | no | no | no | no | Yes | no | no | no | 2 | 5 | 2 | 4 | 2 | 1 | 1 | 5 |  | 55% | 6 | 1 | 5 | 1 | 1 | 2 |  | 40% | 4 |  | 10182.17
1201 | L1 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Montreal | 2030-12-31 | 2030 | 320 | 8 | 2030-02-14 | med | med | high | low | high | 3500000 | 3705220 | 3754725 | 0 | 0 | 1050000 | 2100000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 42.5944 | CAPITAL | No | Station outage | X | X | X | X |  | Yes | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 3 | 1 | 5 | 2 | 5 | 1 | 1 |  | 52.5% | 6 | 4 | 1 | 1 | 4 | 2 |  | 48% | 5 |  | 2310.573
1202 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2026-12-31 | 2026 | 180 | 4 | 2026-07-04 | med | high | low | low | high | 400000 | 405834 | 452505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 98.3964 | EXPENSE | No | pipeline segment outage |  |  |  |  | X | no | Yes | Yes | Yes | no | no | no | Yes | no | 3 | 5 | 2 | 1 | 2 | 2 | 3 | 3 |  | 52.5% | 6 | 5 | 1 | 1 | 2 | 4 |  | 52% | 6 |  | 2369.828
1203 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | North Bay | 2026-12-31 | 2026 | 180 | 8 | 2026-07-04 | low | high | low | high | high | 350000 | 327934 | 382673 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 32.9463 | CAPITAL | No | pipeline segment outage | X | X |  |  |  | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 4 |  | 47.5% | 5 | 5 | 1 | 1 | 2 | 3 |  | 48% | 5 |  | 2480.625
1204 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2030-09-30 | 2030 | 120 | 7 | 2030-06-02 | med | low | high | high | high | 1900000 | 1977581 | 1989278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 950000 | 380000 | 1900000 | 94.5144 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | no | no | Yes | Yes | Yes | Yes | Yes | no | 3 | 2 | 4 | 3 | 4 | 2 | 4 | 1 |  | 57.5% | 6 | 2 | 4 | 1 | 5 | 5 |  | 68% | 7 |  | 2480.625
1205 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | North Bay | 2025-11-30 | 2025 | 120 | 4 | 2025-08-02 | med | high | low | low | med | 250000 | 252651 | 244871 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 0 | 0 | 0 | 0 | 250000 | 56.4922 | EXPENSE | No | NO |  |  | X | X |  | no | Yes | no | Yes | no | no | Yes | no | no | 3 | 1 | 1 | 3 | 3 | 1 | 4 | 4 |  | 50% | 5 | 3 | 5 | 1 | 5 | 2 |  | 64% | 7 |  | 31873.29
1206 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Winnipeg | 2030-03-31 | 2030 | 120 | 4 | 2029-12-01 | med | low | med | high | low | 250000 | 260869 | 306879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 125000 | 50000 | 250000 | 692.039 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X |  | no | Yes | Yes | Yes | Yes | Yes | no | no | no | 3 | 1 | 1 | 4 | 3 | 5 | 3 | 1 |  | 52.5% | 6 | 2 | 4 | 1 | 1 | 1 |  | 36% | 4 |  | 5521.373
1207 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Toronto | 2027-11-30 | 2027 | 180 | 4 | 2027-06-03 | high | high | med | med | med | 850000 | 850944 | 820000 | 0 | 0 | 0 | 255000 | 510000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 24.4354 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X |  | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 1 | 3 | 3 | 4 | 5 | 3 | 4 |  | 62.5% | 6 | 4 | 1 | 1 | 1 | 4 |  | 44% | 5 |  | 3220.812
1208 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2029-11-30 | 2029 | 230 | 15 | 2029-04-14 | low | high | med | high | high | 500000 | 530563 | 545236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 500000 | 60.5912 | CAPITAL | No | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 4 | 3 | 2 | 5 | 2 | 2 | 5 | 1 |  | 60% | 6 | 4 | 1 | 1 | 4 | 4 |  | 56% | 6 |  | 13659.19
1209 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Winnipeg | 2030-12-31 | 2030 | 100 | 5 | 2030-09-22 | med | med | med | low | low | 250000 | 276609 | 286072 | 75000 | 150000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 96.9233 | EXPENSE | Yes | NO | [5 empty] | Yes | no | Yes | Yes | Yes | no | no | Yes | no | 3 | 5 | 1 | 1 | 5 | 1 | 5 | 3 |  | 60% | 6 | 2 | 1 | 1 | 5 | 1 |  | 40% | 4 |  | 19639.87
1210 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Winnipeg | 2027-04-30 | 2027 | 150 | 8 | 2026-12-01 | high | low | high | med | med | 300000 | 469283 | 461267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 150000 | 60000 | 0 | 0 | 300000 | 143.1483 | EXPENSE | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 3 | 1 | 4 | 5 | 1 | 2 | 2 | 5 |  | 57.5% | 6 | 2 | 3 | 1 | 5 | 4 |  | 60% | 6 |  | 2166.583
1211 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2026-12-31 | 2026 | 120 | 8 | 2026-09-02 | high | med | high | med | high | 300000 | 296541 | 294310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 300000 | 86.2445 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | Yes | no | Yes | no | Yes | Yes | no | Yes | 2 | 4 | 1 | 2 | 1 | 2 | 2 | 5 |  | 47.5% | 5 | 1 | 5 | 1 | 5 | 4 |  | 64% | 7 |  | 1184.914
1212 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2026-09-30 | 2026 | 150 | 7 | 2026-05-03 | med | low | high | med | high | 2000000 | 2451951 | 2464009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1000000 | 400000 | 2000000 | 287.5273 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 4 |  | 50% | 5 | 1 | 3 | 1 | 1 | 2 |  | 32% | 4 |  | 1846.619
1213 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2027-04-30 | 2027 | 120 | 2 | 2026-12-31 | med | med | low | med | med | 350000 | 387958 | 348402 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 350000 | 338.5852 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 5 | 3 | 4 | 2 | 4 | 2 | 2 | 4 |  | 65% | 6 | 3 | 5 | 1 | 5 | 4 |  | 72% | 8 |  | 4522
1214 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Saskatoon | 2029-04-30 | 2029 | 180 | 8 | 2028-11-01 | low | high | high | low | low | 300000 | 303443 | 304754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 150000 | 60000 | 0 | 300000 | 122.9237 | EXPENSE | No | Pipeline segment |  |  | X |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 5 | 1 | 5 | 3 | 4 | 4 | 3 |  | 65% | 6 | 3 | 4 | 1 | 5 | 3 |  | 64% | 7 |  | 8429.71
1215 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2025-11-30 | 2025 | 120 | 8 | 2025-08-02 | low | high | med | low | high | 1750000 | 1822372 | 1853987 | 0 | 0 | 0 | 0 | 525000 | 1050000 | 175000 | 0 | 0 | 0 | 0 | 0 | 1750000 | 87.2637 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X | X | X | no | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 4 | 5 | 4 | 2 | 1 | 5 | 4 | 2 |  | 67.5% | 6 | 3 | 4 | 5 | 4 | 1 |  | 68% | 7 |  | 8756
1216 | L1 | PIPE INTEGRITY | Excavation | CORROSION | RECOAT | Winnipeg | 2030-09-30 | 2030 | 150 | 4 | 2030-05-03 | low | low | low | low | high | 350000 | 424886 | 436808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 350000 | 9.937 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | Yes | no | no | Yes | Yes | Yes | Yes | no | 3 | 4 | 3 | 2 | 4 | 5 | 3 | 4 |  | 70% | 6 | 1 | 4 | 1 | 4 | 4 |  | 56% | 6 |  | 52
1217 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Edmonton | 2027-08-31 | 2027 | 150 | 8 | 2027-04-03 | low | low | med | low | med | 300000 | 340748 | 344971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 150000 | 60000 | 0 | 0 | 300000 | 7.9241 | EXPENSE | No | Pipeline segment |  | X | X |  | X | no | no | no | Yes | no | no | no | Yes | no | 1 | 5 | 2 | 1 | 2 | 1 | 5 | 3 |  | 50% | 5 | 5 | 2 | 1 | 4 | 1 |  | 52% | 6 |  | 258
1218 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Quebec City | 2028-12-31 | 2028 | 120 | 4 | 2028-09-02 | low | med | high | high | med | 750000 | 741959 | 741361 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 375000 | 150000 | 0 | 0 | 0 | 750000 | 122.5762 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 5 | 4 | 2 | 5 | 2 | 2 | 1 | 5 |  | 65% | 6 | 2 | 3 | 1 | 4 | 1 |  | 44% | 5 |  | 4101.0339
1219 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | North Bay | 2026-03-31 | 2026 | 150 | 4 | 2025-11-01 | high | med | high | med | med | 350000 | 377958 | 378402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 60.2487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | Yes | Yes | no | Yes | 4 | 4 | 2 | 2 | 3 | 5 | 4 | 4 |  | 70% | 6 | 1 | 2 | 1 | 5 | 1 |  | 40% | 4 |  | 842.9817
1220 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Saskatoon | 2025-11-30 | 2025 | 200 | 2 | 2025-05-14 | low | med | low | low | med | 520000 | 520076 | 517552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156000 | 260000 | 104000 | 520000 | 339.8771 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 2 | 4 | 2 | 3 | 1 | 2 | 4 | 4 |  | 55% | 6 | 1 | 2 | 1 | 1 | 2 |  | 28% | 3 |  | 13420.4072
1221 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2029-04-30 | 2029 | 180 | 4 | 2028-11-01 | med | low | low | low | med | 750000 | 800359 | 808385 | 0 | 225000 | 375000 | 150000 | 0 | 0 | 0 | 0 | 225000 | 375000 | 150000 | 0 | 1500000 | 201.382 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | Yes | no | no | no | no | no | Yes | no | no | 3 | 2 | 2 | 3 | 1 | 2 | 4 | 5 |  | 55% | 6 | 5 | 1 | 1 | 5 | 2 |  | 56% | 6 |  | 1578
1222 | L1 | PIPE INTEGRITY | Excavation | DENT | RECOAT | Montreal | 2028-12-31 | 2028 | 200 | 5 | 2028-06-14 | high | med | low | high | med | 500000 | 580071 | 583077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 500000 | 339.2298 | EXPENSE | No | pipeline segment outage |  | X | X |  |  | no | Yes | no | Yes | no | Yes | no | no | no | 3 | 1 | 3 | 1 | 4 | 1 | 2 | 3 |  | 45% | 5 | 2 | 2 | 1 | 4 | 2 |  | 44% | 5 |  | 278.7236
1223 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Quebec City | 2030-03-31 | 2030 | 120 | 4 | 2029-12-01 | low | high | high | low | med | 125000 | 137635 | 149404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 75000 | 12500 | 0 | 125000 | 946.0832 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 5 | 3 | 3 | 1 | 5 | 3 | 2 | 5 |  | 67.5% | 6 | 1 | 2 | 1 | 2 | 2 |  | 32% | 4 |  | 278.7236
1224 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Regina | 2027-08-31 | 2027 | 120 | 8 | 2027-05-03 | med | med | high | med | low | 450000 | 522096 | 523817 | 135000 | 225000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 101.141 | CAPITAL | No | Pipeline segment |  | X |  | X |  | no | Yes | no | no | Yes | Yes | Yes | no | no | 5 | 2 | 1 | 5 | 5 | 4 | 4 | 5 |  | 77.5% | 8 | 5 | 4 | 1 | 5 | 3 |  | 72% | 8 |  | 203.1281
1225 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Toronto | 2025-06-30 | 2025 | 180 | 4 | 2025-01-01 | low | low | high | low | med | 550000 | 957635 | 1018992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 550000 | 105.7103 | EXPENSE | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 5 | 1 | 1 | 5 | 1 | 4 | 2 | 2 |  | 52.5% | 6 | 4 | 2 | 1 | 1 | 3 |  | 44% | 5 |  | 203.1281
1226 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2026-09-30 | 2026 | 180 | 8 | 2026-04-03 | high | low | low | low | low | 450000 | 407875 | 435270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 450000 | 80.7138 | CAPITAL | No | pipeline segment outage | X | X |  | X |  | no | Yes | no | Yes | no | Yes | no | Yes | no | 3 | 2 | 3 | 1 | 5 | 4 | 3 | 2 |  | 57.5% | 6 | 3 | 3 | 5 | 4 | 1 |  | 64% | 7 |  | 203.1281
1227 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2026-12-31 | 2026 | 120 | 4 | 2026-09-02 | med | low | med | med | med | 1000000 | 1021505 | 1092551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 56.5076 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | no | no | no | no | no | no | no | no | Yes | 5 | 4 | 3 | 5 | 1 | 4 | 2 | 4 |  | 70% | 6 | 3 | 4 | 5 | 3 | 5 |  | 80% | 8 |  | 853.1382
1228 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2028-09-30 | 2028 | 150 | 8 | 2028-05-03 | high | high | high | high | high | 350000 | 404631 | 406242 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 26.1799 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | Yes | no | no | no | Yes | no | Yes | Yes | 4 | 3 | 4 | 3 | 3 | 3 | 1 | 2 |  | 57.5% | 6 | 3 | 2 | 1 | 1 | 2 |  | 36% | 4 |  | 746.1723
1229 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Montreal | 2026-12-31 | 2026 | 200 | 4 | 2026-06-14 | med | med | med | low | low | 500000 | 571069 | 578420 | 150000 | 250000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 20.7067 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | no | no | no | no | Yes | Yes | Yes | 4 | 1 | 1 | 3 | 1 | 1 | 2 | 2 |  | 37.5% | 4 | 2 | 4 | 1 | 1 | 2 |  | 40% | 4 |  | 1174.9707
1230 | L1 | PIPE INTEGRITY | Excavation | SCC | RECOAT | Ottawa | 2025-11-30 | 2025 | 85 | 4 | 2025-09-06 | low | high | low | high | low | 400000 | 574072 | 556987 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 133.3009 | EXPENSE | No | Station outage | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | Yes | no | Yes | 1 | 3 | 1 | 4 | 5 | 3 | 2 | 1 |  | 50% | 5 | 5 | 1 | 1 | 2 | 4 |  | 52% | 6 |  | 16021.8416
1231 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2026-05-31 | 2026 | 150 | 15 | 2026-01-01 | high | med | med | low | low | 450000 | 836197 | 864086 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 65.7764 | CAPITAL | No | Pipeline segment | X | X | X |  | X | Yes | Yes | no | no | no | no | Yes | Yes | Yes | 2 | 2 | 4 | 4 | 2 | 2 | 5 | 5 |  | 65% | 6 | 4 | 5 | 5 | 1 | 3 |  | 72% | 8 |  | 7007.9205
1232 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | North Bay | 2027-11-30 | 2027 | 100 | 2 | 2027-08-22 | med | med | high | med | low | 350000 | 331626 | 366466 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 350000 | 618.2189 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | Yes | no | Yes | Yes | Yes | no | no | no | Yes | 2 | 4 | 4 | 4 | 2 | 5 | 1 | 5 |  | 67.5% | 6 | 5 | 5 | 5 | 1 | 4 |  | 80% | 8 |  | 1685.9635
1233 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | North Bay | 2025-09-30 | 2025 | 100 | 2 | 2025-06-22 | high | med | high | med | high | 125000 | 205456 | 208103 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 62500 | 25000 | 0 | 0 | 0 | 125000 | 713.9495 | EXPENSE | Yes | NO |  | X |  |  |  | Yes | Yes | no | no | Yes | Yes | no | Yes | no | 2 | 1 | 3 | 2 | 5 | 2 | 3 | 1 |  | 47.5% | 5 | 2 | 3 | 1 | 2 | 1 |  | 36% | 4 |  | 121.8769
1234 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2030-09-30 | 2030 | 120 | 7 | 2030-06-02 | low | med | med | high | high | 1500000 | 1460980 | 1558652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 1500000 | 152.9836 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | Yes | no | Yes | Yes | Yes | no | 5 | 5 | 3 | 1 | 3 | 4 | 1 | 1 |  | 57.5% | 6 | 2 | 2 | 1 | 5 | 5 |  | 60% | 6 |  | 267.7598
1235 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2028-12-31 | 2028 | 120 | 2 | 2028-09-02 | high | med | low | med | high | 520000 | 590076 | 591552 | 0 | 156000 | 260000 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 500.6594 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 1 | 1 | 4 | 2 | 5 | 4 | 4 | 1 |  | 55% | 6 | 2 | 2 | 1 | 5 | 4 |  | 56% | 6 |  | 267.7598
1236 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Montreal | 2026-11-30 | 2026 | 100 | 5 | 2026-08-22 | low | high | med | low | low | 800000 | 817249 | 857404 | 0 | 0 | 8500 | 0 | 8500 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 116.0893 | EXPENSE | Yes | NO outage |  | X |  | X | X | no | no | no | no | Yes | Yes | no | Yes | Yes | 3 | 1 | 4 | 3 | 5 | 3 | 5 | 1 |  | 62.5% | 6 | 5 | 2 | 1 | 2 | 1 |  | 44% | 5 |  | 267.7598
1237 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2027-08-31 | 2027 | 150 | 5 | 2027-04-03 | med | low | low | med | med | 400000 | 406220 | 406135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 33.5343 | CAPITAL | Yes | Pipeline segment | X | X | X | X |  | no | no | Yes | no | Yes | no | Yes | no | Yes | 1 | 2 | 4 | 4 | 4 | 4 | 2 | 5 |  | 65% | 6 | 3 | 3 | 1 | 1 | 4 |  | 48% | 5 |  | 17599.3754
1238 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Winnipeg | 2026-05-31 | 2026 | 200 | 15 | 2025-11-12 | med | low | low | high | med | 500000 | 513676 | 518168 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 0 | 0 | 500000 | 511.7996 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 5 | 5 | 4 | 3 | 5 | 2 | 3 | 1 |  | 70% | 6 | 1 | 3 | 1 | 1 | 3 |  | 36% | 4 |  | 7024.2246
1239 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2025-11-30 | 2025 | 200 | 8 | 2025-05-14 | low | low | med | med | med | 500000 | 501921 | 501943 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 500000 | 47.5442 | EXPENSE | No | Pipeline segment | X |  |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 5 | 2 | 3 | 3 | 3 | 4 | 4 |  | 67.5% | 6 | 1 | 4 | 1 | 4 | 2 |  | 48% | 5 |  | 1591.1704
1240 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2028-09-30 | 2028 | 120 | 7 | 2028-06-02 | low | high | low | low | high | 1900000 | 1900004 | 1908751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 950000 | 380000 | 0 | 0 | 1900000 | 44.5632 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  | X |  | Yes | Yes | no | no | no | no | no | no | Yes | 2 | 3 | 2 | 4 | 2 | 1 | 1 | 5 |  | 50% | 5 | 3 | 1 | 1 | 4 | 3 |  | 48% | 5 |  | 6832.4917
1241 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | North Bay | 2027-08-31 | 2025 | 194 | 10 | 2027-02-18 | low | high | low | med | low | 350000 | 835683 | 830953 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 350000 | 55.3744 | CAPITAL | No | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | Yes | no | Yes | no | 4 | 2 | 2 | 4 | 3 | 5 | 3 | 3 |  | 65% | 6 | 4 | 1 | 1 | 5 | 5 |  | 64% | 7 |  | 330
1242 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | North Bay | 2029-04-30 | 2029 | 185 | 8 | 2028-10-27 | high | med | high | high | low | 450000 | 479835 | 487417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 225000 | 90000 | 0 | 450000 | 412.8922 | CAPITAL | No | pipeline segment outage | X |  |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 3 | 3 | 2 | 4 | 2 | 5 | 1 | 1 |  | 52.5% | 6 | 3 | 1 | 1 | 3 | 4 |  | 48% | 5 |  | 5845
1243 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2026-09-30 | 2026 | 85 | 5 | 2026-07-07 | low | med | low | high | med | 350000 | 406595 | 482491 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 350000 | 284.7276 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 2 | 2 | 2 | 5 | 2 | 4 | 5 | 2 |  | 60% | 6 | 2 | 3 | 1 | 5 | 1 |  | 48% | 5 |  | 3077.9635
1244 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2028-04-30 | 2028 | 180 | 10 | 2027-11-02 | high | med | low | high | high | 350000 | 379453 | 378408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 350000 | 58.7845 | CAPITAL | No | Pipeline segment |  |  | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 1 | 4 | 3 | 1 | 5 | 2 | 3 |  | 55% | 6 | 2 | 4 | 1 | 5 | 5 |  | 68% | 7 |  | 13582.277
1245 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2027-08-31 | 2027 | 200 | 8 | 2027-02-12 | low | low | low | high | high | 500000 | 682395 | 696748 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 150000 | 300000 | 50000 | 1000000 | 22.5065 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | no | no | no | Yes | no | no | no | Yes | 5 | 5 | 3 | 5 | 4 | 5 | 4 | 4 |  | 87.5% | 9 | 2 | 1 | 1 | 1 | 5 |  | 40% | 4 |  | 7709.8457
1246 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2027-08-31 | 2027 | 150 | 8 | 2027-04-03 | high | med | med | high | med | 350000 | 318965 | 339197 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 71.4985 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 2 | 2 | 2 | 3 | 2 | 3 | 5 | 2 |  | 52.5% | 6 | 3 | 2 | 1 | 5 | 2 |  | 52% | 6 |  | 7110.0938
1247 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Saskatoon | 2029-11-30 | 2029 | 180 | 8 | 2029-06-03 | high | low | med | med | high | 300000 | 805802 | 891083 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 0 | 0 | 0 | 0 | 300000 | 36.3611 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | no | Yes | no | no | Yes | no | no | Yes | no | 1 | 1 | 2 | 5 | 2 | 5 | 3 | 4 |  | 57.5% | 6 | 5 | 4 | 5 | 3 | 2 |  | 76% | 8 |  | 4314.1949
1248 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2028-04-30 | 2028 | 180 | 2 | 2027-11-02 | low | low | low | high | low | 350000 | 482300 | 486971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 350000 | 593.4244 | EXPENSE | No | Pipeline segment | X | X | X |  | X | no | no | Yes | no | no | no | Yes | Yes | Yes | 3 | 2 | 1 | 1 | 2 | 1 | 4 | 4 |  | 45% | 5 | 4 | 2 | 1 | 2 | 4 |  | 52% | 6 |  | 4858.8867
1249 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2030-09-30 | 2030 | 180 | 8 | 2030-04-03 | med | med | med | low | med | 350000 | 444414 | 440670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 350000 | 101.6158 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 3 | 3 | 4 | 1 | 2 | 2 | 3 | 1 |  | 47.5% | 5 | 5 | 5 | 1 | 1 | 3 |  | 60% | 6 |  | 2178.0735
1250 | L1 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2026-12-31 | 2026 | 150 | 7 | 2026-08-03 | high | low | high | low | high | 750000 | 875896 | 878514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 375000 | 150000 | 750000 | 24.8857 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  |  | no | Yes | no | Yes | no | no | no | no | Yes | 2 | 4 | 2 | 5 | 2 | 1 | 2 | 2 |  | 50% | 5 | 4 | 2 | 5 | 1 | 3 |  | 60% | 6 |  | 1090.5382
1251 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Regina | 2027-11-30 | 2027 | 180 | 15 | 2027-06-03 | high | high | med | high | high | 450000 | 428046 | 421693 | 0 | 135000 | 225000 | 90000 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 850000 | 82.8772 | CAPITAL | No | Pipeline segment |  | X |  | X | X | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 1 | 1 | 1 | 5 | 3 | 3 | 4 | 5 |  | 57.5% | 6 | 2 | 3 | 1 | 3 | 5 |  | 56% | 6 |  | 4052.0846
1252 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Edmonton | 2027-11-30 | 2027 | 100 | 7 | 2027-08-22 | med | med | med | low | low | 2000000 | 2054742 | 2048761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 2000000 | 57.9714 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 3 | 2 | 4 | 4 | 1 | 1 | 2 | 2 |  | 47.5% | 5 | 4 | 5 | 5 | 1 | 4 |  | 76% | 8 |  | 2610.3898
1253 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2025-06-30 | 2025 | 180 | 10 | 2025-01-01 | high | med | low | low | low | 350000 | 379854 | 356546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 350000 | 25.9626 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 3 | 1 | 2 | 1 | 5 | 2 | 1 | 2 |  | 42.5% | 5 | 2 | 4 | 1 | 3 | 3 |  | 52% | 6 |  | 241.5599
1254 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2030-03-31 | 2030 | 180 | 8 | 2029-10-02 | med | med | low | med | med | 350000 | 410000 | 410045 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 350000 | 183.6307 | EXPENSE | Yes | Pipeline segment |  |  | X |  |  | no | no | Yes | Yes | no | Yes | no | Yes | no | 3 | 4 | 4 | 1 | 2 | 4 | 4 | 1 |  | 57.5% | 6 | 2 | 1 | 1 | 1 | 1 |  | 24% | 3 |  | 4995.3897
1255 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | WINNIPEG | 2028-12-31 | 2028 | 180 | 8 | 2028-07-04 | low | med | high | med | low | 350000 | 818560 | 807036 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 0 | 350000 | 31.5417 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 4 | 3 | 2 | 4 | 5 | 2 | 1 | 5 |  | 65% | 6 | 5 | 2 | 1 | 1 | 4 |  | 52% | 6 |  | 6993.5456
1256 | L2 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Regina | 2027-04-30 | 2027 | 120 | 10 | 2026-12-31 | high | high | med | low | high | 750000 | 745189 | 786550 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 300000 | 375000 | 0 | 0 | 0 | 750000 | 57.545 | EXPENSE | No | NO outage | X |  | X |  | X | Yes | Yes | Yes | no | no | no | no | no | no | 2 | 1 | 2 | 2 | 5 | 4 | 4 | 4 |  | 60% | 6 | 5 | 3 | 1 | 2 | 1 |  | 48% | 5 |  | 840.2082
1257 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2025-06-30 | 2025 | 85 | 7 | 2025-04-06 | low | med | high | med | med | 2000000 | 1758655 | 1869566 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 0 | 2000000 | 383.6846 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | no | no | Yes | Yes | Yes | no | 3 | 2 | 2 | 3 | 5 | 3 | 2 | 5 |  | 62.5% | 6 | 2 | 2 | 1 | 3 | 5 |  | 52% | 6 |  | 5000
1258 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2025-09-30 | 2025 | 170 | 2 | 2025-04-13 | high | med | med | med | high | 350000 | 441828 | 446179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 350000 | 16.1628 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X | X | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 4 | 5 | 1 | 4 | 5 | 4 | 5 | 2 |  | 75% | 8 | 2 | 3 | 1 | 4 | 1 |  | 44% | 5 |  | 646
1259 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2030-09-30 | 2030 | 168 | 4 | 2030-04-15 | med | high | high | med | low | 1800000 | 1909884 | 1937687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 1800000 | 97.7988 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | no | no | Yes | no | no | no | no | no | Yes | 2 | 2 | 3 | 4 | 4 | 3 | 4 | 2 |  | 60% | 6 | 4 | 5 | 1 | 4 | 3 |  | 68% | 7 |  | 289
1260 | L1 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Quebec City | 2025-09-30 | 2025 | 245 | 20 | 2025-01-28 | med | low | low | med | med | 28550000 | 28506803 | 28740397 | 0 | 0 | 0 | 0 | 0 | 0 | 8565000 | 14275000 | 5710000 | 0 | 0 | 0 | 28550000 | 96.8203 | CAPITAL | No | pipeline segment outage | X |  | X | X | X | Yes | no | no | no | Yes | Yes | Yes | Yes | no | 3 | 5 | 3 | 1 | 4 | 1 | 5 | 5 |  | 67.5% | 6 | 5 | 5 | 1 | 2 | 5 |  | 72% | 8 |  | 347
1261 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2025-11-30 | 2025 | 85 | 4 | 2025-09-06 | med | med | low | high | low | 1500000 | 1871375 | 1900437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 1500000 | 20.7353 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X | X | Yes | no | Yes | Yes | no | Yes | Yes | no | Yes | 4 | 3 | 4 | 2 | 3 | 3 | 4 | 1 |  | 60% | 6 | 4 | 4 | 1 | 2 | 2 |  | 52% | 6 |  | 158885
1262 | L3 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | North Bay | 2027-08-31 | 2027 | 285 | 25 | 2026-11-19 | med | high | med | high | med | 1405000 | 15158244 | 15509480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421500 | 702500 | 281000 | 1405000 | 80.1164 | CAPITAL | Yes | pipeline segment outage | X |  |  | X | X | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 1 | 2 | 2 | 3 | 2 | 3 | 5 | 4 |  | 55% | 6 | 4 | 2 | 1 | 5 | 5 |  | 68% | 7 |  | 1785
1263 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Montreal | 2030-03-31 | 2030 | 208 | 15 | 2029-09-04 | med | low | low | high | high | 750000 | 1164753 | 1662254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 750000 | 91.2063 | EXPENSE | No | Pipeline segment |  |  | X |  |  | no | Yes | Yes | no | Yes | no | Yes | no | no | 4 | 1 | 3 | 3 | 4 | 3 | 4 | 3 |  | 62.5% | 6 | 3 | 5 | 1 | 2 | 1 |  | 48% | 5 |  | 898
1264 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Edmonton | 2025-11-30 | 2025 | 60 | 15 | 2025-10-01 | high | high | low | med | med | 850000 | 827077 | 841856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 425000 | 170000 | 850000 | 80.7922 | EXPENSE | Yes | pipeline segment outage |  |  | X |  | X | no | Yes | Yes | no | Yes | Yes | Yes | no | Yes | 3 | 2 | 1 | 5 | 3 | 3 | 1 | 1 |  | 47.5% | 5 | 3 | 5 | 1 | 5 | 1 |  | 60% | 6 |  | 172.2548
1265 | L1 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Montreal | 2026-12-31 | 2026 | 180 | 8 | 2026-07-04 | med | med | high | low | med | 1000000 | 1022203 | 1280954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 600000 | 100000 | 0 | 0 | 1000000 | 44.865 | EXPENSE | No | NO outage |  | X | X | X |  | Yes | Yes | no | no | Yes | no | no | no | no | 5 | 2 | 1 | 4 | 4 | 2 | 1 | 5 |  | 60% | 6 | 2 | 5 | 1 | 2 | 3 |  | 52% | 6 |  | 172.2548
1266 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2026-03-31 | 2026 | 150 | 5 | 2025-11-01 | med | high | high | high | high | 400000 | 434790 | 444911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 114.2737 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 5 | 2 | 2 | 5 | 5 | 2 | 5 | 2 |  | 70% | 6 | 2 | 3 | 1 | 2 | 1 |  | 36% | 4 |  | 382.7885
1267 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Regina | 2029-11-30 | 2029 | 85 | 2 | 2029-09-06 | med | med | med | high | med | 650000 | 655557 | 668033 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 0 | 0 | 0 | 650000 | 224.9398 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | Yes | no | 1 | 1 | 3 | 2 | 5 | 3 | 1 | 5 |  | 52.5% | 6 | 1 | 1 | 1 | 3 | 2 |  | 32% | 4 |  | 173.2929
1268 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | North Bay | 2025-06-30 | 2025 | 180 | 2 | 2025-01-01 | low | med | high | high | med | 950000 | 1089229 | 1080770 | 0 | 285000 | 475000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 128.235 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | Yes | no | Yes | Yes | Yes | 4 | 4 | 3 | 5 | 4 | 2 | 1 | 4 |  | 67.5% | 6 | 3 | 2 | 1 | 1 | 3 |  | 40% | 4 |  | 900.2043
1269 | L2 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Winnipeg | 2026-05-31 | 2026 | 287 | 15 | 2025-08-17 | low | med | high | med | high | 6870000 | 6877100 | 7401079 | 0 | 0 | 0 | 0 | 0 | 0 | 2061000 | 4122000 | 687000 | 0 | 0 | 0 | 6870000 | 369.6154 | CAPITAL | Yes | pipeline segment outage | X | X |  |  | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 5 | 5 | 3 | 4 | 4 | 5 | 5 | 5 |  | 90% | 9 | 2 | 4 | 1 | 1 | 5 |  | 52% | 6 |  | 749.7244
1270 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2025-09-30 | 2025 | 150 | 4 | 2025-05-03 | med | high | high | low | high | 400000 | 458461 | 454334 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 125.3264 | EXPENSE | No | Pipeline segment | X |  | X |  | X | no | Yes | no | Yes | no | Yes | no | Yes | no | 5 | 4 | 3 | 3 | 4 | 4 | 2 | 3 |  | 70% | 6 | 5 | 3 | 1 | 5 | 4 |  | 72% | 8 |  | 1022.4116
1271 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | Montreal | 2028-08-31 | 2028 | 150 | 4 | 2028-04-03 | med | high | high | high | high | 250000 | 285616 | 285266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 0 | 250000 | 68.1605 | EXPENSE | No | NO |  |  | X |  | X | no | no | no | Yes | no | Yes | Yes | no | no | 2 | 1 | 4 | 5 | 3 | 5 | 2 | 3 |  | 62.5% | 6 | 5 | 4 | 5 | 4 | 2 |  | 80% | 8 |  | 458
1272 | L1 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Ottawa | 2027-09-30 | 2028 | 226 | 15 | 2027-02-16 | low | low | high | med | low | 9400000 | 19427475 | 9354713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2820000 | 5640000 | 940000 | 0 | 0 | 9400000 | 89.0006 | CAPITAL | No | pipeline segment outage | X |  | X | X |  | Yes | Yes | Yes | no | Yes | no | no | no | no | 3 | 5 | 2 | 5 | 1 | 2 | 4 | 1 |  | 57.5% | 6 | 3 | 4 | 1 | 1 | 2 |  | 44% | 5 |  | 425
1273 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Quebec City | 2025-06-30 | 2025 | 130 | 4 | 2025-02-20 | med | med | med | high | low | 600000 | 757099 | 785103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 300000 | 120000 | 600000 | 484.7808 | CAPITAL | No | Derate/low flow Pipe segment |  |  |  | X |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 2 | 5 | 2 | 2 | 2 | 1 | 4 | 5 |  | 57.5% | 6 | 4 | 2 | 1 | 1 | 2 |  | 40% | 4 |  | 4447
1274 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Montreal | 2025-11-30 | 2025 | 100 | 6 | 2025-08-22 | high | high | med | high | low | 1750000 | 1770877 | 1780700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 1050000 | 175000 | 0 | 0 | 1750000 | 91.2089 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | no | 3 | 1 | 4 | 4 | 3 | 5 | 4 | 4 |  | 70% | 6 | 4 | 5 | 5 | 4 | 5 |  | 92% | 10 |  | 20000
1275 | L3 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Quebec City | 2026-03-31 | 2026 | 200 | 4 | 2025-09-12 | med | high | med | high | high | 1500000 | 1500982 | 1500604 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 750000 | 300000 | 0 | 0 | 0 | 1500000 | 7.9794 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | Yes | Yes | no | no | Yes | no | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 22.22% | 3 | 2 | 1 | 1 | 5 | 2 | 4 | 50% | 5 |  | 8501.429
1275 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Quebec City | 2026-12-31 | 2026 | 275 | 4 | 2026-03-31 | med | high | med | high | high | 1500000 | 1500982 | 1500604 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 1500000 | 7.9794 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | Yes | Yes | no | no | Yes | no | 2 | 4 | 2 | 1 | 4 | 2 | 5 | 5 |  | 62.5% | 6 | 3 | 1 | 1 | 3 | 5 |  | 52% | 6 |  | 2078
1276 | L2 | PIPE INTEGRITY | ILI | SCC | EMAT INSPECTION RUN | Ottawa | 2028-07-31 | 2028 | 120 | 2 | 2028-04-02 | med | low | high | high | high | 1000000 | 1200000 | 1281639 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 500000 | 200000 | 0 | 0 | 0 | 1000000 | 8.2654 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  |  | X | no | no | no | Yes | no | Yes | Yes | no | Yes | 4 | 1 | 3 | 1 | 3 | 1 | 3 | 5 | 1 | 48.89% | 5 | 4 | 2 | 5 | 4 | 1 | 3 | 63.33% | 7 |  | 382.7885
1276 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2029-11-30 | 2029 | 150 | 5 | 2029-07-03 | med | low | med | low | med | 350000 | 363583 | 359590 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 32.0854 | CAPITAL | No | Pipeline segment |  |  | X | X |  | no | Yes | no | no | Yes | no | Yes | no | no | 3 | 2 | 4 | 3 | 1 | 3 | 3 | 4 |  | 57.5% | 6 | 3 | 5 | 1 | 3 | 1 |  | 52% | 6 |  | 1875
1277 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2025-06-30 | 2025 | 120 | 12 | 2025-03-02 | low | med | high | high | high | 450000 | 483200 | 482753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 123.3918 | CAPITAL | No | Pipeline segment |  | X |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 3 | 5 | 2 | 5 | 4 | 4 | 1 | 5 |  | 72.5% | 8 | 3 | 5 | 1 | 4 | 5 |  | 72% | 8 |  | 7718.869
1278 | L1 | FACILITY | MECHANICAL |  | EXHAUST STACK | Toronto | 2025-12-31 | 2025 | 205 | 4 | 2025-06-09 | med | med | high | med | med | 1600000 | 1584716 | 1488477 | 0 | 0 | 0 | 0 | 480000 | 960000 | 160000 | 0 | 0 | 0 | 0 | 0 | 1600000 | 19.4031 | CAPITAL | No | Station outage | X | X | X | X |  | no | no | no | Yes | no | Yes | Yes | no | no | 3 | 5 | 5 | 5 | 1 | 2 | 1 | 4 | 4 | 66.67% | 7 | 4 | 4 | 1 | 3 | 2 | 4 | 60% | 6 |  | 4785
1278 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2025-11-30 | 2025 | 180 | 4 | 2025-06-03 | high | high | low | low | high | 1750000 | 1708182 | 1716547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 45.4478 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 2 | 2 | 4 | 5 | 4 | 4 | 3 | 1 |  | 62.5% | 6 | 5 | 1 | 1 | 2 | 2 |  | 44% | 5 |  | 7718.869
1279 | L3 | FACILITY | MECHANICAL |  | EXHAUST STACK | Ottawa | 2026-03-31 | 2026 | 60 | 3 | 2026-01-30 | high | low | high | med | med | 1700000 | 1669590 | 1692140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 1020000 | 170000 | 1700000 | 214.7122 | EXPENSE | Yes | Unit outage |  |  | X |  | X | Yes | Yes | no | no | Yes | no | no | no | Yes | 1 | 3 | 2 | 2 | 1 | 5 | 4 | 3 | 1 | 48.89% | 5 | 5 | 4 | 5 | 4 | 3 | 4 | 83.33% | 9 |  | 258
1280 | L1 | FACILITY | MECHANICAL |  | EXHAUST STACK | Quebec City | 2026-10-31 | 2026 | 250 | 2 | 2026-02-23 | med | low | low | high | med | 1000000 | 1245237 | 122188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 158.2455 | CAPITAL | Yes | Station outage | X | X | X | X |  | Yes | no | Yes | Yes | Yes | Yes | no | no | no | 4 | 3 | 4 | 2 | 4 | 5 | 1 | 4 | 3 | 66.67% | 7 | 1 | 2 | 1 | 3 | 4 | 4 | 50% | 5 |  | 3981.0002
1279 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2026-03-31 | 2026 | 120 | 2 | 2025-12-01 | high | high | high | low | high | 300000 | 378545 | 398478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 180000 | 30000 | 300000 | 311.1133 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X | X | X | no | no | no | Yes | Yes | no | no | Yes | no | 5 | 5 | 2 | 5 | 5 | 2 | 5 | 4 |  | 82.5% | 9 | 4 | 4 | 5 | 5 | 5 |  | 92% | 10 |  | 6993.5456
1280 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Saskatoon | 2030-09-30 | 2030 | 180 | 8 | 2030-04-03 | high | low | high | low | high | 750000 | 855692 | 855145 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 139.156 | EXPENSE | Yes | NO outage |  | X | X |  | X | Yes | Yes | no | no | no | Yes | no | no | Yes | 3 | 5 | 3 | 3 | 2 | 4 | 2 | 2 |  | 60% | 6 | 4 | 1 | 1 | 1 | 5 |  | 48% | 5 |  | 636.4681
1281 | L3 | FACILITY | AUTOMATION & CONTROLS |  | FIRE DETECTOR UPGRAGE | North Bay | 2027-03-31 | 2027 | 271 | 1 | 2026-07-03 | med | med | low | med | low | 55000 | 52000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 33000 | 5500 | 55000 | 15603.7999 | EXPENSE | Yes | Unit outage |  | X | X |  |  | Yes | no | Yes | no | no | no | no | no | Yes | 1 | 3 | 3 | 1 | 5 | 3 | 4 | 1 | 1 | 48.89% | 5 | 4 | 1 | 1 | 5 | 1 | 3 | 50% | 5 |  | 2480.625
1281 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Edmonton | 2030-03-31 | 2030 | 150 | 4 | 2029-11-01 | med | low | high | low | med | 400000 | 560984 | 561355 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 83.4126 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | no | no | no | Yes | Yes | Yes | Yes | no | Yes | 1 | 2 | 4 | 4 | 2 | 2 | 5 | 5 |  | 62.5% | 6 | 2 | 3 | 1 | 1 | 1 |  | 32% | 4 |  | 25393.3666
1282 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Regina | 2029-11-30 | 2029 | 100 | 4 | 2029-08-22 | med | low | low | low | med | 1800000 | 1825733 | 1857547 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 76.4961 | EXPENSE | No | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 2 | 4 | 3 | 2 | 3 | 4 | 5 | 5 |  | 70% | 6 | 3 | 2 | 1 | 2 | 5 |  | 52% | 6 |  | 2369.8282
1283 | L2 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Saskatoon | 2027-11-30 | 2027 | 100 | 4 | 2027-08-22 | high | high | med | med | high | 425000 | 662668 | 637944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 32.9243 | EXPENSE | Yes | pipeline segment outage | X | X | X |  | X | no | Yes | Yes | no | Yes | no | no | no | no | 2 | 4 | 3 | 4 | 4 | 5 | 5 | 4 |  | 77.5% | 8 | 5 | 4 | 1 | 5 | 1 |  | 64% | 7 |  | 2369.8282
1284 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Saskatoon | 2027-11-30 | 2027 | 100 | 8 | 2027-08-22 | low | low | med | high | med | 1800000 | 1875000 | 1830883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 0 | 1800000 | 49.4725 | EXPENSE | No | pipeline segment outage |  |  |  | X |  | no | no | no | Yes | Yes | Yes | Yes | no | no | 5 | 4 | 2 | 4 | 3 | 2 | 5 | 3 |  | 70% | 6 | 1 | 2 | 1 | 3 | 4 |  | 44% | 5 |  | 3138.8656
1285 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Quebec City | 2028-09-30 | 2028 | 100 | 2 | 2028-06-22 | med | med | high | med | high | 520000 | 686253 | 671492 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 34.7089 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 3 | 3 | 3 | 4 | 5 | 3 | 1 |  | 67.5% | 6 | 2 | 4 | 1 | 1 | 2 |  | 40% | 4 |  | 3138.8656
1286 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2027-08-31 | 2027 | 200 | 4 | 2027-02-12 | med | med | high | med | high | 1000000 | 1649706 | 1663088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 600000 | 100000 | 0 | 1000000 | 96.0767 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X | X | no | Yes | no | no | Yes | Yes | no | no | no | 1 | 2 | 1 | 5 | 3 | 4 | 3 | 2 |  | 52.5% | 6 | 2 | 4 | 1 | 5 | 2 |  | 56% | 6 |  | 14928.9944
1287 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2026-09-30 | 2026 | 150 | 5 | 2026-05-03 | med | low | med | med | low | 400000 | 850000 | 895000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 24.5147 | EXPENSE | No | Pipeline segment |  | X |  | X |  | no | no | no | no | no | no | Yes | Yes | no | 1 | 2 | 3 | 3 | 5 | 3 | 5 | 4 |  | 65% | 6 | 2 | 4 | 1 | 2 | 5 |  | 56% | 6 |  | 4487
1288 | L2 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Edmonton | 2029-04-30 | 2029 | 120 | 8 | 2028-12-31 | low | high | med | high | low | 3200000 | 3281295 | 3570817 | 0 | 0 | 0 | 0 | 0 | 0 | 960000 | 1920000 | 320000 | 0 | 0 | 0 | 3200000 | 714.4143 | EXPENSE | No | pipeline segment outage | X |  | X |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 1 | 1 | 1 | 1 | 4 | 1 | 4 | 1 |  | 35% | 4 | 1 | 4 | 1 | 5 | 5 |  | 64% | 7 |  | 477.3811
1289 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2026-12-31 | 2026 | 150 | 2 | 2026-08-03 | high | low | low | low | med | 350000 | 378827 | 442990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 523.2809 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | no | 5 | 4 | 2 | 5 | 3 | 3 | 3 | 2 |  | 67.5% | 6 | 2 | 2 | 1 | 4 | 2 |  | 44% | 5 |  | 5347.325
1290 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2029-08-31 | 2029 | 150 | 6 | 2029-04-03 | med | low | high | high | high | 1000000 | 1200000 | 1281639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 500000 | 200000 | 1000000 | 8.2654 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  |  | X | no | no | no | Yes | no | Yes | Yes | no | Yes | 5 | 3 | 3 | 1 | 3 | 4 | 1 | 2 |  | 55% | 6 | 4 | 4 | 1 | 1 | 1 |  | 44% | 5 |  | 2679.5194
1291 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Winnipeg | 2029-04-30 | 2029 | 150 | 8 | 2028-12-01 | high | high | med | med | low | 1300000 | 1324785 | 1350260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 780000 | 130000 | 0 | 0 | 1300000 | 2123.4281 | EXPENSE | Yes | pipeline segment outage | X |  |  |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | no | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 20% | 2 | 1 | 1 | 1 | 1 | 1 |  | 20% | 2 |  | 2679.5194
1292 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2028-12-31 | 2028 | 150 | 6 | 2028-08-03 | med | high | med | med | low | 1800000 | 1817708 | 1891840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 73.0943 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 4 | 1 | 3 | 2 | 1 | 4 | 3 |  | 50% | 5 | 1 | 4 | 1 | 5 | 3 |  | 56% | 6 |  | 1072.7658
1293 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2025-09-30 | 2025 | 150 | 8 | 2025-05-03 | low | low | low | low | high | 350000 | 371048 | 377414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 350000 | 41.8408 | CAPITAL | No | Pipeline segment | X |  | X | X | X | no | Yes | Yes | Yes | Yes | no | no | no | no | 3 | 3 | 2 | 3 | 3 | 1 | 1 | 2 |  | 45% | 5 | 2 | 2 | 1 | 5 | 3 |  | 52% | 6 |  | 3333.1342
1294 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2026-03-31 | 2026 | 150 | 4 | 2025-11-01 | high | low | low | high | low | 350000 | 901807 | 925115 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 243.4001 | EXPENSE | No | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 5 | 2 | 5 | 5 | 2 | 5 | 1 |  | 70% | 6 | 5 | 3 | 1 | 4 | 4 |  | 68% | 7 |  | 1300.7103
1295 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2027-08-31 | 2027 | 150 | 8 | 2027-04-03 | med | high | low | low | low | 2000000 | 2534662 | 2571775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 2000000 | 87.159 | EXPENSE | Yes | Derate/low flow Pipe segment | x | x | x | x | x | NR | x | x | x | x | x |  | No | Yes | 2 | 2 | 3 | 2 | 1 | 1 | 5 | 5 |  | 52.5% | 6 | 3 | 4 | 1 | 3 | 1 |  | 48% | 5 |  | 76225.6763
1296 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Montreal | 2027-08-31 | 2027 | 120 | 2 | 2027-05-03 | med | high | high | med | high | 190000 | 196187 | 197468 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 40.7081 | EXPENSE | No | NO |  |  | x | x | x |  | x | x | x | [5 empty] | 3 | 5 | 4 | 2 | 1 | 3 | 5 | 1 |  | 60% | 6 | 4 | 2 | 1 | 3 | 3 |  | 52% | 6 |  | 16.9273
1297 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | North Bay | 2025-09-30 | 2025 | 250 | 8 | 2025-01-23 | low | high | med | high | med | 750000 | 611769 | 669250 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 85.7283 | EXPENSE | Yes | Pipeline segment | x | x | x | x | x | Yes | x | NR | NR | NR | NR | NR | No | Yes | 3 | 5 | 2 | 4 | 2 | 2 | 3 | 2 |  | 57.5% | 6 | 4 | 5 | 5 | 4 | 3 |  | 84% | 9 |  | 16.9273
1298 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2026-05-31 | 2026 | 315 | 4 | 2025-07-20 | high | med | med | high | low | 650000 | 888878 | 879764 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 65.902 | EXPENSE | Yes | Derate/low flow Pipe segment | x | x | x | x | x | Yes | x | x | Yes | Yes | Yes |  | No | No | 5 | 5 | 3 | 2 | 4 | 3 | 4 | 3 |  | 72.5% | 8 | 2 | 1 | 1 | 5 | 4 |  | 52% | 6 |  | 560.1412
1299 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2030-09-30 | 2030 | 263 | 8 | 2030-01-10 | low | high | high | low | low | 350000 | 332894 | 386745 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 27.2404 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | Yes | Yes | 3 | 2 | 2 | 3 | 5 | 3 | 1 | 1 |  | 50% | 5 | 2 | 5 | 1 | 5 | 4 |  | 68% | 7 |  | 560.1412
1300 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2026-09-30 | 2026 | 85 | 8 | 2026-07-07 | med | med | low | low | med | 420000 | 465754 | 449856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 159.1014 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | Yes | Yes | no | Yes | no | Yes | Yes | no | 3 | 4 | 5 | 2 | 3 | 1 | 1 | 5 |  | 60% | 6 | 4 | 2 | 1 | 5 | 5 |  | 68% | 7 |  | 2310.5725
1301 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Calgary | 2025-09-30 | 2025 | 150 | 8 | 2025-05-03 | high | med | med | high | low | 350000 | 358642 | 375845 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 83.0189 | CAPITAL | No | Pipeline segment |  | X |  | X |  | Yes | Yes | no | Yes | Yes | no | no | Yes | Yes | 5 | 5 | 3 | 3 | 4 | 5 | 1 | 3 |  | 72.5% | 8 | 2 | 4 | 1 | 1 | 5 |  | 52% | 6 |  | 2369.8282
1302 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2028-12-31 | 2028 | 185 | 8 | 2028-06-29 | high | med | high | low | low | 550000 | 555744 | 590000 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 32.772 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | Yes | no | no | no | Yes | Yes | no | 5 | 4 | 1 | 3 | 5 | 5 | 4 | 2 |  | 72.5% | 8 | 1 | 5 | 1 | 5 | 3 |  | 60% | 6 |  | 2491.953
1303 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Montreal | 2030-03-31 | 2030 | 250 | 8 | 2029-07-24 | low | low | med | med | med | 650000 | 634470 | 663637 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 147.3292 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | no | Yes | no | no | Yes | 1 | 2 | 3 | 1 | 2 | 3 | 5 | 5 |  | 55% | 6 | 5 | 3 | 1 | 4 | 3 |  | 64% | 7 |  | 16593.6851
1304 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2029-11-30 | 2029 | 185 | 15 | 2029-05-29 | med | high | high | low | med | 500000 | 478589 | 470244 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 800000 | 180.0007 | CAPITAL | Yes | Pipeline segment | X |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 1 | 3 | 5 | 5 | 3 | 3 | 3 |  | 60% | 6 | 2 | 4 | 1 | 4 | 5 |  | 64% | 7 |  | 2480.6254
1305 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2026-09-30 | 2026 | 180 | 8 | 2026-04-03 | low | high | high | high | low | 2000000 | 2058655 | 2014691 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 2000000 | 488.9487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | no | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 5 |  | 37.5% | 4 | 4 | 2 | 1 | 3 | 1 |  | 44% | 5 |  | 2480.6254
1306 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2027-11-30 | 2027 | 260 | 8 | 2027-03-15 | low | low | low | low | low | 2100000 | 2120000 | 2154250 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 40.3349 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | no | no | no | no | no | Yes | no | 2 | 2 | 1 | 2 | 4 | 2 | 2 | 2 |  | 42.5% | 5 | 2 | 5 | 1 | 2 | 2 |  | 48% | 5 |  | 728.1385
1307 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2026-12-31 | 2026 | 200 | 2 | 2026-06-14 | high | low | med | low | low | 650000 | 609531 | 605189 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 242.8512 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X | X | no | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 5 | 3 | 1 | 5 | 5 | 5 | 4 |  | 77.5% | 8 | 5 | 3 | 1 | 3 | 4 |  | 64% | 7 |  | 495.1227
1308 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2028-04-30 | 2028 | 200 | 4 | 2027-10-13 | med | high | high | high | high | 2000000 | 2373474 | 2320004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 25.7224 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | no | Yes | no | no | no | Yes | Yes | 1 | 3 | 1 | 3 | 3 | 3 | 5 | 1 |  | 50% | 5 | 1 | 5 | 1 | 4 | 2 |  | 52% | 6 |  | 6039.0018
1309 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2028-12-31 | 2028 | 180 | 5 | 2028-07-04 | low | high | low | med | low | 400000 | 450563 | 459107 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 800000 | 135.4595 | EXPENSE | No | Pipeline segment |  | X |  |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 2 | 4 | 1 | 4 | 3 | 2 | 2 | 2 |  | 50% | 5 | 2 | 1 | 1 | 3 | 4 |  | 44% | 5 |  | 13659.1884
1310 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2029-08-31 | 2029 | 180 | 5 | 2029-03-04 | low | high | low | med | high | 420000 | 850041 | 889250 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 122.5032 | EXPENSE | Yes | Pipeline segment | X |  |  | X |  | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 4 | 4 | 1 | 2 | 5 | 2 | 5 |  | 62.5% | 6 | 5 | 1 | 1 | 5 | 3 |  | 60% | 6 |  | 13659.1884
1311 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2026-03-31 | 2026 | 200 | 5 | 2025-09-12 | high | med | high | med | med | 420000 | 419283 | 410602 | 126000 | 252000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 148.1189 | EXPENSE | Yes | Pipeline segment | X |  | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 3 | 5 | 4 | 1 | 2 | 2 | 3 | 5 |  | 62.5% | 6 | 4 | 5 | 5 | 3 | 4 |  | 84% | 9 |  | 21537.8368
1312 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Regina | 2025-11-30 | 2025 | 120 | 15 | 2025-08-02 | low | low | low | low | med | 550000 | 615279 | 618240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 184.0435 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | Yes | no | no | no | no | no | 2 | 2 | 4 | 4 | 2 | 2 | 4 | 2 |  | 55% | 6 | 2 | 2 | 1 | 1 | 2 |  | 32% | 4 |  | 2973.4021
1313 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANNUAL SURVEY | Toronto | 2030-03-31 | 2030 | 180 | 10 | 2029-10-02 | med | med | med | high | high | 750000 | 701993 | 706058 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 34.5922 | EXPENSE | No | NO outage | X | X |  |  | X | Yes | no | no | no | Yes | no | no | Yes | Yes | 1 | 4 | 2 | 2 | 1 | 3 | 4 | 5 |  | 55% | 6 | 4 | 4 | 1 | 5 | 3 |  | 68% | 7 |  | 19639.8665
1314 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Montreal | 2028-12-31 | 2028 | 200 | 10 | 2028-06-14 | high | high | low | low | high | 550000 | 620373 | 628500 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 16.0911 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 1 |  | 67.5% | 6 | 2 | 2 | 1 | 1 | 2 |  | 32% | 4 |  | 5776.4313
1315 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2026-03-31 | 2026 | 250 | 10 | 2025-07-24 | low | high | high | low | low | 550000 | 897555 | 933585 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 23.9593 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | Yes | no | no | Yes | Yes | no | Yes | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 4 |  | 42.5% | 5 | 4 | 1 | 1 | 4 | 1 |  | 44% | 5 |  | 6487.5816
1316 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Saskatoon | 2028-12-31 | 2028 | 120 | 10 | 2028-09-02 | high | low | high | med | med | 500000 | 582971 | 589878 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 270.4653 | CAPITAL | No | Pipeline segment |  | X |  |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 2 | 3 | 4 | 5 | 1 | 1 | 2 | 4 |  | 55% | 6 | 4 | 4 | 5 | 5 | 2 |  | 80% | 8 |  | 1083.35
1317 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2028-04-30 | 2028 | 150 | 4 | 2027-12-02 | low | med | low | high | low | 2000000 | 2242580 | 2285780 | 600000 | 1200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 4000000 | 104.3547 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 3 | 4 | 2 | 2 | 4 | 3 | 4 | 2 |  | 60% | 6 | 3 | 1 | 1 | 1 | 4 |  | 40% | 4 |  | 1184.9141
1318 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2028-04-30 | 2028 | 100 | 2 | 2028-01-21 | high | low | high | high | med | 1500000 | 2469351 | 704714 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 800000 | 48.6768 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | no | Yes | no | Yes | Yes | Yes | Yes | no | 2 | 5 | 1 | 4 | 4 | 4 | 4 | 2 |  | 65% | 6 | 1 | 2 | 1 | 2 | 4 |  | 40% | 4 |  | 1846.6194
1319 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2026-12-31 | 2026 | 85 | 10 | 2026-10-07 | high | low | low | med | med | 400000 | 500000 | 489415 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 400000 | 194.4749 | EXPENSE | Yes | Pipeline segment |  |  |  | X | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 1 | 2 | 3 | 1 | 5 | 3 | 5 | 4 |  | 60% | 6 | 3 | 3 | 5 | 2 | 3 |  | 64% | 7 |  | 9580.8769
1320 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2028-09-30 | 2028 | 120 | 2 | 2028-06-02 | low | low | low | low | low | 850000 | 852000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 26.0956 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 5 | 5 | 2 | 5 | 3 | 2 | 4 | 1 |  | 67.5% | 6 | 1 | 2 | 5 | 2 | 4 |  | 56% | 6 |  | 8429.71
1321 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2026-05-31 | 2026 | 200 | 10 | 2025-11-12 | high | med | low | med | low | 500000 | 385254 | 395452 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 500000 | 156.8587 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 2 | 1 | 4 | 3 | 5 | 3 | 5 | 4 |  | 67.5% | 6 | 1 | 1 | 5 | 2 | 2 |  | 44% | 5 |  | 425
1322 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | North Bay | 2026-12-31 | 2026 | 170 | 10 | 2026-07-14 | med | high | high | med | high | 550000 | 852979 | 857775 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 35.5286 | CAPITAL | No | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | Yes | Yes | Yes | Yes | no | 2 | 5 | 3 | 5 | 4 | 4 | 5 | 2 |  | 75% | 8 | 5 | 2 | 5 | 3 | 4 |  | 76% | 8 |  | 5875
1323 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2027-04-30 | 2027 | 150 | 15 | 2026-12-01 | med | high | med | high | med | 550000 | 542014 | 546441 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 550000 | 26.015 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | Yes | Yes | 4 | 5 | 2 | 3 | 2 | 4 | 5 | 4 |  | 72.5% | 8 | 3 | 5 | 1 | 3 | 5 |  | 68% | 7 |  | 25777
1324 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2025-09-30 | 2025 | 150 | 4 | 2025-05-03 | high | high | high | high | med | 420000 | 449044 | 455180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 18.1227 | CAPITAL | No | Pipeline segment | X | X |  |  |  | no | Yes | no | Yes | no | no | no | Yes | no | 4 | 1 | 2 | 1 | 1 | 3 | 1 | 4 |  | 42.5% | 5 | 3 | 1 | 1 | 5 | 1 |  | 44% | 5 |  | 5522
1325 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2028-04-30 | 2028 | 150 | 4 | 2027-12-02 | low | high | high | high | low | 350000 | 534618 | 575616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 350000 | 502.8679 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | no | Yes | no | no | no | no | Yes | no | no | 5 | 1 | 4 | 5 | 2 | 2 | 3 | 4 |  | 65% | 6 | 1 | 3 | 1 | 5 | 3 |  | 52% | 6 |  | 4101.0339
1326 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Calgary | 2030-03-31 | 2030 | 100 | 5 | 2029-12-21 | high | med | high | high | low | 450000 | 476437 | 473514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 98.0993 | CAPITAL | Yes | Derate/low flow Pipe segment | X | X | X | X | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 4 | 3 | 4 | 5 | 1 | 3 | 4 | 1 |  | 62.5% | 6 | 5 | 4 | 1 | 4 | 3 |  | 68% | 7 |  | 22170.3266
1327 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANNUAL SURVEY | Montreal | 2027-05-31 | 2026 | 120 | 5 | 2027-01-31 | high | med | med | med | low | 1000000 | 1550026 | 1443747 | 0 | 0 | 0 | 0 | 300000 | 600000 | 100000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 76.5526 | EXPENSE | No | NO outage | X | X |  |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 1 | 5 | 4 | 5 | 1 | 3 | 5 | 1 |  | 62.5% | 6 | 2 | 5 | 1 | 5 | 5 |  | 72% | 8 |  | 13420.4072
1328 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2028-09-30 | 2028 | 150 | 5 | 2028-05-03 | med | low | high | low | low | 400000 | 495918 | 472825 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 414.8802 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | Yes | 1 | 3 | 3 | 5 | 2 | 3 | 5 | 3 |  | 62.5% | 6 | 1 | 1 | 1 | 5 | 2 |  | 40% | 4 |  | 1727.2647
1329 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2025-11-30 | 2025 | 100 | 5 | 2025-08-22 | low | low | med | high | low | 420000 | 491000 | 485000 | 0 | 0 | 0 | 0 | 126000 | 252000 | 42000 | 0 | 0 | 0 | 0 | 0 | 420000 | 1266.3815 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 3 | 5 | 2 | 3 | 2 | 2 | 2 | 2 |  | 52.5% | 6 | 1 | 5 | 1 | 3 | 4 |  | 56% | 6 |  | 2588
1330 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | Calgary | 2025-09-30 | 2025 | 100 | 2 | 2025-06-22 | med | high | high | low | high | 125000 | 110410 | 117380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 565.0045 | EXPENSE | Yes | NO | X |  |  |  | X | no | Yes | Yes | no | Yes | no | Yes | no | Yes | 4 | 1 | 1 | 1 | 1 | 2 | 2 | 2 |  | 35% | 4 | 4 | 3 | 1 | 3 | 3 |  | 56% | 6 |  | 18109.7232
1331 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | North Bay | 2026-05-31 | 2026 | 150 | 2 | 2026-01-01 | med | high | low | high | med | 1250000 | 1381952 | 1385422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 750000 | 125000 | 0 | 1250000 | 72.2212 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  | X | no | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 4 | 5 | 4 | 5 | 5 | 4 | 3 | 1 |  | 77.5% | 8 | 5 | 2 | 1 | 5 | 1 |  | 56% | 6 |  | 3981.0002
1332 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Ottawa | 2025-11-30 | 2025 | 120 | 15 | 2025-08-02 | low | high | low | low | low | 550000 | 986403 | 1000025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 103.1048 | CAPITAL | No | Pipeline segment | X |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 4 | 4 | 2 | 4 | 4 | 3 | 3 | 3 |  | 67.5% | 6 | 5 | 5 | 1 | 1 | 1 |  | 52% | 6 |  | 20815.3255
1333 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2026-12-31 | 2026 | 250 | 4 | 2026-04-25 | low | high | high | med | low | 500000 | 514135 | 576815 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 500000 | 91.6522 | CAPITAL | Yes | PIpeline segment | X |  |  | X |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 4 | 1 | 2 | 3 | 3 | 2 | 3 | 4 |  | 55% | 6 | 3 | 4 | 1 | 4 | 4 |  | 64% | 7 |  | 278.7236
1334 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2025-09-30 | 2025 | 200 | 8 | 2025-03-14 | high | high | low | high | high | 500000 | 1505538 | 1480254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 500000 | 98.783 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 4 | 2 | 1 | 2 | 2 | 5 | 5 | 2 |  | 57.5% | 6 | 2 | 3 | 1 | 3 | 1 |  | 40% | 4 |  | 278.7236
1335 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2025-11-30 | 2025 | 200 | 8 | 2025-05-14 | med | high | high | high | med | 350000 | 438059 | 432793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 350000 | 279.986 | CAPITAL | No | Pipeline segment |  | X | X |  |  | no | Yes | no | Yes | Yes | no | Yes | no | no | 3 | 3 | 2 | 5 | 2 | 4 | 1 | 5 |  | 62.5% | 6 | 3 | 1 | 1 | 5 | 5 |  | 60% | 6 |  | 203.1281
1336 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | WINNIPEG | 2025-06-30 | 2025 | 150 | 10 | 2025-01-31 | low | med | low | high | high | 550000 | 528864 | 528750 | 0 | 0 | 0 | 0 | 55000 | 220000 | 275000 | 0 | 0 | 0 | 0 | 0 | 550000 | 56.9979 | CAPITAL | Yes | Pipeline segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | no | no | no | 1 | 2 | 4 | 5 | 1 | 4 | 3 | 3 |  | 57.5% | 6 | 3 | 3 | 1 | 2 | 1 |  | 40% | 4 |  | 203.1281
1337 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | WINNIPEG | 2026-12-31 | 2026 | 160 | 10 | 2026-07-24 | med | low | med | med | med | 450000 | 516716 | 510460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 450000 | 30.4676 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | Yes | Yes | Yes | no | Yes | no | Yes | no | Yes | 5 | 2 | 3 | 1 | 3 | 1 | 4 | 1 |  | 50% | 5 | 4 | 1 | 1 | 1 | 4 |  | 44% | 5 |  | 203.1281
1338 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2025-09-30 | 2025 | 160 | 10 | 2025-04-23 | high | low | high | med | med | 400000 | 410639 | 410032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 4.3752 | CAPITAL | No | Pipeline segment | X | X | X |  | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 5 | 4 | 2 | 1 | 1 | 1 | 1 | 3 |  | 45% | 5 | 1 | 2 | 1 | 3 | 4 |  | 44% | 5 |  | 23717.2367
1339 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2027-11-30 | 2027 | 180 | 10 | 2027-06-03 | med | med | low | high | low | 400000 | 451173 | 453222 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 22.175 | EXPENSE | Yes | Pipeline segment | X | X | X |  |  | Yes | no | no | no | Yes | no | no | Yes | no | 3 | 2 | 2 | 4 | 1 | 1 | 5 | 5 |  | 57.5% | 6 | 3 | 4 | 1 | 4 | 1 |  | 52% | 6 |  | 16021.8416
1340 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2027-11-30 | 2027 | 185 | 8 | 2027-05-29 | high | high | low | high | high | 550000 | 680678 | 686152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 550000 | 22.4512 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | no | Yes | no | no | 3 | 5 | 1 | 4 | 3 | 2 | 2 | 2 |  | 55% | 6 | 1 | 5 | 1 | 1 | 5 |  | 52% | 6 |  | 1685.9635
1341 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2025-06-30 | 2025 | 150 | 2 | 2025-01-31 | med | med | high | med | low | 500000 | 608924 | 630832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 100000 | 0 | 500000 | 93.0837 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | Yes | Yes | no | no | 5 | 3 | 2 | 2 | 3 | 1 | 5 | 2 |  | 57.5% | 6 | 3 | 1 | 1 | 1 | 4 |  | 40% | 4 |  | 121.8769
1342 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2028-12-31 | 2028 | 150 | 4 | 2028-08-03 | low | high | low | low | low | 350000 | 539330 | 577636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 350000 | 415.9262 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | no | no | no | Yes | Yes | Yes | no | Yes | 5 | 5 | 2 | 2 | 5 | 4 | 4 | 3 |  | 75% | 8 | 2 | 2 | 1 | 4 | 2 |  | 44% | 5 |  | 643.2391
1343 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2027-04-30 | 2027 | 100 | 4 | 2027-01-20 | med | low | high | med | low | 300000 | 295522 | 290724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 87.5976 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | no | no | 1 | 1 | 2 | 2 | 1 | 1 | 4 | 5 |  | 42.5% | 5 | 1 | 1 | 3 | 1 | 1 |  | 28% | 3 |  | 267.7598
1344 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2027-11-30 | 2027 | 170 | 4 | 2027-06-13 | high | high | high | high | med | 1500000 | 1557641 | 1550000 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 1500000 | 27.6329 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 2 | 4 | 1 | 1 | 1 | 5 | 4 | 4 |  | 55% | 6 | 3 | 2 | 5 | 1 | 1 |  | 48% | 5 |  | 267.7598
1345 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2027-11-30 | 2027 | 100 | 4 | 2027-08-22 | low | high | high | high | med | 1500000 | 1583805 | 1580197 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 110.9054 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | no | no | Yes | no | no | Yes | Yes | Yes | 5 | 2 | 2 | 1 | 3 | 2 | 5 | 3 |  | 57.5% | 6 | 5 | 5 | 5 | 3 | 1 |  | 76% | 8 |  | 17599.3754
1346 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2026-03-31 | 2026 | 100 | 4 | 2025-12-21 | low | high | med | med | low | 1250000 | 1350000 | 1450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 750000 | 125000 | 0 | 1250000 | 96.934 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 4 | 5 | 3 | 3 | 5 | 3 |  | 72.5% | 8 | 1 | 5 | 5 | 1 | 5 |  | 68% | 7 |  | 7024.2246
1347 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2028-04-30 | 2028 | 150 | 15 | 2027-12-02 | low | low | med | high | med | 550000 | 583975 | 578458 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 29.298 | CAPITAL | No | Pipeline segment | X |  |  | X | X | no | Yes | no | Yes | no | no | no | no | Yes | 5 | 4 | 1 | 5 | 1 | 5 | 2 | 2 |  | 62.5% | 6 | 4 | 5 | 1 | 4 | 3 |  | 68% | 7 |  | 1591.1704
1348 | L2 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Quebec City | 2026-09-30 | 2026 | 120 | 8 | 2026-06-02 | high | med | low | high | low | 1000000 | 1514932 | 1512774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 600000 | 100000 | 1000000 | 7.2499 | EXPENSE | No | NO outage | X | X | X |  | X | no | no | no | no | no | no | no | Yes | Yes | 1 | 1 | 2 | 2 | 4 | 4 | 3 | 3 |  | 50% | 5 | 1 | 1 | 1 | 2 | 1 |  | 24% | 3 |  | 4785
1349 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2028-04-30 | 2028 | 100 | 4 | 2028-01-21 | med | low | low | high | low | 1750000 | 1789882 | 1779817 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 4.1819 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | no | no | no | no | no | Yes | Yes | no | no | 2 | 5 | 1 | 3 | 3 | 2 | 3 | 4 |  | 57.5% | 6 | 2 | 3 | 1 | 5 | 2 |  | 52% | 6 |  | 5732.8906
1350 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2025-06-30 | 2025 | 250 | 15 | 2024-10-23 | low | med | low | high | med | 550000 | 575844 | 575478 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 28.5018 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | no | Yes | no | no | Yes | 3 | 2 | 2 | 1 | 1 | 5 | 1 | 2 |  | 42.5% | 5 | 1 | 1 | 1 | 5 | 4 |  | 48% | 5 |  | 5097.2605
1351 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2025-09-30 | 2025 | 180 | 10 | 2025-04-03 | high | low | low | med | med | 350000 | 370016 | 378399 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 96.1798 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | no | no | no | Yes | Yes | 4 | 5 | 3 | 3 | 4 | 5 | 5 | 5 |  | 85% | 9 | 1 | 1 | 1 | 1 | 1 |  | 20% | 2 |  | 13582.277
1352 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Saskatoon | 2029-11-30 | 2029 | 200 | 10 | 2029-05-14 | high | low | med | med | high | 550000 | 1480343 | 1480758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 89.4674 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 4 | 5 | 3 | 1 | 1 | 5 | 3 | 5 |  | 67.5% | 6 | 4 | 1 | 1 | 5 | 3 |  | 56% | 6 |  | 7110.0938
1353 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2030-09-30 | 2030 | 150 | 10 | 2030-05-03 | med | med | low | med | high | 400000 | 477837 | 478567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 68.0307 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 5 | 4 | 3 | 1 | 5 | 1 | 3 | 4 |  | 65% | 6 | 2 | 1 | 1 | 5 | 4 |  | 52% | 6 |  | 4858.8867
1354 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Quebec City | 2026-05-31 | 2026 | 250 | 8 | 2025-09-23 | med | med | low | med | high | 650000 | 662027 | 682144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 390000 | 65000 | 0 | 0 | 650000 | 108.8597 | CAPITAL | No | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | no | Yes | Yes | 4 | 2 | 1 | 5 | 2 | 5 | 3 | 4 |  | 65% | 6 | 4 | 4 | 1 | 5 | 4 |  | 72% | 8 |  | 2178.0735
1355 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2028-12-31 | 2028 | 205 | 4 | 2028-06-09 | high | low | low | med | med | 1800000 | 1964493 | 1902540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 55.4393 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 1 | 5 | 4 | 5 | 1 | 2 | 2 | 1 |  | 52.5% | 6 | 1 | 1 | 5 | 5 | 5 |  | 68% | 7 |  | 1090.5382
1356 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | North Bay | 2028-04-30 | 2028 | 250 | 8 | 2027-08-24 | med | low | med | low | med | 500000 | 786958 | 789562 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 64.1787 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 4 | 3 | 2 | 3 | 1 | 1 | 1 | 3 |  | 45% | 5 | 3 | 2 | 5 | 3 | 5 |  | 72% | 8 |  | 4052.0846
1357 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Calgary | 2029-11-30 | 2029 | 244 | 4 | 2029-03-31 | high | low | low | high | high | 400000 | 545632 | 516927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 93.8623 | EXPENSE | No | Pipeline segment |  | X |  | X | X | no | no | no | no | Yes | no | Yes | no | no | 3 | 4 | 2 | 3 | 1 | 1 | 2 | 2 |  | 45% | 5 | 5 | 4 | 1 | 5 | 5 |  | 80% | 8 |  | 4522
1358 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Regina | 2027-08-31 | 2026 | 180 | 8 | 2027-03-04 | low | med | med | high | high | 500000 | 666455 | 685432 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 12.1249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 3 | 1 | 5 | 2 | 1 | 1 | 2 |  | 42.5% | 5 | 1 | 2 | 1 | 4 | 5 |  | 52% | 6 |  | 8756
1359 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2026-12-31 | 2026 | 357 | 8 | 2026-01-08 | low | low | med | high | high | 500000 | 483098 | 491931 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 94.2513 | CAPITAL | Yes | Pipeline segment |  |  | X |  | X | Yes | no | no | Yes | Yes | Yes | Yes | Yes | no | 4 | 3 | 1 | 2 | 4 | 1 | 5 | 3 |  | 57.5% | 6 | 5 | 2 | 5 | 4 | 5 |  | 84% | 9 |  | 4785
1360 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Toronto | 2028-09-30 | 2028 | 100 | 10 | 2028-06-22 | med | high | high | med | high | 450000 | 821878 | 824096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 99.9422 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | Yes | 4 | 3 | 2 | 4 | 4 | 3 | 5 | 1 |  | 65% | 6 | 1 | 3 | 5 | 4 | 3 |  | 64% | 7 |  | 4101.034
1361 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2026-12-31 | 2026 | 291 | 10 | 2026-03-15 | low | high | low | med | low | 400000 | 669911 | 715057 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 54.5821 | EXPENSE | No | Pipeline segment | X |  |  |  | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 4 | 2 | 2 | 3 | 3 | 5 | 2 | 1 |  | 55% | 6 | 2 | 3 | 5 | 5 | 2 |  | 68% | 7 |  | 13420.41
1362 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2026-12-31 | 2026 | 85 | 10 | 2026-10-07 | med | high | high | low | med | 400000 | 344031 | 340632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 122.8607 | CAPITAL | No | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | no | Yes | no | Yes | Yes | 3 | 2 | 1 | 3 | 3 | 3 | 3 | 4 |  | 55% | 6 | 4 | 3 | 1 | 5 | 5 |  | 72% | 8 |  | 1727.265
1363 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2028-04-30 | 2028 | 85 | 10 | 2028-02-05 | med | med | low | high | med | 350000 | 439702 | 481874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 350000 | 109.8564 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | no | no | no | no | no | no | no | Yes | Yes | 1 | 5 | 1 | 3 | 3 | 5 | 2 | 5 |  | 62.5% | 6 | 2 | 5 | 1 | 3 | 1 |  | 48% | 5 |  | 1578
1364 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2028-04-30 | 2028 | 180 | 10 | 2027-11-02 | high | low | high | low | high | 350000 | 661009 | 682588 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 111.3269 | EXPENSE | Yes | Pipeline segment | X |  | X | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 3 | 2 | 3 | 2 | 5 | 5 | 2 | 5 |  | 67.5% | 6 | 5 | 2 | 1 | 5 | 3 |  | 64% | 7 |  | 3506.871
1365 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2029-11-30 | 2029 | 120 | 10 | 2029-08-02 | high | high | high | low | low | 350000 | 323179 | 320094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 59.7386 | CAPITAL | No | Pipeline segment |  | X |  | X | X | Yes | no | no | no | no | no | no | no | Yes | 3 | 2 | 1 | 5 | 5 | 3 | 3 | 3 |  | 62.5% | 6 | 2 | 2 | 1 | 4 | 3 |  | 48% | 5 |  | 18109.72
1366 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2025-06-30 | 2025 | 170 | 10 | 2025-01-11 | low | med | low | low | high | 500000 | 590681 | 590005 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 24.542 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | Yes | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 |  | 27.5% | 3 | 1 | 5 | 1 | 1 | 1 |  | 36% | 4 |  | 20815.33
1367 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Ottawa | 2026-09-30 | 2026 | 120 | 8 | 2026-06-02 | high | low | low | high | low | 400000 | 801992 | 806981 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 279.7384 | EXPENSE | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 2 | 4 | 2 | 5 | 4 | 4 | 3 | 5 |  | 72.5% | 8 | 5 | 4 | 1 | 1 | 5 |  | 64% | 7 |  | 2789
1368 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2029-11-30 | 2029 | 153 | 8 | 2029-06-30 | med | low | high | high | med | 500000 | 550475 | 595557 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 117.2576 | EXPENSE | No | Pipeline segment |  | X | X |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 4 | 5 | 2 | 4 | 4 | 3 | 5 | 3 |  | 75% | 8 | 5 | 3 | 1 | 4 | 2 |  | 60% | 6 |  | 5666
1369 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2025-11-30 | 2025 | 150 | 10 | 2025-07-03 | med | low | med | low | low | 350000 | 540105 | 540380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 81.2986 | CAPITAL | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | no | no | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 2 |  | 32.5% | 4 | 1 | 2 | 1 | 5 | 2 |  | 44% | 5 |  | 2789
1370 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2025-11-30 | 2025 | 200 | 10 | 2025-05-14 | med | high | high | high | high | 500000 | 724601 | 723464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 98.531 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | no | no | no | Yes | 1 | 3 | 1 | 2 | 3 | 3 | 2 | 5 |  | 50% | 5 | 5 | 2 | 1 | 2 | 4 |  | 56% | 6 |  | 2588
1371 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2025-09-30 | 2025 | 176 | 10 | 2025-04-07 | low | high | med | med | low | 350000 | 352474 | 355000 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 800000 | 37.7222 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | Yes | 2 | 2 | 1 | 4 | 4 | 1 | 3 | 1 |  | 45% | 5 | 4 | 2 | 1 | 3 | 1 |  | 44% | 5 |  | 8792
1372 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Quebec City | 2030-03-31 | 2030 | 200 | 15 | 2029-09-12 | low | med | low | low | low | 550000 | 499129 | 513827 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 77.5311 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | no | Yes | no | Yes | 4 | 3 | 1 | 4 | 3 | 3 | 3 | 1 |  | 55% | 6 | 2 | 2 | 1 | 2 | 3 |  | 40% | 4 |  | 23717.24
1373 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2025-09-30 | 2025 | 200 | 4 | 2025-03-14 | med | low | high | low | high | 400000 | 350785 | 393433 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 109.3207 | EXPENSE | No | Pipeline segment | X | X |  | X | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 3 | 2 | 1 | 1 | 3 | 5 | 2 | 4 |  | 52.5% | 6 | 1 | 2 | 1 | 3 | 5 |  | 48% | 5 |  | 746.1723
1374 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | WINNIPEG | 2030-12-31 | 2030 | 150 | 8 | 2030-08-03 | high | high | high | low | med | 400000 | 422998 | 420888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 74.8121 | CAPITAL | No | Pipeline segment | X | X |  | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 4 | 2 | 3 | 4 | 3 | 5 | 4 |  | 70% | 6 | 5 | 4 | 1 | 1 | 2 |  | 52% | 6 |  | 13677.18
1375 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2030-03-31 | 2030 | 150 | 8 | 2029-11-01 | high | med | med | med | high | 400000 | 381473 | 383108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 142.0502 | CAPITAL | No | Pipeline segment | X | X | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 1 | 4 | 2 | 5 | 4 | 5 | 2 |  | 70% | 6 | 3 | 3 | 1 | 4 | 4 |  | 60% | 6 |  | 7007.921
1376 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2030-12-31 | 2030 | 85 | 8 | 2030-10-07 | med | med | low | med | low | 350000 | 362424 | 362097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 82.7364 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 4 |  | 55% | 6 | 4 | 4 | 1 | 1 | 3 |  | 52% | 6 |  | 1685.963
1377 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2025-09-30 | 2025 | 250 | 8 | 2025-01-23 | low | med | med | low | high | 550000 | 531429 | 533699 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 69.7306 | CAPITAL | No | Pipeline segment | X | X |  | X | X | Yes | Yes | Yes | no | Yes | Yes | Yes | no | no | 4 | 1 | 1 | 4 | 3 | 2 | 4 | 4 |  | 57.5% | 6 | 3 | 1 | 1 | 3 | 4 |  | 48% | 5 |  | 778.6578
1378 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Ottawa | 2027-08-31 | 2027 | 250 | 8 | 2026-12-24 | low | med | low | high | high | 550000 | 565673 | 562884 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 110.153 | CAPITAL | No | Pipeline segment | X | X | X |  | X | no | no | Yes | Yes | Yes | no | no | no | no | 5 | 4 | 4 | 1 | 1 | 1 | 3 | 3 |  | 55% | 6 | 2 | 3 | 1 | 2 | 1 |  | 36% | 4 |  | 267.7598
1379 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Winnipeg | 2030-03-31 | 2030 | 180 | 8 | 2029-10-02 | low | med | med | med | low | 500000 | 780384 | 780364 | 0 | 0 | 0 | 50000 | 400000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 36.7014 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 5 | 4 | 4 | 5 | 1 | 2 | 4 | 1 |  | 65% | 6 | 2 | 5 | 1 | 5 | 2 |  | 60% | 6 |  | 267.7598
1380 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Winnipeg | 2029-11-30 | 2029 | 150 | 8 | 2029-07-03 | high | low | low | med | low | 400000 | 474413 | 474247 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 13.6895 | CAPITAL | No | Pipeline segment | X | X |  | X | X | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 4 | 3 | 1 | 3 | 2 | 5 | 1 | 2 |  | 52.5% | 6 | 5 | 5 | 1 | 4 | 2 |  | 68% | 7 |  | 6832.492
1381 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2027-08-31 | 2027 | 150 | 4 | 2027-04-03 | med | low | high | low | med | 400000 | 487955 | 487622 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 81.7758 | EXPENSE | No | Pipeline segment | X | X | X |  |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 5 | 5 | 3 | 4 | 5 | 2 | 5 | 1 |  | 75% | 8 | 5 | 5 | 1 | 4 | 3 |  | 72% | 8 |  | 25885
1382 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Saskatoon | 2027-11-30 | 2027 | 200 | 15 | 2027-05-14 | med | low | high | high | high | 550000 | 864397 | 866898 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 61.6448 | CAPITAL | Yes | Pipeline segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | no | Yes | Yes | 3 | 3 | 3 | 2 | 2 | 1 | 4 | 5 |  | 57.5% | 6 | 4 | 5 | 1 | 3 | 2 |  | 60% | 6 |  | 5845
1383 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | North Bay | 2030-03-31 | 2030 | 150 | 4 | 2029-11-01 | low | med | med | med | low | 500000 | 595726 | 599706 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 19.694 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 3 | 2 | 3 | 1 | 1 | 4 | 4 | 2 |  | 50% | 5 | 2 | 5 | 5 | 4 | 2 |  | 72% | 8 |  | 13582.28
1384 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2030-03-31 | 2030 | 100 | 8 | 2029-12-21 | low | med | high | high | low | 2000000 | 2063711 | 2060699 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 35.0188 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | no | no | no | 1 | 3 | 4 | 5 | 1 | 3 | 4 | 5 |  | 65% | 6 | 3 | 4 | 5 | 5 | 1 |  | 72% | 8 |  | 7709.846
1385 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2026-12-31 | 2026 | 120 | 8 | 2026-09-02 | low | low | med | low | med | 2100000 | 2089588 | 2100050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 1745.308 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | Yes | no | no | no | no | no | Yes | 1 | 4 | 3 | 3 | 2 | 5 | 2 | 2 |  | 55% | 6 | 5 | 3 | 1 | 5 | 5 |  | 76% | 8 |  | 7110.094
1386 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Winnipeg | 2030-09-30 | 2030 | 85 | 10 | 2030-07-07 | high | high | high | high | med | 400000 | 443423 | 420247 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 400000 | 167.1303 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 1 | 4 | 5 | 2 | 2 | 2 | 5 |  | 57.5% | 6 | 1 | 5 | 1 | 5 | 5 |  | 68% | 7 |  | 4391.637
1387 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Ottawa | 2027-08-31 | 2027 | 250 | 10 | 2026-12-24 | high | high | low | low | low | 550000 | 464113 | 471206 | 0 | 0 | 0 | 0 | 0 | 165000 | 275000 | 110000 | 0 | 0 | 0 | 0 | 550000 | 51.5723 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 1 | 1 | 1 | 5 | 1 | 2 | 5 | 5 |  | 52.5% | 6 | 5 | 1 | 1 | 3 | 1 |  | 44% | 5 |  | 4314.195
1388 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Calgary | 2030-12-31 | 2030 | 100 | 10 | 2030-09-22 | low | low | med | med | high | 500000 | 490412 | 496874 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 19.5924 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | no | no | no | no | no | no | Yes | 5 | 2 | 1 | 5 | 3 | 3 | 4 | 5 |  | 70% | 6 | 5 | 1 | 1 | 2 | 5 |  | 56% | 6 |  | 4858.887
1389 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2027-04-30 | 2027 | 150 | 8 | 2026-12-01 | high | med | low | high | low | 400000 | 827809 | 927128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 245.1045 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | no | no | 2 | 3 | 1 | 2 | 3 | 5 | 2 | 3 |  | 52.5% | 6 | 1 | 3 | 1 | 2 | 5 |  | 48% | 5 |  | 2178.073
1390 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Saskatoon | 2030-09-30 | 2030 | 100 | 10 | 2030-06-22 | high | high | low | med | med | 550000 | 489598 | 483329 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 57.38 | CAPITAL | Yes | Pipeline segment | X | X |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 4 | 2 | 3 | 1 | 2 | 5 | 4 |  | 60% | 6 | 5 | 4 | 1 | 4 | 2 |  | 64% | 7 |  | 1090.538
1391 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Saskatoon | 2028-04-30 | 2028 | 100 | 10 | 2028-01-21 | low | med | med | high | low | 500000 | 487877 | 486522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 121.3811 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | no | no | Yes | no | no | Yes | no | no | Yes | 4 | 1 | 1 | 1 | 5 | 1 | 4 | 3 |  | 50% | 5 | 5 | 4 | 1 | 1 | 3 |  | 56% | 6 |  | 8501.429
1392 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2026-12-31 | 2026 | 120 | 8 | 2026-09-02 | high | low | med | med | med | 2000000 | 1987275 | 1896800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 0 | 2000000 | 526.2579 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 5 | 2 | 3 | 4 | 1 | 4 | 3 | 2 |  | 60% | 6 | 4 | 1 | 1 | 3 | 3 |  | 48% | 5 |  | 4052.085
1393 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2027-08-31 | 2027 | 150 | 10 | 2027-04-03 | low | med | med | high | med | 350000 | 474581 | 482853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 0 | 0 | 350000 | 166.8084 | CAPITAL | Yes | Pipeline segment |  | X |  | X |  | no | no | no | Yes | Yes | Yes | no | no | no | 2 | 5 | 2 | 2 | 1 | 1 | 2 | 5 |  | 50% | 5 | 1 | 4 | 5 | 1 | 3 |  | 56% | 6 |  | 2610.39
1394 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Edmonton | 2029-08-31 | 2029 | 180 | 8 | 2029-03-04 | low | high | high | low | high | 750000 | 861410 | 860656 | 0 | 0 | 0 | 225000 | 450000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 15.3529 | EXPENSE | No | NO outage |  | X | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | no | 3 | 1 | 1 | 1 | 4 | 4 | 4 | 2 |  | 50% | 5 | 5 | 2 | 5 | 1 | 2 |  | 60% | 6 |  | 241.5599
1395 | L2 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Regina | 2030-12-31 | 2030 | 100 | 8 | 2030-09-22 | high | high | high | high | low | 1800000 | 1807733 | 1857547 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 1080000 | 180000 | 0 | 0 | 0 | 1800000 | 102.2668 | EXPENSE | No | Pipeline segment | X |  | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 3 | 3 | 1 | 3 | 4 | 1 | 1 | 1 |  | 42.5% | 5 | 2 | 5 | 5 | 2 | 1 |  | 60% | 6 |  | 4995.39
1396 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2028-04-30 | 2028 | 150 | 8 | 2027-12-02 | high | low | high | low | high | 400000 | 555442 | 543668 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 400000 | 71.2228 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | no | Yes | Yes | Yes | no | 5 | 2 | 4 | 1 | 3 | 2 | 3 | 1 |  | 52.5% | 6 | 3 | 2 | 1 | 2 | 1 |  | 36% | 4 |  | 5000
1397 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Ottawa | 2026-12-31 | 2026 | 150 | 8 | 2026-08-03 | high | med | high | low | med | 500000 | 827580 | 888541 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 53.7439 | CAPITAL | No | Pipeline segment | X |  |  |  |  | Yes | Yes | no | no | no | Yes | Yes | no | Yes | 2 | 2 | 1 | 5 | 5 | 3 | 2 | 3 |  | 57.5% | 6 | 1 | 1 | 1 | 2 | 5 |  | 40% | 4 |  | 347
1398 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2029-11-30 | 2025 | 200 | 8 | 2029-05-14 | med | high | low | low | low | 350000 | 380645 | 388809 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 117.9206 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | no | 5 | 3 | 1 | 2 | 1 | 1 | 5 | 2 |  | 50% | 5 | 2 | 4 | 1 | 2 | 3 |  | 48% | 5 |  | 158885
1399 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2025-09-30 | 2025 | 250 | 8 | 2025-01-23 | high | high | low | high | low | 550000 | 1575306 | 1571669 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 68.6381 | CAPITAL | Yes | Pipeline segment | X |  | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 1 | 2 | 3 | 2 | 4 | 5 | 3 | 4 |  | 60% | 6 | 4 | 4 | 1 | 1 | 1 |  | 44% | 5 |  | 1207.799
1400 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2026-12-31 | 2026 | 250 | 10 | 2026-04-25 | med | low | med | low | med | 500000 | 509915 | 513929 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 72.3249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | no | no | no | no | Yes | no | no | 1 | 3 | 3 | 2 | 1 | 2 | 5 | 1 |  | 45% | 5 | 5 | 3 | 1 | 3 | 4 |  | 64% | 7 |  | 1785
1401 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Winnipeg | 2026-03-31 | 2026 | 85 | 10 | 2026-01-05 | high | high | low | low | low | 500000 | 488609 | 483956 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 84.9423 | CAPITAL | No | pipeline segment | X | X | X | X |  | no | no | Yes | Yes | no | no | no | Yes | Yes | 2 | 1 | 1 | 1 | 4 | 3 | 5 | 2 |  | 47.5% | 5 | 1 | 3 | 5 | 2 | 5 |  | 64% | 7 |  | 172.2548
1402 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2025-11-30 | 2025 | 120 | 4 | 2025-08-02 | med | low | high | high | low | 1500000 | 1506928 | 1495675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 750000 | 300000 | 0 | 1500000 | 33.796 | CAPITAL | Yes | Derate/low flow Pipe segment | X |  | X |  | X | Yes | no | no | Yes | no | no | Yes | no | no | 2 | 1 | 4 | 5 | 2 | 4 | 5 | 2 |  | 62.5% | 6 | 5 | 3 | 1 | 1 | 3 |  | 52% | 6 |  | 191.3942
1403 | L1 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Calgary | 2030-09-30 | 2030 | 180 | 10 | 2030-04-03 | high | low | low | low | med | 750000 | 751968 | 754634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 41.9164 | EXPENSE | Yes | NO outage |  | X | X | X |  | Yes | no | Yes | Yes | no | Yes | Yes | Yes | no | 5 | 1 | 3 | 5 | 3 | 1 | 5 | 1 |  | 60% | 6 | 2 | 3 | 1 | 2 | 3 |  | 44% | 5 |  | 173.2929
1404 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Calgary | 2027-08-31 | 2027 | 85 | 5 | 2027-06-07 | low | med | high | high | low | 350000 | 320570 | 415873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 375.5287 | EXPENSE | No | Pipeline segment |  |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | Yes | 1 | 3 | 2 | 1 | 4 | 5 | 2 | 3 |  | 52.5% | 6 | 4 | 1 | 1 | 5 | 5 |  | 64% | 7 |  | 900.2043
1405 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2025-09-30 | 2025 | 150 | 10 | 2025-05-03 | high | med | high | low | med | 400000 | 709452 | 706903 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 34.9002 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 1 | 4 | 1 | 1 | 5 | 2 | 2 | 3 |  | 47.5% | 5 | 2 | 3 | 1 | 2 | 5 |  | 52% | 6 |  | 749.7244
1406 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2028-09-30 | 2028 | 150 | 10 | 2028-05-03 | med | med | low | low | low | 500000 | 624655 | 652754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 95.8703 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | no | no | Yes | no | no | no | no | Yes | 3 | 1 | 1 | 1 | 5 | 1 | 4 | 3 |  | 47.5% | 5 | 2 | 2 | 1 | 4 | 3 |  | 48% | 5 |  | 41798.52
1407 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2027-08-31 | 2027 | 200 | 4 | 2027-02-12 | med | high | med | low | med | 400000 | 454302 | 487376 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 71.1665 | EXPENSE | No | Pipeline segment |  | X |  |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | 3 | 3 | 4 | 2 | 2 | 3 | 1 | 2 |  | 50% | 5 | 3 | 3 | 1 | 5 | 5 |  | 68% | 7 |  | 32.5005
1408 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2029-11-30 | 2029 | 100 | 8 | 2029-08-22 | high | med | med | low | low | 550000 | 931419 | 934750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 76.4614 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | no | no | 2 | 4 | 1 | 2 | 2 | 2 | 5 | 1 |  | 47.5% | 5 | 5 | 3 | 1 | 5 | 3 |  | 68% | 7 |  | 1022.412
1409 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Regina | 2030-12-31 | 2030 | 100 | 8 | 2030-09-22 | med | med | low | low | high | 700000 | 437705 | 443302 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 800000 | 228.8332 | CAPITAL | Yes | Pipeline segment | X | X |  | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | no | 1 | 5 | 4 | 4 | 5 | 1 | 1 | 3 |  | 60% | 6 | 4 | 4 | 1 | 1 | 5 |  | 60% | 6 |  | 4447
1410 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Winnipeg | 2027-08-31 | 2027 | 150 | 8 | 2027-04-03 | med | low | med | med | high | 400000 | 485478 | 480917 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 28.2991 | EXPENSE | No | Pipeline segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 2 | 2 | 1 | 2 | 5 | 1 | 1 | 1 |  | 37.5% | 4 | 3 | 4 | 1 | 4 | 2 |  | 56% | 6 |  | 7718.869
1411 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Toronto | 2029-11-30 | 2029 | 250 | 8 | 2029-03-25 | low | low | high | med | low | 550000 | 558450 | 559906 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 800000 | 134.4344 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | no | no | Yes | Yes | Yes | no | no | Yes | 2 | 3 | 2 | 4 | 3 | 3 | 1 | 3 |  | 52.5% | 6 | 3 | 2 | 1 | 5 | 4 |  | 60% | 6 |  | 7718.869
1412 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Edmonton | 2026-05-31 | 2026 | 85 | 10 | 2026-03-07 | high | high | high | low | high | 550000 | 792798 | 734137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 890.1864 | CAPITAL | No | Pipeline segment |  | X | X | X | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 3 | 2 | 1 | 5 | 5 | 5 | 4 | 5 |  | 75% | 8 | 1 | 3 | 5 | 4 | 4 |  | 68% | 7 |  | 6993.546
1413 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2028-09-30 | 2028 | 100 | 4 | 2028-06-22 | high | med | low | high | med | 1500000 | 1580829 | 1584305 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 800000 | 143.1102 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 3 | 5 | 2 | 2 | 4 | 2 | 4 | 3 |  | 62.5% | 6 | 3 | 1 | 1 | 5 | 2 |  | 48% | 5 |  | 636.4681
1414 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2026-05-31 | 2026 | 125 | 10 | 2026-01-26 | med | high | high | high | low | 500000 | 351865 | 354621 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 86.0466 | CAPITAL | Yes | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 1 | 3 | 4 | 4 | 4 | 3 | 2 | 1 |  | 55% | 6 | 1 | 5 | 1 | 4 | 4 |  | 60% | 6 |  | 2369.828
1415 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2029-11-30 | 2029 | 250 | 10 | 2029-03-25 | low | med | low | med | low | 500000 | 985848 | 988631 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 71.0178 | EXPENSE | Yes | Pipeline segment |  |  |  | X |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 3 | 3 | 1 | 5 | 2 | 1 | 3 |  | 47.5% | 5 | 4 | 5 | 1 | 5 | 3 |  | 72% | 8 |  | 2369.828
1416 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2027-08-31 | 2027 | 204 | 15 | 2027-02-08 | high | high | high | med | med | 500000 | 897582 | 890760 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 56.3678 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | Yes | no | no | no | no | no | no | no | no | 3 | 5 | 1 | 5 | 3 | 2 | 2 | 4 |  | 62.5% | 6 | 1 | 5 | 1 | 1 | 1 |  | 36% | 4 |  | 3138.866
1417 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2028-04-30 | 2028 | 85 | 15 | 2028-02-05 | low | high | high | low | high | 400000 | 623417 | 635508 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 204.7502 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 5 |  | 45% | 5 | 3 | 4 | 1 | 2 | 4 |  | 56% | 6 |  | 14928.99
1418 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Saskatoon | 2030-12-31 | 2030 | 120 | 5 | 2030-09-02 | high | high | med | med | med | 420000 | 384800 | 395163 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 193.3484 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | no | Yes | Yes | no | no | Yes | Yes | Yes | 1 | 4 | 3 | 4 | 4 | 3 | 5 | 1 |  | 62.5% | 6 | 2 | 2 | 1 | 2 | 2 |  | 36% | 4 |  | 4785
1419 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Quebec City | 2029-11-30 | 2029 | 200 | 10 | 2029-05-14 | high | med | high | low | low | 650000 | 769127 | 763937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 53.022 | CAPITAL | No | Pipeline segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 3 | 1 | 3 | 3 | 5 | 1 | 5 | 5 |  | 65% | 6 | 3 | 2 | 1 | 4 | 5 |  | 60% | 6 |  | 4487
1420 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2027-11-30 | 2027 | 181 | 4 | 2027-06-02 | high | low | low | low | med | 1800000 | 1789522 | 1832500 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 2.6813 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 5 | 5 | 3 | 5 | 2 | 2 | 4 | 4 |  | 75% | 8 | 1 | 5 | 1 | 3 | 1 |  | 44% | 5 |  | 477.3811
1421 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2028-09-30 | 2028 | 217 | 8 | 2028-02-26 | med | high | low | high | high | 2000000 | 1920848 | 1689578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 304.5368 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X | X | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 1 | 1 | 5 | 5 | 4 | 1 | 1 |  | 52.5% | 6 | 3 | 2 | 1 | 4 | 5 |  | 60% | 6 |  | 5347.325
1422 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2029-04-30 | 2029 | 150 | 10 | 2028-12-01 | med | med | low | high | high | 400000 | 499341 | 496308 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 44.7596 | CAPITAL | No | Pipeline segment | X | X |  | X | X | no | no | Yes | Yes | Yes | Yes | no | Yes | no | 1 | 4 | 2 | 1 | 2 | 1 | 3 | 5 |  | 47.5% | 5 | 2 | 1 | 1 | 1 | 1 |  | 24% | 3 |  | 4542.743
1423 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2028-04-30 | 2028 | 150 | 8 | 2027-12-02 | med | med | low | low | low | 400000 | 423560 | 460010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 86.1551 | EXPENSE | No | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | Yes | Yes | Yes | no | no | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 2 |  | 35% | 4 | 1 | 1 | 1 | 1 | 5 |  | 36% | 4 |  | 2679.519
1424 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANNUAL SURVEY | Saskatoon | 2029-11-30 | 2029 | 180 | 10 | 2029-06-03 | med | low | high | low | med | 750000 | 752055 | 721982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 100.5902 | EXPENSE | No | NO outage |  | X | X |  | X | no | Yes | no | no | no | Yes | no | no | Yes | 2 | 5 | 3 | 2 | 4 | 4 | 5 | 1 |  | 65% | 6 | 5 | 3 | 1 | 1 | 2 |  | 48% | 5 |  | 45.3112
1425 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2029-11-30 | 2029 | 229 | 8 | 2029-04-15 | high | high | med | high | high | 500000 | 725080 | 725529 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 32.563 | EXPENSE | No | Pipeline segment |  |  | X | X | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 2 | 1 | 4 | 2 | 1 | 3 | 2 | 5 |  | 50% | 5 | 2 | 5 | 1 | 1 | 3 |  | 48% | 5 |  | 263.7275
1426 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Winnipeg | 2027-08-31 | 2027 | 85 | 10 | 2027-06-07 | med | low | low | low | high | 500000 | 496475 | 495002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 500000 | 13.0596 | CAPITAL | No | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 1 | 2 | 2 | 3 | 5 | 2 | 5 | 1 |  | 52.5% | 6 | 2 | 3 | 1 | 5 | 5 |  | 64% | 7 |  | 18394.3
1427 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2026-05-31 | 2026 | 286 | 8 | 2025-08-18 | low | med | low | high | med | 500000 | 478617 | 519000 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 3.8339 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 5 | 2 | 2 | 3 | 5 | 3 | 5 |  | 65% | 6 | 4 | 3 | 1 | 3 | 4 |  | 60% | 6 |  | 76225.68
1428 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2028-04-30 | 2028 | 140 | 8 | 2027-12-12 | med | high | low | med | high | 520000 | 986111 | 1100500 | 156000 | 312000 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 89.8531 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 5 | 5 | 2 | 1 | 5 | 2 | 5 | 3 |  | 70% | 6 | 3 | 3 | 1 | 5 | 1 |  | 52% | 6 |  | 16.9273
1429 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | Toronto | 2025-06-30 | 2025 | 215 | 12 | 2024-11-27 | med | high | high | low | high | 300000 | 362980 | 335201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 1124.6434 | EXPENSE | No | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 2 | 2 | 1 | 4 | 1 | 2 | 5 | 3 |  | 50% | 5 | 4 | 4 | 1 | 1 | 5 |  | 60% | 6 |  | 560.1412
1430 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Winnipeg | 2025-09-30 | 2025 | 85 | 8 | 2025-07-07 | med | high | high | high | high | 400000 | 371481 | 367796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 137.4312 | CAPITAL | No | Pipeline segment |  |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 4 | 1 | 3 | 1 | 3 | 3 | 4 | 5 |  | 60% | 6 | 4 | 2 | 1 | 4 | 2 |  | 52% | 6 |  | 10535.75
1431 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | Calgary | 2030-09-30 | 2030 | 184 | 8 | 2030-03-30 | high | high | high | med | high | 250000 | 298807 | 298469 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 14.7788 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X |  | no | no | Yes | Yes | no | no | Yes | no | Yes | 1 | 2 | 2 | 5 | 2 | 4 | 4 | 3 |  | 57.5% | 6 | 4 | 1 | 1 | 2 | 1 |  | 36% | 4 |  | 2491.953
1432 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | North Bay | 2027-04-30 | 2027 | 301 | 8 | 2026-07-03 | high | med | high | high | low | 550000 | 529833 | 522678 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 550000 | 78.3491 | EXPENSE | Yes | Pipeline segment |  |  |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 5 | 4 | 4 | 5 | 1 | 5 | 1 | 2 |  | 67.5% | 6 | 1 | 5 | 1 | 2 | 1 |  | 40% | 4 |  | 16593.69
1433 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2025-06-30 | 2025 | 120 | 8 | 2025-03-02 | med | high | high | med | low | 400000 | 636064 | 696142 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 188.6819 | EXPENSE | Yes | Pipeline segment |  | X |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 5 | 5 | 1 | 1 | 1 | 4 | 5 | 3 |  | 62.5% | 6 | 1 | 2 | 5 | 5 | 3 |  | 64% | 7 |  | 31873.29
1434 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2030-09-30 | 2030 | 205 | 4 | 2030-03-09 | low | low | low | high | med | 950000 | 951400 | 1073713 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 165.7118 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | no | no | no | Yes | 2 | 3 | 2 | 1 | 4 | 5 | 4 | 3 |  | 60% | 6 | 4 | 2 | 1 | 2 | 3 |  | 48% | 5 |  | 495.1227
1435 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2027-08-31 | 2027 | 240 | 4 | 2027-01-03 | high | low | low | low | high | 1250000 | 1201124 | 1215797 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 800000 | 732.8044 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  |  |  | no | Yes | Yes | Yes | Yes | no | no | no | no | 3 | 4 | 1 | 2 | 3 | 1 | 4 | 1 |  | 47.5% | 5 | 5 | 5 | 1 | 4 | 3 |  | 72% | 8 |  | 5521.373
1436 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Quebec City | 2029-04-30 | 2029 | 56 | 2 | 2029-03-05 | low | high | med | low | med | 450000 | 493301 | 555422 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 146.1537 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | no | no | Yes | Yes | no | Yes | no | Yes | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 4 |  | 85% | 9 | 1 | 2 | 1 | 3 | 5 |  | 48% | 5 |  | 13659.19
1437 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2025-11-30 | 2025 | 265 | 7 | 2025-03-10 | low | high | low | low | med | 2000000 | 2222026 | 2251913 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 12.9047 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | no | no | no | no | Yes | no | 5 | 3 | 2 | 2 | 1 | 2 | 5 | 1 |  | 52.5% | 6 | 4 | 5 | 1 | 3 | 5 |  | 72% | 8 |  | 13659.19
1438 | L2 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Winnipeg | 2029-08-31 | 2029 | 84 | 10 | 2029-06-08 | high | high | low | med | med | 1300000 | 1324785 | 1350260 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 800000 | 119.9716 | EXPENSE | No | Pipeline segment | X |  |  |  | X | Yes | no | no | Yes | Yes | no | no | Yes | no | 3 | 4 | 2 | 3 | 1 | 2 | 2 | 1 |  | 45% | 5 | 2 | 5 | 1 | 2 | 5 |  | 60% | 6 |  | 17906.94
1439 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Regina | 2028-12-31 | 2028 | 85 | 5 | 2028-10-07 | high | med | med | high | med | 400000 | 393878 | 395581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 318.2127 | EXPENSE | No | Pipeline segment | X |  |  | X | X | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 4 | 4 | 2 | 4 | 5 | 5 | 3 | 1 |  | 70% | 6 | 5 | 4 | 1 | 1 | 1 |  | 48% | 5 |  | 19639.87
1440 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2026-05-31 | 2026 | 150 | 10 | 2026-01-01 | high | low | med | med | low | 550000 | 875950 | 888752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 59.654 | CAPITAL | No | Pipeline segment |  | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 5 | 1 | 3 | 3 | 2 | 1 | 4 | 3 |  | 55% | 6 | 4 | 1 | 1 | 2 | 2 |  | 40% | 4 |  | 6487.582
1441 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Toronto | 2025-06-30 | 2025 | 153 | 10 | 2025-01-28 | low | med | med | low | low | 550000 | 870821 | 874947 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 250.7139 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | no | no | no | Yes | 5 | 5 | 3 | 1 | 5 | 2 | 1 | 5 |  | 67.5% | 6 | 1 | 5 | 1 | 2 | 1 |  | 40% | 4 |  | 1083.35
1442 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | North Bay | 2029-08-31 | 2029 | 150 | 8 | 2029-04-03 | low | low | high | med | med | 400000 | 617515 | 618701 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 129.2729 | EXPENSE | No | Pipeline segment | X | X |  | X |  | no | Yes | Yes | Yes | no | no | no | Yes | no | 1 | 1 | 3 | 3 | 4 | 1 | 4 | 1 |  | 45% | 5 | 4 | 1 | 1 | 1 | 5 |  | 48% | 5 |  | 1184.914
1443 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | North Bay | 2029-04-30 | 2029 | 150 | 10 | 2028-12-01 | med | low | high | med | high | 300000 | 314592 | 316431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 134.8065 | EXPENSE | No | Pipeline segment | X | X |  |  | X | Yes | no | Yes | Yes | no | no | no | no | no | 4 | 4 | 4 | 1 | 1 | 5 | 4 | 5 |  | 70% | 6 | 4 | 4 | 1 | 2 | 2 |  | 52% | 6 |  | 1846.619
1444 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Quebec City | 2027-11-30 | 2027 | 150 | 8 | 2027-07-03 | high | high | high | low | med | 700000 | 770309 | 770000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 28.6028 | CAPITAL | No | pipeline segment outage |  |  | X |  | X | Yes | no | no | no | no | Yes | no | Yes | Yes | 2 | 5 | 4 | 2 | 2 | 3 | 2 | 4 |  | 60% | 6 | 4 | 5 | 1 | 1 | 1 |  | 48% | 5 |  | 8429.71
1445 | L1 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Winnipeg | 2026-10-31 | 2026 | 180 | 10 | 2026-05-04 | low | low | high | high | high | 750000 | 701590 | 708037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 118.806 | EXPENSE | No | NO outage | X | X |  |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 5 | 3 | 3 | 4 | 2 | 2 | 2 | 3 |  | 60% | 6 | 5 | 4 | 5 | 1 | 2 |  | 68% | 7 |  | 258
1446 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2030-03-31 | 2030 | 280 | 4 | 2029-06-24 | high | high | low | high | low | 1000000 | 1024910 | 1058330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 61.0855 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 1 | 1 | 4 | 2 | 2 | 3 | 2 | 4 |  | 47.5% | 5 | 2 | 1 | 5 | 1 | 3 |  | 48% | 5 |  | 842.9817
1447 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Quebec City | 2026-09-30 | 2026 | 200 | 10 | 2026-03-14 | low | low | low | low | low | 500000 | 677573 | 672660 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 11.9354 | EXPENSE | No | Pipeline segment |  |  | X |  |  | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 3 | 1 | 1 | 1 | 4 | 2 | 1 | 3 |  | 40% | 4 | 5 | 5 | 5 | 4 | 4 |  | 92% | 10 |  | 842.9817
1448 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2030-03-31 | 2030 | 139 | 8 | 2029-11-12 | med | med | med | med | low | 400000 | 425230 | 434107 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 383.2311 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | no | Yes | no | Yes | no | no | Yes | no | 3 | 3 | 2 | 4 | 4 | 3 | 4 | 2 |  | 62.5% | 6 | 5 | 3 | 1 | 2 | 5 |  | 64% | 7 |  | 1727.2647
1449 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2025-09-30 | 2025 | 74 | 4 | 2025-07-18 | low | low | high | low | low | 1000000 | 1295898 | 1247471 | 0 | 0 | 0 | 35000 | 35000 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 78.2163 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X | X | Yes | no | no | no | no | no | Yes | no | Yes | 1 | 3 | 1 | 1 | 4 | 3 | 2 | 5 |  | 50% | 5 | 2 | 4 | 1 | 1 | 2 |  | 40% | 4 |  | 1578
1450 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Winnipeg | 2025-06-30 | 2025 | 85 | 8 | 2025-04-06 | high | high | high | low | high | 400000 | 493729 | 468570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 162.7571 | EXPENSE | No | Pipeline segment | X | X |  |  | X | no | Yes | Yes | Yes | no | no | Yes | no | Yes | 5 | 3 | 2 | 4 | 2 | 5 | 5 | 3 |  | 72.5% | 8 | 4 | 1 | 5 | 5 | 4 |  | 76% | 8 |  | 3506.8708
1451 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Calgary | 2030-03-31 | 2030 | 85 | 5 | 2030-01-05 | low | low | low | med | low | 550000 | 544446 | 575417 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 145.3755 | CAPITAL | No | Pipeline segment |  |  | X | X | X | Yes | no | Yes | Yes | Yes | no | Yes | Yes | Yes | 1 | 4 | 1 | 2 | 2 | 2 | 5 | 2 |  | 47.5% | 5 | 5 | 4 | 1 | 5 | 3 |  | 72% | 8 |  | 3981.0002
1452 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Calgary | 2028-04-30 | 2028 | 150 | 8 | 2027-12-02 | high | low | med | high | high | 500000 | 458949 | 459364 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 44.4078 | CAPITAL | Yes | pipeline segment | X | X |  |  | X | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 4 | 4 | 3 | 1 | 4 | 4 | 1 | 3 |  | 60% | 6 | 3 | 1 | 1 | 1 | 5 |  | 44% | 5 |  | 20815.3255
1453 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | WINNIPEG | 2027-11-30 | 2027 | 265 | 4 | 2027-03-10 | med | low | low | med | high | 850000 | 795426 | 800000 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 287.411 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 3 | 4 | 3 | 1 | 4 | 2 | 5 | 1 |  | 57.5% | 6 | 2 | 2 | 5 | 5 | 1 |  | 60% | 6 |  | 425
1454 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2028-04-30 | 2028 | 45 | 4 | 2028-03-16 | low | med | med | low | high | 1000000 | 1035786 | 1004048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 336.0415 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 4 | 1 | 3 | 1 | 5 | 5 | 3 |  | 62.5% | 6 | 1 | 1 | 1 | 4 | 1 |  | 32% | 4 |  | 278.7236
1455 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Montreal | 2029-11-30 | 2029 | 101 | 8 | 2029-08-21 | med | high | med | med | high | 550000 | 467194 | 477060 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 49.109 | EXPENSE | No | Pipeline segment | X | X |  |  |  | Yes | Yes | no | no | Yes | no | no | Yes | Yes | 4 | 5 | 2 | 2 | 3 | 2 | 4 | 4 |  | 65% | 6 | 3 | 4 | 1 | 5 | 5 |  | 72% | 8 |  | 203.1281
1456 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2027-08-31 | 2027 | 85 | 8 | 2027-06-07 | med | med | med | high | med | 350000 | 356367 | 314154 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 56.2148 | CAPITAL | Yes | Pipeline segment |  | X | X |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 2 | 4 | 2 | 3 | 5 | 2 | 4 | 4 |  | 65% | 6 | 2 | 4 | 1 | 2 | 4 |  | 52% | 6 |  | 203.1281
1457 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Toronto | 2028-04-30 | 2028 | 200 | 8 | 2027-10-13 | low | high | med | low | med | 550000 | 1496322 | 1504238 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 800000 | 104.2124 | CAPITAL | No | Pipeline segment | X | X | X |  | X | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 2 | 3 | 2 | 2 | 3 | 5 | 5 |  | 65% | 6 | 5 | 1 | 1 | 3 | 4 |  | 56% | 6 |  | 853.1382
1458 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2027-08-31 | 2027 | 153 | 2 | 2027-03-31 | med | med | high | high | low | 300000 | 351489 | 352567 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 256.8876 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  | X | X | Yes | Yes | no | Yes | Yes | no | no | no | no | 1 | 2 | 3 | 3 | 1 | 1 | 4 | 3 |  | 45% | 5 | 4 | 5 | 5 | 3 | 4 |  | 84% | 9 |  | 23717.2367
1459 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Edmonton | 2026-03-31 | 2026 | 150 | 10 | 2025-11-01 | med | low | med | low | med | 550000 | 750527 | 763520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 21.7053 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | no | Yes | no | no | Yes | no | Yes | 4 | 1 | 4 | 4 | 1 | 4 | 3 | 3 |  | 60% | 6 | 2 | 4 | 1 | 3 | 5 |  | 60% | 6 |  | 746.1723
1460 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2025-09-30 | 2025 | 150 | 8 | 2025-05-03 | high | low | med | med | high | 400000 | 567316 | 563023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 42.7227 | CAPITAL | No | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 1 | 4 | 5 | 4 | 2 | 4 | 5 |  | 70% | 6 | 2 | 2 | 1 | 2 | 1 |  | 32% | 4 |  | 1174.9707
1461 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Regina | 2026-03-31 | 2026 | 120 | 10 | 2025-12-01 | low | med | low | low | low | 400000 | 380028 | 388094 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 90.2519 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | no | 2 | 2 | 4 | 4 | 2 | 2 | 4 | 2 |  | 55% | 6 | 1 | 4 | 1 | 2 | 1 |  | 36% | 4 |  | 13677.1818
1462 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Regina | 2030-12-31 | 2030 | 85 | 10 | 2030-10-07 | low | high | med | low | low | 400000 | 424238 | 427119 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 61.5753 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 2 | 2 | 3 | 5 | 1 | 1 | 3 | 4 |  | 52.5% | 6 | 4 | 4 | 1 | 2 | 2 |  | 52% | 6 |  | 16021.8416
1463 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2028-04-30 | 2028 | 216 | 4 | 2027-09-27 | med | low | low | high | low | 1900000 | 2439945 | 2463759 | 0 | 0 | 0 | 570000 | 1140000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 28.0968 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 1 | 4 | 4 | 4 | 1 | 5 | 4 |  | 60% | 6 | 2 | 2 | 1 | 5 | 3 |  | 52% | 6 |  | 7007.9205
1464 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Ottawa | 2030-12-31 | 2030 | 120 | 10 | 2030-09-02 | low | low | high | high | low | 400000 | 400160 | 405476 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 7.1499 | CAPITAL | No | Pipeline segment | X |  |  | X |  | no | no | Yes | no | no | no | Yes | no | Yes | 1 | 3 | 1 | 4 | 4 | 1 | 4 | 3 |  | 52.5% | 6 | 3 | 3 | 1 | 3 | 1 |  | 44% | 5 |  | 1685.9635
1465 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2025-11-30 | 2025 | 85 | 15 | 2025-09-06 | med | low | low | low | low | 500000 | 495184 | 495568 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 15.392 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | no | no | Yes | 5 | 5 | 3 | 4 | 1 | 3 | 1 | 2 |  | 60% | 6 | 4 | 5 | 1 | 2 | 3 |  | 60% | 6 |  | 643.2391
1466 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Calgary | 2026-03-31 | 2026 | 85 | 10 | 2026-01-05 | low | med | low | med | med | 350000 | 400542 | 406801 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 120.5022 | CAPITAL | Yes | Pipeline segment | X | X | X |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 2 | 4 | 1 | 2 | 3 | 5 | 1 | 2 |  | 50% | 5 | 5 | 4 | 5 | 3 | 4 |  | 84% | 9 |  | 267.7598
1467 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Ottawa | 2027-08-31 | 2027 | 100 | 8 | 2027-05-23 | high | low | high | med | high | 450000 | 379319 | 375544 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 35.2892 | CAPITAL | No | pipeline segment outage | X |  | X | X | X | Yes | Yes | Yes | no | no | Yes | no | no | no | 5 | 5 | 3 | 4 | 5 | 4 | 4 | 3 |  | 82.5% | 9 | 1 | 4 | 1 | 3 | 4 |  | 52% | 6 |  | 17599.3754
1468 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Edmonton | 2029-11-30 | 2029 | 200 | 8 | 2029-05-14 | med | med | med | low | low | 500000 | 544088 | 549248 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 800000 | 152.364 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | no | Yes | no | Yes | Yes | no | Yes | Yes | 2 | 2 | 4 | 5 | 5 | 4 | 1 | 3 |  | 65% | 6 | 5 | 5 | 1 | 1 | 4 |  | 64% | 7 |  | 7024.2246
1469 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Edmonton | 2029-04-30 | 2029 | 150 | 8 | 2028-12-01 | low | med | med | med | low | 500000 | 990834 | 987555 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 177.3607 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | Yes | no | no | Yes | no | Yes | no | no | 5 | 1 | 4 | 1 | 3 | 5 | 4 | 3 |  | 65% | 6 | 4 | 3 | 1 | 2 | 3 |  | 52% | 6 |  | 1591.1704
1470 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Montreal | 2028-04-30 | 2028 | 200 | 8 | 2027-10-13 | high | low | high | med | med | 500000 | 598707 | 598210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 152.9866 | EXPENSE | No | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | Yes | no | no | no | no | 5 | 1 | 1 | 2 | 5 | 3 | 1 | 2 |  | 50% | 5 | 4 | 3 | 1 | 3 | 1 |  | 48% | 5 |  | 330
1471 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2026-03-31 | 2026 | 327 | 4 | 2025-05-08 | high | high | med | high | med | 1500000 | 1812742 | 1842116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 1500000 | 34.0888 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 5 | 1 | 2 | 5 | 4 | 1 | 2 | 4 |  | 60% | 6 | 5 | 4 | 1 | 1 | 4 |  | 60% | 6 |  | 5845
1472 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Edmonton | 2030-12-31 | 2030 | 130 | 2 | 2030-08-23 | high | low | low | low | high | 700000 | 598833 | 611085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 218.6029 | CAPITAL | No | pipeline segment outage | X |  | X | X |  | no | no | no | Yes | no | Yes | Yes | Yes | no | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 2 |  | 37.5% | 4 | 1 | 1 | 1 | 1 | 1 |  | 20% | 2 |  | 7709.8457
1473 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2027-04-30 | 2027 | 85 | 4 | 2027-02-04 | high | low | high | high | low | 400000 | 587205 | 589911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 242.1342 | CAPITAL | No | Pipeline segment |  |  |  | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 3 | 1 | 4 | 2 | 2 | 4 | 2 |  | 52.5% | 6 | 3 | 3 | 1 | 2 | 1 |  | 40% | 4 |  | 4391.6369
1474 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Quebec City | 2026-05-31 | 2026 | 180 | 4 | 2025-12-02 | med | high | low | med | low | 400000 | 408000 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 218.7171 | EXPENSE | Yes | pipeline segment |  |  | X | X | X | no | no | no | no | no | Yes | Yes | Yes | no | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 |  | 35% | 4 | 1 | 1 | 1 | 5 | 3 |  | 44% | 5 |  | 4314.1949
1475 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Toronto | 2030-12-31 | 2030 | 150 | 4 | 2030-08-03 | low | high | med | med | high | 550000 | 526296 | 558571 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 163.365 | CAPITAL | No | Pipeline segment |  | X | X | X | X | no | no | Yes | no | no | no | Yes | no | no | 1 | 4 | 1 | 4 | 5 | 2 | 1 | 5 |  | 57.5% | 6 | 2 | 2 | 1 | 1 | 1 |  | 28% | 3 |  | 4858.8867
1476 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Quebec City | 2029-04-30 | 2029 | 106 | 8 | 2029-01-14 | high | high | med | high | high | 500000 | 481652 | 445736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 41.1751 | EXPENSE | No | Pipeline segment |  | X | X |  |  | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 2 | 2 | 2 | 4 | 5 | 3 | 4 | 1 |  | 57.5% | 6 | 3 | 1 | 1 | 5 | 1 |  | 44% | 5 |  | 2178.0735
1477 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2029-11-30 | 2029 | 200 | 8 | 2029-05-14 | low | med | med | med | low | 520000 | 523241 | 529365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156000 | 312000 | 52000 | 520000 | 5.9556 | CAPITAL | No | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | no | 5 | 4 | 2 | 1 | 2 | 1 | 3 | 4 |  | 55% | 6 | 1 | 5 | 1 | 1 | 4 |  | 48% | 5 |  | 1090.5382
1478 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2028-04-30 | 2028 | 330 | 4 | 2027-06-05 | low | high | high | high | high | 1500000 | 1804556 | 1813074 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 83.977 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  | X | Yes | Yes | no | no | Yes | no | no | no | no | 5 | 4 | 1 | 1 | 3 | 5 | 5 | 2 |  | 65% | 6 | 3 | 1 | 1 | 3 | 4 |  | 48% | 5 |  | 8501.4285
1479 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2025-11-30 | 2025 | 343 | 4 | 2024-12-22 | low | high | low | med | high | 1500000 | 1853330 | 1827797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 600000 | 750000 | 0 | 0 | 1500000 | 200.4576 | EXPENSE | No | Derate/low flow Pipe segment | [5 empty] | no | no | no | no | Yes | Yes | no | no | Yes | 5 | 3 | 2 | 3 | 1 | 5 | 4 | 3 |  | 65% | 6 | 3 | 3 | 1 | 3 | 1 |  | 44% | 5 |  | 4052.0846
1480 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2030-03-31 | 2030 | 61 | 4 | 2030-01-29 | med | high | low | high | med | 520000 | 582895 | 685540 | 0 | 0 | 0 | 0 | 156000 | 312000 | 52000 | 0 | 0 | 0 | 0 | 0 | 520000 | 199.4572 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 2 | 1 | 3 | 3 | 5 | 5 |  | 60% | 6 | 4 | 4 | 1 | 1 | 1 |  | 44% | 5 |  | 4995.3897
1481 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2027-11-30 | 2027 | 298 | 2 | 2027-02-05 | high | low | med | high | high | 450000 | 442587 | 452847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 172.7549 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 3 | 3 | 3 | 5 | 2 | 1 | 4 |  | 62.5% | 6 | 4 | 3 | 1 | 2 | 5 |  | 60% | 6 |  | 6993.5456
1482 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Montreal | 2030-09-30 | 2030 | 200 | 10 | 2030-03-14 | high | low | med | high | high | 550000 | 549928 | 591050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 550000 | 59.9299 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | Yes | Yes | no | no | no | Yes | no | Yes | 1 | 2 | 2 | 1 | 1 | 2 | 4 | 5 |  | 45% | 5 | 4 | 1 | 1 | 2 | 1 |  | 36% | 4 |  | 222.8052
1483 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Ottawa | 2029-11-30 | 2029 | 200 | 10 | 2029-05-14 | med | high | med | high | high | 500000 | 987000 | 954825 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 0 | 0 | 0 | 0 | 500000 | 24.4952 | CAPITAL | No | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 1 | 4 | 2 | 1 | 2 | 2 | 4 | 3 |  | 47.5% | 5 | 3 | 5 | 5 | 2 | 5 |  | 80% | 8 |  | 840.2082
1484 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2027-04-30 | 2027 | 36 | 4 | 2027-03-25 | high | high | med | med | med | 1500000 | 1517309 | 1527293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 56.1178 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  |  | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | no | 4 | 5 | 3 | 3 | 4 | 1 | 3 | 1 |  | 60% | 6 | 1 | 5 | 5 | 1 | 3 |  | 60% | 6 |  | 5000
1485 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Edmonton | 2026-03-31 | 2026 | 120 | 4 | 2025-12-01 | med | med | low | high | med | 500000 | 583881 | 573876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 300000 | 50000 | 0 | 500000 | 11.6418 | EXPENSE | No | Pipeline segment |  | X |  | X | X | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 5 | 4 | 2 | 2 | 1 | 2 | 3 | 5 |  | 60% | 6 | 4 | 2 | 1 | 4 | 1 |  | 48% | 5 |  | 1207.7993
1486 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Quebec City | 2025-06-30 | 2025 | 250 | 15 | 2024-10-23 | low | med | low | low | high | 550000 | 554230 | 580197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 550000 | 6.3304 | CAPITAL | No | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | no | no | no | 2 | 1 | 3 | 4 | 2 | 2 | 4 | 2 |  | 50% | 5 | 4 | 4 | 1 | 1 | 1 |  | 44% | 5 |  | 191.3942
1487 | L2 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Saskatoon | 2029-11-30 | 2029 | 180 | 10 | 2029-06-03 | low | low | med | high | low | 800000 | 962796 | 971191 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 107.4224 | EXPENSE | No | NO outage |  | X | X |  | X | no | Yes | Yes | no | no | no | no | Yes | Yes | 5 | 5 | 3 | 5 | 3 | 5 | 2 | 3 |  | 77.5% | 8 | 3 | 5 | 1 | 5 | 4 |  | 72% | 8 |  | 173.2929
1488 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Edmonton | 2027-08-31 | 2027 | 120 | 10 | 2027-05-03 | med | med | low | med | low | 400000 | 422034 | 425419 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 101.2735 | EXPENSE | Yes | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 4 | 1 | 4 | 2 | 1 | 1 | 2 |  | 40% | 4 | 2 | 2 | 5 | 2 | 4 |  | 60% | 6 |  | 900.2043
1489 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2030-09-30 | 2030 | 170 | 8 | 2030-04-13 | high | low | high | med | high | 420000 | 488222 | 478271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 252000 | 42000 | 420000 | 202.8834 | CAPITAL | Yes | Pipeline segment |  | X |  | X | X | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 1 | 2 | 5 | 3 | 1 | 3 | 5 |  | 57.5% | 6 | 1 | 1 | 1 | 4 | 3 |  | 40% | 4 |  | 749.7244
1490 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | WINNIPEG | 2028-04-30 | 2028 | 85 | 15 | 2028-02-05 | med | med | high | med | low | 450000 | 416535 | 407647 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 90.3714 | CAPITAL | No | Pipeline segment | X | X | X |  |  | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 3 | 5 | 2 | 4 | 3 | 5 | 4 | 3 |  | 72.5% | 8 | 1 | 2 | 1 | 5 | 3 |  | 48% | 5 |  | 41798.5165
1491 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | North Bay | 2030-12-31 | 2030 | 108 | 4 | 2030-09-14 | med | med | high | low | med | 250000 | 200338 | 207290 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 0 | 0 | 250000 | 167.215 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 3 | 4 | 2 | 5 | 4 | 1 | 5 | 5 |  | 72.5% | 8 | 5 | 5 | 1 | 3 | 5 |  | 76% | 8 |  | 1022.4116
1492 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2025-06-30 | 2025 | 67 | 4 | 2025-04-24 | high | low | high | med | high | 1500000 | 1450980 | 1458652 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 1500000 | 118.0594 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 2 | 4 | 3 | 2 | 2 | 1 | 3 | 1 |  | 45% | 5 | 5 | 5 | 1 | 2 | 3 |  | 64% | 7 |  | 1022.4116
1493 | L1 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Quebec City | 2030-09-30 | 2030 | 53 | 8 | 2030-08-08 | med | low | med | high | high | 4585000 | 4680012 | 4700046 | 1375500 | 2751000 | 458500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4585000 | 91.5834 | CAPITAL | Yes | Station outage |  |  | X |  |  | no | Yes | Yes | no | Yes | no | no | no | Yes | 5 | 4 | 2 | 3 | 2 | 5 | 2 | 3 |  | 65% | 6 | 5 | 1 | 1 | 1 | 5 |  | 52% | 6 |  | 458
1494 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2028-12-31 | 2028 | 17 | 4 | 2028-12-14 | high | low | low | low | med | 1500000 | 1410189 | 1490446 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 61.5579 | EXPENSE | No | Derate/low flow Pipe segment | X |  |  | X | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 5 | 3 | 2 | 1 | 5 | 3 | 1 | 3 |  | 57.5% | 6 | 4 | 3 | 1 | 5 | 5 |  | 72% | 8 |  | 425
1495 | L3 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Winnipeg | 2029-04-30 | 2029 | 259 | 4 | 2028-08-14 | med | low | low | med | low | 2500500 | 2557663 | 2756617 | 750150 | 1500300 | 250050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500500 | 1023.831 | CAPITAL | No | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | Yes | no | Yes | no | Yes | no | 4 | 1 | 2 | 2 | 3 | 4 | 4 | 3 |  | 57.5% | 6 | 5 | 3 | 1 | 2 | 3 |  | 56% | 6 |  | 20000
1496 | L3 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Saskatoon | 2026-12-31 | 2026 | 160 | 4 | 2026-07-24 | med | high | low | high | high | 6620000 | 6005868 | 6132189 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 33.0673 | CAPITAL | No | Station outage |  | X |  | X |  | no | no | Yes | Yes | no | Yes | no | Yes | Yes | 3 | 5 | 2 | 3 | 3 | 2 | 4 | 5 |  | 67.5% | 6 | 1 | 4 | 1 | 2 | 1 |  | 36% | 4 |  | 1875
1497 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2029-11-30 | 2029 | 120 | 8 | 2029-08-02 | med | med | med | low | high | 400000 | 892844 | 905260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 400000 | 190.1713 | CAPITAL | No | Pipeline segment |  |  |  | X | X | Yes | no | no | no | no | Yes | no | no | no | 1 | 2 | 3 | 1 | 3 | 3 | 4 | 1 |  | 45% | 5 | 1 | 4 | 1 | 3 | 2 |  | 44% | 5 |  | 7718.869
1498 | L2 | PIPE INTEGRITY | L&R |  | LAUNCHER RECEIVER INSTALL | Montreal | 2028-04-30 | 2028 | 44 | 8 | 2028-03-17 | med | med | high | low | high | 3500000 | 3561440 | 3450325 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 42.5944 | CAPITAL | No | Station outage | X | X | X | X |  | Yes | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 5 | 2 | 5 | 2 | 2 | 1 | 3 |  | 57.5% | 6 | 5 | 2 | 1 | 5 | 3 |  | 64% | 7 |  | 7718.869
1499 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2026-03-31 | 2026 | 85 | 8 | 2026-01-05 | med | high | low | low | high | 420000 | 405834 | 402505 | 0 | 0 | 42000 | 336000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 98.3964 | EXPENSE | No | pipeline segment outage |  |  |  |  | X | no | Yes | Yes | Yes | no | no | no | Yes | no | 2 | 3 | 2 | 2 | 5 | 3 | 1 | 4 |  | 55% | 6 | 2 | 4 | 1 | 4 | 5 |  | 64% | 7 |  | 6993.5456
1500 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2029-04-30 | 2029 | 150 | 8 | 2028-12-01 | low | high | low | high | high | 350000 | 307934 | 302673 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 350000 | 32.9463 | CAPITAL | No | pipeline segment outage | X | X |  |  |  | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 5 | 1 | 1 | 5 | 2 | 2 | 2 | 4 |  | 55% | 6 | 1 | 5 | 1 | 5 | 2 |  | 56% | 6 |  | 25393.3666
1501 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Calgary | 2026-03-31 | 2026 | 248 | 7 | 2025-07-26 | med | low | high | high | high | 1900000 | 1977581 | 1989278 | 0 | 570000 | 1140000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 94.5144 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | no | no | Yes | Yes | Yes | Yes | Yes | no | 2 | 4 | 2 | 3 | 4 | 2 | 5 | 3 |  | 62.5% | 6 | 4 | 1 | 1 | 3 | 3 |  | 48% | 5 |  | 2369.8282
1502 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | North Bay | 2029-04-30 | 2029 | 266 | 8 | 2028-08-07 | med | high | low | low | med | 250000 | 252651 | 284871 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 56.4922 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | no | Yes | no | Yes | no | no | Yes | no | no | 2 | 2 | 1 | 2 | 2 | 5 | 5 | 3 |  | 55% | 6 | 3 | 5 | 1 | 2 | 4 |  | 60% | 6 |  | 2369.8282
1503 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | VALIDATION | Winnipeg | 2028-12-31 | 2028 | 200 | 8 | 2028-06-14 | med | low | med | high | low | 250000 | 410869 | 416879 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 25000 | 0 | 0 | 0 | 0 | 250000 | 692.039 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X |  | no | Yes | Yes | Yes | Yes | Yes | no | no | no | 1 | 3 | 3 | 3 | 5 | 4 | 4 | 5 |  | 70% | 6 | 5 | 4 | 1 | 2 | 1 |  | 52% | 6 |  | 14928.9944
1504 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2028-12-31 | 2028 | 75 | 4 | 2028-10-17 | high | high | med | med | med | 850000 | 850944 | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 24.4354 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X |  | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 4 |  | 80% | 8 | 4 | 2 | 5 | 1 | 1 |  | 52% | 6 |  | 4785
1505 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Toronto | 2030-12-31 | 2030 | 150 | 15 | 2030-08-03 | low | high | med | high | high | 450000 | 530563 | 545236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 270000 | 45000 | 0 | 0 | 450000 | 60.5912 | CAPITAL | No | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 1 | 2 | 3 | 4 | 3 | 5 | 3 | 4 |  | 62.5% | 6 | 1 | 2 | 1 | 1 | 3 |  | 32% | 4 |  | 477.3811
1506 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | VALIDATION | Winnipeg | 2028-09-30 | 2028 | 224 | 8 | 2028-02-19 | med | med | med | low | low | 250000 | 236609 | 246072 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 96.9233 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | Yes | no | Yes | Yes | Yes | no | no | Yes | no | 2 | 2 | 1 | 2 | 1 | 3 | 3 | 5 |  | 47.5% | 5 | 2 | 4 | 1 | 1 | 1 |  | 36% | 4 |  | 2679.5194
1507 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Winnipeg | 2026-03-31 | 2026 | 85 | 8 | 2026-01-05 | high | low | high | med | med | 400000 | 469283 | 472670 | 120000 | 240000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 143.1483 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 2 | 4 | 3 | 1 | 1 | 4 | 3 | 2 |  | 50% | 5 | 5 | 3 | 1 | 5 | 5 |  | 76% | 8 |  | 1072.7658
1508 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2029-11-30 | 2029 | 202 | 4 | 2029-05-12 | high | med | high | med | high | 300000 | 496541 | 474310 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 86.2445 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | Yes | no | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 4 | 4 | 3 | 1 | 1 | 2 |  | 50% | 5 | 4 | 4 | 1 | 2 | 5 |  | 64% | 7 |  | 1117.2047
1509 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2027-11-30 | 2027 | 223 | 7 | 2027-04-21 | med | low | high | med | high | 2000000 | 2451951 | 2464009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 1200000 | 200000 | 0 | 2000000 | 287.5273 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 4 | 1 | 3 | 4 | 3 | 2 | 4 |  | 55% | 6 | 3 | 2 | 1 | 1 | 4 |  | 44% | 5 |  | 45.3112
1510 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2029-08-31 | 2029 | 206 | 2 | 2029-02-06 | med | med | low | med | med | 350000 | 387958 | 348402 | 0 | 0 | 0 | 0 | 105000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 350000 | 338.5852 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 2 | 5 | 1 | 1 | 1 | 4 |  | 47.5% | 5 | 2 | 5 | 1 | 4 | 4 |  | 64% | 7 |  | 18394.3019
1511 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2029-08-31 | 2029 | 85 | 8 | 2029-06-07 | low | high | high | low | low | 420000 | 480344 | 486953 | 0 | 0 | 0 | 0 | 0 | 126000 | 252000 | 42000 | 0 | 0 | 0 | 0 | 420000 | 122.9237 | CAPITAL | No | Pipeline segment |  |  | X |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 1 | 1 | 4 | 2 | 5 | 3 | 3 |  | 52.5% | 6 | 2 | 5 | 1 | 2 | 3 |  | 52% | 6 |  | 76225.6763
1512 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2025-09-30 | 2025 | 360 | 4 | 2024-10-05 | low | high | med | low | high | 1750000 | 1822372 | 1853987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 87.2637 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X | X | X | no | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 1 | 3 | 1 | 1 | 3 | 5 | 1 | 2 |  | 42.5% | 5 | 2 | 5 | 1 | 2 | 2 |  | 48% | 5 |  | 16.9273
1513 | L1 | PIPE INTEGRITY | Excavation | SCC | RECOAT | Winnipeg | 2027-08-31 | 2027 | 135 | 5 | 2027-04-18 | low | low | low | low | high | 400000 | 424886 | 436808 | 0 | 0 | 40000 | 320000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 9.937 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | Yes | no | no | Yes | Yes | Yes | Yes | no | 4 | 2 | 3 | 3 | 2 | 1 | 4 | 5 |  | 60% | 6 | 4 | 1 | 1 | 3 | 3 |  | 48% | 5 |  | 16.9273
1514 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Edmonton | 2030-03-31 | 2030 | 120 | 10 | 2029-12-01 | low | low | med | low | med | 400000 | 340748 | 84971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 240000 | 40000 | 0 | 0 | 400000 | 7.9241 | CAPITAL | No | Pipeline segment |  | X | X |  | X | no | no | no | Yes | no | no | no | Yes | no | 3 | 4 | 3 | 5 | 4 | 4 | 1 | 5 |  | 72.5% | 8 | 5 | 3 | 1 | 4 | 4 |  | 68% | 7 |  | 560.1412
1515 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Quebec City | 2025-06-30 | 2025 | 131 | 4 | 2025-02-19 | low | med | high | high | med | 1500000 | 1411959 | 1411361 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 122.5762 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 4 | 2 | 2 | 2 | 2 | 4 | 2 | 2 |  | 50% | 5 | 5 | 3 | 1 | 2 | 2 |  | 52% | 6 |  | 16059.7772
1516 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | North Bay | 2025-06-30 | 2025 | 204 | 2 | 2024-12-08 | high | med | high | med | med | 1000000 | 1015946 | 1061154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 60.2487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | Yes | Yes | no | Yes | 5 | 3 | 3 | 4 | 1 | 3 | 5 | 2 |  | 65% | 6 | 1 | 1 | 5 | 5 | 3 |  | 60% | 6 |  | 2369.8282
1517 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2027-08-31 | 2027 | 133 | 2 | 2027-04-20 | low | med | low | low | med | 520000 | 520076 | 521552 | 0 | 156000 | 312000 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 339.8771 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 2 | 3 | 1 | 4 | 4 | 2 | 2 | 2 |  | 50% | 5 | 5 | 5 | 1 | 1 | 2 |  | 56% | 6 |  | 2491.953
1518 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2026-12-31 | 2026 | 158 | 4 | 2026-07-26 | med | low | low | low | med | 1750000 | 1800359 | 1858385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 201.382 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | Yes | no | no | no | no | no | Yes | no | no | 4 | 3 | 1 | 3 | 4 | 1 | 4 | 3 |  | 57.5% | 6 | 5 | 5 | 1 | 3 | 3 |  | 68% | 7 |  | 2480.6254
1519 | L3 | PIPE INTEGRITY | Excavation | SCC | RECOAT | Montreal | 2030-09-30 | 2030 | 200 | 5 | 2030-03-14 | high | med | low | high | med | 500000 | 580071 | 863077 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 339.2298 | CAPITAL | No | pipeline segment outage |  | X | X |  |  | no | Yes | no | Yes | no | Yes | no | no | no | 2 | 4 | 2 | 1 | 5 | 3 | 5 | 4 |  | 65% | 6 | 2 | 5 | 1 | 1 | 4 |  | 52% | 6 |  | 6039.0018
1520 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Quebec City | 2027-04-30 | 2027 | 284 | 4 | 2026-07-20 | low | high | high | low | med | 125000 | 137635 | 149404 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 946.0832 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 2 | 2 | 3 | 2 | 3 | 3 | 3 | 5 |  | 57.5% | 6 | 1 | 4 | 1 | 2 | 2 |  | 40% | 4 |  | 13659.1884
1521 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Regina | 2025-06-30 | 2025 | 150 | 10 | 2025-01-31 | med | med | high | med | low | 500000 | 758562 | 785895 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 101.141 | CAPITAL | No | Pipeline segment |  | X |  | X |  | no | Yes | no | no | Yes | Yes | Yes | no | no | 3 | 3 | 3 | 3 | 5 | 1 | 5 | 4 |  | 67.5% | 6 | 4 | 2 | 1 | 2 | 5 |  | 56% | 6 |  | 13659.1884
1522 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Toronto | 2028-12-31 | 2028 | 103 | 8 | 2028-09-19 | low | low | high | low | med | 400000 | 1157635 | 1189920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 105.7103 | CAPITAL | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 4 | 2 | 2 | 3 | 3 | 1 | 3 | 2 |  | 50% | 5 | 3 | 5 | 1 | 5 | 2 |  | 64% | 7 |  | 17906.9371
1523 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | North Bay | 2025-06-30 | 2025 | 185 | 4 | 2024-12-27 | high | low | low | low | low | 450000 | 878955 | 905888 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80.7138 | CAPITAL | No | pipeline segment outage | X | X |  | X |  | no | Yes | no | Yes | no | Yes | no | Yes | no | 2 | 1 | 3 | 5 | 1 | 1 | 5 | 1 |  | 47.5% | 5 | 2 | 2 | 1 | 5 | 1 |  | 44% | 5 |  | 21537.8368
1524 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2026-12-31 | 2026 | 34 | 4 | 2026-11-27 | med | low | med | med | med | 1000000 | 1021505 | 1092551 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 56.5076 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | no | no | no | no | no | no | no | no | Yes | 5 | 2 | 1 | 3 | 2 | 4 | 1 | 3 |  | 52.5% | 6 | 2 | 5 | 1 | 3 | 4 |  | 60% | 6 |  | 2973.4021
1525 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2028-12-31 | 2028 | 113 | 4 | 2028-09-09 | high | high | high | high | high | 350000 | 304631 | 304242 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 26.1799 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | Yes | no | no | no | Yes | no | Yes | Yes | 2 | 4 | 2 | 2 | 5 | 2 | 2 | 4 |  | 57.5% | 6 | 3 | 4 | 1 | 5 | 2 |  | 60% | 6 |  | 5776.4313
1526 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Montreal | 2026-05-31 | 2026 | 200 | 8 | 2025-11-12 | med | med | med | low | low | 500000 | 501069 | 508000 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 800000 | 20.7067 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | no | no | no | no | Yes | Yes | Yes | 3 | 3 | 3 | 3 | 4 | 1 | 5 | 5 |  | 67.5% | 6 | 5 | 2 | 1 | 2 | 2 |  | 48% | 5 |  | 2166.5828
1527 | L3 | PIPE INTEGRITY | Excavation | SCC | RECOAT | Ottawa | 2026-05-31 | 2026 | 160 | 2 | 2025-12-22 | low | high | low | high | low | 400000 | 674072 | 656987 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 133.3009 | EXPENSE | No | Station outage | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | Yes | no | Yes | 3 | 2 | 4 | 3 | 3 | 5 | 1 | 4 |  | 62.5% | 6 | 2 | 5 | 1 | 1 | 2 |  | 44% | 5 |  | 1083.35
1528 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | CUTOUT | Toronto | 2030-03-31 | 2030 | 200 | 15 | 2029-09-12 | high | med | med | low | low | 450000 | 1236197 | 1274450 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 65.7764 | CAPITAL | No | Pipeline segment | X | X | X |  | X | Yes | Yes | no | no | no | no | Yes | Yes | Yes | 5 | 4 | 1 | 3 | 3 | 3 | 1 | 1 |  | 52.5% | 6 | 3 | 4 | 1 | 1 | 3 |  | 48% | 5 |  | 1846.6194
1529 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | North Bay | 2029-11-30 | 2029 | 150 | 1 | 2029-07-03 | med | med | high | med | low | 550000 | 531626 | 566466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 618.2189 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | Yes | no | Yes | Yes | Yes | no | no | no | Yes | 3 | 3 | 3 | 3 | 4 | 2 | 4 | 3 |  | 62.5% | 6 | 1 | 1 | 1 | 4 | 5 |  | 48% | 5 |  | 9580.8769
1530 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | North Bay | 2029-04-30 | 2029 | 120 | 1 | 2028-12-31 | high | med | high | med | high | 125000 | 105456 | 105103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 713.9495 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  |  |  | Yes | Yes | no | no | Yes | Yes | no | Yes | no | 5 | 3 | 2 | 1 | 2 | 1 | 4 | 4 |  | 55% | 6 | 2 | 5 | 1 | 5 | 4 |  | 68% | 7 |  | 5875
1531 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2029-04-30 | 2029 | 292 | 7 | 2028-07-12 | low | med | med | high | high | 1500000 | 1307852 | 1350870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 150000 | 0 | 0 | 1500000 | 152.9836 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 1 | 1 | 3 | 1 | 1 | 5 | 2 |  | 42.5% | 5 | 5 | 1 | 1 | 5 | 5 |  | 68% | 7 |  | 25777
1532 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Saskatoon | 2026-03-31 | 2026 | 184 | 2 | 2025-09-28 | high | med | low | med | high | 275000 | 279845 | 309640 | 0 | 0 | 0 | 0 | 0 | 82500 | 165000 | 27500 | 0 | 0 | 0 | 0 | 275000 | 500.6594 | EXPENSE | No | Derate/low flow Pipe segment | X | X |  | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 2 | 2 | 3 | 4 | 2 | 2 | 1 | 4 |  | 50% | 5 | 3 | 5 | 5 | 2 | 4 |  | 76% | 8 |  | 5522
1533 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP- ANODE REPL | Montreal | 2026-12-31 | 2026 | 150 | 5 | 2026-08-03 | low | high | med | low | low | 600000 | 851724 | 857404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 116.0893 | CAPITAL | Yes | pipeline segment outage |  | X |  | X | X | no | no | no | no | Yes | Yes | no | Yes | Yes | 2 | 5 | 1 | 3 | 2 | 5 | 4 | 1 |  | 57.5% | 6 | 1 | 3 | 1 | 2 | 1 |  | 32% | 4 |  | 4101.0339
1534 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | SLEEVE | Saskatoon | 2029-04-30 | 2029 | 170 | 4 | 2028-11-11 | med | low | low | med | med | 550000 | 586220 | 590135 | 0 | 0 | 0 | 0 | 0 | 165000 | 330000 | 55000 | 0 | 0 | 0 | 0 | 550000 | 33.5343 | EXPENSE | Yes | Pipeline segment | X | X | X | X |  | no | no | Yes | no | Yes | no | Yes | no | Yes | 2 | 2 | 2 | 5 | 3 | 1 | 3 | 3 |  | 52.5% | 6 | 1 | 5 | 1 | 4 | 1 |  | 48% | 5 |  | 22170.3266
1535 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Winnipeg | 2028-04-30 | 2028 | 120 | 15 | 2028-01-01 | med | low | low | high | med | 500000 | 513676 | 518168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 511.7996 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 2 | 5 | 3 | 2 | 2 | 3 | 1 | 1 |  | 47.5% | 5 | 4 | 3 | 1 | 2 | 1 |  | 44% | 5 |  | 842.9817
1536 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2026-09-30 | 2026 | 200 | 10 | 2026-03-14 | low | low | med | med | med | 500000 | 491921 | 499436 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 47.5442 | EXPENSE | No | Pipeline segment | X |  |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 4 | 3 | 2 | 5 | 1 | 5 | 5 | 1 |  | 65% | 6 | 4 | 4 | 1 | 3 | 4 |  | 64% | 7 |  | 842.9817
1537 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2029-11-30 | 2029 | 41 | 4 | 2029-10-20 | low | high | low | low | high | 1900000 | 1900004 | 1920751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 44.5632 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  | X |  | Yes | Yes | no | no | no | no | no | no | Yes | 4 | 5 | 4 | 2 | 2 | 2 | 2 | 4 |  | 62.5% | 6 | 1 | 1 | 1 | 5 | 5 |  | 52% | 6 |  | 13420.4072
1538 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | North Bay | 2026-05-31 | 2026 | 150 | 10 | 2026-01-01 | low | high | low | med | low | 400000 | 555683 | 550953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 55.3744 | CAPITAL | No | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | Yes | no | Yes | no | 2 | 2 | 1 | 4 | 2 | 2 | 1 | 3 |  | 42.5% | 5 | 1 | 2 | 5 | 2 | 5 |  | 60% | 6 |  | 1727.2647
1539 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | North Bay | 2030-12-31 | 2030 | 150 | 10 | 2030-08-03 | high | med | high | high | low | 550000 | 689835 | 687417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 412.8922 | CAPITAL | No | pipeline segment outage | X |  |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 5 | 3 | 4 | 5 | 1 | 5 | 1 | 5 |  | 72.5% | 8 | 5 | 3 | 1 | 1 | 2 |  | 48% | 5 |  | 2588
1540 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Calgary | 2028-09-30 | 2028 | 150 | 4 | 2028-05-03 | low | med | low | high | med | 350000 | 406595 | 482491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 284.7276 | CAPITAL | No | Pipeline segment | X | X |  | X | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 2 | 1 | 4 | 4 | 4 | 4 | 3 | 4 |  | 65% | 6 | 2 | 4 | 1 | 2 | 2 |  | 44% | 5 |  | 18109.7232
1541 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2030-03-31 | 2030 | 191 | 12 | 2029-09-21 | high | med | low | high | high | 350000 | 479453 | 498408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 58.7845 | CAPITAL | No | Pipeline segment |  |  | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 4 | 2 | 3 | 5 | 5 | 5 | 4 | 5 |  | 82.5% | 9 | 2 | 5 | 1 | 4 | 5 |  | 68% | 7 |  | 20815.3255
1542 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2028-12-31 | 2027 | 200 | 10 | 2028-06-14 | low | low | low | high | high | 500000 | 852395 | 896748 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 22.5065 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | no | no | no | Yes | no | no | no | Yes | 1 | 1 | 2 | 2 | 4 | 3 | 4 | 3 |  | 50% | 5 | 3 | 2 | 1 | 5 | 4 |  | 60% | 6 |  | 48955
1543 | L1 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Calgary | 2026-12-31 | 2026 | 180 | 10 | 2026-07-04 | high | med | med | high | med | 400000 | 398965 | 399197 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 71.4985 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 1 | 5 | 4 | 2 | 2 | 3 | 3 | 4 |  | 60% | 6 | 4 | 3 | 1 | 4 | 1 |  | 52% | 6 |  | 278.7236
1544 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2028-12-31 | 2028 | 85 | 10 | 2028-10-07 | high | low | med | med | high | 400000 | 805802 | 391083 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 36.3611 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | no | Yes | no | no | Yes | no | no | Yes | no | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 5 |  | 42.5% | 5 | 4 | 2 | 5 | 4 | 5 |  | 80% | 8 |  | 278.7236
1545 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Montreal | 2025-11-30 | 2025 | 165 | 1 | 2025-06-18 | low | low | low | high | low | 350000 | 374582 | 376971 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 593.4244 | EXPENSE | No | Pipeline segment | X | X | X |  | X | no | no | Yes | no | no | no | Yes | Yes | Yes | 1 | 1 | 1 | 5 | 4 | 5 | 5 | 2 |  | 60% | 6 | 5 | 4 | 1 | 4 | 4 |  | 72% | 8 |  | 203.1281
1546 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Ottawa | 2028-09-30 | 2028 | 175 | 10 | 2028-04-08 | med | med | med | low | med | 400000 | 644214 | 640670 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 800000 | 101.6158 | CAPITAL | No | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 5 | 5 | 3 | 1 | 2 | 1 | 2 | 1 |  | 50% | 5 | 4 | 3 | 5 | 1 | 2 |  | 60% | 6 |  | 203.1281
1547 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2025-09-30 | 2025 | 81 | 4 | 2025-07-11 | high | low | high | low | high | 1750000 | 1875896 | 1478514 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 800000 | 24.8857 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  |  | no | Yes | no | Yes | no | no | no | no | Yes | 5 | 5 | 4 | 3 | 5 | 1 | 5 | 1 |  | 72.5% | 8 | 3 | 5 | 1 | 3 | 5 |  | 68% | 7 |  | 203.1281
1548 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | CUTOUT | Regina | 2028-12-31 | 2028 | 85 | 15 | 2028-10-07 | high | high | med | high | high | 450000 | 868046 | 874514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 82.8772 | CAPITAL | No | Pipeline segment |  | X |  | X | X | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 1 | 5 | 2 | 2 | 3 | 1 | 1 | 1 |  | 40% | 4 | 2 | 3 | 1 | 1 | 1 |  | 32% | 4 |  | 23717.2367
1549 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Edmonton | 2028-12-31 | 2028 | 75 | 4 | 2028-10-17 | med | med | med | low | low | 2450000 | 2254742 | 2248761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 57.9714 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 1 | 4 | 4 | 1 | 4 | 5 | 1 | 4 |  | 60% | 6 | 5 | 5 | 1 | 5 | 2 |  | 72% | 8 |  | 1174.9707
1550 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2026-09-30 | 2026 | 85 | 8 | 2026-07-07 | high | med | low | low | low | 350000 | 379854 | 376546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 25.9626 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 5 | 2 | 1 | 1 | 4 | 3 | 4 | 2 |  | 55% | 6 | 3 | 2 | 1 | 5 | 1 |  | 48% | 5 |  | 13677.1818
1551 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Calgary | 2026-03-31 | 2026 | 100 | 8 | 2025-12-21 | med | med | low | med | med | 400000 | 380000 | 358470 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 183.6307 | EXPENSE | Yes | Pipeline segment |  |  | X |  |  | no | no | Yes | Yes | no | Yes | no | Yes | no | 5 | 5 | 1 | 2 | 1 | 1 | 4 | 5 |  | 60% | 6 | 2 | 5 | 1 | 4 | 4 |  | 64% | 7 |  | 16021.8416
1552 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | WINNIPEG | 2030-03-31 | 2030 | 150 | 10 | 2029-11-01 | low | med | high | med | low | 400000 | 388560 | 387036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 31.5417 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 1 | 4 | 3 | 2 | 3 | 4 | 5 | 1 |  | 57.5% | 6 | 3 | 3 | 1 | 5 | 5 |  | 68% | 7 |  | 7007.9205
1553 | L2 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Regina | 2028-09-30 | 2028 | 180 | 10 | 2028-04-03 | high | high | med | low | high | 750000 | 754518 | 786550 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 57.545 | EXPENSE | No | NO outage | X |  | X |  | X | Yes | Yes | Yes | no | no | no | no | no | no | 4 | 5 | 2 | 3 | 1 | 4 | 2 | 3 |  | 60% | 6 | 3 | 1 | 1 | 1 | 5 |  | 44% | 5 |  | 1685.963
1554 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Winnipeg | 2028-12-31 | 2028 | 85 | 4 | 2028-10-07 | low | med | high | med | med | 2500000 | 2758655 | 2869566 | 0 | 0 | 250000 | 1000000 | 1000000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 383.6846 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | no | no | Yes | Yes | Yes | no | 4 | 5 | 4 | 3 | 2 | 1 | 1 | 1 |  | 52.5% | 6 | 5 | 5 | 1 | 1 | 1 |  | 52% | 6 |  | 778.6578
1555 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2026-09-30 | 2026 | 159 | 2 | 2026-04-24 | high | med | med | med | high | 350000 | 441828 | 446179 | 0 | 35000 | 280000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 16.1628 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X | X | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 5 | 1 | 4 | 3 | 3 | 4 | 2 | 3 |  | 62.5% | 6 | 2 | 5 | 1 | 4 | 2 |  | 56% | 6 |  | 121.8769
1556 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2028-09-30 | 2028 | 197 | 4 | 2028-03-17 | med | high | high | med | low | 1800000 | 1909884 | 1937687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 97.7988 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | no | no | Yes | no | no | no | no | no | Yes | 5 | 4 | 2 | 5 | 1 | 3 | 3 | 2 |  | 62.5% | 6 | 1 | 3 | 1 | 2 | 2 |  | 36% | 4 |  | 643.2391
1557 | L1 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Quebec City | 2026-12-31 | 2026 | 245 | 20 | 2026-04-30 | med | low | low | med | med | 8550000 | 8506803 | 8740397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855000 | 6840000 | 855000 | 0 | 0 | 8550000 | 96.8203 | CAPITAL | No | pipeline segment outage | X |  | X | X | X | Yes | no | no | no | Yes | Yes | Yes | Yes | no | 3 | 3 | 1 | 2 | 3 | 2 | 5 | 3 |  | 55% | 6 | 4 | 5 | 1 | 5 | 4 |  | 76% | 8 |  | 267.7598
1558 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Toronto | 2026-05-31 | 2026 | 335 | 4 | 2025-06-30 | med | med | low | high | low | 1500000 | 1871375 | 1900437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 20.7353 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X | X | Yes | no | Yes | Yes | no | Yes | Yes | no | Yes | 5 | 2 | 3 | 3 | 5 | 2 | 3 | 5 |  | 70% | 6 | 5 | 5 | 1 | 2 | 2 |  | 60% | 6 |  | 267.7598
1559 | L3 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | North Bay | 2025-06-30 | 2025 | 180 | 25 | 2025-01-01 | med | high | med | high | med | 14050000 | 15158244 | 15509480 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80.1164 | CAPITAL | Yes | pipeline segment outage | X |  |  | X | X | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 1 | 3 | 1 | 2 | 4 | 3 |  | 50% | 5 | 2 | 5 | 1 | 1 | 4 |  | 52% | 6 |  | 17599.38
1560 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Montreal | 2025-09-30 | 2025 | 200 | 10 | 2025-03-14 | med | low | low | high | high | 500000 | 564753 | 562254 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 91.2063 | CAPITAL | No | Pipeline segment |  |  | X |  |  | no | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 5 | 4 | 5 | 4 | 1 | 2 | 5 |  | 72.5% | 8 | 4 | 2 | 1 | 1 | 1 |  | 36% | 4 |  | 7024.225
1561 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Edmonton | 2028-04-30 | 2028 | 60 | 10 | 2028-03-01 | high | high | low | med | med | 1300000 | 1227077 | 1411856 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 80.7922 | EXPENSE | Yes | pipeline segment outage |  |  | X |  | X | no | Yes | Yes | no | Yes | Yes | Yes | no | Yes | 4 | 4 | 4 | 5 | 1 | 1 | 3 | 5 |  | 67.5% | 6 | 2 | 1 | 1 | 4 | 3 |  | 44% | 5 |  | 1591.17
1562 | L3 | PIPE INTEGRITY | CATHODIC PROTECT |  | CP-BRUSHING | Montreal | 2028-04-30 | 2028 | 180 | 8 | 2027-11-02 | med | med | high | low | med | 1000000 | 1022203 | 1280954 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 44.865 | EXPENSE | No | NO outage |  | X | X | X |  | Yes | Yes | no | no | Yes | no | no | no | no | 4 | 1 | 4 | 4 | 3 | 2 | 5 | 3 |  | 65% | 6 | 2 | 1 | 5 | 1 | 4 |  | 52% | 6 |  | 6832.492
1563 | L3 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Toronto | 2028-04-30 | 2028 | 150 | 5 | 2027-12-02 | med | high | high | high | high | 420000 | 434790 | 444911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 114.2737 | EXPENSE | No | Pipeline segment | X |  |  |  |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 2 | 5 | 1 | 3 | 2 | 2 | 3 | 2 |  | 50% | 5 | 3 | 4 | 5 | 1 | 5 |  | 72% | 8 |  | 5845
1564 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2027-08-31 | 2027 | 201 | 2 | 2027-02-11 | med | med | med | high | med | 650000 | 835557 | 838033 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 224.9398 | EXPENSE | No | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | Yes | no | 5 | 5 | 1 | 2 | 4 | 2 | 2 | 1 |  | 55% | 6 | 1 | 5 | 1 | 5 | 1 |  | 52% | 6 |  | 5732.891
1565 | L2 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Winnipeg | 2030-03-31 | 2030 | 168 | 12 | 2029-10-14 | low | med | high | med | high | 3420000 | 3477100 | 3401079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 369.6154 | CAPITAL | Yes | pipeline segment outage | X | X |  |  | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 5 | 5 | 1 | 4 | 3 | 3 | 3 | 1 |  | 62.5% | 6 | 1 | 5 | 1 | 3 | 4 |  | 56% | 6 |  | 5097.261
1566 | L2 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2029-11-30 | 2029 | 120 | 5 | 2029-08-02 | med | high | high | low | high | 400000 | 408461 | 404334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 125.3264 | EXPENSE | No | Pipeline segment | X |  | X |  | X | no | Yes | no | Yes | no | Yes | no | Yes | no | 3 | 1 | 2 | 1 | 5 | 3 | 2 | 5 |  | 55% | 6 | 1 | 1 | 1 | 4 | 2 |  | 36% | 4 |  | 4391.637
1567 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | VALIDATION | Montreal | 2027-04-30 | 2027 | 226 | 5 | 2026-09-16 | med | high | high | high | high | 250000 | 282472 | 312000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 68.1605 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X |  | X | no | no | no | Yes | no | Yes | Yes | no | no | 2 | 1 | 3 | 3 | 1 | 4 | 5 | 5 |  | 60% | 6 | 5 | 2 | 5 | 2 | 1 |  | 60% | 6 |  | 4314.195
1568 | L2 | PIPE INTEGRITY | CLASS |  | CLASS UPGRADE | Ottawa | 2028-09-30 | 2028 | 225 | 15 | 2028-02-18 | low | low | high | med | low | 5400000 | 5427475 | 5354713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 89.0006 | CAPITAL | No | pipeline segment outage | X |  | X | X |  | Yes | Yes | Yes | no | Yes | no | no | no | no | 2 | 1 | 1 | 4 | 3 | 1 | 3 | 3 |  | 45% | 5 | 2 | 5 | 5 | 2 | 1 |  | 60% | 6 |  | 4858.887
1569 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Quebec City | 2030-12-31 | 2030 | 150 | 4 | 2030-08-03 | med | med | med | high | low | 700000 | 657099 | 685103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 350000 | 140000 | 0 | 700000 | 484.7808 | CAPITAL | No | Derate/low flow Pipe segment |  |  |  | X |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 1 | 2 | 2 | 4 | 1 | 4 | 2 | 3 |  | 47.5% | 5 | 3 | 2 | 5 | 4 | 4 |  | 72% | 8 |  | 2178.073
1570 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2028-12-31 | 2028 | 238 | 4 | 2028-05-07 | high | high | med | high | low | 1750000 | 1770877 | 1780700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 91.2089 | EXPENSE | No | Derate/low flow Pipe segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | no | 3 | 2 | 1 | 5 | 1 | 3 | 1 | 4 |  | 50% | 5 | 5 | 3 | 1 | 3 | 4 |  | 64% | 7 |  | 1090.538
1571 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Quebec City | 2028-12-31 | 2028 | 320 | 4 | 2028-02-15 | med | high | med | high | high | 1500000 | 1500982 | 1500604 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 7.9794 | EXPENSE | No | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | Yes | Yes | no | no | Yes | no | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 20% | 2 | 2 | 1 | 1 | 5 | 2 |  | 44% | 5 |  | 8501.429
1572 | L1 | PIPE INTEGRITY | EXCAVATION | SCC | RECOAT | Saskatoon | 2027-11-30 | 2027 | 150 | 8 | 2027-07-03 | med | low | med | low | med | 400000 | 366358 | 369590 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 32.0854 | CAPITAL | No | Pipeline segment |  |  | X | X |  | no | Yes | no | no | Yes | no | Yes | no | no | 2 | 3 | 4 | 1 | 1 | 1 | 2 | 1 |  | 37.5% | 4 | 1 | 1 | 1 | 1 | 3 |  | 28% | 3 |  | 4052.085
1573 | L2 | PIPE INTEGRITY | EXCAVATION | SCC | CUTOUT | Edmonton | 2026-09-30 | 2026 | 85 | 8 | 2026-07-07 | low | med | high | high | high | 550000 | 553200 | 542753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 123.3918 | CAPITAL | No | Pipeline segment |  | X |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 1 | 1 | 2 | 4 | 4 | 3 | 2 | 1 |  | 45% | 5 | 1 | 1 | 1 | 1 | 1 |  | 20% | 2 |  | 6062.603
1574 | L2 | FACILITY | MECHANICAL |  | DOMESTIC WATER | Saskatoon | 2027-10-31 | 2027 | 251 | 0 | 2027-02-22 | high | high | low | low | med | 65716 | 80320 | 72802 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 2325.1948 | EXPENSE | No | no | X |  | X |  | X | Yes | Yes | no | no | no | no | Yes | Yes | Yes | 3 | 3 | 3 | 3 | 4 | 3 | 4 | 5 | 3 | 68.89% | 7 | 1 | 1 | 1 | 4 | 1 | 4 | 40% | 4 |  | 31873.2921
1574 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2028-12-31 | 2028 | 355 | 4 | 2028-01-11 | high | high | low | low | high | 1500000 | 1708182 | 1716547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 45.4478 | EXPENSE | No | Derate/low flow Pipe segment | X | X | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 3 | 3 | 3 | 2 | 5 | 4 | 3 | 2 |  | 62.5% | 6 | 1 | 5 | 1 | 4 | 4 |  | 60% | 6 |  | 2610.39
1575 | L3 | FACILITY | MECHANICAL |  | DOMESTIC WATER | Saskatoon | 2028-10-31 | 2028 | 177 | 1 | 2028-05-07 | high | med | med | high | med | 60000 | 98500 | 102500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 94.0727 | CAPITAL | No | Unit outage | X |  | X | X | X | no | Yes | Yes | no | Yes | Yes | no | Yes | no | 2 | 3 | 3 | 2 | 4 | 3 | 1 | 1 | 2 | 46.67% | 5 | 4 | 2 | 1 | 5 | 2 | 3 | 56.67% | 6 |  | 8756
1575 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2029-04-30 | 2029 | 71 | 2 | 2029-02-18 | high | high | high | low | high | 300000 | 378545 | 398478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 311.1133 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X | X | X | no | no | no | Yes | Yes | no | no | Yes | no | 3 | 5 | 3 | 3 | 3 | 4 | 2 | 5 |  | 70% | 6 | 3 | 1 | 1 | 5 | 4 |  | 56% | 6 |  | 241.5599
1576 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CORROSION | CP-RECTIFIER | Saskatoon | 2026-09-30 | 2026 | 130 | 8 | 2026-05-23 | high | low | high | low | high | 700000 | 855692 | 885145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 400000 | 139.156 | CAPITAL | Yes | Derate/low flow Pipe segment |  | X | X |  | X | Yes | Yes | no | no | no | Yes | no | no | Yes | 5 | 1 | 2 | 1 | 1 | 2 | 1 | 4 |  | 42.5% | 5 | 2 | 1 | 1 | 3 | 1 |  | 32% | 4 |  | 6993.546
1577 | L1 | PIPE INTEGRITY | EXCAVATION | DENT | SLEEVE | Edmonton | 2029-11-30 | 2029 | 150 | 4 | 2029-07-03 | med | low | high | low | med | 550000 | 600984 | 601355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 83.4126 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | no | no | no | Yes | Yes | Yes | Yes | no | Yes | 3 | 5 | 2 | 3 | 5 | 5 | 4 | 3 |  | 75% | 8 | 4 | 1 | 1 | 4 | 4 |  | 56% | 6 |  | 222.8052
1578 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Regina | 2027-11-30 | 2027 | 206 | 10 | 2027-05-08 | med | low | low | low | med | 1800000 | 1807733 | 1857547 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 76.4961 | EXPENSE | No | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 5 | 1 | 1 | 5 | 4 | 4 | 4 | 1 |  | 62.5% | 6 | 4 | 3 | 1 | 4 | 5 |  | 68% | 7 |  | 840.2082
1579 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Saskatoon | 2030-09-30 | 2030 | 12 | 4 | 2030-09-18 | high | high | med | med | high | 425000 | 662668 | 637944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127500 | 212500 | 85000 | 425000 | 32.9243 | EXPENSE | Yes | pipeline segment outage | X | X | X |  | X | no | Yes | Yes | no | Yes | no | no | no | no | 4 | 2 | 4 | 3 | 2 | 2 | 4 | 2 |  | 57.5% | 6 | 5 | 1 | 1 | 4 | 1 |  | 48% | 5 |  | 5000
1580 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Saskatoon | 2028-12-31 | 2028 | 64 | 10 | 2028-10-28 | low | low | med | high | med | 1800000 | 1875000 | 1830883 | 540000 | 900000 | 360000 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 2200000 | 49.4725 | EXPENSE | No | pipeline segment outage |  |  |  | X |  | no | no | no | Yes | Yes | Yes | Yes | no | no | 1 | 2 | 4 | 5 | 5 | 2 | 5 | 2 |  | 65% | 6 | 5 | 2 | 1 | 3 | 3 |  | 56% | 6 |  | 646
1581 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Quebec City | 2026-12-31 | 2026 | 52 | 2 | 2026-11-09 | med | med | high | med | high | 450000 | 486253 | 471492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 400000 | 34.7089 | EXPENSE | No | Derate/low flow Pipe segment |  |  | X | X |  | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 1 | 4 | 5 | 4 | 4 | 5 | 4 |  | 80% | 8 | 4 | 1 | 1 | 2 | 2 |  | 40% | 4 |  | 289
1582 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Montreal | 2027-08-31 | 2027 | 41 | 4 | 2027-07-21 | med | med | high | med | high | 1000000 | 1649706 | 1663088 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 96.0767 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X | X | no | Yes | no | no | Yes | Yes | no | no | no | 5 | 5 | 3 | 2 | 5 | 2 | 2 | 3 |  | 67.5% | 6 | 3 | 5 | 1 | 4 | 1 |  | 56% | 6 |  | 347
1583 | L3 | PIPE INTEGRITY | EXCAVATION | DENT | RECOAT | Saskatoon | 2030-09-30 | 2030 | 150 | 4 | 2030-05-03 | med | low | med | med | low | 400000 | 450000 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 24.5147 | EXPENSE | No | Pipeline segment |  | X |  | X |  | no | no | no | no | no | no | Yes | Yes | no | 3 | 1 | 1 | 3 | 5 | 5 | 3 | 1 |  | 55% | 6 | 5 | 2 | 1 | 2 | 3 |  | 52% | 6 |  | 1207.799
1584 | L1 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Edmonton | 2026-03-31 | 2026 | 184 | 10 | 2025-09-28 | low | high | med | high | low | 1300000 | 1281295 | 1270817 | 0 | 130000 | 1040000 | 130000 | 0 | 0 | 0 | 0 | 520000 | 650000 | 130000 | 0 | 2600000 | 714.4143 | EXPENSE | No | pipeline segment outage | X |  | X |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 4 | 1 | 4 | 5 | 2 | 4 | 1 |  | 60% | 6 | 2 | 1 | 1 | 1 | 5 |  | 40% | 4 |  | 898
1585 | L3 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2028-12-31 | 2028 | 296 | 2 | 2028-03-10 | high | low | low | low | med | 350000 | 378827 | 442990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 175000 | 70000 | 350000 | 523.2809 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | no | 5 | 4 | 2 | 2 | 2 | 2 | 5 | 1 |  | 57.5% | 6 | 2 | 2 | 5 | 3 | 1 |  | 52% | 6 |  | 172.2548
1586 | L1 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Ottawa | 2025-06-30 | 2025 | 214 | 2 | 2024-11-28 | med | low | high | high | high | 1000000 | 1200000 | 1281639 | 0 | 0 | 0 | 200000 | 50000 | 100000 | 0 | 0 | 600000 | 50000 | 0 | 0 | 1000000 | 8.2654 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  |  | X | no | no | no | Yes | no | Yes | Yes | no | Yes | 4 | 1 | 3 | 1 | 3 | 1 | 3 | 1 |  | 42.5% | 5 | 4 | 2 | 5 | 4 | 1 |  | 64% | 7 |  | 382.7885
1587 | L3 | PIPE INTEGRITY | HYDROTEST | SCC | CUTOUT | Winnipeg | 2025-09-30 | 2025 | 250 | 10 | 2025-01-23 | high | high | med | med | low | 1300000 | 1424785 | 1450260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 520000 | 650000 | 0 | 0 | 1300000 | 2123.4281 | EXPENSE | Yes | pipeline segment outage | X |  |  |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | no | 1 | 4 | 2 | 2 | 4 | 4 | 4 | 1 |  | 55% | 6 | 2 | 3 | 5 | 5 | 4 |  | 76% | 8 |  | 173.2929
1588 | L2 | PIPE INTEGRITY | ILI | CORROSION | MFL INSPECTION RUN | Regina | 2028-09-30 | 2028 | 114 | 4 | 2028-06-08 | med | high | med | med | low | 1800000 | 1817708 | 1819840 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 400000 | 73.0943 | EXPENSE | No | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 2 | 4 | 4 | 4 | 4 | 1 | 1 |  | 55% | 6 | 2 | 5 | 1 | 4 | 3 |  | 60% | 6 |  | 900.2043
1589 | L3 | PIPE INTEGRITY | EXCAVATION | CORROSION | SLEEVE | North Bay | 2027-08-31 | 2027 | 186 | 10 | 2027-02-26 | low | low | low | low | high | 550000 | 781048 | 788414 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 400000 | 41.8408 | EXPENSE | No | Pipeline segment | X |  | X | X | X | no | Yes | Yes | Yes | Yes | no | no | no | no | 1 | 5 | 1 | 3 | 1 | 1 | 4 | 3 |  | 47.5% | 5 | 3 | 1 | 1 | 4 | 3 |  | 48% | 5 |  | 749.7244
1590 | L2 | PIPE INTEGRITY | EXCAVATION | CORROSION | RECOAT | Toronto | 2026-03-31 | 2026 | 137 | 4 | 2025-11-14 | high | low | low | high | low | 400000 | 301807 | 325115 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 243.4001 | EXPENSE | No | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 5 | 4 | 1 | 3 | 1 | 4 | 5 |  | 60% | 6 | 1 | 1 | 1 | 1 | 3 |  | 28% | 3 |  | 1022.412
1591 | L3 | FACILITY | MECHANICAL |  | SUMP PUMP | North Bay | 2026-07-31 | 2026 | 79 | 2 | 2026-05-13 | low | high | high | med | med | 75000 | 75846 | 75007 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 465.7694 | EXPENSE | Yes | Unit outage |  | X |  |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 3 | 5 | 2 | 5 | 5 | 3 | 4 | 2 | 1 | 66.67% | 7 | 1 | 3 | 5 | 4 | 2 | 5 | 66.67% | 7 |  | 840.2082
1592 | L2 | FACILITY | AUTOMATION & CONTROLS |  | REPAIR | Calgary | 2029-12-31 | 2029 | 86 | 1 | 2029-10-06 | low | low | high | low | med | 47791 | 35167 | 38921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 400000 | 2496.1206 | EXPENSE | No | Unit outage | [5 empty] | Yes | Yes | no | Yes | Yes | no | Yes | no | no | 5 | 5 | 1 | 3 | 5 | 4 | 5 | 3 | 2 | 73.33% | 8 | 1 | 3 | 1 | 3 | 4 | 4 | 53.33% | 6 |  | 22170.3266
1593 | L3 | FACILITY | MEASUREMENT |  | H2S GAS SAMPLER | Winnipeg | 2028-07-31 | 2028 | 60 | 4 | 2028-06-01 | low | low | low | med | low | 500000 | 598050 | 593468 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 25.2562 | CAPITAL | Yes | Derate/low flow Pipe segment |  | X | X | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 3 | 3 | 1 | 2 | 3 | 1 | 3 | 4 | 4 | 53.33% | 6 | 1 | 5 | 1 | 1 | 2 | 2 | 40% | 4 |  | 1588
1594 | L1 | FACILITY | MAJOR EQUIP |  | PT MINOR OH | Quebec City | 2027-07-31 | 2027 | 246 | 4 | 2026-11-27 | med | med | high | high | low | 2615905 | 2573335 | 2610990 | 0 | 0 | 0 | 0 | 120000 | 200000 | 80000 | 0 | 0 | 0 | 0 | 0 | 400000 | 294.0372 | CAPITAL | Yes | unit outage | [5 empty] | Yes | no | no | Yes | no | Yes | no | Yes | no | 4 | 2 | 4 | 3 | 5 | 3 | 1 | 2 | 1 | 55.56% | 6 | 3 | 3 | 5 | 4 | 4 | 4 | 76.67% | 8 |  | 267.7598
Formulas:
Projected Project Start Date = [Required Work Completion Date]-[Project Duration (days)]

## FACILITY LISTS
Province | Line of Business | LOB ID # | Facility Name | PLANT NO. | Unit No. | GAS GEN TYPE | PT TYPE | COMPRESSOR TYPE
Alberta | Gateway | L! | MAYYBURY | B-PLANT | B1 | SOLAR MARS 15000S | PT MARS | MARS COMP
Alberta | Gateway | L! | MAYYBURY | B-PLANT | B2 | SOLAR MARS 15000S | PT MARS | MARS COMP
Alberta | Gateway | L! | MAYYBURY | C-PLANT | C3 | Solar Titan 130 | TITAN PT | TITAN COMP
Alberta | Gateway | L! | MAYYBURY | C-PLANT | C4 | Solar Titan 130 | TITAN PT | TITAN COMP
Alberta | Gateway | L! | NORBURG | A-PLANT | A1 | RB211 - 24G | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | NORBURG | A-PLANT | A2 | RB211 - 24G | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | NORBURG | A-PLANT | A3 | LM2500+ | LM2500 PT | LM 2500
Alberta | Gateway | L! | LAKEVIEW | A-PLANT | A1 | Centaur T-4500 | T4500-PT | CENTAUR COMP
Alberta | Gateway | L! | LAKEVIEW | A-PLANT | A2 | Centaur T-4500 | T4500-PT | CENTAUR COMP
Alberta | Gateway | L! | PAUL CREEK | A-PLANT | A1 | LM2500+ | LM2500 PT | LM 2500
Alberta | Gateway | L! | PAUL CREEK | A-PLANT | A2 | LM2500+ | LM2500 PT | LM 2500
Alberta | Gateway | L! | PAUL CREEK | A-PLANT | A3 | RB211 - DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | SCHOFIELD | A-PLANT | A1 | RB211 - DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | SCHOFIELD | A-PLANT | A2 | LM1600 | ELM116/2
Alberta | Gateway | L! | SCHOFIELD | B-PLANT | B2 | Solar Titan 130 | TITAN PT | TITAN COMP
Alberta | Gateway | L! | SHEFFIELD | A-PLANT | A1 | Centaur T-4500 | CENTAUR PT | CENTAUR COMP
Alberta | Gateway | L! | SHEFFIELD | A-PLANT | A2 | Centaur T-4500 | CENTAUR PT | CENTAUR COMP
Alberta | Gateway | L! | SHEFFIELD | A-PLANT | A3 | Centaur T-4500 | CENTAUR PT | CENTAUR COMP
Alberta | Gateway | L! | OAKENWALD | A-PLANT | A1 | LM1600 | ELM116/2
Alberta | Gateway | L! | OAKENWALD | B-PLANT | B1 | RB211 -DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | LAKEVIEW | A-PLANT | A1 | RB211 - DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | LAKEVIEW | A-PLANT | A2 | Centaur T-4500 | CENTAUR PT | CENTAUR COMP
Alberta | Gateway | L! | BRANBURY | A-PLANT | A1 | RB211 - DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | BRANBURY | A-PLANT | A2 | RB211 - DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | STUART | B-PLANT | B1 | RB211 - DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | STUART | A-PLANT | A1 | RB211 - DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | WOODHALL | A-PLANT | A1 | RB211 - 24C | RT-56 | RFA36 COMPRESSOR
Alberta | Gateway | L! | WOODHALL | A-PLANT | A2 | RB211 - 24C | RT-56 | RFA36 COMPRESSOR
Alberta | Gateway | L! | STUART | A-PLANT | A1 | RB211-24DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | TIMMONS | A-PLANT | A1 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | TIMMONS | A-PLANT | A2 | RB211 - 24C | RT-56 | RFA36 COMPRESSOR
Alberta | Gateway | L! | TIMMONS | C-PLANT | C1 | RB211-24DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | MULDER | C-PLANT | C2 | RECIP |  | RFA36 COMPRESSOR
Alberta | Gateway | L! | MULDER | B-PLANT | B1 | LM2500 | PT-LM2500 | 2500 COMP
Alberta | Gateway | L! | CAUSEWAY | C-PLANT | C2 | Centaur T-4500 | PT-4500 | TAURUS COMP
Alberta | Gateway | L! | VARSITY | A-PLANT | A3 | RB211-24DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | VARSITY | A-PLANT | A4 | RB211-24DLE | RT-62 | RFA36 COMPRESSOR
Alberta | Gateway | L! | VARSITY | B-PLANT | B1 | SOLAR MARS 15000S | PT MARS | MARS COMP
Alberta | Gateway | L! | VARSITY | B-PLANT | B2 | SOLAR MARS 15000S | PT MARS | MARS COMP
Alberta | Gateway | L! | MARSH | A-PLANT | A1 | SOLAR TAURUS 90 | PT TAURUS 90 | TAURUS COMP
Alberta | Gateway | L! | CLIFF | C-PLANT | C1 | SOLAR TAURUS 90 | PT TAURUS 90 | TAURUS COMP
SK | CENTURY | L2 | BURNELL | A-PLANT | A1 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
SK | CENTURY | L2 | CAMBRIDGE | A-PLANT | A1 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
SK | CENTURY | L2 | CONLLEY | A-PLANT | A1 | RB211 - 24G | RT-62 | RFA36 COMPRESSOR
SK | CENTURY | L2 | GATWICK | A-PLANT | A1 | SOLAR MARS 15000S | PT MARS | MARS COMP
SK | CENTURY | L2 | GATWICK | B-PLANT | B1 | Solar Titan 130 | PT TITAN 130 | TITAN COMP
SK | CENTURY | L2 | DECLAN | A-PLANT | A1 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
SK | CENTURY | L2 | DECLAN | A-PLANT | A2 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
SK | CENTURY | L2 | HARROLD | A-PLANT | A1 | LM2500 | LM2500 PT | LM 2500
SK | CENTURY | L2 | HARROLD | A-PLANT | A2 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
SK | CENTURY | L2 | MONROE | A-PLANT | A1 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
MB | CENTURY | L2 | GLOVER | A-PLANT | A1 | LM2500+ | LM2500 PT | LM 2500
MB | CENTURY | L2 | VALLEYRIDGE | A-PLANT | A1 | Solar Titan 130 | TITAN PT | TITAN COMP
MB | CENTURY | L2 | VALLEYRIDGE | A-PLANT | A2 | SOLAR MARS 15000S | PT MARS | MARS COMP
MB | CENTURY | L2 | VALLEYRIDGE | A-PLANT | A3 | SOLAR MARS 15000S | PT MARS | MARS COMP
MB | CENTURY | L2 | VALLEYRIDGE | B-PLANT | B1 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
BC | MOUNTAIN | L3 | ARCHES | A-PLANT | A1 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
BC | MOUNTAIN | L3 | ARCHES | A-PLANT | A2 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
BC | MOUNTAIN | L3 | BIGHORN | A-PLANT | A1 | Solar Titan 130 | TITAN PT | TITAN COMP
BC | MOUNTAIN | L3 | BIGHORN | B-PLANT | B1 | Solar Titan 130 | TITAN PT | TITAN COMP
BC | MOUNTAIN | L3 | CLOVER | A-PLANT | A1 | LM2500+ | LM2500 PT | LM 2500
BC | MOUNTAIN | L3 | CLOVER | B-PLANT | B1 | LM2500+ | LM2500 PT | LM 2500
BC | MOUNTAIN | L3 | SAGE | A-PLANT | A1 | LM2500+ | LM2500 PT | LM 2500
BC | MOUNTAIN | L3 | SAGE | A-PLANT | A2 | LM2500+ | LM2500 PT | LM 2500
ONT | SHIELD | L2 | BURGESS | A-PLANT | A1 | SOLAR MARS 15000S | PT MARS | MARS COMP
ONT | SHIELD | L2 | BURGESS | A-PLANT | A2 | SOLAR MARS 15000S | PT MARS | MARS COMP
ONT | SHIELD | L2 | BURGESS | A-PLANT | A3 | SOLAR MARS 15000S | PT MARS | MARS COMP
ONT | SHIELD | L2 | MARSH | A-PLANT | A1 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
ONT | SHIELD | L2 | MARSH | A-PLANT | A2 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
ONT | SHIELD | L2 | MARSH | A-PLANT | A3 | RB211 - 24DLE | RT-62 | RFA36 COMPRESSOR
ONT | SHIELD | L2 | FOXGLOVE | A-PLANT | A1 | LM2500+ | LM2500 PT | LM 2500
ONT | SHIELD | L2 | FOXGLOVE | A-PLANT | A2 | LM2500+ | LM2500 PT | LM 2500

## Work Requests v7
workRequest | LOB | pipeOrFacility | workType | location | noLaterDate | plannedYear | duration | driverSafety | driverOperational | driverEnvironment | driverRegulatory | driverCompliance | projectedStandardCost | projectedCost | actualCost | burnRate | repairTypeBudget | fullyScoped | outageConfirmed | outagePlanned | outageRequired | detailsScoped | designCompleted | longLeadMaterialsOrdered | resourcesIdentified | transferCompressor | permitsReceived | siteVisitsPerformed | stakeholdersEngaged | stakeholdersSupport | projectReimburseable | projectPlanEst | readinessRank | riskRank
Project 1 | L1 | Facility | replacement | Regina | Dec 31, 2024 | Oct 31, 2026 | 289 | med | low | med | low | low | 1403596 | 819599 | 1476293 | 105.1793 | gpmc | [5 empty] | x | x | x | NR |  |  | x | x |  |  | 9 | 7
Project 2 | L3 | Facility | r/o | North Bay | Jul 31, 2025 | Oct 31, 2025 | 202 | high | med | high | med | med | 323509 | 117034 | 435509 | 134.6204 | r/o |  | x | x | x | x | x | x | x | NR | x | x | x | x | no | x | 1 | 2
Project 3 | L2 | Pipe | Maintenance | Regina | Dec 31, 2024 | Dec 31, 2027 | 287 | low | high | high | med | med | 362622 | 355104 | 1064607 | 293.5859 | gpmc | yes | x | x | x | x | x | NR | x | x | x | x | x |  | No | Yes | 5 | 6
Project 4 | L1 | Pipe | Excavation | Calgary | Dec 31, 2024 | Oct 31, 2027 | 11 | high | low | high | high | low | 1203382 | 463665 | 998950 | 83.0119 | capital | no |  |  | x | x | x |  | x | x | x | [5 empty] | 1 | 8
Project 5 | L2 | Pipe | Inspection | Montreal | Dec 31, 2025 | Dec 31, 2026 | 299 | high | high | med | low | low | 888208 | 349323 | 643855 | 72.4892 | gpmc | yes | x | x | x | x | x | Yes | x | NR | NR | NR | NR | NR | No | Yes | 9 | 1
Project 6 | L1 | Pipe | Piggable | Saskatoon | Dec 31, 2025 | Dec 31, 2026 | 44 | med | high | med | med | high | 1419481 | 861545 | 966688 | 68.1015 | capital | yes | x | x | x | x | x | Yes | x | x | Yes | Yes | Yes |  | No | No | 6 | 9
Project 7 | L2 | Facility | repair | North Bay | Mar 31, 2025 | Dec 31, 2027 | 275 | med | med | med | med | low | 1897274 | 2121976 | 826229 | 43.5482 | capital | Yes |  |  |  | X |  | no | no | Yes | Yes | no | Yes | no | no | no | 5 | 5
Project 8 | L3 | Pipe | replacement | Quebec City | Dec 31, 2025 | Jul 31, 2027 | 149 | med | low | high | high | high | 782902 | 1164077 | 643322 | 82.1715 | capital | Yes | X |  |  | X |  | Yes | no | no | Yes | no | no | no | no | no | 7 | 7
Project 9 | L3 | Facility |  | North Bay | Dec 31, 2025 | Oct 31, 2025 | 203 | med | med | high | low | high | 1030823 | 922832 | 910898 | 88.3661 | r/o | no |  |  | X |  | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 7 | 6
Project 10 | L1 | Facility | inspection | Quebec City | Oct 31, 2025 | Dec 31, 2025 | 243 | high | low | low | med | low | 900862 | 1086029 | 1711671 | 190.0037 | r/o | Yes | X |  |  | X | X | no | no | no | Yes | no | Yes | Yes | no | no | 8 | 3
Project 11 | L3 | Facility | replacement | Saskatoon | Oct 31, 2025 | Jul 31, 2025 | 99 | med | low | high | med | med | 1996053 | 1026873 | 908898 | 45.5348 | gpmc | no |  | X |  |  |  | no | Yes | no | Yes | Yes | no | no | no | no | 8 | 7
Project 12 | L2 | Facility | replacement | Edmonton | Jul 31, 2025 | Jul 31, 2026 | 178 | high | high | high | high | high | 1405775 | 1175219 | 632021 | 44.9589 | r/o | no | X | X |  | X |  | no | Yes | Yes | no | no | no | Yes | Yes | no | 2 | 6
Project 13 | L3 | Pipe | repair | Edmonton | Jul 31, 2025 | Oct 31, 2026 | 215 | high | high | med | low | med | 1920929 | 2616260 | 573469 | 29.8537 | capital | no |  |  |  |  | X | no | no | Yes | no | Yes | no | Yes | no | Yes | 1 | 6
Project 14 | L1 | Facility | excavation | Quebec City | Mar 31, 2025 | Jul 31, 2026 | 211 | high | med | high | low | high | 1972903 | 3134085 | 1527414 | 77.4196 | r/o | Yes | X |  | X |  | X | Yes | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 7
Project 15 | L2 | Facility | inspection | North Bay | Dec 31, 2025 | Dec 31, 2025 | 171 | low | med | low | med | low | 81466 | 63650 | 1098087 | 1347.9083 | r/o | Yes |  | X |  | X |  | Yes | no | no | Yes | Yes | no | Yes | Yes | no | 7 | 1
Project 16 | L1 | Facility |  | Ottawa | Dec 31, 2025 | Jul 31, 2025 | 63 | high | high | med | high | med | 1959126 | 3371052 | 242803 | 12.3934 | gpmc | no |  | X | X | X |  | no | no | no | no | Yes | no | Yes | no | Yes | 2 | 2
Project 17 | L3 | Pipe | inspection | Toronto | Dec 31, 2024 | Jul 31, 2025 | 277 | low | low | med | high | low | 635160 | 989154 | 668872 | 105.3076 | r/o | no | X |  | X | X |  | no | Yes | Yes | no | no | no | no | no | no | 5 | 6
Project 18 | L2 | Pipe | excavation | Quebec City | Jul 31, 2025 | Jul 31, 2026 | 197 | high | low | high | low | med | 1108151 | 375368 | 1476065 | 133.2007 | r/o | no | X |  | X |  | X | Yes | no | no | Yes | no | no | Yes | no | Yes | 6 | 6
Project 19 | L2 | Pipe | inspection | Toronto | Jul 31, 2025 | Oct 31, 2025 | 102 | med | high | high | low | high | 1590263 | 1546054 | 128374 | 8.0725 | r/o | Yes | X |  |  | X | X | Yes | no | Yes | Yes | Yes | no | Yes | Yes | Yes | 7 | 8
Project 20 | L1 | Facility | repair | Edmonton | Jul 31, 2025 | Jul 31, 2026 | 259 | low | low | high | low | low | 1425922 | 632804 | 1669515 | 117.0832 | capital | no |  |  | X |  | X | Yes | no | no | no | no | no | Yes | no | Yes | 8 | 8
Project 21 | L1 | Pipe | inspection | Saskatoon | Dec 31, 2024 | Jul 31, 2027 | 353 | med | low | high | low | high | 962407 | 516105 | 464188 | 48.232 | capital | Yes |  |  | X |  |  | Yes | Yes | no | Yes | no | Yes | Yes | no | no | 3 | 8
Project 22 | L3 | Facility | inspection | Quebec City | Dec 31, 2025 | Jul 31, 2027 | 117 | med | high | low | low | low | 1381712 | 2211022 | 325117 | 23.53 | gpmc | Yes |  |  | X |  |  | Yes | no | Yes | no | no | no | Yes | no | Yes | 9 | 4
Project 23 | L1 | Facility | r/o | Toronto | Oct 31, 2025 | Dec 31, 2025 | 81 | low | high | med | high | low | 161628 | 94209 | 1831911 | 1133.4119 | gpmc | no |  | X |  |  | X | no | Yes | no | Yes | no | no | no | Yes | Yes | 3 | 7
Project 24 | L2 | Facility | inspection | Edmonton | Jul 31, 2025 | Dec 31, 2027 | 363 | low | med | high | high | high | 543065 | 721036 | 1534537 | 282.5697 | gpmc | no | X | X | X | X | X | no | no | no | no | Yes | no | Yes | no | Yes | 7 | 3
Project 25 | L2 | Pipe | inspection | Quebec City | Dec 31, 2025 | Jul 31, 2026 | 103 | high | med | low | high | low | 408365 | 327903 | 639116 | 156.5061 | r/o | no |  | X | X |  |  | no | Yes | no | Yes | no | no | Yes | no | no | 3 | 9
Project 26 | L1 | Facility | r/o | Edmonton | Mar 31, 2025 | Jul 31, 2027 | 148 | med | low | med | low | med | 1910720 | 2510962 | 768859 | 40.2392 | capital | Yes |  |  | X | X |  | no | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 5 | 7
Project 27 | L2 | Facility | inspection | Quebec City | Dec 31, 2025 | Dec 31, 2027 | 167 | med | med | high | high | med | 1865259 | 1668454 | 43395 | 2.3265 | capital | Yes | X | X |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 8 | 2
Project 28 | L1 | Facility | inspection | Calgary | Dec 31, 2025 | Dec 31, 2026 | 214 | low | high | high | med | med | 189065 | 260712 | 286898 | 151.7457 | capital | Yes |  |  | X |  |  | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 1 | 2
Project 29 | L3 | Pipe | repair | Quebec City | Dec 31, 2025 | Dec 31, 2027 | 321 | high | high | high | low | med | 402443 | 193439 | 902166 | 224.1724 | capital | no | X |  |  | X |  | no | Yes | Yes | Yes | Yes | no | no | no | Yes | 6 | 1
Project 30 | L3 | Facility | inspection | Regina | Jul 31, 2025 | Oct 31, 2025 | 316 | low | high | high | low | med | 852248 | 1121939 | 158963 | 18.6522 | capital | no |  |  | X |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 8 | 3
Project 31 | L3 | Facility |  | Saskatoon | Mar 31, 2025 | Oct 31, 2026 | 208 | med | med | med | high | low | 1104970 | 906504 | 766239 | 69.3448 | gpmc | Yes |  | X |  |  | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 8 | 5
Project 32 | L1 | Facility |  | Toronto | Oct 31, 2025 | Dec 31, 2026 | 192 | med | low | med | high | high | 48631 | 49663 | 686100 | 1410.8285 | r/o | no | X | X |  | X |  | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 8 | 7
Project 33 | L2 | Facility | repair | Regina | Jul 31, 2025 | Dec 31, 2027 | 163 | low | med | med | low | high | 1745610 | 945298 | 124929 | 7.1568 | capital | Yes |  | X | X |  | X | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 7 | 2
Project 34 | L2 | Facility |  | Calgary | Dec 31, 2024 | Jul 31, 2026 | 50 | med | low | low | low | high | 1731925 | 2300997 | 657701 | 37.9751 | r/o | no | X | X |  | X | X | no | Yes | Yes | no | no | Yes | no | Yes | Yes | 9 | 5
Project 35 | L3 | Facility | excavation | Edmonton | Jul 31, 2025 | Dec 31, 2025 | 144 | med | high | med | high | low | 1393360 | 473161 | 1397482 | 100.2958 | r/o | Yes | X |  | X |  | X | Yes | no | Yes | no | no | Yes | Yes | no | no | 2 | 3
Project 36 | L2 | Facility |  | Edmonton | Dec 31, 2025 | Jul 31, 2026 | 139 | high | low | high | med | high | 516646 | 796776 | 126179 | 24.4227 | gpmc | no |  | X | X | X | X | no | no | Yes | Yes | no | Yes | no | Yes | no | 1 | 9
Project 37 | L1 | Facility | replacement | Saskatoon | Mar 31, 2025 | Oct 31, 2027 | 260 | high | low | med | med | high | 1518882 | 1180385 | 1450924 | 95.5258 | gpmc | Yes |  | X | X | X | X | Yes | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 8 | 7
Project 38 | L1 | Facility |  | North Bay | Mar 31, 2025 | Jul 31, 2025 | 346 | low | med | med | med | med | 1482699 | 2320512 | 969174 | 65.3655 | gpmc | no |  |  | X |  | X | no | Yes | no | Yes | no | no | no | no | no | 8 | 9
Project 39 | L3 | Facility | replacement | Regina | Jul 31, 2025 | Oct 31, 2026 | 290 | high | high | med | high | med | 1551734 | 2380911 | 1459376 | 94.0481 | r/o | no | X |  |  |  | X | no | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 3 | 6
Project 40 | L1 | Pipe | excavation | Ottawa | Dec 31, 2024 | Dec 31, 2025 | 261 | med | low | low | low | high | 1991858 | 2723844 | 1534008 | 77.0139 | r/o | Yes | X | X | X |  | X | Yes | no | no | no | Yes | Yes | no | Yes | Yes | 3 | 3
Project 41 | L2 | Pipe | replacement | Montreal | Dec 31, 2025 | Dec 31, 2026 | 152 | med | low | low | med | high | 776875 | 615724 | 173290 | 22.306 | gpmc | Yes |  |  |  | X |  | no | no | no | no | no | Yes | no | Yes | no | 8 | 4
Project 42 | L3 | Facility | r/o | Calgary | Mar 31, 2025 | Jul 31, 2025 | 166 | low | high | low | high | high | 718425 | 672876 | 1704559 | 237.2633 | r/o | Yes | X | X | X | X |  | Yes | no | no | no | no | no | no | no | no | 5 | 9
Project 43 | L2 | Facility | r/o | Calgary | Oct 31, 2025 | Dec 31, 2026 | 15 | high | high | med | low | low | 1540410 | 725456 | 1417269 | 92.006 | capital | Yes |  |  | X | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | Yes | 5 | 4
Project 44 | L1 | Facility | r/o | Ottawa | Oct 31, 2025 | Jul 31, 2025 | 12 | low | med | high | med | high | 1915607 | 2667811 | 1448111 | 75.5954 | capital | no | X | X |  | X |  | no | no | no | no | no | Yes | no | no | Yes | 5 | 1
Project 45 | L3 | Facility | inspection | Edmonton | Dec 31, 2024 | Oct 31, 2026 | 301 | low | med | med | low | high | 101550 | 92789 | 445131 | 438.3368 | r/o | no | X |  | X | X | X | no | Yes | Yes | Yes | no | no | Yes | no | no | 4 | 2
Project 46 | L1 | Pipe | replacement | Ottawa | Mar 31, 2025 | Oct 31, 2026 | 100 | low | high | med | high | low | 1898211 | 2484210 | 1329911 | 70.0613 | capital | no | X |  | X | X |  | Yes | Yes | Yes | no | no | no | no | Yes | Yes | 4 | 7
Project 47 | L1 | Facility | r/o | Calgary | Mar 31, 2025 | Oct 31, 2026 | 330 | high | high | low | high | med | 1072828 | 742263 | 1341069 | 125.0032 | capital | no |  |  |  |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 6
Project 48 | L3 | Pipe | r/o | Ottawa | Dec 31, 2025 | Jul 31, 2026 | 225 | high | med | low | low | med | 1480482 | 2444790 | 1365758 | 92.2509 | r/o | Yes | X | X |  |  |  | Yes | Yes | Yes | no | Yes | no | no | no | no | 5 | 8
Project 49 | L1 | Facility | repair | Saskatoon | Oct 31, 2025 | Jul 31, 2025 | 248 | low | med | med | med | high | 1221377 | 1958214 | 1309871 | 107.2454 | capital | Yes | X |  |  | X |  | Yes | Yes | no | no | no | no | no | no | Yes | 1 | 5
Project 50 | L3 | Facility | replacement | Calgary | Dec 31, 2025 | Oct 31, 2027 | 281 | med | high | low | high | high | 242946 | 68622 | 1996570 | 821.8164 | r/o | Yes |  | X |  | X |  | no | no | Yes | no | no | Yes | Yes | no | Yes | 9 | 6
Project 51 | L1 | Pipe | r/o | Edmonton | Jul 31, 2025 | Dec 31, 2025 | 151 | low | high | med | med | high | 310541 | 287882 | 1886020 | 607.3337 | capital | no | X |  | X | X |  | Yes | no | Yes | no | Yes | Yes | no | no | no | 5 | 3
Project 52 | L3 | Facility | replacement | Quebec City | Dec 31, 2024 | Jul 31, 2025 | 41 | med | high | med | med | low | 1435197 | 1077347 | 1559044 | 108.6293 | gpmc | Yes | X |  | X | X |  | no | Yes | no | no | no | no | Yes | no | Yes | 2 | 7
Project 53 | L1 | Facility | r/o | Edmonton | Mar 31, 2025 | Jul 31, 2027 | 220 | high | med | low | low | med | 271927 | 270994 | 496587 | 182.6178 | r/o | no | X | X |  | X | X | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 1 | 4
Project 54 | L1 | Facility | replacement | Winnepeg | Oct 31, 2025 | Jul 31, 2026 | 161 | med | high | high | high | high | 1910160 | 969505 | 1607033 | 84.1308 | r/o | Yes |  |  |  |  | X | Yes | no | no | Yes | no | Yes | no | no | no | 4 | 1
Project 55 | L3 | Facility | r/o | Regina | Jul 31, 2025 | Oct 31, 2025 | 266 | med | med | low | low | high | 1105055 | 1182456 | 1460557 | 132.1705 | r/o | no | X |  | X | X | X | Yes | no | Yes | no | no | no | Yes | Yes | Yes | 5 | 2
Project 56 | L3 | Facility | inspection | Calgary | Dec 31, 2024 | Jul 31, 2025 | 297 | low | high | med | high | med | 303900 | 211382 | 1960886 | 645.2405 | gpmc | Yes |  | X |  | X | X | Yes | no | no | no | no | Yes | no | no | Yes | 6 | 6
Project 57 | L2 | Facility | excavation | Regina | Jul 31, 2025 | Jul 31, 2025 | 12 | med | med | high | low | high | 1482107 | 656280 | 1761596 | 118.8575 | capital | Yes | X | X |  | X | X | no | no | Yes | no | Yes | Yes | Yes | Yes | Yes | 9 | 2
Project 58 | L1 | Pipe | replacement | Edmonton | Dec 31, 2025 | Oct 31, 2027 | 356 | high | high | high | low | low | 227476 | 387230 | 804888 | 353.8343 | r/o | no |  | X | X | X |  | no | no | no | no | Yes | Yes | no | Yes | Yes | 3 | 6
Project 59 | L2 | Pipe |  | Edmonton | Mar 31, 2025 | Jul 31, 2027 | 334 | med | med | med | low | high | 116132 | 39630 | 1162693 | 1001.1823 | capital | Yes |  | X |  | X |  | no | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 8 | 4
Project 60 | L3 | Facility | replacement | Calgary | Dec 31, 2025 | Jul 31, 2027 | 252 | high | low | low | high | med | 1033629 | 411081 | 1971266 | 190.7131 | gpmc | no |  | X |  |  | X | Yes | no | no | no | Yes | no | no | Yes | no | 1 | 8
Project 61 | L3 | Facility | excavation | North Bay | Oct 31, 2025 | Jul 31, 2025 | 177 | med | med | high | med | med | 949128 | 1003499 | 791323 | 83.3737 | capital | no |  | X |  | X |  | no | no | no | no | Yes | no | no | no | no | 8 | 5
Project 62 | L1 | Pipe | repair | Calgary | Dec 31, 2024 | Jul 31, 2026 | 210 | low | high | high | high | low | 182271 | 70670 | 79490 | 43.6109 | gpmc | no |  | X |  |  |  | no | no | no | no | Yes | no | no | Yes | Yes | 6 | 5
Project 63 | L3 | Pipe |  | Quebec City | Oct 31, 2025 | Oct 31, 2027 | 292 | low | med | low | med | med | 522422 | 348851 | 805457 | 154.1775 | gpmc | Yes | X |  |  |  |  | Yes | no | Yes | no | Yes | Yes | no | no | Yes | 2 | 4
Project 64 | L2 | Pipe | r/o | Ottawa | Mar 31, 2025 | Oct 31, 2025 | 360 | high | low | med | low | low | 1916286 | 2746572 | 533835 | 27.8578 | gpmc | no | X |  | X | X | X | Yes | Yes | Yes | Yes | no | no | Yes | Yes | Yes | 5 | 1
Project 65 | L1 | Facility | excavation | Winnepeg | Dec 31, 2025 | Jul 31, 2027 | 262 | med | high | med | high | high | 1467447 | 2025808 | 1214504 | 82.7631 | gpmc | Yes |  | X | X | X |  | Yes | no | no | no | Yes | Yes | no | Yes | Yes | 4 | 5
Project 66 | L2 | Pipe | inspection | Winnepeg | Dec 31, 2025 | Oct 31, 2026 | 18 | med | med | med | med | low | 898203 | 1393625 | 778427 | 86.6649 | gpmc | Yes | X |  | X |  |  | no | no | no | Yes | no | Yes | no | no | no | 3 | 2
Project 67 | L1 | Facility | excavation | North Bay | Mar 31, 2025 | Dec 31, 2027 | 175 | high | med | low | high | high | 765899 | 924157 | 1967657 | 256.9082 | capital | Yes | X | X |  | X |  | Yes | Yes | Yes | no | no | no | Yes | no | Yes | 7 | 9
Project 68 | L3 | Pipe | repair | Regina | Oct 31, 2025 | Oct 31, 2027 | 113 | high | low | high | med | med | 1541969 | 526930 | 31187 | 2.0225 | r/o | no |  | X |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 5
Project 69 | L1 | Pipe | inspection | Toronto | Dec 31, 2024 | Dec 31, 2025 | 252 | med | high | med | high | med | 1380942 | 1728004 | 1900754 | 137.6418 | gpmc | no | X |  |  |  |  | Yes | no | Yes | no | no | no | no | Yes | no | 6 | 2
Project 70 | L1 | Pipe | inspection | Edmonton | Jul 31, 2025 | Oct 31, 2025 | 12 | low | low | high | low | high | 1759507 | 480323 | 151833 | 8.6293 | capital | no |  | X | X |  |  | no | no | no | no | Yes | Yes | no | Yes | Yes | 9 | 7
Project 71 | L2 | Facility | inspection | Edmonton | Oct 31, 2025 | Oct 31, 2027 | 45 | med | low | med | high | high | 1913792 | 2640515 | 662687 | 34.6269 | r/o | Yes | X | X |  | X | X | no | no | Yes | no | no | no | no | no | no | 7 | 7
Project 72 | L3 | Pipe | excavation | Regina | Dec 31, 2024 | Jul 31, 2027 | 24 | med | low | med | high | high | 829801 | 468190 | 390914 | 47.1094 | gpmc | no |  | X |  |  |  | no | Yes | Yes | Yes | no | no | Yes | no | Yes | 6 | 7
Project 73 | L3 | Facility | repair | Ottawa | Jul 31, 2025 | Dec 31, 2027 | 285 | high | med | high | high | low | 561250 | 835729 | 1055144 | 187.9989 | gpmc | no |  | X |  | X |  | no | Yes | no | Yes | no | Yes | Yes | no | no | 5 | 2
Project 74 | L3 | Facility | inspection | Toronto | Dec 31, 2025 | Dec 31, 2026 | 124 | high | high | low | high | med | 1048245 | 1357331 | 194476 | 18.5525 | r/o | Yes |  |  |  |  | X | Yes | no | no | Yes | Yes | Yes | Yes | no | no | 5 | 8
Project 75 | L1 | Pipe | r/o | Quebec City | Dec 31, 2025 | Dec 31, 2027 | 58 | low | low | med | high | med | 1231161 | 607209 | 1281247 | 104.0682 | capital | no |  | X |  | X |  | no | Yes | no | no | Yes | Yes | no | Yes | no | 4 | 7
Project 76 | L2 | Facility | excavation | Winnepeg | Oct 31, 2025 | Jul 31, 2025 | 261 | low | low | high | med | high | 1561462 | 800398 | 1402291 | 89.8063 | capital | Yes |  | X | X |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 6 | 9
Project 77 | L1 | Facility |  | Ottawa | Jul 31, 2025 | Jul 31, 2026 | 173 | med | med | low | high | low | 13348 | 4300 | 1091080 | 8174.1085 | gpmc | Yes |  | X |  | X |  | Yes | Yes | Yes | Yes | no | no | no | no | Yes | 8 | 5
Project 78 | L1 | Facility | excavation | Regina | Mar 31, 2025 | Oct 31, 2027 | 34 | low | high | high | low | high | 1042067 | 586708 | 1520284 | 145.8912 | r/o | Yes | X |  | X | X |  | Yes | no | no | no | Yes | Yes | no | Yes | no | 9 | 8
Project 79 | L2 | Pipe | replacement | Winnepeg | Jul 31, 2025 | Jul 31, 2026 | 127 | med | low | high | high | high | 1076247 | 1338412 | 1748039 | 162.4199 | capital | Yes |  | X |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 6 | 3
Project 80 | L1 | Pipe | replacement | Winnepeg | Oct 31, 2025 | Jul 31, 2027 | 300 | high | med | med | low | med | 590113 | 608837 | 510368 | 86.4865 | capital | no | X |  |  |  | X | no | no | Yes | Yes | no | Yes | Yes | no | no | 6 | 7
Project 81 | L1 | Facility | inspection | Quebec City | Dec 31, 2025 | Oct 31, 2025 | 317 | low | high | high | low | med | 1024739 | 1755693 | 1627998 | 158.8695 | capital | Yes | X |  |  |  | X | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | Yes | 9 | 4
Project 82 | L2 | Facility | excavation | Quebec City | Dec 31, 2024 | Dec 31, 2025 | 311 | low | high | high | high | low | 1246093 | 1585738 | 1775613 | 142.4944 | gpmc | Yes |  |  | X |  | X | no | no | Yes | no | Yes | Yes | Yes | no | no | 4 | 4
Project 83 | L3 | Facility | r/o | Regina | Oct 31, 2025 | Oct 31, 2027 | 114 | med | med | low | low | low | 1287362 | 772387 | 1296217 | 100.6878 | r/o | Yes | X | X |  | X |  | no | Yes | no | no | no | Yes | Yes | Yes | no | 3 | 2
Project 84 | L2 | Facility | inspection | Quebec City | Dec 31, 2025 | Oct 31, 2025 | 350 | high | low | high | high | low | 1320452 | 2240954 | 1480017 | 112.0841 | r/o | no |  | X | X |  |  | no | Yes | no | Yes | no | no | Yes | Yes | Yes | 2 | 9
Project 85 | L1 | Pipe |  | Montreal | Mar 31, 2025 | Oct 31, 2026 | 285 | med | high | med | high | low | 1250257 | 1350007 | 1604728 | 128.3519 | gpmc | Yes | X |  | X |  |  | no | Yes | no | no | Yes | no | Yes | Yes | Yes | 3 | 7
Project 86 | L1 | Facility | repair | Montreal | Oct 31, 2025 | Jul 31, 2025 | 254 | low | med | low | low | low | 1476082 | 713070 | 1037657 | 70.2981 | gpmc | Yes | X | X | X | X | X | Yes | Yes | Yes | no | no | no | Yes | no | Yes | 3 | 3
Project 87 | L1 | Facility | replacement | Edmonton | Jul 31, 2025 | Jul 31, 2026 | 114 | high | med | low | low | high | 317550 | 412874 | 918403 | 289.2152 | r/o | no |  |  |  |  | X | Yes | no | Yes | Yes | no | no | Yes | no | no | 8 | 7
Project 88 | L3 | Pipe |  | Montreal | Mar 31, 2025 | Jul 31, 2026 | 107 | med | med | med | low | high | 438192 | 613552 | 643116 | 146.7658 | capital | Yes | X | X |  | X |  | no | no | Yes | no | no | Yes | no | Yes | Yes | 3 | 5
Project 89 | L3 | Pipe | replacement | Toronto | Oct 31, 2025 | Jul 31, 2027 | 273 | med | low | low | high | high | 1999414 | 1439150 | 1029674 | 51.4988 | gpmc | Yes | X | X |  |  |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | no | 2 | 4
Project 90 | L2 | Facility |  | North Bay | Dec 31, 2024 | Dec 31, 2026 | 243 | high | med | low | high | high | 1953834 | 671642 | 152568 | 7.8086 | r/o | Yes | X | X |  | X |  | Yes | no | no | no | no | no | Yes | no | Yes | 7 | 1
Project 91 | L2 | Facility | repair | Saskatoon | Jul 31, 2025 | Jul 31, 2025 | 242 | high | high | high | high | med | 1383092 | 817657 | 1216107 | 87.9267 | capital | Yes | X | X | X |  |  | no | no | Yes | Yes | no | Yes | no | Yes | Yes | 2 | 9
Project 92 | L2 | Pipe | r/o | Montreal | Oct 31, 2025 | Jul 31, 2025 | 21 | med | med | low | med | med | 1307890 | 1176366 | 1714533 | 131.0915 | capital | Yes |  |  | X |  | X | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 6 | 7
Project 93 | L2 | Facility |  | Calgary | Jul 31, 2025 | Jul 31, 2025 | 238 | med | med | high | high | high | 44157 | 49223 | 1040840 | 2357.1348 | gpmc | Yes | X | X |  |  |  | no | Yes | Yes | Yes | no | no | Yes | Yes | no | 2 | 4
Project 94 | L2 | Pipe | inspection | Ottawa | Dec 31, 2025 | Oct 31, 2026 | 212 | med | med | low | high | low | 679160 | 728334 | 1380186 | 203.2196 | capital | no |  |  | X | X |  | no | Yes | no | Yes | no | no | Yes | Yes | Yes | 9 | 1
Project 95 | L3 | Pipe | repair | Regina | Dec 31, 2025 | Oct 31, 2026 | 172 | low | low | low | low | low | 208070 | 348534 | 1883101 | 905.0324 | r/o | Yes | X |  | X | X | X | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 3 | 8
Project 96 | L1 | Facility | inspection | Saskatoon | Dec 31, 2025 | Dec 31, 2027 | 57 | high | low | low | low | low | 557829 | 388539 | 214808 | 38.5079 | r/o | no |  | X |  | X | X | no | no | no | Yes | no | no | no | no | no | 4 | 5
Project 97 | L3 | Pipe |  | North Bay | Dec 31, 2025 | Dec 31, 2025 | 184 | low | low | high | high | med | 1641079 | 2796510 | 53761 | 3.276 | r/o | no | X |  |  |  |  | no | Yes | no | no | no | Yes | Yes | no | Yes | 2 | 4
Project 98 | L3 | Pipe | inspection | Edmonton | Mar 31, 2025 | Dec 31, 2025 | 202 | med | low | low | high | high | 1328932 | 726468 | 285009 | 21.4465 | gpmc | Yes | X | X |  | X | X | no | no | no | no | no | no | Yes | Yes | no | 8 | 7
Project 99 | L1 | Pipe | replacement | North Bay | Dec 31, 2025 | Dec 31, 2027 | 240 | high | med | high | low | low | 1632678 | 1782197 | 693986 | 42.506 | gpmc | no |  |  |  | X | X | no | no | Yes | no | no | no | no | no | no | 9 | 8
Project 100 | L3 | Pipe | repair | Winnepeg | Dec 31, 2025 | Dec 31, 2027 | 222 | high | high | low | med | med | 1664974 | 2518422 | 1186631 | 71.2702 | gpmc | Yes | X |  | X |  |  | Yes | no | no | Yes | Yes | no | no | Yes | no | 6 | 9
Project 101 | L2 | Pipe | replacement | Edmonton | Mar 31, 2025 | Dec 31, 2026 | 134 | low | high | high | low | med | 1663234 | 2320285 | 1422908 | 85.5507 | r/o | no |  | X | X | X |  | no | no | Yes | Yes | no | Yes | Yes | no | Yes | 6 | 9
Project 102 | L1 | Pipe | replacement | Calgary | Dec 31, 2025 | Oct 31, 2026 | 237 | med | med | med | high | high | 150137 | 160933 | 1980073 | 1318.8441 | r/o | no |  | X | X | X |  | no | no | Yes | no | no | no | Yes | no | no | 9 | 6
Project 103 | L2 | Pipe |  | Ottawa | Jul 31, 2025 | Oct 31, 2027 | 159 | low | med | low | high | high | 748916 | 1145032 | 1185225 | 158.2587 | gpmc | no |  | X | X |  | X | no | no | Yes | Yes | no | no | Yes | Yes | no | 2 | 4
Project 104 | L3 | Facility | inspection | Quebec City | Dec 31, 2025 | Jul 31, 2025 | 82 | high | high | low | low | low | 291899 | 360396 | 696989 | 238.7775 | capital | no | X |  | X |  | X | Yes | Yes | Yes | Yes | no | no | no | no | no | 9 | 7
Project 105 | L2 | Facility | excavation | Toronto | Oct 31, 2025 | Jul 31, 2025 | 327 | low | low | med | med | med | 1347730 | 896229 | 178314 | 13.2307 | r/o | no | X |  | X |  | X | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 6 | 1
Project 106 | L2 | Pipe |  | Quebec City | Dec 31, 2025 | Jul 31, 2025 | 167 | low | med | high | high | high | 264075 | 362887 | 751320 | 284.5101 | capital | Yes |  |  | X | X | X | no | no | no | Yes | Yes | Yes | Yes | no | Yes | 8 | 7
Project 107 | L2 | Pipe | repair | Winnepeg | Dec 31, 2024 | Dec 31, 2026 | 151 | med | low | high | low | low | 1093797 | 1443192 | 1820502 | 166.4387 | capital | Yes |  | X |  |  | X | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 5 | 2
Project 108 | L1 | Facility | inspection | Winnepeg | Oct 31, 2025 | Jul 31, 2027 | 187 | high | med | high | high | high | 231804 | 356589 | 720910 | 310.9998 | r/o | Yes | X | X | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 7 | 8
Project 109 | L1 | Facility | r/o | Regina | Mar 31, 2025 | Jul 31, 2026 | 81 | high | med | low | med | low | 212487 | 251598 | 994429 | 467.9952 | capital | Yes | X |  | X | X | X | Yes | no | Yes | no | no | no | no | no | Yes | 8 | 7
Project 110 | L1 | Pipe | excavation | Quebec City | Jul 31, 2025 | Dec 31, 2025 | 243 | med | med | high | low | low | 1429846 | 2379419 | 605473 | 42.3453 | gpmc | Yes | X | X | X | X |  | no | no | no | no | no | Yes | Yes | Yes | no | 4 | 1
Project 111 | L2 | Pipe | inspection | Edmonton | Dec 31, 2024 | Jul 31, 2027 | 271 | high | med | med | low | low | 1964280 | 1590291 | 755104 | 38.4418 | r/o | Yes |  |  | X |  | X | no | Yes | Yes | no | Yes | no | Yes | no | Yes | 9 | 1
Project 112 | L1 | Facility | inspection | Regina | Jul 31, 2025 | Oct 31, 2025 | 89 | med | high | low | med | high | 1088474 | 933883 | 1076311 | 98.8826 | capital | Yes |  |  | X | X | X | no | Yes | no | Yes | Yes | Yes | Yes | Yes | no | 5 | 1
Project 113 | L1 | Facility | replacement | Winnepeg | Dec 31, 2025 | Dec 31, 2026 | 281 | low | med | high | med | high | 269788 | 457800 | 1640852 | 608.2005 | capital | no | X |  | X |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | no | Yes | 7 | 1
Project 114 | L3 | Pipe | repair | Saskatoon | Oct 31, 2025 | Dec 31, 2025 | 138 | low | high | high | high | high | 1027631 | 1063847 | 1007464 | 98.0375 | r/o | no | X |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 7 | 5
Project 115 | L3 | Pipe | r/o | Calgary | Mar 31, 2025 | Dec 31, 2026 | 326 | low | med | high | med | high | 421256 | 592302 | 867516 | 205.9356 | gpmc | no | [5 empty] | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 6 | 8
Project 116 | L1 | Pipe | excavation | Calgary | Mar 31, 2025 | Dec 31, 2026 | 228 | med | low | high | low | low | 1209453 | 1127490 | 1792801 | 148.2324 | capital | Yes | X | X |  | X | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 8 | 5
Project 117 | L3 | Pipe |  | Ottawa | Jul 31, 2025 | Oct 31, 2025 | 94 | med | high | med | med | med | 705925 | 1218502 | 655835 | 92.9043 | gpmc | no | X |  | X |  | X | no | no | Yes | no | no | no | no | Yes | no | 1 | 9
Project 118 | L1 | Pipe | replacement | Calgary | Dec 31, 2025 | Dec 31, 2027 | 95 | low | high | med | low | high | 1941685 | 712753 | 1225455 | 63.113 | gpmc | Yes |  |  |  | X | X | no | Yes | Yes | Yes | no | Yes | Yes | no | no | 1 | 4
Project 119 | L1 | Pipe | excavation | Montreal | Dec 31, 2024 | Oct 31, 2026 | 342 | med | high | med | med | high | 1960309 | 1411617 | 311482 | 15.8894 | r/o | Yes |  | X |  | X |  | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 9 | 4
Project 120 | L3 | Pipe |  | Saskatoon | Oct 31, 2025 | Jul 31, 2025 | 100 | high | low | med | med | low | 371081 | 377311 | 1088707 | 293.388 | gpmc | Yes | X | X | X | X |  | Yes | Yes | no | no | no | no | no | Yes | no | 5 | 4
Project 121 | L1 | Pipe | inspection | Edmonton | Dec 31, 2025 | Dec 31, 2027 | 193 | low | high | low | high | low | 145761 | 115105 | 1058981 | 726.5188 | r/o | no |  | X | X | X | X | no | Yes | no | no | no | no | no | Yes | no | 4 | 8
Project 122 | L3 | Facility | repair | Montreal | Oct 31, 2025 | Dec 31, 2027 | 335 | high | low | high | high | low | 113004 | 120583 | 1706268 | 1509.9182 | capital | no |  | X | X | X | X | Yes | no | no | Yes | Yes | Yes | no | no | Yes | 3 | 6
Project 123 | L3 | Pipe | r/o | Edmonton | Jul 31, 2025 | Jul 31, 2026 | 110 | high | high | med | high | high | 1243364 | 1000784 | 1779063 | 143.0846 | gpmc | no |  |  | X |  |  | Yes | no | no | Yes | no | no | no | Yes | no | 2 | 4
Project 124 | L1 | Pipe | repair | Regina | Mar 31, 2025 | Jul 31, 2026 | 181 | low | high | low | low | high | 691230 | 391365 | 23536 | 3.4049 | r/o | Yes |  |  |  | X |  | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 4
Project 125 | L3 | Pipe | replacement | Winnepeg | Jul 31, 2025 | Jul 31, 2027 | 99 | low | med | high | med | med | 1868529 | 722164 | 639324 | 34.2154 | capital | no |  | X | X |  |  | Yes | no | Yes | Yes | no | no | no | Yes | Yes | 7 | 1
Project 126 | L1 | Facility | excavation | Saskatoon | Jul 31, 2025 | Dec 31, 2026 | 257 | low | low | med | med | med | 220746 | 343549 | 1737243 | 786.9873 | capital | no | X |  | X | X | X | Yes | Yes | no | no | no | no | no | Yes | Yes | 8 | 4
Project 127 | L2 | Facility |  | Edmonton | Jul 31, 2025 | Oct 31, 2025 | 105 | med | med | med | low | med | 71979 | 39272 | 1967645 | 2733.6376 | capital | no | X | X | X |  |  | no | Yes | Yes | no | no | Yes | no | Yes | no | 9 | 3
Project 128 | L2 | Pipe | excavation | Montreal | Dec 31, 2025 | Jul 31, 2027 | 141 | low | low | high | low | high | 596355 | 621491 | 746899 | 125.244 | r/o | Yes |  |  | X | X |  | Yes | no | no | Yes | Yes | no | Yes | Yes | no | 3 | 3
Project 129 | L3 | Facility | r/o | Winnepeg | Oct 31, 2025 | Jul 31, 2026 | 54 | high | high | high | high | med | 1176679 | 1757579 | 961424 | 81.7066 | capital | no | [5 empty] | Yes | Yes | no | no | no | no | no | no | no | 8 | 7
Project 130 | L3 | Facility | replacement | Winnepeg | Mar 31, 2025 | Dec 31, 2027 | 54 | med | med | med | high | high | 1598541 | 2695200 | 651676 | 40.7669 | r/o | Yes |  | X | X | X | X | no | no | Yes | no | Yes | Yes | Yes | no | no | 8 | 1
Project 131 | L3 | Pipe |  | Quebec City | Dec 31, 2025 | Dec 31, 2025 | 244 | high | high | low | med | low | 1769449 | 2864683 | 1932734 | 109.228 | r/o | no |  | X |  |  | X | no | no | no | Yes | Yes | Yes | Yes | Yes | no | 2 | 3
Project 132 | L2 | Pipe | excavation | Quebec City | Mar 31, 2025 | Jul 31, 2027 | 286 | med | low | med | med | med | 1670039 | 1069027 | 99579 | 5.9627 | r/o | Yes | X |  | X |  | X | Yes | no | no | Yes | Yes | no | Yes | no | Yes | 2 | 8
Project 133 | L2 | Pipe |  | Quebec City | Oct 31, 2025 | Dec 31, 2027 | 168 | med | high | low | high | med | 138394 | 170883 | 726247 | 524.7677 | gpmc | Yes |  | X |  | X |  | Yes | no | Yes | Yes | no | Yes | no | no | no | 8 | 2
Project 134 | L1 | Facility | inspection | Toronto | Dec 31, 2024 | Dec 31, 2025 | 360 | low | med | high | med | med | 115765 | 125523 | 1233729 | 1065.7185 | r/o | Yes | X | X |  |  | X | Yes | Yes | Yes | no | no | no | no | no | no | 3 | 6
Project 135 | L2 | Pipe |  | Montreal | Mar 31, 2025 | Dec 31, 2025 | 267 | med | low | high | med | med | 29133 | 28760 | 1268962 | 4355.7546 | gpmc | no | X |  |  |  | X | Yes | no | no | Yes | no | Yes | no | Yes | Yes | 5 | 3
Project 136 | L1 | Facility | inspection | Montreal | Dec 31, 2025 | Oct 31, 2026 | 132 | low | high | low | med | low | 408681 | 452929 | 784099 | 191.8609 | capital | Yes | X |  |  |  | X | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 2 | 3
Project 137 | L3 | Pipe | r/o | Quebec City | Oct 31, 2025 | Jul 31, 2026 | 320 | med | high | high | low | med | 153713 | 210779 | 560524 | 364.6562 | gpmc | no |  | X | X |  |  | Yes | no | no | Yes | Yes | Yes | no | no | no | 6 | 6
Project 138 | L2 | Facility |  | Regina | Jul 31, 2025 | Oct 31, 2026 | 108 | low | high | high | high | high | 1968880 | 1539287 | 508517 | 25.8277 | gpmc | Yes |  | X | X | X |  | no | no | no | Yes | Yes | no | no | Yes | no | 2 | 2
Project 139 | L1 | Facility | inspection | Saskatoon | Dec 31, 2024 | Jul 31, 2027 | 153 | med | low | low | med | med | 1438852 | 2314675 | 1345928 | 93.5418 | r/o | no |  |  |  | X | X | no | no | no | Yes | no | Yes | no | Yes | no | 5 | 7
Project 140 | L1 | Pipe | replacement | Winnepeg | Dec 31, 2025 | Dec 31, 2025 | 96 | med | med | high | med | low | 199686 | 295134 | 1530604 | 766.5054 | r/o | no |  | X | X |  | X | Yes | no | no | no | no | no | Yes | Yes | Yes | 8 | 6
Project 141 | L1 | Pipe | inspection | North Bay | Dec 31, 2024 | Dec 31, 2026 | 220 | low | low | high | high | high | 778039 | 787109 | 1588727 | 204.1963 | r/o | no | X |  | X |  | X | no | no | no | no | Yes | Yes | Yes | Yes | Yes | 5 | 8
Project 142 | L2 | Facility | replacement | Montreal | Dec 31, 2024 | Oct 31, 2025 | 134 | med | low | high | med | low | 545648 | 393154 | 48594 | 8.9057 | r/o | Yes | X | X | X |  | X | no | Yes | Yes | no | no | no | no | Yes | Yes | 3 | 3
Project 143 | L2 | Facility |  | Winnepeg | Mar 31, 2025 | Oct 31, 2026 | 44 | med | med | high | low | high | 635790 | 450791 | 290426 | 45.6795 | gpmc | no | X |  | X |  | X | no | no | Yes | Yes | no | no | Yes | Yes | Yes | 8 | 6
Project 144 | L2 | Pipe | replacement | Calgary | Mar 31, 2025 | Oct 31, 2025 | 220 | low | med | med | med | low | 1377953 | 994765 | 810158 | 58.7943 | capital | no | X | X | X | X |  | no | no | Yes | Yes | no | Yes | Yes | no | no | 8 | 5
Project 145 | L3 | Pipe | inspection | Toronto | Jul 31, 2025 | Dec 31, 2027 | 167 | med | med | low | high | med | 1886108 | 2404620 | 1103678 | 58.5162 | capital | Yes |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | 8 | 8
Project 146 | L3 | Facility |  | Edmonton | Dec 31, 2025 | Dec 31, 2026 | 100 | low | low | low | med | low | 328462 | 292193 | 943099 | 287.1258 | capital | Yes | X |  | X |  | X | no | no | no | no | Yes | no | Yes | no | Yes | 5 | 1
Project 147 | L3 | Facility | excavation | North Bay | Mar 31, 2025 | Jul 31, 2026 | 91 | low | high | med | med | med | 1141825 | 1472385 | 1264806 | 110.7706 | gpmc | Yes | X |  | X |  | X | Yes | no | Yes | no | Yes | no | no | Yes | no | 4 | 8
Project 148 | L2 | Pipe | excavation | North Bay | Jul 31, 2025 | Jul 31, 2025 | 355 | high | high | med | med | high | 1270710 | 1471451 | 1275401 | 100.3692 | gpmc | Yes |  |  | X | X |  | no | no | no | no | no | Yes | no | Yes | Yes | 2 | 1
Project 149 | L1 | Pipe | inspection | Saskatoon | Dec 31, 2024 | Dec 31, 2025 | 276 | low | low | med | med | low | 1417818 | 2109052 | 489251 | 34.5073 | capital | Yes | X |  | X | X | X | no | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | 2 | 6
Project 150 | L3 | Pipe | inspection | Quebec City | Oct 31, 2025 | Dec 31, 2027 | 281 | med | high | med | med | med | 65057 | 66856 | 162661 | 250.0284 | capital | Yes | X | X |  | X |  | Yes | Yes | no | Yes | no | Yes | no | no | no | 3 | 8
Project 151 | L2 | Facility | r/o | Edmonton | Jul 31, 2025 | Jul 31, 2025 | 58 | high | med | high | high | med | 372014 | 540166 | 139481 | 37.4935 | r/o | no |  | X |  |  | X | Yes | no | no | no | no | Yes | no | Yes | no | 2 | 8
Project 152 | L1 | Pipe | inspection | Edmonton | Oct 31, 2025 | Dec 31, 2025 | 250 | high | med | med | med | low | 1374269 | 2297477 | 38399 | 2.7941 | r/o | no | X |  | X |  |  | Yes | no | Yes | no | no | Yes | Yes | no | Yes | 7 | 3
Project 153 | L1 | Pipe | inspection | Edmonton | Dec 31, 2024 | Dec 31, 2026 | 258 | high | high | high | med | med | 627332 | 627590 | 350999 | 55.9511 | r/o | Yes |  | X | X | X | X | Yes | Yes | Yes | Yes | no | no | no | no | no | 8 | 7
Project 154 | L2 | Pipe | inspection | Montreal | Oct 31, 2025 | Jul 31, 2027 | 95 | low | high | high | high | low | 392645 | 362344 | 1212430 | 308.7853 | gpmc | no |  | X |  |  |  | no | no | Yes | no | no | no | no | Yes | Yes | 7 | 1
Project 155 | L1 | Pipe |  | Edmonton | Mar 31, 2025 | Dec 31, 2026 | 108 | med | low | low | med | high | 1332765 | 1205131 | 1847520 | 138.6231 | capital | no |  |  | X |  |  | Yes | no | Yes | no | no | no | Yes | Yes | Yes | 4 | 1
Project 156 | L1 | Facility |  | Ottawa | Dec 31, 2025 | Jul 31, 2027 | 83 | med | low | med | high | med | 1465049 | 908828 | 1859781 | 126.9433 | gpmc | no |  | X |  |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | Yes | no | 4 | 6
Project 157 | L2 | Facility | replacement | Calgary | Mar 31, 2025 | Dec 31, 2026 | 273 | med | low | med | med | low | 833495 | 999082 | 1139327 | 136.6927 | capital | Yes | X |  |  | X | X | Yes | no | Yes | no | no | Yes | no | Yes | Yes | 1 | 2
Project 158 | L3 | Facility | r/o | Winnepeg | Dec 31, 2025 | Dec 31, 2027 | 171 | low | low | high | high | med | 815323 | 1162000 | 1234727 | 151.4402 | capital | Yes | X | X |  | X | X | no | no | no | no | no | Yes | no | no | Yes | 3 | 3
Project 159 | L1 | Pipe | replacement | Regina | Dec 31, 2024 | Dec 31, 2027 | 150 | high | high | low | high | med | 648848 | 304866 | 1358818 | 209.4201 | gpmc | Yes | X | X |  |  |  | Yes | no | Yes | Yes | no | Yes | no | no | Yes | 9 | 9
Project 160 | L3 | Pipe | excavation | Saskatoon | Oct 31, 2025 | Dec 31, 2026 | 208 | high | high | high | med | low | 1686245 | 2628291 | 658438 | 39.0476 | capital | Yes |  |  |  | X |  | no | no | no | no | Yes | Yes | Yes | Yes | no | 3 | 3
Project 161 | L1 | Facility | replacement | Quebec City | Mar 31, 2025 | Dec 31, 2025 | 300 | low | high | med | high | med | 535103 | 202789 | 1107883 | 207.0411 | gpmc | no |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | no | 2 | 8
Project 162 | L3 | Pipe | replacement | Montreal | Mar 31, 2025 | Oct 31, 2026 | 155 | med | high | med | med | med | 171325 | 139891 | 479888 | 280.1039 | r/o | no |  |  |  | X | X | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 8 | 4
Project 163 | L3 | Facility | replacement | Regina | Mar 31, 2025 | Oct 31, 2027 | 333 | med | med | high | med | low | 74919 | 110238 | 1988057 | 2653.6086 | r/o | Yes | X |  | X | X |  | no | no | Yes | Yes | Yes | no | Yes | no | Yes | 6 | 3
Project 164 | L1 | Facility | replacement | Calgary | Dec 31, 2024 | Dec 31, 2025 | 233 | med | low | low | med | med | 154522 | 189159 | 708610 | 458.5819 | capital | no | X |  |  | X | X | Yes | no | no | no | no | no | Yes | no | Yes | 9 | 8
Project 165 | L3 | Pipe | excavation | Edmonton | Mar 31, 2025 | Oct 31, 2025 | 102 | high | high | med | med | high | 915457 | 673972 | 1298394 | 141.8301 | gpmc | Yes | X | X | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | no | Yes | 6 | 3
Project 166 | L1 | Pipe | excavation | Quebec City | Oct 31, 2025 | Dec 31, 2026 | 240 | low | med | med | high | med | 666005 | 221266 | 943373 | 141.6465 | r/o | Yes |  | X |  |  |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 5 | 1
Project 167 | L2 | Facility | replacement | Ottawa | Oct 31, 2025 | Oct 31, 2027 | 264 | low | med | high | high | med | 1458134 | 499520 | 1948710 | 133.6441 | capital | no |  | X |  | X |  | Yes | no | Yes | no | no | no | no | Yes | Yes | 2 | 1
Project 168 | L3 | Facility | replacement | Regina | Jul 31, 2025 | Jul 31, 2027 | 214 | med | low | med | med | low | 451007 | 761857 | 850893 | 188.6651 | r/o | no |  | X |  |  | X | Yes | Yes | Yes | Yes | no | no | Yes | Yes | Yes | 9 | 4
Project 169 | L3 | Pipe | replacement | Montreal | Dec 31, 2025 | Oct 31, 2027 | 120 | high | low | med | high | med | 1747759 | 1655895 | 1936005 | 110.7707 | capital | Yes |  | X | X | X | X | Yes | Yes | Yes | no | Yes | no | no | no | no | 2 | 9
Project 170 | L2 | Pipe | excavation | Toronto | Oct 31, 2025 | Oct 31, 2026 | 82 | high | high | med | low | med | 1405865 | 1108018 | 61505 | 4.3749 | gpmc | Yes |  |  | X |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 5 | 3
Project 171 | L3 | Facility | r/o | Winnepeg | Mar 31, 2025 | Dec 31, 2027 | 130 | med | low | high | high | high | 1076853 | 1247645 | 1410495 | 130.9831 | r/o | no | X | X |  | X |  | Yes | Yes | no | no | no | no | Yes | Yes | no | 6 | 4
Project 172 | L2 | Facility | repair | Saskatoon | Dec 31, 2025 | Dec 31, 2026 | 316 | high | low | high | high | high | 1152464 | 1932750 | 241845 | 20.985 | gpmc | Yes |  |  | X | X | X | no | no | no | no | Yes | no | no | Yes | Yes | 4 | 5
Project 173 | L1 | Facility | r/o | Edmonton | Dec 31, 2024 | Jul 31, 2026 | 298 | low | med | low | low | high | 593740 | 586418 | 158600 | 26.712 | r/o | no | X | X |  |  | X | Yes | Yes | Yes | no | Yes | Yes | Yes | no | no | 3 | 1
Project 174 | L3 | Facility | repair | Winnepeg | Dec 31, 2025 | Oct 31, 2026 | 260 | med | med | med | low | med | 1521866 | 1938148 | 1013817 | 66.6167 | gpmc | Yes |  |  | X |  |  | no | Yes | no | Yes | Yes | Yes | Yes | no | Yes | 8 | 8
Project 175 | L1 | Facility | replacement | Edmonton | Dec 31, 2025 | Oct 31, 2025 | 33 | high | high | med | med | med | 868110 | 1222938 | 1574969 | 181.425 | capital | no |  | X | X | X | X | Yes | Yes | no | no | no | Yes | Yes | no | no | 2 | 2
Project 176 | L3 | Pipe | inspection | Calgary | Jul 31, 2025 | Jul 31, 2025 | 286 | high | med | high | high | high | 1623910 | 2389409 | 990444 | 60.9913 | gpmc | Yes |  |  |  | X | X | no | no | Yes | no | no | no | no | Yes | Yes | 2 | 9
Project 177 | L1 | Pipe |  | Saskatoon | Oct 31, 2025 | Dec 31, 2025 | 174 | med | high | med | low | med | 1651514 | 1145961 | 1344664 | 81.4201 | gpmc | no | X |  |  |  |  | Yes | no | no | no | no | Yes | Yes | Yes | no | 3 | 2
Project 178 | L2 | Facility | replacement | Winnepeg | Dec 31, 2025 | Oct 31, 2027 | 230 | low | high | low | low | high | 1493807 | 2074626 | 624864 | 41.8303 | r/o | no | X | X |  |  |  | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 3 | 7
Project 179 | L1 | Facility | repair | Toronto | Dec 31, 2024 | Oct 31, 2027 | 343 | med | med | low | high | high | 863834 | 271151 | 1585826 | 183.5799 | capital | no | X | X |  |  | X | no | no | no | Yes | Yes | no | no | Yes | Yes | 2 | 3
Project 180 | L2 | Pipe | excavation | North Bay | Dec 31, 2024 | Oct 31, 2026 | 237 | low | med | med | med | med | 376673 | 286675 | 1230629 | 326.7102 | r/o | Yes |  | X | X | X | X | Yes | no | Yes | no | Yes | Yes | Yes | no | no | 8 | 3
Project 181 | L3 | Pipe | inspection | Montreal | Mar 31, 2025 | Dec 31, 2027 | 224 | med | low | low | med | med | 59869 | 72185 | 1076085 | 1797.3993 | capital | no | X | X | X |  |  | no | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 3 | 9
Project 182 | L2 | Pipe | r/o | Montreal | Oct 31, 2025 | Dec 31, 2027 | 172 | high | low | high | low | low | 1257705 | 937589 | 1572340 | 125.0166 | gpmc | Yes | X |  | X |  |  | no | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | 4 | 1
Project 183 | L2 | Pipe | r/o | Quebec City | Dec 31, 2024 | Oct 31, 2025 | 226 | high | low | low | high | med | 1255931 | 1462145 | 628810 | 50.0672 | gpmc | Yes | X | X |  |  |  | no | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 8 | 9
Project 184 | L3 | Pipe | inspection | Montreal | Jul 31, 2025 | Oct 31, 2027 | 78 | low | med | med | high | high | 1394672 | 1874339 | 1935749 | 138.796 | capital | Yes | X | X | X | X | X | Yes | no | Yes | no | no | no | Yes | Yes | no | 8 | 8
Project 185 | L3 | Pipe |  | Regina | Dec 31, 2024 | Jul 31, 2027 | 190 | med | low | high | low | low | 343581 | 473106 | 598253 | 174.1228 | capital | Yes | X |  |  | X |  | Yes | no | Yes | no | Yes | no | Yes | Yes | Yes | 8 | 8
Project 186 | L3 | Pipe | r/o | Montreal | Mar 31, 2025 | Dec 31, 2025 | 347 | high | high | high | high | high | 467304 | 195982 | 1159710 | 248.1704 | capital | Yes |  | X |  |  |  | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 7 | 1
Project 187 | L1 | Facility | repair | Winnepeg | Dec 31, 2024 | Jul 31, 2027 | 84 | low | high | high | med | med | 924709 | 773193 | 528686 | 57.1732 | r/o | Yes | X | X | X |  | X | Yes | Yes | no | no | Yes | Yes | no | Yes | no | 1 | 4
Project 188 | L2 | Facility |  | Calgary | Oct 31, 2025 | Dec 31, 2025 | 112 | high | low | low | med | low | 1577797 | 2086491 | 643517 | 40.7858 | r/o | Yes |  |  |  | X | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 6 | 3
Project 189 | L1 | Pipe | inspection | Toronto | Jul 31, 2025 | Dec 31, 2027 | 252 | med | high | high | low | high | 1313018 | 1890369 | 1349623 | 102.7879 | gpmc | no | X | X | X | X |  | Yes | no | no | no | no | Yes | no | Yes | Yes | 1 | 8
Project 190 | L2 | Facility | inspection | Winnepeg | Oct 31, 2025 | Oct 31, 2025 | 357 | low | med | med | low | low | 194233 | 164078 | 855463 | 440.4313 | r/o | no | X |  |  | X | X | Yes | no | Yes | Yes | Yes | no | Yes | no | no | 7 | 1
Project 191 | L1 | Facility | r/o | Montreal | Dec 31, 2024 | Jul 31, 2026 | 250 | med | high | low | low | high | 318846 | 541409 | 1526004 | 478.6022 | r/o | no |  | X |  | X | X | Yes | no | Yes | no | no | Yes | no | Yes | Yes | 8 | 5
Project 192 | L3 | Facility | repair | Saskatoon | Dec 31, 2025 | Jul 31, 2027 | 288 | low | high | low | high | low | 169895 | 269018 | 283196 | 166.6888 | r/o | no | X | X | X | X |  | no | Yes | no | no | no | Yes | Yes | no | no | 1 | 6
Project 193 | L2 | Pipe | excavation | Calgary | Jul 31, 2025 | Oct 31, 2026 | 76 | low | low | high | med | med | 672581 | 498121 | 1572134 | 233.7464 | r/o | Yes |  | X |  | X | X | no | no | no | Yes | no | no | Yes | no | Yes | 8 | 4
Project 194 | L1 | Facility | r/o | Saskatoon | Oct 31, 2025 | Oct 31, 2026 | 271 | high | high | high | med | high | 445986 | 329798 | 1488704 | 333.8006 | capital | Yes |  |  | X |  | X | no | Yes | no | no | no | no | Yes | Yes | no | 8 | 9
Project 195 | L2 | Pipe | repair | Toronto | Dec 31, 2025 | Oct 31, 2027 | 109 | med | high | high | med | high | 1697752 | 655112 | 357513 | 21.058 | capital | Yes |  | X | X | X | X | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 9 | 7
Project 196 | L1 | Facility | repair | Regina | Dec 31, 2025 | Jul 31, 2025 | 322 | high | med | low | med | high | 1354103 | 2214297 | 263857 | 19.4857 | capital | no |  |  | X |  | X | Yes | Yes | Yes | Yes | no | no | Yes | no | Yes | 8 | 3
Project 197 | L2 | Pipe | excavation | Ottawa | Dec 31, 2025 | Jul 31, 2026 | 196 | low | med | high | med | low | 281184 | 161284 | 1708681 | 607.6736 | gpmc | Yes | X | X | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 5 | 9
Project 198 | L3 | Pipe | inspection | Edmonton | Dec 31, 2025 | Dec 31, 2026 | 315 | high | med | low | med | low | 1801405 | 1134216 | 1081515 | 60.0373 | r/o | no | X |  | X |  |  | no | Yes | Yes | no | Yes | no | no | no | no | 8 | 1
Project 199 | L3 | Pipe | r/o | Regina | Dec 31, 2024 | Dec 31, 2026 | 281 | med | med | high | med | high | 1125653 | 467063 | 1767432 | 157.0139 | capital | Yes | X |  |  |  | X | no | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 1 | 9
Project 200 | L2 | Facility | repair | Montreal | Oct 31, 2025 | Jul 31, 2025 | 283 | low | low | low | low | low | 592198 | 734120 | 1951701 | 329.569 | capital | no |  |  |  | X |  | Yes | no | no | Yes | Yes | no | no | no | no | 8 | 9
Project 201 | L3 | Facility | excavation | Winnepeg | Oct 31, 2025 | Dec 31, 2025 | 220 | med | high | high | low | med | 1925739 | 1032159 | 456772 | 23.7193 | capital | Yes | X | X | X |  | X | no | Yes | Yes | Yes | Yes | Yes | no | Yes | no | 6 | 3
Project 202 | L3 | Pipe | repair | Winnepeg | Jul 31, 2025 | Dec 31, 2026 | 330 | med | low | low | low | low | 314985 | 211126 | 1889948 | 600.0121 | r/o | no |  | X | X | X | X | no | no | no | Yes | no | no | Yes | Yes | Yes | 1 | 5
Project 203 | L3 | Pipe | excavation | Montreal | Dec 31, 2024 | Jul 31, 2025 | 117 | high | high | med | high | med | 1847002 | 1830634 | 64234 | 3.4777 | r/o | Yes | X | X |  |  | X | no | Yes | Yes | no | Yes | no | no | Yes | no | 4 | 4
Project 204 | L1 | Facility | repair | Montreal | Jul 31, 2025 | Dec 31, 2027 | 141 | med | high | low | med | high | 671749 | 347832 | 735398 | 109.4751 | gpmc | Yes |  |  | X | X |  | Yes | Yes | Yes | no | no | Yes | no | Yes | no | 4 | 4
Project 205 | L2 | Facility | replacement | Toronto | Jul 31, 2025 | Dec 31, 2026 | 237 | high | low | med | high | med | 376342 | 276191 | 1138465 | 302.5081 | r/o | no |  |  | X |  | X | no | no | no | no | no | Yes | Yes | no | no | 9 | 6
Project 206 | L3 | Facility |  | Quebec City | Oct 31, 2025 | Oct 31, 2025 | 281 | high | med | low | high | med | 912484 | 875997 | 1486942 | 162.9554 | gpmc | Yes | X | X |  | X |  | no | no | Yes | Yes | Yes | no | Yes | no | Yes | 8 | 8
Project 207 | L1 | Facility | r/o | Ottawa | Oct 31, 2025 | Dec 31, 2027 | 15 | high | high | med | low | low | 1038945 | 620738 | 1679586 | 161.6626 | capital | Yes | X | X | X |  | X | no | no | Yes | no | Yes | Yes | no | no | no | 1 | 5
Project 208 | L3 | Facility | inspection | Edmonton | Dec 31, 2024 | Jul 31, 2027 | 264 | high | med | low | low | high | 1763913 | 1434726 | 1986033 | 112.5925 | r/o | no |  |  |  |  | X | Yes | Yes | no | no | no | Yes | Yes | no | Yes | 1 | 1
Project 209 | L2 | Pipe | repair | Montreal | Dec 31, 2024 | Oct 31, 2025 | 70 | high | high | high | med | high | 930038 | 552315 | 345033 | 37.0988 | gpmc | Yes |  |  |  | X | X | no | Yes | no | no | Yes | Yes | Yes | Yes | no | 4 | 7
Project 210 | L3 | Pipe | excavation | Ottawa | Dec 31, 2025 | Oct 31, 2025 | 300 | high | med | low | med | med | 690541 | 938882 | 1070364 | 155.0037 | capital | Yes |  | X |  |  |  | Yes | Yes | Yes | no | Yes | no | no | no | Yes | 7 | 8
Project 211 | L1 | Pipe | r/o | Regina | Oct 31, 2025 | Jul 31, 2027 | 314 | low | low | low | low | low | 1050575 | 1317829 | 676118 | 64.3569 | r/o | no | X |  |  |  |  | no | Yes | no | no | Yes | no | Yes | Yes | no | 8 | 7
Project 212 | L3 | Facility | excavation | Quebec City | Dec 31, 2024 | Dec 31, 2026 | 44 | high | high | med | med | low | 1221452 | 952905 | 1413213 | 115.6994 | gpmc | Yes | X |  | X | X | X | no | Yes | no | no | no | no | Yes | Yes | Yes | 3 | 1
Project 213 | L1 | Pipe | excavation | Winnepeg | Mar 31, 2025 | Oct 31, 2027 | 248 | med | high | high | med | high | 1982007 | 3277895 | 631467 | 31.86 | capital | Yes |  | X | X |  |  | no | no | no | Yes | no | no | no | no | no | 4 | 3
Project 214 | L2 | Facility |  | Winnepeg | Dec 31, 2024 | Jul 31, 2027 | 80 | med | high | med | low | high | 236720 | 200686 | 708414 | 299.2624 | r/o | no | [5 empty] | Yes | no | no | no | no | Yes | Yes | Yes | Yes | 9 | 2
Project 215 | L2 | Facility | repair | Winnepeg | Oct 31, 2025 | Jul 31, 2026 | 246 | low | med | low | med | med | 1675923 | 2569582 | 1295278 | 77.2874 | gpmc | no | X |  | X | X | X | no | no | no | no | Yes | Yes | no | Yes | Yes | 4 | 5
Project 216 | L3 | Facility | inspection | North Bay | Dec 31, 2025 | Dec 31, 2026 | 325 | low | high | high | high | med | 1563060 | 2217164 | 1166451 | 74.6261 | capital | no | X | X | X | X | X | Yes | Yes | Yes | Yes | no | no | Yes | Yes | Yes | 5 | 7
Project 217 | L1 | Facility | replacement | Edmonton | Mar 31, 2025 | Oct 31, 2026 | 88 | low | med | high | low | high | 746992 | 957984 | 1178927 | 157.8232 | capital | no | X | X |  |  | X | Yes | no | no | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 6
Project 218 | L3 | Facility | r/o | Toronto | Dec 31, 2025 | Dec 31, 2026 | 155 | med | high | low | high | low | 891328 | 1178480 | 1404560 | 157.5806 | capital | Yes |  |  |  |  | X | Yes | Yes | Yes | no | no | no | Yes | no | no | 8 | 6
Project 219 | L1 | Pipe | inspection | Regina | Oct 31, 2025 | Oct 31, 2026 | 261 | high | high | high | high | low | 312805 | 93623 | 951669 | 304.2371 | capital | no |  |  | X |  | X | Yes | Yes | no | Yes | no | Yes | no | no | Yes | 3 | 1
Project 220 | L2 | Pipe | inspection | North Bay | Dec 31, 2025 | Oct 31, 2027 | 196 | med | low | low | high | low | 1298438 | 1699965 | 746789 | 57.5144 | capital | no | X | X | X | X | X | no | no | Yes | no | no | no | no | Yes | no | 7 | 3
Project 221 | L2 | Pipe | repair | Calgary | Dec 31, 2024 | Dec 31, 2025 | 159 | high | low | low | high | high | 1861677 | 1867362 | 97877 | 5.2575 | gpmc | no |  | X | X | X |  | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 7 | 8
Project 222 | L3 | Facility | replacement | North Bay | Oct 31, 2025 | Dec 31, 2026 | 169 | high | med | low | med | med | 622124 | 973208 | 624036 | 100.3073 | r/o | no |  | X |  |  |  | no | no | Yes | no | no | no | Yes | no | no | 2 | 2
Project 223 | L2 | Pipe |  | Regina | Dec 31, 2025 | Oct 31, 2025 | 319 | low | high | high | low | med | 282052 | 250747 | 1054786 | 373.9686 | gpmc | no |  | X |  | X |  | no | no | no | Yes | Yes | Yes | Yes | no | no | 9 | 4
Project 224 | L1 | Pipe | repair | Regina | Dec 31, 2025 | Oct 31, 2027 | 355 | high | high | low | high | low | 493957 | 302110 | 60256 | 12.1986 | gpmc | Yes |  |  |  | X | X | Yes | Yes | Yes | no | no | no | no | Yes | no | 6 | 2
Project 225 | L3 | Facility | repair | Regina | Dec 31, 2025 | Dec 31, 2025 | 205 | high | low | low | med | med | 997971 | 1147486 | 318018 | 31.8665 | r/o | Yes |  |  | X | X |  | Yes | no | Yes | no | Yes | no | no | no | no | 6 | 8
Project 226 | L2 | Pipe | excavation | Regina | Dec 31, 2025 | Dec 31, 2026 | 87 | high | med | low | med | low | 840909 | 986030 | 979664 | 116.5006 | capital | no |  | X | X |  |  | no | Yes | no | Yes | Yes | Yes | no | Yes | no | 6 | 9
Project 227 | L1 | Pipe | excavation | Ottawa | Jul 31, 2025 | Oct 31, 2026 | 272 | med | high | med | med | high | 25177 | 38920 | 1896373 | 7532.1643 | gpmc | no |  |  |  |  | X | no | Yes | no | Yes | Yes | no | Yes | no | Yes | 6 | 7
Project 228 | L2 | Pipe | excavation | Calgary | Dec 31, 2024 | Oct 31, 2026 | 69 | low | low | med | low | med | 740227 | 265016 | 1790442 | 241.8774 | r/o | no |  | X |  | X |  | no | Yes | no | Yes | Yes | no | no | no | no | 6 | 2
Project 229 | L2 | Facility | excavation | Saskatoon | Jul 31, 2025 | Oct 31, 2027 | 180 | high | med | low | low | low | 958604 | 267333 | 465984 | 48.6107 | gpmc | Yes |  |  |  | X | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 9 | 8
Project 230 | L3 | Facility | excavation | Montreal | Dec 31, 2024 | Oct 31, 2025 | 45 | med | high | low | low | high | 477699 | 348142 | 1979863 | 414.4583 | gpmc | no |  |  | X |  | X | no | no | no | no | Yes | no | Yes | no | no | 1 | 6
Project 231 | L2 | Pipe | repair | North Bay | Dec 31, 2025 | Oct 31, 2026 | 172 | low | med | med | high | low | 301597 | 305243 | 268071 | 88.8838 | r/o | Yes | X | X | X | X |  | Yes | no | Yes | Yes | Yes | no | no | Yes | no | 1 | 8
Project 232 | L1 | Pipe |  | Edmonton | Mar 31, 2025 | Jul 31, 2027 | 39 | high | high | low | med | med | 1006509 | 1528512 | 279894 | 27.8084 | capital | Yes | [5 empty] | Yes | no | Yes | no | Yes | Yes | Yes | no | Yes | 1 | 8
Project 233 | L2 | Pipe | replacement | Saskatoon | Oct 31, 2025 | Dec 31, 2026 | 215 | low | high | low | low | high | 387341 | 492853 | 1261605 | 325.7091 | r/o | Yes |  | X | X | X |  | no | Yes | Yes | no | no | Yes | Yes | no | Yes | 5 | 5
Project 234 | L2 | Pipe | inspection | Montreal | Oct 31, 2025 | Oct 31, 2027 | 202 | high | med | med | high | med | 1176038 | 1623102 | 593741 | 50.4865 | capital | Yes | X | X |  |  | X | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 6 | 6
Project 235 | L1 | Facility |  | North Bay | Mar 31, 2025 | Oct 31, 2026 | 91 | low | med | high | med | high | 1944544 | 2470325 | 1727801 | 88.8538 | r/o | no |  |  |  |  | X | no | Yes | no | Yes | no | Yes | no | Yes | no | 1 | 6
Project 236 | L3 | Facility | replacement | Ottawa | Mar 31, 2025 | Jul 31, 2026 | 309 | high | high | high | med | low | 1074850 | 802770 | 452634 | 42.1114 | gpmc | no |  | X |  |  | X | no | no | no | Yes | Yes | no | Yes | Yes | Yes | 6 | 5
Project 237 | L2 | Pipe | inspection | Saskatoon | Mar 31, 2025 | Oct 31, 2026 | 248 | med | med | high | med | low | 685971 | 903371 | 1735908 | 253.0585 | r/o | Yes |  |  | X | X |  | no | no | no | Yes | no | Yes | Yes | no | Yes | 6 | 4
Project 238 | L3 | Pipe | repair | North Bay | Dec 31, 2024 | Oct 31, 2027 | 23 | high | low | high | med | med | 1890183 | 1196938 | 1166750 | 61.7268 | gpmc | no | X | X |  |  |  | Yes | Yes | no | Yes | no | no | no | no | Yes | 8 | 1
Project 239 | L3 | Facility | inspection | Ottawa | Mar 31, 2025 | Jul 31, 2026 | 309 | low | med | med | low | med | 1556219 | 2283822 | 1253621 | 80.5556 | gpmc | Yes |  |  | X |  | X | no | Yes | no | Yes | no | no | Yes | no | Yes | 5 | 5
Project 240 | L2 | Facility | r/o | Regina | Mar 31, 2025 | Jul 31, 2026 | 44 | low | high | high | high | med | 896571 | 1457036 | 258381 | 28.8188 | gpmc | no |  | X |  | X | X | no | Yes | Yes | Yes | no | no | Yes | no | Yes | 7 | 5
Project 241 | L1 | Pipe | r/o | Ottawa | Jul 31, 2025 | Jul 31, 2026 | 302 | med | med | high | low | low | 1628157 | 1391096 | 1818982 | 111.7203 | gpmc | Yes | X | X |  | X | X | no | Yes | no | Yes | no | no | Yes | Yes | Yes | 7 | 1
Project 242 | L3 | Facility | inspection | Toronto | Jul 31, 2025 | Dec 31, 2026 | 105 | low | med | high | med | low | 177803 | 292686 | 853817 | 480.2039 | r/o | no | X | X |  |  |  | Yes | Yes | no | no | no | Yes | Yes | Yes | Yes | 6 | 1
Project 243 | L1 | Pipe | r/o | Calgary | Mar 31, 2025 | Oct 31, 2025 | 107 | low | med | med | low | low | 1241268 | 1990816 | 1327129 | 106.9172 | gpmc | no | X | X | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 9 | 6
Project 244 | L3 | Pipe |  | Ottawa | Oct 31, 2025 | Jul 31, 2026 | 179 | med | med | low | med | med | 1949223 | 1094538 | 1944669 | 99.7664 | gpmc | no | X |  |  | X | X | Yes | Yes | no | no | Yes | no | Yes | no | no | 9 | 6
Project 245 | L1 | Pipe | inspection | Montreal | Jul 31, 2025 | Jul 31, 2027 | 121 | med | med | high | low | low | 1586279 | 2091864 | 1049585 | 66.1665 | gpmc | no | X |  |  |  |  | no | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 2 | 5
Project 246 | L3 | Facility | excavation | Regina | Dec 31, 2024 | Jul 31, 2027 | 102 | med | high | med | high | med | 149740 | 112143 | 452877 | 302.4422 | gpmc | no | [5 empty] | no | no | no | no | Yes | no | Yes | no | no | 2 | 6
Project 247 | L1 | Pipe | excavation | Montreal | Jul 31, 2025 | Oct 31, 2026 | 330 | low | low | high | med | high | 1591701 | 1941965 | 1203005 | 75.5798 | r/o | no | X |  | X | X | X | no | no | no | no | Yes | no | Yes | Yes | Yes | 7 | 6
Project 248 | L2 | Pipe | repair | Quebec City | Mar 31, 2025 | Dec 31, 2025 | 238 | high | high | high | high | high | 606534 | 393963 | 496868 | 81.9192 | gpmc | no |  | X | X | X |  | no | Yes | no | Yes | Yes | Yes | no | no | Yes | 6 | 9
Project 249 | L2 | Pipe | r/o | Toronto | Mar 31, 2025 | Oct 31, 2025 | 287 | high | low | low | low | high | 320614 | 384530 | 1215189 | 379.0193 | capital | Yes | X |  | X |  | X | Yes | no | Yes | Yes | Yes | no | no | no | Yes | 1 | 8
Project 250 | L1 | Pipe | r/o | Calgary | Dec 31, 2024 | Oct 31, 2026 | 48 | med | med | high | med | high | 1552678 | 495759 | 291182 | 18.7535 | capital | Yes | X | X |  |  | X | Yes | Yes | no | Yes | no | no | Yes | no | Yes | 4 | 8
Project 251 | L1 | Facility | inspection | Montreal | Oct 31, 2025 | Jul 31, 2026 | 207 | med | high | med | low | low | 1103009 | 444072 | 1405108 | 127.3886 | gpmc | no | X | X |  |  | X | no | no | no | Yes | Yes | no | Yes | Yes | no | 7 | 5
Project 252 | L3 | Pipe | inspection | Quebec City | Oct 31, 2025 | Dec 31, 2027 | 270 | med | high | high | low | med | 404103 | 293669 | 569130 | 140.8379 | capital | no | X |  | X |  | X | Yes | no | Yes | Yes | Yes | Yes | no | no | no | 2 | 9
Project 253 | L1 | Facility | replacement | Regina | Oct 31, 2025 | Oct 31, 2026 | 331 | med | high | high | high | med | 1243639 | 662091 | 413546 | 33.2529 | capital | Yes |  | X | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 8 | 8
Project 254 | L3 | Facility | inspection | Calgary | Mar 31, 2025 | Oct 31, 2027 | 43 | high | low | high | low | high | 208883 | 328647 | 1075672 | 514.9639 | capital | Yes | X |  | X |  |  | Yes | Yes | no | no | no | no | no | Yes | no | 4 | 2
Project 255 | L2 | Facility | repair | Montreal | Mar 31, 2025 | Dec 31, 2025 | 275 | high | med | low | low | med | 95423 | 123547 | 1170239 | 1226.37 | r/o | Yes | X |  |  | X |  | no | no | no | Yes | Yes | Yes | Yes | Yes | no | 9 | 9
Project 256 | L1 | Facility | excavation | Regina | Jul 31, 2025 | Jul 31, 2026 | 284 | low | high | low | med | med | 1589500 | 2602571 | 1585465 | 99.7461 | gpmc | Yes | X |  |  | X | X | no | no | Yes | Yes | no | Yes | Yes | no | Yes | 8 | 3
Project 257 | L3 | Pipe | excavation | Ottawa | Jul 31, 2025 | Jul 31, 2025 | 349 | low | med | low | high | high | 1964893 | 1260599 | 1362165 | 69.3251 | r/o | no | X | X | X | X | X | no | no | Yes | Yes | Yes | no | Yes | Yes | Yes | 2 | 4
Project 258 | L2 | Pipe | repair | Winnepeg | Dec 31, 2025 | Oct 31, 2025 | 279 | med | low | low | med | low | 332355 | 241283 | 1694659 | 509.8942 | capital | no | X |  | X | X | X | Yes | Yes | no | Yes | Yes | no | no | no | Yes | 9 | 4
Project 259 | L3 | Facility | r/o | Toronto | Jul 31, 2025 | Dec 31, 2025 | 291 | low | low | high | high | low | 1845751 | 2975373 | 433973 | 23.512 | r/o | no | X |  | X |  | X | Yes | Yes | no | no | Yes | no | Yes | Yes | no | 6 | 3
Project 260 | L2 | Facility | inspection | North Bay | Dec 31, 2025 | Dec 31, 2025 | 39 | low | high | high | high | high | 866913 | 234964 | 1136163 | 131.0585 | r/o | Yes |  |  | X |  | X | Yes | no | no | no | Yes | no | Yes | Yes | no | 4 | 5
Project 261 | L2 | Pipe | replacement | Regina | Oct 31, 2025 | Dec 31, 2025 | 191 | low | low | high | high | med | 1970394 | 3282182 | 1297377 | 65.8435 | r/o | Yes | X |  | X |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | no | 5 | 9
Project 262 | L1 | Facility | repair | Montreal | Jul 31, 2025 | Oct 31, 2025 | 232 | med | high | med | low | low | 796445 | 524562 | 156104 | 19.6001 | gpmc | Yes |  | X | X | X |  | no | Yes | no | Yes | Yes | Yes | no | no | Yes | 6 | 8
Project 263 | L1 | Pipe | replacement | Edmonton | Mar 31, 2025 | Jul 31, 2025 | 23 | high | high | low | high | high | 1584033 | 664770 | 1944357 | 122.7473 | gpmc | Yes |  | X | X |  |  | Yes | no | Yes | Yes | Yes | no | no | Yes | no | 2 | 7
Project 264 | L2 | Facility | excavation | Montreal | Dec 31, 2025 | Jul 31, 2027 | 320 | med | high | high | high | low | 422596 | 299973 | 312597 | 73.9706 | r/o | no |  |  |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 6 | 4
Project 265 | L3 | Pipe | inspection | Calgary | Mar 31, 2025 | Oct 31, 2025 | 141 | med | high | med | med | high | 1573912 | 1777824 | 1609459 | 102.2585 | capital | Yes |  | X |  |  |  | Yes | no | no | Yes | no | Yes | Yes | no | no | 8 | 6
Project 266 | L3 | Facility | inspection | Ottawa | Jul 31, 2025 | Oct 31, 2025 | 98 | med | high | low | high | low | 1621969 | 2526161 | 78411 | 4.8343 | capital | Yes | X | X |  |  | X | no | no | no | Yes | no | Yes | Yes | no | no | 4 | 4
Project 267 | L1 | Pipe | r/o | Calgary | Dec 31, 2025 | Dec 31, 2025 | 95 | low | low | high | med | low | 1802142 | 1455137 | 1996694 | 110.7956 | gpmc | no |  |  | X |  | X | Yes | Yes | Yes | no | no | Yes | no | no | no | 1 | 4
Project 268 | L1 | Pipe | r/o | Ottawa | Dec 31, 2025 | Jul 31, 2027 | 225 | low | high | high | high | low | 1089509 | 826510 | 1785226 | 163.856 | gpmc | no |  | X | X |  |  | Yes | no | Yes | Yes | no | Yes | no | Yes | Yes | 2 | 7
Project 269 | L3 | Pipe | excavation | Saskatoon | Jul 31, 2025 | Jul 31, 2026 | 359 | med | med | high | med | low | 444748 | 488689 | 1941857 | 436.6196 | r/o | Yes |  |  |  |  | X | no | Yes | Yes | no | Yes | Yes | no | no | no | 2 | 4
Project 270 | L3 | Pipe |  | Montreal | Dec 31, 2024 | Oct 31, 2027 | 306 | med | low | high | med | low | 1396573 | 1643780 | 134875 | 9.6576 | capital | no |  | X |  | X | X | no | no | Yes | no | Yes | Yes | Yes | Yes | Yes | 9 | 1
Project 271 | L3 | Pipe | inspection | Calgary | Dec 31, 2024 | Oct 31, 2025 | 160 | high | low | high | low | high | 683888 | 652279 | 1164711 | 170.3073 | gpmc | Yes | X | X | X | X |  | no | Yes | Yes | no | no | no | no | Yes | no | 2 | 2
Project 272 | L1 | Facility | replacement | Winnepeg | Jul 31, 2025 | Oct 31, 2026 | 173 | med | low | high | high | med | 81375 | 40630 | 760868 | 935.0144 | r/o | Yes | X |  |  |  |  | Yes | Yes | no | Yes | Yes | no | no | Yes | no | 6 | 3
Project 273 | L2 | Pipe | replacement | Regina | Mar 31, 2025 | Oct 31, 2027 | 247 | low | med | high | low | low | 85886 | 53109 | 1944558 | 2264.1152 | capital | no | X | X |  | X |  | no | no | Yes | no | Yes | Yes | no | no | Yes | 8 | 9
Project 274 | L1 | Pipe | excavation | Saskatoon | Oct 31, 2025 | Jul 31, 2026 | 240 | med | high | low | high | med | 1790044 | 537316 | 147788 | 8.2561 | gpmc | Yes |  |  |  | X | X | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 3 | 8
Project 275 | L3 | Pipe | r/o | Regina | Dec 31, 2024 | Jul 31, 2025 | 140 | high | high | med | med | high | 1561623 | 641678 | 281782 | 18.0442 | gpmc | no | X | X | X |  | X | Yes | no | Yes | Yes | no | no | no | Yes | no | 2 | 6
Project 276 | L2 | Facility | replacement | Regina | Mar 31, 2025 | Oct 31, 2026 | 160 | med | low | med | low | med | 276833 | 147610 | 224904 | 81.2418 | r/o | no |  |  | X | X |  | no | no | Yes | no | no | no | no | no | no | 7 | 2
Project 277 | L1 | Facility | r/o | Edmonton | Dec 31, 2024 | Dec 31, 2026 | 355 | low | low | low | low | low | 52738 | 71761 | 1260219 | 2389.5844 | capital | Yes | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | Yes | no | no | 7 | 5
Project 278 | L1 | Facility | r/o | Saskatoon | Oct 31, 2025 | Dec 31, 2025 | 85 | med | low | high | med | low | 1323286 | 1392649 | 1629785 | 123.162 | capital | Yes |  | X |  |  | X | Yes | Yes | no | Yes | Yes | Yes | no | no | Yes | 8 | 9
Project 279 | L1 | Facility | inspection | Montreal | Mar 31, 2025 | Jul 31, 2026 | 259 | low | low | med | low | med | 1688854 | 2041814 | 1405261 | 83.208 | gpmc | Yes | X |  | X |  |  | no | Yes | no | Yes | no | no | no | no | Yes | 1 | 4
Project 280 | L2 | Pipe | r/o | Saskatoon | Oct 31, 2025 | Oct 31, 2025 | 317 | high | low | med | high | high | 1874257 | 1869182 | 1514009 | 80.7792 | r/o | Yes |  | X |  |  | X | no | no | no | no | Yes | Yes | Yes | no | no | 3 | 2
Project 281 | L1 | Pipe | excavation | Saskatoon | Mar 31, 2025 | Oct 31, 2026 | 269 | high | low | high | med | med | 769035 | 235481 | 1426353 | 185.4731 | gpmc | Yes |  |  | X | X | X | Yes | Yes | no | Yes | Yes | no | no | no | Yes | 5 | 3
Project 282 | L2 | Facility | replacement | Edmonton | Oct 31, 2025 | Oct 31, 2027 | 189 | low | high | low | low | low | 991104 | 959033 | 1110396 | 112.0363 | gpmc | no |  |  |  |  | X | Yes | no | no | Yes | no | Yes | no | Yes | Yes | 1 | 4
Project 283 | L2 | Pipe | r/o | Saskatoon | Dec 31, 2024 | Oct 31, 2025 | 227 | med | high | high | med | med | 478046 | 683445 | 1550429 | 324.3263 | capital | Yes | X |  | X | X | X | no | no | no | Yes | no | no | no | no | no | 9 | 8
Project 284 | L3 | Facility |  | Edmonton | Dec 31, 2024 | Oct 31, 2026 | 246 | low | med | high | high | low | 1384114 | 914562 | 1739274 | 125.6597 | capital | Yes |  | X | X | X |  | Yes | no | no | no | no | no | no | Yes | no | 3 | 7
Project 285 | L1 | Facility | excavation | Regina | Oct 31, 2025 | Jul 31, 2025 | 196 | high | med | med | high | med | 545838 | 719019 | 1910042 | 349.9284 | gpmc | no |  |  |  | X | X | Yes | Yes | no | no | no | Yes | Yes | no | no | 3 | 1
Project 286 | L2 | Facility |  | North Bay | Oct 31, 2025 | Jul 31, 2026 | 279 | med | med | high | med | low | 1223133 | 1169362 | 1706537 | 139.5218 | gpmc | no |  |  | X |  | X | no | no | no | Yes | Yes | Yes | no | Yes | Yes | 6 | 1
Project 287 | L1 | Facility | replacement | Edmonton | Oct 31, 2025 | Jul 31, 2027 | 311 | low | med | high | high | med | 871322 | 400254 | 414158 | 47.5321 | capital | Yes | X | X | X | X |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 4 | 4
Project 288 | L3 | Pipe | replacement | Edmonton | Jul 31, 2025 | Dec 31, 2027 | 28 | low | high | high | high | med | 820074 | 838581 | 838837 | 102.288 | r/o | Yes |  |  |  | X | X | no | Yes | no | no | Yes | no | no | no | no | 1 | 4
Project 289 | L2 | Facility | repair | North Bay | Dec 31, 2024 | Dec 31, 2025 | 18 | high | high | low | med | med | 295554 | 186887 | 1087922 | 368.0958 | capital | Yes |  |  |  | X | X | no | no | no | Yes | no | Yes | no | no | no | 1 | 5
Project 290 | L3 | Facility | inspection | Ottawa | Oct 31, 2025 | Oct 31, 2027 | 79 | high | high | high | low | low | 1859247 | 1924392 | 291432 | 15.6747 | gpmc | no |  |  | X | X |  | Yes | no | no | no | no | no | Yes | no | Yes | 7 | 2
Project 291 | L3 | Facility | replacement | Ottawa | Dec 31, 2025 | Oct 31, 2025 | 277 | med | high | med | med | low | 1954542 | 959473 | 195803 | 10.0178 | gpmc | no |  | X | X |  |  | no | Yes | Yes | no | no | no | no | no | no | 4 | 1
Project 292 | L3 | Pipe |  | North Bay | Dec 31, 2025 | Dec 31, 2027 | 273 | med | high | low | med | low | 1192151 | 1695204 | 562631 | 47.1946 | capital | no |  | X |  | X | X | no | no | Yes | no | no | Yes | no | Yes | no | 8 | 1
Project 293 | L2 | Pipe | excavation | Regina | Dec 31, 2024 | Oct 31, 2027 | 294 | high | high | low | med | low | 1304703 | 1617005 | 894366 | 68.5494 | r/o | Yes | X |  |  |  |  | no | Yes | Yes | no | no | no | no | no | Yes | 1 | 6
Project 294 | L2 | Pipe | r/o | Ottawa | Oct 31, 2025 | Dec 31, 2027 | 362 | high | med | high | high | low | 1332015 | 1335753 | 1133132 | 85.069 | gpmc | Yes | X | X |  |  |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 2 | 5
Project 295 | L1 | Facility | replacement | Quebec City | Mar 31, 2025 | Oct 31, 2025 | 251 | low | low | low | high | high | 1401747 | 1278722 | 150475 | 10.7348 | capital | Yes |  | X | X | X |  | Yes | Yes | Yes | Yes | Yes | Yes | no | no | no | 8 | 8
Project 296 | L3 | Facility |  | Winnepeg | Jul 31, 2025 | Oct 31, 2027 | 319 | low | med | high | high | low | 1799836 | 2048214 | 894210 | 49.6829 | capital | no | X | X | X | X |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 8 | 1
Project 297 | L2 | Facility | r/o | Saskatoon | Oct 31, 2025 | Dec 31, 2025 | 336 | low | low | med | high | med | 1479314 | 669633 | 1500359 | 101.4226 | capital | no |  |  | X |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 9 | 4
Project 298 | L3 | Pipe |  | Montreal | Oct 31, 2025 | Jul 31, 2025 | 327 | low | med | low | high | low | 191073 | 127295 | 1679790 | 879.1352 | r/o | Yes | X |  |  | X | X | no | no | Yes | Yes | Yes | Yes | no | no | no | 5 | 6
Project 299 | L3 | Facility |  | North Bay | Oct 31, 2025 | Oct 31, 2027 | 82 | high | low | med | high | high | 173803 | 173741 | 1336164 | 768.7807 | capital | no |  |  | X | X | X | no | Yes | Yes | no | no | no | Yes | no | no | 8 | 2
Project 300 | L2 | Facility | replacement | Montreal | Oct 31, 2025 | Oct 31, 2027 | 178 | high | med | low | low | high | 425675 | 263148 | 89614 | 21.0522 | capital | Yes |  | X |  |  | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 1
Project 301 | L2 | Facility | excavation | Quebec City | Mar 31, 2025 | Dec 31, 2025 | 162 | med | low | high | med | med | 901700 | 1258225 | 679784 | 75.3892 | gpmc | no |  |  |  | X |  | Yes | Yes | no | Yes | no | Yes | Yes | Yes | no | 7 | 6
Project 302 | L1 | Pipe | excavation | Winnepeg | Jul 31, 2025 | Dec 31, 2027 | 221 | low | high | med | low | high | 998701 | 392855 | 522814 | 52.3494 | gpmc | no |  |  |  | X | X | no | Yes | Yes | Yes | no | Yes | Yes | no | no | 5 | 9
Project 303 | L3 | Facility | inspection | North Bay | Dec 31, 2025 | Oct 31, 2026 | 45 | med | high | high | high | low | 1747532 | 1428039 | 440411 | 25.2019 | capital | Yes |  | X | X | X | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 6
Project 304 | L1 | Facility | inspection | Calgary | Dec 31, 2024 | Jul 31, 2025 | 240 | high | high | high | high | high | 1903471 | 1773444 | 668938 | 35.1431 | capital | Yes | X |  |  |  | X | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 2 | 9
Project 305 | L2 | Pipe |  | Saskatoon | Jul 31, 2025 | Oct 31, 2026 | 233 | med | low | low | low | med | 1192622 | 1080086 | 875929 | 73.4457 | gpmc | Yes |  |  | X |  | X | Yes | Yes | Yes | no | no | Yes | no | no | no | 8 | 9
Project 306 | L1 | Pipe | repair | Toronto | Mar 31, 2025 | Jul 31, 2026 | 300 | low | high | high | low | med | 865643 | 1359115 | 41855 | 4.8351 | gpmc | Yes |  |  | X |  |  | no | Yes | no | Yes | no | no | no | Yes | Yes | 6 | 3
Project 307 | L2 | Pipe | inspection | North Bay | Jul 31, 2025 | Jul 31, 2026 | 229 | low | med | low | high | med | 991022 | 1626398 | 135685 | 13.6914 | capital | Yes | X |  | X |  |  | no | no | Yes | no | Yes | Yes | Yes | no | no | 8 | 1
Project 308 | L1 | Facility | replacement | North Bay | Mar 31, 2025 | Dec 31, 2025 | 116 | med | low | high | high | low | 673905 | 1107423 | 441177 | 65.4658 | gpmc | no | X |  |  | X |  | Yes | no | Yes | no | Yes | no | no | no | no | 5 | 7
Project 309 | L3 | Facility | repair | Edmonton | Mar 31, 2025 | Dec 31, 2026 | 184 | high | high | med | med | med | 1697751 | 2799355 | 623080 | 36.7003 | gpmc | no | X | X |  |  |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 2 | 3
Project 310 | L3 | Pipe | repair | Quebec City | Oct 31, 2025 | Dec 31, 2026 | 362 | low | high | high | low | med | 1128156 | 1676906 | 1486393 | 131.7542 | r/o | Yes | X | X |  | X |  | no | no | no | Yes | Yes | Yes | no | no | Yes | 4 | 3
Project 311 | L1 | Facility |  | Toronto | Mar 31, 2025 | Jul 31, 2026 | 180 | high | med | high | low | high | 1645643 | 2156461 | 1475344 | 89.6515 | gpmc | no | X | X | X |  |  | no | no | no | Yes | no | no | Yes | no | no | 4 | 7
Project 312 | L3 | Facility | replacement | Winnepeg | Mar 31, 2025 | Jul 31, 2026 | 299 | high | high | high | low | low | 1388624 | 2331581 | 772137 | 55.6045 | gpmc | no |  |  |  |  | X | Yes | Yes | no | Yes | no | Yes | no | Yes | no | 4 | 1
Project 313 | L1 | Facility |  | Edmonton | Jul 31, 2025 | Jul 31, 2026 | 335 | low | low | high | high | med | 182509 | 158390 | 1626985 | 891.4547 | gpmc | no | X | X |  | X | X | no | Yes | no | no | Yes | no | Yes | Yes | Yes | 4 | 8
Project 314 | L2 | Facility | repair | Quebec City | Dec 31, 2025 | Dec 31, 2025 | 54 | med | low | high | med | low | 1676766 | 693658 | 1602910 | 95.5953 | gpmc | Yes | X | X | X | X | X | Yes | no | no | Yes | Yes | no | no | Yes | no | 7 | 5
Project 315 | L3 | Pipe | excavation | Regina | Oct 31, 2025 | Jul 31, 2026 | 172 | med | med | high | med | low | 1294832 | 1873191 | 520503 | 40.1985 | gpmc | Yes | X |  | X | X |  | no | no | Yes | Yes | no | Yes | no | no | Yes | 2 | 7
Project 316 | L3 | Pipe |  | Saskatoon | Dec 31, 2024 | Dec 31, 2027 | 188 | high | high | low | high | low | 1389237 | 976776 | 419886 | 30.2242 | capital | no |  | X | X | X | X | Yes | no | no | Yes | Yes | Yes | no | no | no | 6 | 3
Project 317 | L2 | Pipe | repair | Regina | Oct 31, 2025 | Dec 31, 2027 | 344 | med | high | low | low | high | 1391928 | 2266220 | 200853 | 14.4298 | gpmc | no | X |  |  |  | X | Yes | no | no | Yes | no | no | no | no | no | 8 | 4
Project 318 | L1 | Pipe | excavation | Saskatoon | Mar 31, 2025 | Oct 31, 2026 | 66 | med | high | low | high | high | 1102578 | 1120960 | 1521383 | 137.9842 | r/o | Yes | X |  |  | X | X | Yes | no | no | Yes | Yes | Yes | no | no | no | 7 | 7
Project 319 | L2 | Pipe | replacement | North Bay | Oct 31, 2025 | Oct 31, 2027 | 329 | high | med | low | low | low | 1311464 | 1610050 | 924884 | 70.523 | gpmc | Yes |  |  | X | X | X | no | Yes | Yes | no | no | Yes | no | no | Yes | 7 | 6
Project 320 | L3 | Pipe | excavation | Regina | Mar 31, 2025 | Dec 31, 2025 | 162 | high | high | high | med | high | 1851652 | 2297198 | 1135986 | 61.3499 | r/o | no |  |  |  | X |  | Yes | Yes | Yes | no | no | Yes | no | Yes | Yes | 8 | 2
Project 321 | L2 | Pipe | inspection | Calgary | Oct 31, 2025 | Dec 31, 2027 | 313 | high | med | med | high | med | 1493619 | 1103352 | 156401 | 10.4713 | r/o | Yes | X | X | X |  |  | no | no | no | Yes | no | Yes | no | Yes | no | 1 | 5
Project 322 | L2 | Pipe | inspection | Toronto | Dec 31, 2024 | Jul 31, 2026 | 126 | high | high | med | low | med | 588436 | 781378 | 1398056 | 237.5885 | capital | Yes | X | X | X |  | X | no | Yes | Yes | no | Yes | Yes | Yes | no | no | 4 | 2
Project 323 | L1 | Facility | inspection | Edmonton | Jul 31, 2025 | Oct 31, 2027 | 99 | med | high | low | med | high | 1785515 | 2539539 | 932135 | 52.2054 | r/o | Yes | X | X |  | X |  | no | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 3 | 4
Project 324 | L3 | Pipe | excavation | Toronto | Dec 31, 2024 | Oct 31, 2027 | 171 | low | med | low | low | low | 459448 | 159542 | 702722 | 152.9492 | capital | Yes |  | X | X | X | X | Yes | Yes | Yes | no | no | Yes | no | no | no | 6 | 6
Project 325 | L1 | Facility |  | Saskatoon | Jul 31, 2025 | Dec 31, 2026 | 360 | high | med | high | low | high | 1980270 | 1568153 | 307431 | 15.5247 | capital | Yes |  |  | X |  |  | Yes | no | Yes | no | Yes | no | Yes | Yes | Yes | 3 | 8
Project 326 | L2 | Pipe | repair | Ottawa | Dec 31, 2025 | Dec 31, 2025 | 45 | high | low | high | med | low | 284704 | 405579 | 835523 | 293.4708 | r/o | Yes |  |  |  | X | X | Yes | no | Yes | Yes | no | no | Yes | Yes | Yes | 2 | 3
Project 327 | L1 | Facility | excavation | Ottawa | Oct 31, 2025 | Oct 31, 2026 | 308 | med | med | low | low | med | 1845587 | 881111 | 417117 | 22.6008 | capital | Yes |  |  | X |  |  | Yes | no | Yes | Yes | no | Yes | no | Yes | Yes | 8 | 2
Project 328 | L1 | Facility | inspection | Winnepeg | Dec 31, 2025 | Oct 31, 2027 | 115 | high | high | med | low | low | 1645798 | 1982622 | 1961271 | 119.1684 | capital | no |  |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | no | Yes | no | 4 | 9
Project 329 | L3 | Facility | r/o | Quebec City | Dec 31, 2025 | Dec 31, 2027 | 364 | high | high | low | low | high | 1308377 | 1248569 | 1841567 | 140.752 | gpmc | no | X | X | X | X |  | no | Yes | no | no | no | no | no | Yes | Yes | 2 | 3
Project 330 | L1 | Facility | inspection | Calgary | Mar 31, 2025 | Dec 31, 2027 | 89 | med | high | high | med | low | 1805584 | 3082914 | 1936237 | 107.2361 | r/o | Yes | X |  |  |  | X | Yes | no | Yes | Yes | no | Yes | no | Yes | no | 4 | 2
Project 331 | L3 | Pipe | repair | Regina | Mar 31, 2025 | Jul 31, 2025 | 314 | low | high | med | med | high | 629368 | 696439 | 1603994 | 254.8579 | capital | Yes | [5 empty] | Yes | no | no | no | Yes | Yes | no | Yes | Yes | 6 | 3
Project 332 | L2 | Pipe |  | Quebec City | Jul 31, 2025 | Oct 31, 2025 | 34 | med | low | low | med | high | 228344 | 392070 | 557138 | 243.9906 | gpmc | Yes | X |  |  | X | X | no | no | Yes | Yes | Yes | no | no | no | no | 1 | 2
Project 333 | L3 | Facility | r/o | Toronto | Dec 31, 2024 | Oct 31, 2027 | 52 | low | high | med | low | high | 1887342 | 3163616 | 1715682 | 90.9047 | capital | no | X | X |  |  | X | Yes | Yes | Yes | no | no | no | no | Yes | no | 1 | 5
Project 334 | L1 | Pipe | repair | Regina | Jul 31, 2025 | Oct 31, 2025 | 249 | med | high | high | low | high | 406336 | 509055 | 1259240 | 309.9012 | gpmc | no |  |  |  | X | X | Yes | Yes | no | no | no | Yes | no | Yes | no | 7 | 6
Project 335 | L3 | Pipe |  | Ottawa | Oct 31, 2025 | Jul 31, 2027 | 183 | low | high | med | med | med | 258909 | 196373 | 793723 | 306.5645 | capital | Yes |  | X |  | X | X | no | no | no | no | no | no | no | no | Yes | 6 | 9
Project 336 | L1 | Facility | replacement | Saskatoon | Dec 31, 2024 | Oct 31, 2027 | 321 | low | med | med | low | high | 636600 | 946743 | 664697 | 104.4136 | gpmc | Yes |  | X |  | X | X | no | Yes | Yes | Yes | no | no | Yes | Yes | Yes | 2 | 8
Project 337 | L2 | Facility | repair | North Bay | Dec 31, 2025 | Jul 31, 2027 | 154 | low | low | high | high | low | 1812338 | 494031 | 783083 | 43.2084 | capital | no | X |  | X |  | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 7 | 7
Project 338 | L1 | Pipe | r/o | Saskatoon | Mar 31, 2025 | Dec 31, 2027 | 315 | med | low | high | low | low | 1414287 | 764954 | 1121398 | 79.2907 | gpmc | Yes |  | X |  |  |  | no | no | no | no | Yes | Yes | no | no | Yes | 3 | 7
Project 339 | L1 | Facility | excavation | North Bay | Oct 31, 2025 | Jul 31, 2026 | 177 | low | low | high | high | med | 416962 | 393069 | 907649 | 217.6815 | gpmc | no | X | X | X | X |  | no | no | Yes | Yes | no | no | Yes | Yes | Yes | 7 | 1
Project 340 | L3 | Facility | inspection | Toronto | Dec 31, 2024 | Jul 31, 2025 | 226 | high | low | low | high | med | 1405575 | 1324177 | 1357010 | 96.5448 | r/o | no | X |  | X | X |  | Yes | Yes | no | Yes | Yes | Yes | no | no | Yes | 3 | 6
Project 341 | L2 | Pipe | r/o | Quebec City | Dec 31, 2025 | Jul 31, 2026 | 13 | med | med | low | high | med | 1519717 | 1881006 | 1309559 | 86.1712 | gpmc | no |  |  | X | X | X | Yes | Yes | no | no | no | Yes | no | Yes | no | 1 | 2
Project 342 | L2 | Facility |  | Toronto | Dec 31, 2025 | Jul 31, 2025 | 89 | low | med | high | med | med | 355658 | 524161 | 1039902 | 292.3882 | capital | no | X |  | X |  |  | no | Yes | Yes | Yes | no | no | no | Yes | no | 9 | 7
Project 343 | L2 | Pipe | r/o | Ottawa | Jul 31, 2025 | Oct 31, 2026 | 295 | med | low | low | high | low | 1734363 | 1738400 | 389706 | 22.4697 | gpmc | Yes | X |  | X | X |  | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 7 | 4
Project 344 | L1 | Pipe | inspection | Montreal | Dec 31, 2024 | Jul 31, 2025 | 116 | med | med | low | low | low | 407208 | 114606 | 730388 | 179.3648 | gpmc | no | X |  |  |  |  | Yes | no | no | Yes | Yes | Yes | Yes | Yes | no | 7 | 4
Project 345 | L2 | Pipe | inspection | North Bay | Dec 31, 2024 | Oct 31, 2027 | 123 | high | low | high | low | med | 1333802 | 813958 | 1994496 | 149.5346 | capital | no | X | X | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 4 | 2
Project 346 | L1 | Pipe | inspection | Toronto | Jul 31, 2025 | Dec 31, 2026 | 42 | low | med | high | low | med | 509457 | 660376 | 94500 | 18.5492 | gpmc | Yes | X |  |  | X | X | no | no | Yes | Yes | Yes | no | no | no | no | 2 | 1
Project 347 | L1 | Facility |  | Saskatoon | Oct 31, 2025 | Dec 31, 2025 | 354 | med | low | high | high | med | 557123 | 230519 | 995131 | 178.6196 | r/o | no | X | X | X | X |  | no | Yes | no | Yes | no | Yes | no | no | no | 8 | 7
Project 348 | L1 | Pipe | excavation | Winnepeg | Dec 31, 2025 | Dec 31, 2026 | 138 | low | low | high | med | high | 419947 | 506724 | 847122 | 201.7212 | r/o | no | X | X |  |  | X | Yes | Yes | Yes | no | Yes | Yes | Yes | no | no | 7 | 7
Project 349 | L2 | Facility | inspection | Montreal | Dec 31, 2024 | Oct 31, 2027 | 125 | high | high | high | med | low | 1672490 | 1639102 | 229941 | 13.7484 | capital | no |  | X |  |  | X | no | no | Yes | Yes | no | Yes | Yes | no | no | 3 | 9
Project 350 | L3 | Facility |  | Toronto | Dec 31, 2024 | Oct 31, 2026 | 358 | high | low | low | low | low | 192858 | 146925 | 648434 | 336.2235 | capital | no | X | X |  |  | X | Yes | Yes | no | Yes | no | Yes | Yes | no | no | 9 | 2
Project 351 | L1 | Facility | repair | Saskatoon | Oct 31, 2025 | Dec 31, 2027 | 12 | low | med | med | med | low | 1437344 | 1962417 | 36760 | 2.5575 | gpmc | Yes |  | X |  |  |  | Yes | Yes | no | no | Yes | no | no | Yes | no | 9 | 8
Project 352 | L3 | Pipe | r/o | Calgary | Jul 31, 2025 | Jul 31, 2026 | 263 | med | high | high | low | med | 329359 | 309537 | 1954675 | 593.4785 | r/o | no | [5 empty] | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 9 | 8
Project 353 | L3 | Facility |  | Quebec City | Jul 31, 2025 | Dec 31, 2026 | 40 | med | low | high | med | high | 1263775 | 604957 | 1767166 | 139.8323 | r/o | Yes |  | X |  | X |  | no | Yes | no | Yes | no | no | Yes | Yes | no | 9 | 2
Project 354 | L2 | Facility | repair | Regina | Oct 31, 2025 | Dec 31, 2025 | 118 | low | high | med | high | low | 647997 | 294368 | 430912 | 66.4991 | capital | no |  |  | X | X | X | Yes | no | Yes | Yes | no | no | no | Yes | Yes | 1 | 8
Project 355 | L1 | Facility | replacement | Calgary | Dec 31, 2025 | Jul 31, 2025 | 235 | low | low | high | med | high | 1466789 | 1201579 | 930035 | 63.4062 | capital | no |  |  | X |  | X | no | Yes | no | Yes | Yes | no | no | no | Yes | 6 | 4
Project 356 | L2 | Pipe | inspection | Winnepeg | Jul 31, 2025 | Oct 31, 2026 | 186 | low | med | med | high | med | 1007350 | 655931 | 1192090 | 118.3392 | r/o | no | X | X | X | X | X | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 9 | 8
Project 357 | L2 | Pipe | excavation | Edmonton | Oct 31, 2025 | Oct 31, 2027 | 183 | low | high | low | low | high | 679555 | 594783 | 694867 | 102.2532 | capital | Yes | X | X |  |  |  | Yes | no | no | Yes | Yes | no | Yes | Yes | no | 8 | 2
Project 358 | L1 | Facility | excavation | Winnepeg | Jul 31, 2025 | Dec 31, 2025 | 210 | high | low | high | low | med | 1335237 | 1010831 | 358486 | 26.8481 | gpmc | no | [5 empty] | no | no | Yes | Yes | no | Yes | no | Yes | Yes | 3 | 9
Project 359 | L2 | Facility | repair | Edmonton | Oct 31, 2025 | Oct 31, 2026 | 241 | med | low | low | med | low | 1583850 | 1156134 | 799997 | 50.5096 | capital | no | X |  | X |  |  | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 4 | 6
Project 360 | L1 | Facility | excavation | Winnepeg | Oct 31, 2025 | Jul 31, 2027 | 360 | med | high | med | low | low | 457429 | 454056 | 1279293 | 279.6703 | capital | Yes |  |  | X | X |  | Yes | Yes | Yes | Yes | no | Yes | no | Yes | no | 6 | 2
Project 361 | L3 | Facility | replacement | Calgary | Oct 31, 2025 | Oct 31, 2025 | 325 | high | med | low | low | low | 1875105 | 621544 | 1686374 | 89.9349 | r/o | no |  |  | X | X | X | no | no | no | Yes | Yes | no | Yes | no | Yes | 6 | 6
Project 362 | L3 | Pipe | excavation | Montreal | Mar 31, 2025 | Oct 31, 2027 | 38 | high | high | high | high | high | 579997 | 823111 | 1927758 | 332.3738 | gpmc | no | X |  |  |  |  | no | Yes | no | no | Yes | no | no | Yes | Yes | 8 | 4
Project 363 | L3 | Facility | repair | Calgary | Jul 31, 2025 | Dec 31, 2026 | 29 | med | high | low | med | low | 1188279 | 441406 | 409371 | 34.4507 | r/o | no | [5 empty] | no | no | no | no | no | no | no | Yes | no | 2 | 1
Project 364 | L1 | Pipe | excavation | Toronto | Oct 31, 2025 | Jul 31, 2025 | 277 | low | low | med | high | low | 1956531 | 1168670 | 446028 | 22.7969 | r/o | no | X | X | X | X | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 5 | 8
Project 365 | L1 | Pipe | r/o | Winnepeg | Mar 31, 2025 | Oct 31, 2025 | 38 | low | med | med | med | low | 577785 | 184172 | 1014464 | 175.5781 | capital | Yes | X |  |  | X | X | Yes | no | Yes | Yes | no | Yes | no | Yes | Yes | 9 | 4
Project 366 | L1 | Pipe |  | North Bay | Dec 31, 2024 | Dec 31, 2025 | 219 | med | med | med | low | high | 1863342 | 1936458 | 1321912 | 70.9431 | r/o | Yes | X | X |  | X |  | Yes | Yes | no | Yes | no | no | Yes | no | Yes | 3 | 5
Project 367 | L1 | Facility |  | Edmonton | Oct 31, 2025 | Oct 31, 2026 | 125 | med | low | med | low | high | 1207424 | 1525091 | 481865 | 39.9085 | capital | no |  |  |  | X | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 8 | 9
Project 368 | L1 | Pipe | excavation | Saskatoon | Dec 31, 2025 | Dec 31, 2025 | 68 | low | med | med | med | high | 968688 | 705704 | 588216 | 60.723 | r/o | no | X |  | X | X |  | no | Yes | Yes | Yes | no | Yes | no | no | Yes | 8 | 9
Project 369 | L3 | Pipe | r/o | Calgary | Oct 31, 2025 | Jul 31, 2027 | 48 | low | med | low | high | low | 989759 | 623968 | 1771771 | 179.0103 | capital | Yes |  |  | X |  | X | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 4 | 5
Project 370 | L2 | Facility | r/o | Winnepeg | Jul 31, 2025 | Jul 31, 2025 | 174 | med | med | high | med | med | 535525 | 154227 | 1990578 | 371.7059 | r/o | no | X |  | X | X |  | Yes | no | no | no | Yes | no | no | no | no | 4 | 2
Project 371 | L2 | Facility | replacement | Calgary | Dec 31, 2024 | Oct 31, 2027 | 204 | high | med | low | med | med | 976583 | 1505043 | 1070059 | 109.5717 | capital | Yes | X | X | X |  | X | Yes | no | no | Yes | Yes | no | no | no | Yes | 7 | 3
Project 372 | L1 | Pipe |  | Quebec City | Dec 31, 2025 | Jul 31, 2025 | 267 | med | med | med | med | low | 1568544 | 2061847 | 94535 | 6.0269 | capital | Yes |  |  |  | X | X | Yes | no | Yes | Yes | no | no | no | no | Yes | 3 | 1
Project 373 | L3 | Facility |  | Montreal | Oct 31, 2025 | Oct 31, 2027 | 64 | med | low | med | low | med | 213757 | 367533 | 1539183 | 720.062 | gpmc | Yes |  | X | X |  | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 3 | 3
Project 374 | L2 | Pipe | replacement | Montreal | Mar 31, 2025 | Dec 31, 2027 | 261 | med | med | high | high | low | 1816320 | 992178 | 1097944 | 60.4488 | gpmc | Yes | X |  |  |  | X | no | no | no | Yes | Yes | no | no | Yes | Yes | 3 | 7
Project 375 | L3 | Pipe |  | Winnepeg | Jul 31, 2025 | Jul 31, 2027 | 225 | low | high | low | med | high | 606108 | 872898 | 1845466 | 304.4781 | capital | no | X | X |  | X | X | Yes | Yes | no | Yes | no | Yes | no | Yes | no | 4 | 1
Project 376 | L2 | Pipe | r/o | Saskatoon | Oct 31, 2025 | Oct 31, 2025 | 156 | low | med | high | low | high | 116947 | 170375 | 661273 | 565.4467 | capital | Yes |  | X |  | X | X | Yes | Yes | no | no | no | Yes | Yes | Yes | Yes | 5 | 9
Project 377 | L3 | Pipe | inspection | Ottawa | Oct 31, 2025 | Dec 31, 2025 | 303 | high | low | low | med | med | 310072 | 341193 | 503698 | 162.4455 | r/o | Yes |  | X | X |  |  | Yes | no | no | no | Yes | no | Yes | no | no | 9 | 1
Project 378 | L3 | Facility | replacement | Saskatoon | Mar 31, 2025 | Jul 31, 2027 | 300 | low | low | high | low | med | 1197207 | 945946 | 404543 | 33.7906 | r/o | Yes |  |  | X | X | X | Yes | Yes | Yes | no | Yes | no | no | Yes | Yes | 7 | 2
Project 379 | L1 | Pipe | r/o | Regina | Jul 31, 2025 | Oct 31, 2026 | 113 | low | low | high | high | med | 614155 | 1033673 | 1007361 | 164.0239 | r/o | no |  | X | X |  |  | Yes | no | Yes | no | Yes | no | Yes | no | no | 7 | 8
Project 380 | L1 | Pipe | excavation | North Bay | Mar 31, 2025 | Oct 31, 2025 | 40 | med | low | low | med | med | 999824 | 690149 | 325495 | 32.5552 | gpmc | no |  | X | X | X | X | no | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 2 | 5
Project 381 | L2 | Facility | inspection | Regina | Oct 31, 2025 | Jul 31, 2026 | 269 | med | low | high | high | med | 933857 | 1408890 | 171557 | 18.3708 | capital | no |  | X | X |  | X | Yes | no | no | Yes | no | no | Yes | Yes | no | 3 | 5
Project 382 | L1 | Facility | excavation | Saskatoon | Dec 31, 2024 | Jul 31, 2025 | 269 | low | high | high | med | low | 625499 | 429206 | 1760586 | 281.469 | gpmc | Yes | X |  | X |  |  | no | Yes | no | no | no | no | Yes | Yes | Yes | 7 | 7
Project 383 | L2 | Facility | replacement | Edmonton | Oct 31, 2025 | Jul 31, 2026 | 287 | med | low | high | med | high | 932872 | 300770 | 1915520 | 205.3358 | r/o | Yes |  | X |  | X |  | Yes | no | no | Yes | no | no | no | Yes | Yes | 2 | 6
Project 384 | L1 | Facility | replacement | Edmonton | Oct 31, 2025 | Dec 31, 2025 | 334 | med | low | high | low | high | 1941677 | 1062655 | 396073 | 20.3985 | capital | no | X | X |  | X | X | Yes | no | no | no | no | no | no | Yes | no | 2 | 9
Project 385 | L1 | Facility | inspection | Calgary | Oct 31, 2025 | Jul 31, 2027 | 134 | low | med | low | low | med | 1332944 | 1615494 | 1860046 | 139.5442 | capital | no | X |  | X |  | X | Yes | no | no | no | Yes | Yes | Yes | no | no | 9 | 3
Project 386 | L3 | Pipe | repair | Winnepeg | Dec 31, 2024 | Oct 31, 2025 | 115 | low | high | med | med | med | 604025 | 174932 | 430191 | 71.2207 | r/o | Yes |  |  | X | X |  | no | Yes | Yes | Yes | Yes | Yes | no | no | no | 5 | 4
Project 387 | L3 | Pipe | excavation | Regina | Dec 31, 2025 | Dec 31, 2027 | 310 | high | med | low | low | high | 1003536 | 586428 | 1816496 | 181.0096 | r/o | Yes | X |  |  |  |  | Yes | no | no | Yes | no | Yes | Yes | no | no | 3 | 1
Project 388 | L2 | Pipe | excavation | Regina | Dec 31, 2024 | Jul 31, 2025 | 308 | high | high | high | med | low | 1610372 | 1104166 | 684598 | 42.5118 | gpmc | Yes |  | X |  | X | X | Yes | Yes | no | no | no | Yes | Yes | Yes | Yes | 1 | 2
Project 389 | L2 | Pipe | repair | Montreal | Jul 31, 2025 | Oct 31, 2027 | 145 | high | high | high | low | med | 794857 | 881863 | 1558168 | 196.0312 | r/o | no |  | X |  |  |  | no | no | no | Yes | Yes | Yes | no | Yes | no | 2 | 9
Project 390 | L1 | Facility | r/o | Regina | Jul 31, 2025 | Oct 31, 2027 | 143 | low | low | high | med | high | 880473 | 1028825 | 1694648 | 192.4702 | r/o | no |  | X |  |  | X | Yes | Yes | no | no | no | no | no | no | Yes | 1 | 7
Project 391 | L2 | Facility | inspection | Regina | Jul 31, 2025 | Jul 31, 2025 | 67 | high | med | low | high | low | 1318481 | 536982 | 1511805 | 114.6626 | r/o | Yes | X | X |  | X | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 5 | 8
Project 392 | L2 | Facility | excavation | Regina | Oct 31, 2025 | Dec 31, 2027 | 171 | med | high | med | low | med | 1931979 | 3179681 | 716008 | 37.0609 | r/o | Yes |  | X |  |  |  | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 5 | 5
Project 393 | L3 | Facility |  | Saskatoon | Mar 31, 2025 | Oct 31, 2027 | 24 | med | med | low | high | low | 1220641 | 1926487 | 967665 | 79.2752 | capital | Yes | X |  | X | X |  | no | no | Yes | Yes | no | no | no | Yes | no | 5 | 5
Project 394 | L2 | Pipe | r/o | Quebec City | Dec 31, 2024 | Oct 31, 2026 | 80 | med | high | low | low | med | 1594020 | 657412 | 1907024 | 119.6361 | capital | Yes | X |  | X | X |  | Yes | no | Yes | no | Yes | Yes | Yes | Yes | Yes | 3 | 8
Project 395 | L3 | Facility | inspection | Edmonton | Oct 31, 2025 | Oct 31, 2025 | 75 | med | low | high | med | low | 889556 | 308020 | 1799857 | 202.3321 | gpmc | no | X |  | X | X |  | Yes | Yes | no | Yes | no | no | Yes | no | no | 7 | 5
Project 396 | L2 | Pipe | inspection | North Bay | Mar 31, 2025 | Dec 31, 2025 | 81 | low | low | high | high | low | 1159502 | 1966547 | 1580027 | 136.2677 | gpmc | Yes | X | X | X |  |  | Yes | no | Yes | Yes | no | no | Yes | Yes | no | 7 | 7
Project 397 | L2 | Pipe | repair | Quebec City | Jul 31, 2025 | Jul 31, 2026 | 341 | med | med | high | med | high | 331205 | 116631 | 1906904 | 575.7473 | gpmc | no |  | X | X | X | X | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 8 | 8
Project 398 | L3 | Pipe | r/o | Saskatoon | Dec 31, 2024 | Dec 31, 2025 | 208 | med | high | low | high | high | 879389 | 1018172 | 1048567 | 119.2381 | capital | Yes | X |  |  |  |  | Yes | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 2 | 5
Project 399 | L2 | Pipe | replacement | Winnepeg | Dec 31, 2025 | Jul 31, 2027 | 78 | high | high | low | med | low | 1549282 | 477272 | 113098 | 7.3 | capital | no | X | X | X | X |  | no | Yes | Yes | Yes | no | Yes | no | Yes | Yes | 3 | 6
Project 400 | L3 | Pipe | r/o | Montreal | Dec 31, 2024 | Jul 31, 2025 | 199 | low | low | low | low | low | 820243 | 535272 | 430416 | 52.4742 | gpmc | no |  | X |  |  |  | no | no | no | no | no | no | no | no | no | 5 | 1
Project 401 | L3 | Facility | repair | Toronto | Dec 31, 2025 | Jul 31, 2026 | 291 | high | high | low | low | high | 191716 | 165449 | 488991 | 255.0601 | capital | Yes | X | X | X | X |  | no | no | no | Yes | no | no | no | Yes | no | 8 | 5
Project 402 | L2 | Pipe | replacement | Montreal | Dec 31, 2025 | Jul 31, 2026 | 155 | low | low | med | med | low | 1936580 | 818055 | 1594003 | 82.3102 | gpmc | Yes |  |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | no | Yes | 6 | 3
Project 403 | L2 | Pipe | repair | Quebec City | Dec 31, 2024 | Oct 31, 2025 | 205 | high | low | low | high | high | 379418 | 401024 | 1834693 | 483.5545 | gpmc | Yes |  |  | X |  |  | no | Yes | Yes | no | no | no | no | no | Yes | 2 | 7
Project 404 | L1 | Pipe |  | Calgary | Dec 31, 2024 | Jul 31, 2026 | 206 | low | high | high | med | med | 1903020 | 962540 | 1946068 | 102.2621 | r/o | Yes |  | X |  |  | X | Yes | no | Yes | no | Yes | no | no | no | no | 9 | 8
Project 405 | L2 | Facility | r/o | Ottawa | Jul 31, 2025 | Dec 31, 2027 | 33 | high | high | low | med | low | 1086756 | 792239 | 1153372 | 106.1298 | gpmc | no | X |  |  |  |  | Yes | Yes | no | Yes | no | Yes | no | Yes | Yes | 6 | 3
Project 406 | L3 | Pipe | inspection | Calgary | Dec 31, 2024 | Dec 31, 2027 | 95 | med | high | low | low | med | 587953 | 339000 | 1296813 | 220.5641 | r/o | Yes | X |  | X |  |  | no | no | no | no | Yes | no | no | no | no | 9 | 4
Project 407 | L3 | Pipe | replacement | Edmonton | Dec 31, 2025 | Jul 31, 2026 | 174 | high | low | low | med | low | 53351 | 36891 | 645950 | 1210.7552 | capital | no | X | X | X | X |  | no | no | no | Yes | Yes | Yes | no | no | no | 6 | 9
Project 408 | L1 | Pipe | repair | Toronto | Dec 31, 2025 | Jul 31, 2025 | 35 | high | med | high | high | high | 685214 | 677333 | 231523 | 33.7884 | capital | Yes | X |  |  | X | X | Yes | no | no | no | Yes | no | no | Yes | Yes | 2 | 2
Project 409 | L2 | Facility | inspection | Montreal | Dec 31, 2024 | Jul 31, 2026 | 34 | low | high | high | high | low | 1490591 | 1972000 | 1884673 | 126.438 | gpmc | no | X | X |  |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 7 | 8
Project 410 | L3 | Pipe | r/o | Toronto | Dec 31, 2025 | Oct 31, 2026 | 153 | med | high | high | med | low | 705607 | 877054 | 1444583 | 204.7291 | gpmc | no |  | X | X | X |  | Yes | no | Yes | Yes | Yes | no | no | no | Yes | 3 | 2
Project 411 | L3 | Facility | excavation | North Bay | Dec 31, 2025 | Jul 31, 2025 | 75 | med | med | low | high | med | 466261 | 234341 | 785277 | 168.42 | gpmc | no |  |  | X |  | X | no | no | no | Yes | no | no | Yes | no | no | 2 | 2
Project 412 | L3 | Pipe | excavation | Toronto | Oct 31, 2025 | Oct 31, 2026 | 107 | low | low | high | high | med | 977825 | 928812 | 1748385 | 178.8035 | gpmc | no |  |  | X | X |  | no | no | no | no | Yes | no | no | Yes | no | 8 | 3
Project 413 | L3 | Pipe | repair | Winnepeg | Jul 31, 2025 | Dec 31, 2025 | 218 | low | low | med | high | med | 324663 | 409780 | 1406036 | 433.0755 | capital | no | X |  | X | X |  | Yes | Yes | no | Yes | Yes | Yes | no | no | no | 2 | 9
Project 414 | L3 | Facility | r/o | Winnepeg | Dec 31, 2024 | Jul 31, 2026 | 173 | low | low | med | low | high | 524382 | 681913 | 1416846 | 270.1935 | capital | no | X | X |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 1 | 5
Project 415 | L1 | Pipe | repair | Montreal | Dec 31, 2025 | Dec 31, 2026 | 30 | med | med | high | low | med | 482924 | 647254 | 1000599 | 207.196 | capital | no | X | X |  |  | X | Yes | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 1 | 9
Project 416 | L1 | Facility | inspection | Edmonton | Oct 31, 2025 | Jul 31, 2026 | 331 | low | low | high | low | low | 1497611 | 680263 | 1035456 | 69.1405 | r/o | no |  | X | X |  | X | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 8 | 6
Project 417 | L2 | Pipe |  | Montreal | Dec 31, 2025 | Dec 31, 2027 | 63 | high | med | high | high | high | 1003319 | 1286220 | 1867148 | 186.0971 | r/o | Yes | [5 empty] | Yes | Yes | Yes | no | Yes | Yes | Yes | no | no | 5 | 5
Project 418 | L1 | Pipe |  | Ottawa | Mar 31, 2025 | Dec 31, 2027 | 119 | med | low | high | low | med | 1333269 | 2014655 | 127761 | 9.5825 | capital | Yes | X |  |  |  |  | Yes | Yes | Yes | no | no | no | Yes | no | no | 4 | 7
Project 419 | L3 | Pipe | replacement | Montreal | Mar 31, 2025 | Oct 31, 2025 | 191 | low | med | high | low | med | 487698 | 693531 | 1574875 | 322.9201 | gpmc | no | [5 empty] | Yes | no | Yes | no | no | Yes | no | no | no | 6 | 1
Project 420 | L1 | Pipe |  | Saskatoon | Dec 31, 2025 | Oct 31, 2027 | 108 | low | med | low | high | med | 1331529 | 396771 | 854116 | 64.1455 | r/o | Yes | X |  | X | X |  | no | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 7
Project 421 | L3 | Facility | excavation | Regina | Oct 31, 2025 | Oct 31, 2025 | 305 | med | high | med | high | med | 1261448 | 2167914 | 1571867 | 124.6081 | r/o | Yes |  |  |  | X | X | Yes | Yes | Yes | Yes | Yes | no | no | no | Yes | 2 | 2
Project 422 | L2 | Pipe | replacement | Winnepeg | Jul 31, 2025 | Dec 31, 2026 | 245 | med | low | med | low | high | 40944 | 30243 | 81023 | 197.8874 | gpmc | no | X |  | X |  | X | no | no | Yes | Yes | no | Yes | Yes | no | no | 1 | 9
Project 423 | L1 | Pipe | inspection | Saskatoon | Dec 31, 2024 | Oct 31, 2025 | 63 | high | low | med | low | med | 417868 | 170162 | 54084 | 12.9428 | gpmc | no |  |  |  | X | X | Yes | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 6 | 4
Project 424 | L2 | Facility |  | Calgary | Oct 31, 2025 | Oct 31, 2027 | 332 | med | low | low | med | low | 736499 | 1255797 | 425557 | 57.7811 | gpmc | no |  | X | X | X |  | no | no | Yes | Yes | no | Yes | no | Yes | no | 2 | 4
Project 425 | L1 | Pipe | repair | Quebec City | Dec 31, 2024 | Oct 31, 2025 | 25 | high | high | med | low | low | 1681006 | 744255 | 180989 | 10.7667 | r/o | Yes |  |  | X |  | X | no | Yes | Yes | no | no | no | no | no | no | 6 | 2
Project 426 | L3 | Facility | replacement | Toronto | Mar 31, 2025 | Dec 31, 2026 | 254 | high | high | med | low | med | 1951207 | 1035651 | 1223668 | 62.7134 | gpmc | Yes | X |  |  | X | X | Yes | Yes | no | no | Yes | no | no | Yes | Yes | 7 | 2
Project 427 | L2 | Pipe | replacement | Saskatoon | Dec 31, 2024 | Oct 31, 2025 | 363 | low | high | high | high | low | 925318 | 1213123 | 167946 | 18.1501 | gpmc | no | X |  |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | no | 6 | 2
Project 428 | L2 | Facility | r/o | Saskatoon | Mar 31, 2025 | Dec 31, 2025 | 17 | low | high | low | high | med | 132661 | 163689 | 787417 | 593.5558 | r/o | Yes | X | X | X |  |  | Yes | Yes | no | no | Yes | Yes | Yes | no | no | 6 | 1
Project 429 | L3 | Pipe | excavation | Regina | Mar 31, 2025 | Jul 31, 2027 | 113 | low | low | high | high | high | 909953 | 573653 | 1989330 | 218.619 | r/o | Yes | X |  | X |  | X | no | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 6
Project 430 | L1 | Pipe | replacement | Quebec City | Oct 31, 2025 | Oct 31, 2027 | 307 | low | high | med | high | med | 1510279 | 2439703 | 1834392 | 121.4605 | capital | Yes |  | X | X |  | X | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 7 | 9
Project 431 | L3 | Pipe | repair | Winnepeg | Dec 31, 2024 | Oct 31, 2025 | 63 | med | low | low | high | high | 1267551 | 825116 | 1484470 | 117.1132 | gpmc | Yes | X |  |  |  |  | Yes | no | no | Yes | no | no | no | Yes | Yes | 7 | 9
Project 432 | L1 | Pipe | repair | Saskatoon | Jul 31, 2025 | Jul 31, 2025 | 25 | low | high | med | high | med | 867561 | 712258 | 1890803 | 217.9447 | capital | no | X |  | X | X |  | Yes | no | no | no | no | Yes | Yes | no | no | 5 | 3
Project 433 | L1 | Pipe | repair | Montreal | Dec 31, 2024 | Dec 31, 2027 | 320 | low | med | med | low | med | 783351 | 1280273 | 1757254 | 224.3252 | gpmc | Yes | X |  |  |  |  | Yes | no | Yes | Yes | no | no | Yes | Yes | no | 9 | 1
Project 434 | L3 | Facility | replacement | Winnepeg | Oct 31, 2025 | Dec 31, 2026 | 240 | med | high | low | low | med | 1161861 | 1694264 | 61620 | 5.3036 | gpmc | Yes |  |  | X |  | X | no | Yes | no | Yes | Yes | no | no | Yes | no | 9 | 2
Project 435 | L3 | Pipe | excavation | Winnepeg | Dec 31, 2024 | Dec 31, 2025 | 93 | high | low | high | low | high | 1575182 | 1175537 | 301760 | 19.1572 | r/o | no |  | X |  | X | X | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 4 | 1
Project 436 | L2 | Facility | r/o | Regina | Oct 31, 2025 | Dec 31, 2025 | 286 | high | low | med | high | low | 1096599 | 931390 | 1787706 | 163.0228 | r/o | no |  |  | X | X | X | no | no | no | no | no | Yes | no | Yes | no | 4 | 6
Project 437 | L3 | Facility | r/o | Quebec City | Oct 31, 2025 | Dec 31, 2026 | 53 | high | low | low | low | high | 691948 | 360245 | 1118204 | 161.6023 | capital | no | X |  | X |  |  | Yes | no | no | no | no | no | no | no | no | 7 | 8
Project 438 | L2 | Pipe | replacement | Winnepeg | Mar 31, 2025 | Jul 31, 2027 | 234 | high | high | med | low | low | 1466480 | 1312611 | 720242 | 49.1137 | gpmc | Yes |  | X |  | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 3 | 7
Project 439 | L3 | Pipe |  | North Bay | Oct 31, 2025 | Oct 31, 2025 | 175 | high | med | low | high | low | 1552123 | 930107 | 494889 | 31.8847 | gpmc | Yes |  | X | X |  | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 1 | 5
Project 440 | L3 | Facility | repair | Quebec City | Dec 31, 2025 | Dec 31, 2027 | 54 | low | med | low | med | med | 143198 | 102624 | 136843 | 95.5621 | capital | no | X | X | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 4 | 9
Project 441 | L2 | Pipe | repair | Saskatoon | Mar 31, 2025 | Oct 31, 2027 | 304 | low | low | low | low | low | 34057 | 57353 | 764879 | 2245.879 | capital | Yes |  | X |  |  |  | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 9 | 4
Project 442 | L1 | Pipe | r/o | Winnepeg | Mar 31, 2025 | Oct 31, 2026 | 257 | low | high | high | low | low | 806284 | 477631 | 1626417 | 201.7176 | capital | no |  | X | X |  |  | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 8 | 8
Project 443 | L2 | Facility | excavation | North Bay | Jul 31, 2025 | Jul 31, 2027 | 364 | high | med | high | low | low | 710020 | 707975 | 1749606 | 246.4164 | gpmc | no | X | X | X | X |  | no | Yes | no | no | no | Yes | Yes | Yes | Yes | 1 | 8
Project 444 | L1 | Pipe | r/o | Montreal | Jul 31, 2025 | Jul 31, 2027 | 295 | med | med | high | high | med | 1779645 | 1986708 | 121549 | 6.83 | r/o | no |  |  | X |  |  | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 9 | 2
Project 445 | L2 | Pipe | replacement | North Bay | Dec 31, 2024 | Dec 31, 2026 | 271 | low | med | low | high | med | 1934510 | 2536080 | 785687 | 40.6143 | capital | Yes |  |  |  | X |  | Yes | no | no | Yes | Yes | Yes | Yes | no | no | 6 | 3
Project 446 | L1 | Pipe |  | Montreal | Dec 31, 2025 | Dec 31, 2026 | 98 | low | high | med | high | high | 49969 | 69383 | 1356845 | 2715.3735 | r/o | Yes | [5 empty] | Yes | Yes | no | no | no | Yes | no | Yes | no | 1 | 8
Project 447 | L3 | Facility | repair | Ottawa | Dec 31, 2025 | Jul 31, 2027 | 194 | med | med | high | low | high | 480729 | 704084 | 1403287 | 291.9081 | r/o | Yes | X | X |  |  |  | Yes | no | Yes | no | Yes | no | Yes | no | Yes | 4 | 3
Project 448 | L2 | Facility | inspection | Quebec City | Mar 31, 2025 | Oct 31, 2025 | 206 | low | med | high | high | med | 1215989 | 1747494 | 1096092 | 90.14 | r/o | no | X | X | X | X | X | Yes | no | Yes | no | Yes | Yes | Yes | no | no | 6 | 4
Project 449 | L1 | Facility | repair | Edmonton | Mar 31, 2025 | Dec 31, 2026 | 20 | high | low | low | high | high | 255692 | 153215 | 806712 | 315.5015 | gpmc | Yes |  | X | X | X |  | Yes | Yes | Yes | Yes | Yes | Yes | no | no | no | 6 | 5
Project 450 | L1 | Facility | r/o | Edmonton | Dec 31, 2024 | Jul 31, 2027 | 336 | low | med | low | high | low | 769287 | 1282760 | 406438 | 52.8331 | capital | Yes |  |  | X |  | X | no | no | Yes | Yes | no | no | no | Yes | Yes | 1 | 6
Project 451 | L3 | Facility | inspection | Calgary | Dec 31, 2025 | Jul 31, 2026 | 135 | high | med | high | high | low | 27136 | 8986 | 1303186 | 4802.4248 | capital | Yes | X |  |  |  |  | no | no | no | no | Yes | Yes | no | Yes | Yes | 9 | 6
Project 452 | L1 | Facility | replacement | Regina | Dec 31, 2024 | Jul 31, 2027 | 93 | low | med | high | low | high | 1379403 | 1797392 | 524127 | 37.9967 | gpmc | Yes | X |  | X | X | X | no | Yes | Yes | Yes | no | no | Yes | no | Yes | 7 | 2
Project 453 | L2 | Facility | excavation | Montreal | Oct 31, 2025 | Jul 31, 2027 | 55 | low | high | high | high | med | 576741 | 274133 | 908431 | 157.5111 | r/o | Yes |  | X |  |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | no | 8 | 1
Project 454 | L2 | Facility | excavation | Regina | Dec 31, 2025 | Dec 31, 2025 | 322 | med | low | med | low | high | 422966 | 513868 | 1687231 | 398.9046 | capital | no |  | X | X |  |  | Yes | no | Yes | no | Yes | no | no | no | no | 5 | 9
Project 455 | L3 | Facility | r/o | Quebec City | Jul 31, 2025 | Dec 31, 2027 | 126 | high | med | low | med | high | 1006254 | 1703538 | 901494 | 89.5891 | r/o | no | X |  |  | X |  | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 3 | 8
Project 456 | L3 | Facility | inspection | Montreal | Oct 31, 2025 | Jul 31, 2025 | 67 | low | high | med | med | med | 149066 | 245801 | 818766 | 549.2641 | gpmc | no | [5 empty] | no | no | no | Yes | Yes | no | no | no | Yes | 4 | 8
Project 457 | L1 | Facility | r/o | Toronto | Mar 31, 2025 | Dec 31, 2026 | 169 | high | low | high | med | high | 1213026 | 449138 | 1093970 | 90.1852 | r/o | Yes |  | X |  |  | X | no | Yes | no | Yes | no | no | no | no | Yes | 9 | 2
Project 458 | L1 | Facility |  | Quebec City | Dec 31, 2024 | Dec 31, 2026 | 337 | med | med | high | low | med | 1575468 | 2167488 | 1741730 | 110.5532 | gpmc | no |  |  | X | X | X | Yes | Yes | no | Yes | no | no | no | no | no | 9 | 6
Project 459 | L3 | Facility | inspection | Winnepeg | Dec 31, 2024 | Jul 31, 2027 | 84 | med | med | med | low | med | 504029 | 684607 | 1528968 | 303.3492 | gpmc | no |  |  | X |  |  | Yes | no | Yes | no | Yes | Yes | Yes | no | Yes | 9 | 4
Project 460 | L1 | Facility | inspection | North Bay | Dec 31, 2024 | Oct 31, 2025 | 199 | low | low | med | med | low | 1434128 | 893184 | 1765444 | 123.1023 | capital | Yes | X |  |  |  | X | Yes | no | no | no | Yes | Yes | Yes | no | Yes | 2 | 1
Project 461 | L1 | Facility | r/o | Edmonton | Dec 31, 2024 | Jul 31, 2027 | 248 | low | high | low | low | low | 587516 | 566413 | 800084 | 136.1808 | r/o | no |  |  | X |  |  | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 1 | 9
Project 462 | L3 | Facility | r/o | Ottawa | Mar 31, 2025 | Oct 31, 2025 | 313 | high | med | med | high | high | 1887560 | 1894521 | 351604 | 18.6274 | r/o | no | X | X |  |  |  | no | Yes | no | Yes | no | Yes | Yes | no | Yes | 9 | 9
Project 463 | L2 | Pipe | inspection | Calgary | Mar 31, 2025 | Jul 31, 2027 | 20 | high | low | low | low | high | 1285784 | 1976191 | 827236 | 64.3371 | capital | Yes |  | X |  |  |  | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 2 | 3
Project 464 | L2 | Facility | repair | Ottawa | Mar 31, 2025 | Dec 31, 2026 | 242 | low | high | med | med | low | 1773553 | 954959 | 1691935 | 95.3981 | gpmc | Yes | X |  |  | X | X | Yes | Yes | Yes | Yes | Yes | no | no | Yes | Yes | 3 | 5
Project 465 | L3 | Facility |  | Saskatoon | Mar 31, 2025 | Jul 31, 2026 | 53 | med | high | low | low | high | 880548 | 1159044 | 1547191 | 175.7077 | capital | no | X | X | X | X |  | no | no | no | Yes | Yes | no | no | no | Yes | 4 | 5
Project 466 | L2 | Facility | repair | Edmonton | Jul 31, 2025 | Jul 31, 2027 | 354 | high | high | low | low | low | 1885804 | 2202170 | 865033 | 45.8708 | capital | Yes | X |  | X | X |  | no | no | no | no | Yes | no | Yes | Yes | no | 7 | 1
Project 467 | L3 | Facility |  | North Bay | Oct 31, 2025 | Jul 31, 2027 | 108 | high | med | high | high | high | 1929248 | 3103630 | 596113 | 30.8987 | gpmc | no | X | X |  | X | X | no | no | no | Yes | Yes | Yes | no | no | Yes | 8 | 4
Project 468 | L3 | Facility | replacement | Montreal | Dec 31, 2025 | Dec 31, 2026 | 126 | high | high | high | low | high | 689067 | 1078153 | 1342777 | 194.8689 | r/o | Yes | X | X | X | X | X | Yes | no | no | Yes | no | no | Yes | Yes | no | 7 | 2
Project 469 | L1 | Pipe | r/o | North Bay | Mar 31, 2025 | Dec 31, 2026 | 247 | low | med | med | high | low | 1695782 | 1480521 | 162635 | 9.5906 | r/o | no | X | X |  | X |  | Yes | Yes | no | no | no | no | Yes | Yes | no | 1 | 5
Project 470 | L3 | Pipe | repair | Ottawa | Dec 31, 2024 | Jul 31, 2027 | 194 | low | high | med | high | high | 320863 | 312591 | 118861 | 37.0442 | capital | Yes | X |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | no | 6 | 9
Project 471 | L2 | Facility | replacement | Ottawa | Dec 31, 2025 | Oct 31, 2025 | 215 | high | low | med | med | low | 1756430 | 2275239 | 1777437 | 101.196 | gpmc | Yes |  |  |  | X | X | no | Yes | no | Yes | Yes | no | Yes | no | no | 6 | 8
Project 472 | L2 | Facility |  | Calgary | Dec 31, 2025 | Oct 31, 2025 | 166 | med | high | low | med | high | 49743 | 18860 | 1597023 | 3210.5482 | r/o | no | X | X |  | X | X | no | Yes | Yes | no | no | Yes | no | Yes | Yes | 4 | 1
Project 473 | L1 | Facility | r/o | Winnepeg | Mar 31, 2025 | Dec 31, 2027 | 89 | low | med | med | low | low | 1027419 | 1227658 | 481042 | 46.8204 | capital | no |  |  |  |  | X | no | no | no | no | no | no | Yes | no | Yes | 9 | 5
Project 474 | L3 | Facility | r/o | Winnepeg | Jul 31, 2025 | Dec 31, 2026 | 231 | low | med | low | high | high | 1704376 | 2612609 | 1205762 | 70.7451 | capital | no |  | X | X |  | X | no | no | no | no | Yes | Yes | Yes | Yes | Yes | 5 | 5
Project 475 | L2 | Pipe | inspection | Winnepeg | Dec 31, 2024 | Oct 31, 2027 | 179 | high | low | low | med | low | 1488233 | 1190000 | 1736935 | 116.7112 | r/o | no |  |  |  | X |  | no | no | Yes | no | no | no | no | no | no | 1 | 3
Project 476 | L2 | Facility | r/o | Winnepeg | Jul 31, 2025 | Oct 31, 2026 | 134 | med | med | high | med | low | 716484 | 935771 | 75743 | 10.5715 | r/o | Yes |  | X |  |  |  | no | Yes | Yes | no | no | Yes | Yes | no | Yes | 5 | 7
Project 477 | L2 | Facility | excavation | Edmonton | Jul 31, 2025 | Dec 31, 2026 | 271 | med | med | low | med | high | 1293920 | 802956 | 1847438 | 142.7784 | r/o | no | X |  |  |  | X | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 8 | 3
Project 478 | L2 | Facility | excavation | Calgary | Dec 31, 2024 | Dec 31, 2025 | 70 | high | med | low | high | high | 1655311 | 2304440 | 618078 | 37.3391 | gpmc | no | X |  | X | X |  | no | Yes | no | Yes | Yes | Yes | no | Yes | no | 2 | 2
Project 479 | L3 | Pipe | r/o | Saskatoon | Oct 31, 2025 | Oct 31, 2026 | 226 | low | high | high | med | high | 1721557 | 2108093 | 681529 | 39.5879 | r/o | no | X |  |  |  | X | Yes | no | no | no | no | no | Yes | Yes | no | 9 | 4
Project 480 | L2 | Pipe |  | Saskatoon | Mar 31, 2025 | Dec 31, 2025 | 309 | high | high | med | low | high | 1912826 | 1523325 | 273944 | 14.3214 | capital | no |  |  | X | X | X | no | no | Yes | Yes | Yes | no | no | no | no | 6 | 3
Project 481 | L2 | Facility | excavation | Winnepeg | Oct 31, 2025 | Oct 31, 2026 | 296 | low | low | high | med | med | 337912 | 471035 | 809042 | 239.4239 | capital | no |  | X | X |  |  | no | no | no | Yes | Yes | no | Yes | Yes | no | 2 | 5
Project 482 | L2 | Facility | repair | North Bay | Dec 31, 2025 | Dec 31, 2025 | 227 | high | high | med | low | low | 1655807 | 2589864 | 927752 | 56.0302 | capital | Yes |  |  | X | X | X | no | Yes | no | no | no | Yes | Yes | no | Yes | 9 | 1
Project 483 | L3 | Pipe | excavation | Saskatoon | Dec 31, 2025 | Oct 31, 2026 | 70 | med | med | low | med | high | 725137 | 1210793 | 1873774 | 258.4028 | capital | Yes |  | X |  |  | X | no | no | Yes | no | no | Yes | no | Yes | Yes | 8 | 6
Project 484 | L2 | Facility | replacement | Winnepeg | Dec 31, 2024 | Dec 31, 2026 | 88 | high | high | low | med | med | 745400 | 606354 | 1685960 | 226.1819 | gpmc | Yes |  |  |  | X |  | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 1 | 1
Project 485 | L2 | Pipe |  | Montreal | Mar 31, 2025 | Oct 31, 2026 | 332 | high | high | low | low | high | 1434756 | 584763 | 1615324 | 112.5853 | r/o | no | X |  |  |  |  | Yes | no | no | Yes | Yes | Yes | Yes | Yes | no | 4 | 4
Project 486 | L3 | Facility | replacement | Toronto | Mar 31, 2025 | Dec 31, 2026 | 14 | high | low | low | low | med | 515948 | 667662 | 546085 | 105.8411 | gpmc | no | X | X |  | X | X | no | no | Yes | no | no | no | no | no | Yes | 7 | 2
Project 487 | L3 | Pipe | replacement | Winnepeg | Dec 31, 2025 | Dec 31, 2026 | 131 | med | low | med | low | low | 17230 | 10570 | 235387 | 1366.1463 | r/o | Yes |  |  |  | X | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 8 | 3
Project 488 | L1 | Pipe | replacement | North Bay | Dec 31, 2024 | Oct 31, 2027 | 344 | med | high | high | low | low | 666104 | 270264 | 166544 | 25.0027 | gpmc | no |  | X | X | X | X | Yes | no | Yes | Yes | no | no | Yes | Yes | no | 5 | 5
Project 489 | L3 | Pipe |  | Ottawa | Dec 31, 2025 | Jul 31, 2025 | 362 | med | med | low | high | high | 348625 | 254640 | 985827 | 282.7758 | r/o | Yes |  |  |  |  | X | no | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 2 | 3
Project 490 | L3 | Facility | r/o | North Bay | Mar 31, 2025 | Jul 31, 2027 | 350 | low | med | med | high | low | 458790 | 189823 | 995557 | 216.9962 | gpmc | Yes | X | X |  | X |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | no | 9 | 8
Project 491 | L1 | Pipe | r/o | North Bay | Mar 31, 2025 | Jul 31, 2025 | 81 | low | med | low | low | low | 1482295 | 2475058 | 426147 | 28.7491 | capital | Yes |  |  |  | X | X | no | Yes | Yes | no | no | no | Yes | Yes | no | 8 | 9
Project 492 | L1 | Pipe |  | Edmonton | Dec 31, 2025 | Jul 31, 2025 | 288 | low | high | low | med | high | 390951 | 384344 | 978645 | 250.3242 | capital | no | X |  |  |  |  | Yes | Yes | no | no | Yes | no | Yes | no | no | 3 | 1
Project 493 | L1 | Pipe | inspection | Winnepeg | Mar 31, 2025 | Jul 31, 2027 | 181 | high | high | high | med | low | 1129224 | 1038202 | 1457121 | 129.0374 | gpmc | Yes | X |  |  | X | X | no | no | Yes | Yes | Yes | no | Yes | Yes | no | 1 | 2
Project 494 | L2 | Pipe | r/o | Edmonton | Jul 31, 2025 | Jul 31, 2026 | 328 | med | med | high | med | low | 1349639 | 1560329 | 1850973 | 137.1458 | capital | no |  |  |  |  | X | no | Yes | no | Yes | Yes | no | no | no | Yes | 4 | 5
Project 495 | L1 | Pipe | replacement | Regina | Oct 31, 2025 | Jul 31, 2026 | 208 | low | med | low | med | high | 716448 | 457795 | 1706776 | 238.2275 | r/o | Yes |  | X |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 7 | 3
Project 496 | L1 | Facility |  | Winnepeg | Mar 31, 2025 | Jul 31, 2027 | 309 | low | high | low | low | high | 1242303 | 1439098 | 1370713 | 110.3364 | r/o | Yes | X | X | X |  | X | Yes | Yes | no | no | no | no | no | no | Yes | 9 | 5
Project 497 | L3 | Facility | repair | Calgary | Oct 31, 2025 | Jul 31, 2027 | 168 | low | high | med | high | high | 80709 | 138490 | 498231 | 617.3178 | capital | Yes |  |  |  |  | X | no | no | no | Yes | no | no | no | no | Yes | 5 | 4
Project 498 | L1 | Facility | repair | Montreal | Jul 31, 2025 | Jul 31, 2025 | 74 | med | low | med | high | med | 253293 | 132130 | 1852298 | 731.2867 | r/o | Yes | X |  |  | X | X | no | no | Yes | Yes | Yes | no | Yes | Yes | no | 6 | 9

## Project Names (hidden)
499
500 | Project | Project 500
501 | Project | Project 501
502 | Project | Project 502
503 | Project | Project 503
504 | Project | Project 504
505 | Project | Project 505
506 | Project | Project 506
507 | Project | Project 507
508 | Project | Project 508
509 | Project | Project 509
510 | Project | Project 510
511 | Project | Project 511
512 | Project | Project 512
513 | Project | Project 513
514 | Project | Project 514
515 | Project | Project 515
516 | Project | Project 516
517 | Project | Project 517
518 | Project | Project 518
519 | Project | Project 519
520 | Project | Project 520
521 | Project | Project 521
522 | Project | Project 522
523 | Project | Project 523
524 | Project | Project 524
525 | Project | Project 525
526 | Project | Project 526
527 | Project | Project 527
528 | Project | Project 528
529 | Project | Project 529
530 | Project | Project 530
531 | Project | Project 531
532 | Project | Project 532
533 | Project | Project 533
534 | Project | Project 534
535 | Project | Project 535
536 | Project | Project 536
537 | Project | Project 537
538 | Project | Project 538
539 | Project | Project 539
540 | Project | Project 540
541 | Project | Project 541
542 | Project | Project 542
543 | Project | Project 543
544 | Project | Project 544
545 | Project | Project 545
546 | Project | Project 546
547 | Project | Project 547
548 | Project | Project 548
549 | Project | Project 549
550 | Project | Project 550
551 | Project | Project 551
552 | Project | Project 552
553 | Project | Project 553
554 | Project | Project 554
555 | Project | Project 555
556 | Project | Project 556
557 | Project | Project 557
558 | Project | Project 558
559 | Project | Project 559
560 | Project | Project 560
561 | Project | Project 561
562 | Project | Project 562
563 | Project | Project 563
564 | Project | Project 564
565 | Project | Project 565
566 | Project | Project 566
567 | Project | Project 567
568 | Project | Project 568
569 | Project | Project 569
570 | Project | Project 570
571 | Project | Project 571
572 | Project | Project 572
573 | Project | Project 573
574 | Project | Project 574
575 | Project | Project 575
576 | Project | Project 576
577 | Project | Project 577
578 | Project | Project 578
579 | Project | Project 579
580 | Project | Project 580
581 | Project | Project 581
582 | Project | Project 582
583 | Project | Project 583
584 | Project | Project 584
585 | Project | Project 585
586 | Project | Project 586
587 | Project | Project 587
588 | Project | Project 588
589 | Project | Project 589
590 | Project | Project 590
591 | Project | Project 591
592 | Project | Project 592
593 | Project | Project 593
594 | Project | Project 594
595 | Project | Project 595
596 | Project | Project 596
597 | Project | Project 597
598 | Project | Project 598
599 | Project | Project 599
600 | Project | Project 600
601 | Project | Project 601
602 | Project | Project 602
603 | Project | Project 603
604 | Project | Project 604
605 | Project | Project 605
606 | Project | Project 606
607 | Project | Project 607
608 | Project | Project 608
609 | Project | Project 609
610 | Project | Project 610
611 | Project | Project 611
612 | Project | Project 612
613 | Project | Project 613
614 | Project | Project 614
615 | Project | Project 615
616 | Project | Project 616
617 | Project | Project 617
618 | Project | Project 618
619 | Project | Project 619
620 | Project | Project 620
621 | Project | Project 621
622 | Project | Project 622
623 | Project | Project 623
624 | Project | Project 624
625 | Project | Project 625
626 | Project | Project 626
627 | Project | Project 627
628 | Project | Project 628
629 | Project | Project 629
630 | Project | Project 630
631 | Project | Project 631
632 | Project | Project 632
633 | Project | Project 633
634 | Project | Project 634
635 | Project | Project 635
636 | Project | Project 636
637 | Project | Project 637
638 | Project | Project 638
639 | Project | Project 639
640 | Project | Project 640
641 | Project | Project 641
642 | Project | Project 642
643 | Project | Project 643
644 | Project | Project 644
645 | Project | Project 645
646 | Project | Project 646
647 | Project | Project 647
648 | Project | Project 648
649 | Project | Project 649
650 | Project | Project 650
651 | Project | Project 651
652 | Project | Project 652
653 | Project | Project 653
654 | Project | Project 654
655 | Project | Project 655
656 | Project | Project 656
657 | Project | Project 657
658 | Project | Project 658
659 | Project | Project 659
660 | Project | Project 660
661 | Project | Project 661
662 | Project | Project 662
663 | Project | Project 663
664 | Project | Project 664
665 | Project | Project 665
666 | Project | Project 666
667 | Project | Project 667
668 | Project | Project 668
669 | Project | Project 669
670 | Project | Project 670
671 | Project | Project 671
672 | Project | Project 672
673 | Project | Project 673
674 | Project | Project 674
675 | Project | Project 675
676 | Project | Project 676
677 | Project | Project 677
678 | Project | Project 678
679 | Project | Project 679
680 | Project | Project 680
681 | Project | Project 681
682 | Project | Project 682
683 | Project | Project 683
684 | Project | Project 684
685 | Project | Project 685
686 | Project | Project 686
687 | Project | Project 687
688 | Project | Project 688
689 | Project | Project 689
690 | Project | Project 690
691 | Project | Project 691
692 | Project | Project 692
693 | Project | Project 693
694 | Project | Project 694
695 | Project | Project 695
696 | Project | Project 696
697 | Project | Project 697
698 | Project | Project 698
699 | Project | Project 699
700 | Project | Project 700
701 | Project | Project 701
702 | Project | Project 702
703 | Project | Project 703
704 | Project | Project 704
705 | Project | Project 705
706 | Project | Project 706
707 | Project | Project 707
708 | Project | Project 708
709 | Project | Project 709
710 | Project | Project 710
711 | Project | Project 711
712 | Project | Project 712
713 | Project | Project 713
714 | Project | Project 714
715 | Project | Project 715
716 | Project | Project 716
717 | Project | Project 717
718 | Project | Project 718
719 | Project | Project 719
720 | Project | Project 720
721 | Project | Project 721
722 | Project | Project 722
723 | Project | Project 723
724 | Project | Project 724
725 | Project | Project 725
726 | Project | Project 726
727 | Project | Project 727
728 | Project | Project 728
729 | Project | Project 729
730 | Project | Project 730
731 | Project | Project 731
732 | Project | Project 732
733 | Project | Project 733
734 | Project | Project 734
735 | Project | Project 735
736 | Project | Project 736
737 | Project | Project 737
738 | Project | Project 738
739 | Project | Project 739
740 | Project | Project 740
741 | Project | Project 741
742 | Project | Project 742
743 | Project | Project 743
744 | Project | Project 744
745 | Project | Project 745
746 | Project | Project 746
747 | Project | Project 747
748 | Project | Project 748
749 | Project | Project 749
750 | Project | Project 750
751 | Project | Project 751
752 | Project | Project 752
753 | Project | Project 753
754 | Project | Project 754
755 | Project | Project 755
756 | Project | Project 756
757 | Project | Project 757
758 | Project | Project 758
759 | Project | Project 759
760 | Project | Project 760
761 | Project | Project 761
762 | Project | Project 762
763 | Project | Project 763
764 | Project | Project 764
765 | Project | Project 765
766 | Project | Project 766
767 | Project | Project 767
768 | Project | Project 768
769 | Project | Project 769
770 | Project | Project 770
771 | Project | Project 771
772 | Project | Project 772
773 | Project | Project 773
774 | Project | Project 774
775 | Project | Project 775
776 | Project | Project 776
777 | Project | Project 777
778 | Project | Project 778
779 | Project | Project 779
780 | Project | Project 780
781 | Project | Project 781
782 | Project | Project 782
783 | Project | Project 783
784 | Project | Project 784
785 | Project | Project 785
786 | Project | Project 786
787 | Project | Project 787
788 | Project | Project 788
789 | Project | Project 789
790 | Project | Project 790
791 | Project | Project 791
792 | Project | Project 792
793 | Project | Project 793
794 | Project | Project 794
795 | Project | Project 795
796 | Project | Project 796
797 | Project | Project 797
798 | Project | Project 798
799 | Project | Project 799
800 | Project | Project 800
801 | Project | Project 801
802 | Project | Project 802
803 | Project | Project 803
804 | Project | Project 804
805 | Project | Project 805
806 | Project | Project 806
807 | Project | Project 807
808 | Project | Project 808
809 | Project | Project 809
810 | Project | Project 810
811 | Project | Project 811
812 | Project | Project 812
813 | Project | Project 813
814 | Project | Project 814
815 | Project | Project 815
816 | Project | Project 816
817 | Project | Project 817
818 | Project | Project 818
819 | Project | Project 819
820 | Project | Project 820
821 | Project | Project 821
822 | Project | Project 822
823 | Project | Project 823
824 | Project | Project 824
825 | Project | Project 825
826 | Project | Project 826
827 | Project | Project 827
828 | Project | Project 828
829 | Project | Project 829
830 | Project | Project 830
831 | Project | Project 831
832 | Project | Project 832
833 | Project | Project 833
834 | Project | Project 834
835 | Project | Project 835
836 | Project | Project 836
837 | Project | Project 837
838 | Project | Project 838
839 | Project | Project 839
840 | Project | Project 840
841 | Project | Project 841
842 | Project | Project 842
843 | Project | Project 843
844 | Project | Project 844
845 | Project | Project 845
846 | Project | Project 846
847 | Project | Project 847
848 | Project | Project 848
849 | Project | Project 849
850 | Project | Project 850
851 | Project | Project 851
852 | Project | Project 852
853 | Project | Project 853
854 | Project | Project 854
855 | Project | Project 855
856 | Project | Project 856
857 | Project | Project 857
858 | Project | Project 858
859 | Project | Project 859
860 | Project | Project 860
861 | Project | Project 861
862 | Project | Project 862
863 | Project | Project 863
864 | Project | Project 864
865 | Project | Project 865
866 | Project | Project 866
867 | Project | Project 867
868 | Project | Project 868
869 | Project | Project 869
870 | Project | Project 870
871 | Project | Project 871
872 | Project | Project 872
873 | Project | Project 873
874 | Project | Project 874
875 | Project | Project 875
876 | Project | Project 876
877 | Project | Project 877
878 | Project | Project 878
879 | Project | Project 879
880 | Project | Project 880
881 | Project | Project 881
882 | Project | Project 882
883 | Project | Project 883
884 | Project | Project 884
885 | Project | Project 885
886 | Project | Project 886
887 | Project | Project 887
888 | Project | Project 888
889 | Project | Project 889
890 | Project | Project 890
891 | Project | Project 891
892 | Project | Project 892
893 | Project | Project 893
894 | Project | Project 894
895 | Project | Project 895
896 | Project | Project 896
897 | Project | Project 897
898 | Project | Project 898
899 | Project | Project 899
900 | Project | Project 900
901 | Project | Project 901
902 | Project | Project 902
903 | Project | Project 903
904 | Project | Project 904
905 | Project | Project 905
906 | Project | Project 906
907 | Project | Project 907
908 | Project | Project 908
909 | Project | Project 909
910 | Project | Project 910
911 | Project | Project 911
912 | Project | Project 912
913 | Project | Project 913
914 | Project | Project 914
915 | Project | Project 915
916 | Project | Project 916
917 | Project | Project 917
918 | Project | Project 918
919 | Project | Project 919
920 | Project | Project 920
921 | Project | Project 921
922 | Project | Project 922
923 | Project | Project 923
924 | Project | Project 924
925 | Project | Project 925
926 | Project | Project 926
927 | Project | Project 927
928 | Project | Project 928
929 | Project | Project 929
930 | Project | Project 930
931 | Project | Project 931
932 | Project | Project 932
933 | Project | Project 933
934 | Project | Project 934
935 | Project | Project 935
936 | Project | Project 936
937 | Project | Project 937
938 | Project | Project 938
939 | Project | Project 939
940 | Project | Project 940
941 | Project | Project 941
942 | Project | Project 942
943 | Project | Project 943
944 | Project | Project 944
945 | Project | Project 945
946 | Project | Project 946
947 | Project | Project 947
948 | Project | Project 948
949 | Project | Project 949
950 | Project | Project 950
951 | Project | Project 951
952 | Project | Project 952
953 | Project | Project 953
954 | Project | Project 954
955 | Project | Project 955
956 | Project | Project 956
957 | Project | Project 957
958 | Project | Project 958
959 | Project | Project 959
960 | Project | Project 960
961 | Project | Project 961
962 | Project | Project 962
963 | Project | Project 963
964 | Project | Project 964
965 | Project | Project 965
966 | Project | Project 966
967 | Project | Project 967
968 | Project | Project 968
969 | Project | Project 969
970 | Project | Project 970
971 | Project | Project 971
972 | Project | Project 972
973 | Project | Project 973
974 | Project | Project 974
975 | Project | Project 975
976 | Project | Project 976
977 | Project | Project 977
978 | Project | Project 978
979 | Project | Project 979
980 | Project | Project 980
981 | Project | Project 981
982 | Project | Project 982
983 | Project | Project 983
984 | Project | Project 984
985 | Project | Project 985
986 | Project | Project 986
987 | Project | Project 987
988 | Project | Project 988
989 | Project | Project 989
990 | Project | Project 990
991 | Project | Project 991
992 | Project | Project 992
993 | Project | Project 993
994 | Project | Project 994
995 | Project | Project 995
996 | Project | Project 996

## example trials
ProjectReadinessScope | ProjectEngDesign | ProjectFunding | ProjectPermits | ProjectStkholdrEngagmnt | ProjectProcurementScm | ProjectResourceMgmt | ProjectOutageMgmt | ProjectExeqtnSched | ProjectReadinessPerct | ProjectReadinessRank | PriorityScopeClarity | PriorityImpact Assessmt | PrioritySafetyReqmt | PriorityCommCapacityReliabiilty | PriorityOutageImpacts | REGULATORY COMPLIANCE | PriorityRank (RISK) | PriorityReadinessPerct | Methodology for ranking
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | #NAME? | 5 | 3 | 5 | 3 | 4 | 4 | 80% | #NAME? | 1-20% | 1
3 | 5 | 2 | 2 | 5 | 5 | 5 | 5 | 1 | 73.33% | #NAME? | 2 | 1 | 5 | 1 | 2 | 5 | 53.33% | #NAME? | 21-29% | 2
5 | 1 | 1 | 4 | 2 | 5 | 1 | 5 | 4 | 62.22% | #NAME? | 4 | 4 | 1 | 3 | 3 | 5 | 66.67% | #NAME? | 30-39% | 3
3 | 1 | 4 | 3 | 1 | 4 | 1 | 5 | 4 | 57.78% | #NAME? | 1 | 3 | 1 | 4 | 4 | 1 | 46.67% | #NAME? | 40-49% | 4
4 | 5 | 2 | 3 | 1 | 4 | 5 | 5 | 3 | 71.11% | #NAME? | 5 | 5 | 1 | 5 | 1 | 3 | 66.67% | #NAME? | 50-59% | 5
5 | 5 | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 77.78% | #NAME? | 3 | 1 | 1 | 1 | 1 | 2 | 30% | #NAME? | 60-69% | 6
2 | 3 | 2 | 1 | 3 | 1 | 5 | 1 | 3 | 46.67% | #NAME? | 4 | 5 | 1 | 4 | 2 | 4 | 66.67% | #NAME? | 70-79% | 7
5 | 5 | 1 | 3 | 3 | 1 | 4 | 4 | 1 | 60% | #NAME? | 1 | 4 | 1 | 4 | 1 | 4 | 50% | #NAME? | 80-89% | 8
2 | 3 | 2 | 1 | 5 | 2 | 3 | 1 | 3 | 48.89% | #NAME? | 4 | 2 | 1 | 3 | 4 | 1 | 50% | #NAME? | 90-95% | 9
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | #NAME? | 5 | 2 | 1 | 5 | 4 | 1 | 60% | #NAME? | 96-100% | 10
4 | 5 | 3 | 4 | 5 | 3 | 4 | 5 | 4 | 82.22% | #NAME? | 2 | 5 | 1 | 2 | 1 | 5 | 53.33% | #NAME?
2 | 3 | 2 | 3 | 4 | 3 | 4 | 3 | 2 | 57.78% | #NAME? | 1 | 4 | 1 | 3 | 2 | 3 | 46.67% | #NAME?
1 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 35.56% | #NAME? | 3 | 4 | 1 | 1 | 3 | 5 | 56.67% | #NAME?
5 | 1 | 1 | 4 | 4 | 4 | 1 | 5 | 2 | 60% | #NAME? | 1 | 1 | 1 | 5 | 5 | 1 | 46.67% | #NAME?
1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 35.56% | #NAME? | 2 | 4 | 1 | 5 | 2 | 2 | 53.33% | #NAME?
2 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 33.33% | #NAME? | 1 | 4 | 1 | 1 | 3 | 4 | 46.67% | #NAME?
1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 26.67% | #NAME? | 1 | 1 | 1 | 1 | 1 | 3 | 26.67% | #NAME?
3 | 5 | 2 | 4 | 4 | 4 | 4 | 5 | 3 | 75.56% | #NAME? | 2 | 5 | 1 | 2 | 3 | 1 | 46.67% | #NAME?
2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 33.33% | #NAME? | 3 | 1 | 1 | 2 | 2 | 4 | 43.33% | #NAME?
4 | 2 | 2 | 3 | 2 | 1 | 5 | 5 | 2 | 57.78% | #NAME? | 5 | 5 | 1 | 5 | 2 | 5 | 76.67% | #NAME?
5 | 5 | 3 | 3 | 4 | 4 | 5 | 1 | 4 | 75.56% | #NAME? | 5 | 2 | 1 | 1 | 2 | 5 | 53.33% | #NAME?
3 | 3 | 3 | 4 | 4 | 3 | 3 | 2 | 5 | 66.67% | #NAME? | 2 | 5 | 5 | 1 | 2 | 5 | 66.67% | #NAME?
4 | 4 | 4 | 1 | 3 | 4 | 1 | 5 | 3 | 64.44% | #NAME? | 1 | 5 | 5 | 4 | 1 | 3 | 63.33% | #NAME?
2 | 3 | 2 | 2 | 4 | 3 | 2 | 1 | 1 | 44.44% | #NAME? | 5 | 4 | 5 | 4 | 4 | 5 | 90% | #NAME?
2 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 3 | 40% | #NAME? | 4 | 5 | 5 | 5 | 3 | 1 | 76.67% | #NAME?
5 | 5 | 1 | 4 | 4 | 5 | 5 | 3 | 4 | 80% | #NAME? | 5 | 3 | 5 | 3 | 2 | 4 | 73.33% | #NAME?
2 | 2 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 37.78% | #NAME? | 4 | 5 | 1 | 2 | 3 | 4 | 63.33% | #NAME?
3 | 1 | 2 | 4 | 3 | 2 | 4 | 5 | 2 | 57.78% | #NAME? | 4 | 5 | 1 | 1 | 5 | 1 | 56.67% | #NAME?
4 | 2 | 5 | 1 | 3 | 3 | 1 | 4 | 2 | 55.56% | #NAME? | 2 | 3 | 1 | 3 | 3 | 5 | 56.67% | #NAME?
3 | 4 | 3 | 2 | 1 | 3 | 3 | 4 | 5 | 62.22% | #NAME? | 5 | 3 | 1 | 5 | 2 | 3 | 63.33% | #NAME?
3 | 3 | 2 | 1 | 4 | 3 | 5 | 3 | 1 | 55.56% | #NAME? | 1 | 2 | 1 | 2 | 3 | 4 | 43.33% | #NAME?
1 | 3 | 3 | 3 | 1 | 3 | 2 | 2 | 2 | 44.44% | #NAME? | 1 | 4 | 1 | 4 | 3 | 5 | 60% | #NAME?
4 | 2 | 4 | 2 | 4 | 5 | 2 | 3 | 4 | 66.67% | #NAME? | 1 | 5 | 1 | 2 | 4 | 3 | 53.33% | #NAME?
4 | 2 | 4 | 3 | 2 | 3 | 4 | 4 | 5 | 68.89% | #NAME? | 2 | 1 | 1 | 5 | 2 | 3 | 46.67% | #NAME?
4 | 3 | 1 | 5 | 3 | 1 | 5 | 2 | 1 | 55.56% | #NAME? | 2 | 4 | 1 | 4 | 1 | 1 | 43.33% | #NAME?
1 | 2 | 3 | 2 | 1 | 1 | 4 | 1 | 4 | 42.22% | #NAME? | 1 | 1 | 1 | 4 | 3 | 3 | 43.33% | #NAME?
2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 31.11% | #NAME? | 2 | 1 | 1 | 1 | 3 | 1 | 30% | #NAME?
1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 22.22% | #NAME? | 1 | 1 | 1 | 1 | 2 | 1 | 23.33% | #NAME?
2 | 4 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 40% | #NAME? | 1 | 4 | 1 | 5 | 2 | 4 | 56.67% | #NAME?
2 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 37.78% | #NAME? | 3 | 2 | 1 | 4 | 4 | 5 | 63.33% | #NAME?
1 | 4 | 2 | 1 | 2 | 1 | 4 | 1 | 2 | 40% | #NAME? | 3 | 5 | 5 | 3 | 5 | 1 | 73.33% | #NAME?
1 | 5 | 1 | 1 | 5 | 3 | 3 | 1 | 1 | 46.67% | #NAME? | 2 | 1 | 5 | 3 | 1 | 5 | 56.67% | #NAME?
3 | 4 | 2 | 5 | 5 | 3 | 1 | 5 | 1 | 64.44% | #NAME? | 2 | 2 | 5 | 3 | 1 | 2 | 50% | #NAME?
3 | 4 | 1 | 5 | 4 | 5 | 4 | 4 | 1 | 68.89% | #NAME? | 1 | 3 | 5 | 5 | 3 | 2 | 63.33% | #NAME?
4 | 5 | 2 | 5 | 2 | 5 | 2 | 4 | 3 | 71.11% | #NAME? | 3 | 2 | 5 | 2 | 4 | 4 | 66.67% | #NAME?
5 | 5 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 60% | #NAME? | 4 | 1 | 1 | 1 | 3 | 5 | 50% | #NAME?
3 | 2 | 1 | 5 | 3 | 4 | 3 | 4 | 3 | 62.22% | #NAME? | 4 | 2 | 1 | 4 | 2 | 1 | 46.67% | #NAME?
3 | 3 | 1 | 5 | 2 | 1 | 1 | 4 | 5 | 55.56% | #NAME? | 1 | 5 | 1 | 4 | 5 | 1 | 56.67% | #NAME?
2 | 4 | 1 | 2 | 1 | 3 | 4 | 2 | 1 | 44.44% | #NAME? | 4 | 2 | 1 | 2 | 4 | 1 | 46.67% | #NAME?
5 | 4 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 44.44% | #NAME? | 1 | 1 | 1 | 5 | 4 | 2 | 46.67% | #NAME?
1 | 4 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 35.56% | #NAME? | 1 | 1 | 1 | 2 | 4 | 3 | 40% | #NAME?
3 | 1 | 2 | 3 | 5 | 2 | 1 | 2 | 1 | 44.44% | #NAME? | 5 | 3 | 1 | 2 | 4 | 4 | 63.33% | #NAME?
5 | 5 | 1 | 3 | 5 | 5 | 5 | 2 | 4 | 77.78% | #NAME? | 4 | 5 | 5 | 2 | 2 | 2 | 66.67% | #NAME?
4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 2 | 71.11% | #NAME? | 4 | 5 | 5 | 4 | 3 | 1 | 73.33% | #NAME?
5 | 2 | 1 | 4 | 4 | 4 | 4 | 3 | 1 | 62.22% | #NAME? | 5 | 2 | 5 | 2 | 5 | 4 | 76.67% | #NAME?
5 | 1 | 2 | 4 | 3 | 1 | 5 | 5 | 5 | 68.89% | #NAME? | 3 | 4 | 5 | 5 | 2 | 4 | 76.67% | #NAME?
2 | 5 | 1 | 2 | 1 | 4 | 2 | 3 | 1 | 46.67% | #NAME? | 1 | 1 | 5 | 5 | 2 | 1 | 50% | #NAME?
2 | 5 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 37.78% | #NAME? | 5 | 4 | 5 | 5 | 1 | 3 | 76.67% | #NAME?
2 | 1 | 2 | 2 | 2 | 4 | 1 | 3 | 1 | 40% | #NAME? | 1 | 5 | 5 | 2 | 5 | 3 | 70% | #NAME?
5 | 5 | 2 | 3 | 4 | 5 | 5 | 4 | 4 | 82.22% | #NAME? | 1 | 4 | 1 | 4 | 3 | 5 | 60% | #NAME?
2 | 1 | 1 | 1 | 4 | 5 | 4 | 2 | 1 | 46.67% | #NAME? | 1 | 2 | 1 | 4 | 5 | 1 | 46.67% | #NAME?
3 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 4 | 46.67% | #NAME? | 2 | 1 | 1 | 3 | 4 | 3 | 46.67% | #NAME?
2 | 4 | 3 | 1 | 3 | 4 | 1 | 2 | 5 | 55.56% | #NAME? | 3 | 2 | 1 | 1 | 1 | 3 | 36.67% | #NAME?
5 | 4 | 3 | 4 | 1 | 2 | 2 | 3 | 3 | 60% | #NAME? | 2 | 2 | 1 | 3 | 3 | 2 | 43.33% | #NAME?
2 | 3 | 2 | 1 | 5 | 1 | 1 | 1 | 5 | 46.67% | #NAME? | 1 | 5 | 1 | 4 | 2 | 2 | 50% | #NAME?
4 | 1 | 5 | 4 | 4 | 5 | 1 | 3 | 2 | 64.44% | #NAME? | 3 | 4 | 1 | 4 | 5 | 5 | 73.33% | #NAME?
5 | 1 | 3 | 3 | 5 | 3 | 3 | 2 | 4 | 64.44% | #NAME? | 1 | 3 | 1 | 5 | 2 | 1 | 43.33% | #NAME?
2 | 5 | 1 | 2 | 5 | 5 | 4 | 1 | 1 | 57.78% | #NAME? | 1 | 5 | 1 | 4 | 5 | 1 | 56.67% | #NAME?
3 | 2 | 4 | 2 | 5 | 4 | 3 | 2 | 5 | 66.67% | #NAME? | 1 | 1 | 1 | 4 | 4 | 4 | 50% | #NAME?
2 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 42.22% | #NAME? | 3 | 3 | 1 | 2 | 2 | 4 | 50% | #NAME?
3 | 5 | 4 | 2 | 2 | 1 | 5 | 3 | 5 | 66.67% | #NAME? | 5 | 3 | 1 | 2 | 5 | 2 | 60% | #NAME?
3 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 4 | 48.89% | #NAME? | 3 | 3 | 1 | 3 | 1 | 2 | 43.33% | #NAME?
4 | 4 | 3 | 4 | 1 | 2 | 4 | 1 | 1 | 53.33% | #NAME? | 2 | 3 | 1 | 3 | 1 | 3 | 43.33% | #NAME?
4 | 2 | 4 | 3 | 3 | 5 | 2 | 5 | 5 | 73.33% | #NAME? | 4 | 3 | 1 | 5 | 5 | 2 | 66.67% | #NAME?
3 | 5 | 5 | 2 | 3 | 1 | 3 | 1 | 4 | 60% | #NAME? | 3 | 5 | 1 | 2 | 2 | 5 | 60% | #NAME?
5 | 4 | 3 | 2 | 1 | 1 | 5 | 5 | 4 | 66.67% | #NAME? | 1 | 3 | 1 | 1 | 5 | 2 | 43.33% | #NAME?
1 | 5 | 1 | 2 | 5 | 3 | 5 | 2 | 3 | 60% | #NAME? | 3 | 3 | 1 | 2 | 3 | 4 | 53.33% | #NAME?
4 | 1 | 3 | 4 | 4 | 2 | 3 | 1 | 4 | 57.78% | #NAME? | 1 | 1 | 1 | 2 | 3 | 3 | 36.67% | #NAME?
2 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 5 | 44.44% | #NAME? | 2 | 1 | 1 | 5 | 4 | 4 | 56.67% | #NAME?
1 | 4 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 42.22% | #NAME? | 2 | 3 | 1 | 4 | 4 | 3 | 56.67% | #NAME?
5 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 42.22% | #NAME? | 1 | 4 | 1 | 5 | 2 | 5 | 60% | #NAME?
5 | 4 | 2 | 1 | 5 | 2 | 1 | 5 | 1 | 57.78% | #NAME? | 2 | 1 | 1 | 4 | 4 | 1 | 43.33% | #NAME?
5 | 5 | 4 | 5 | 5 | 5 | 4 | 5 | 3 | 91.11% | #NAME? | 2 | 2 | 1 | 1 | 2 | 1 | 30% | #NAME?
2 | 1 | 1 | 1 | 2 | 3 | 4 | 1 | 5 | 44.44% | #NAME? | 2 | 1 | 1 | 1 | 3 | 2 | 33.33% | #NAME?
5 | 5 | 2 | 2 | 3 | 5 | 4 | 1 | 1 | 62.22% | #NAME? | 2 | 3 | 1 | 4 | 3 | 4 | 56.67% | #NAME?
1 | 1 | 3 | 1 | 5 | 2 | 2 | 1 | 4 | 44.44% | #NAME? | 1 | 2 | 1 | 1 | 1 | 4 | 33.33% | #NAME?
5 | 2 | 2 | 2 | 3 | 1 | 3 | 3 | 1 | 48.89% | #NAME? | 2 | 3 | 1 | 5 | 4 | 5 | 66.67% | #NAME?
2 | 3 | 1 | 2 | 4 | 1 | 5 | 1 | 1 | 44.44% | #NAME? | 2 | 3 | 1 | 2 | 4 | 5 | 56.67% | #NAME?
5 | 4 | 5 | 5 | 1 | 3 | 2 | 1 | 3 | 64.44% | #NAME? | 4 | 1 | 1 | 2 | 3 | 2 | 43.33% | #NAME?
2 | 5 | 2 | 1 | 3 | 4 | 3 | 1 | 2 | 51.11% | #NAME? | 2 | 2 | 1 | 2 | 1 | 1 | 30% | #NAME?
3 | 3 | 3 | 2 | 1 | 4 | 1 | 2 | 1 | 44.44% | #NAME? | 2 | 4 | 1 | 1 | 5 | 5 | 60% | #NAME?
2 | 1 | 2 | 1 | 5 | 4 | 4 | 3 | 1 | 51.11% | #NAME? | 1 | 1 | 1 | 2 | 2 | 3 | 33.33% | #NAME?
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | #NAME? | 1 | 1 | 1 | 3 | 1 | 2 | 30% | #NAME?
5 | 4 | 4 | 2 | 1 | 2 | 4 | 2 | 4 | 62.22% | #NAME? | 5 | 1 | 1 | 1 | 4 | 5 | 56.67% | #NAME?
5 | 4 | 3 | 5 | 4 | 1 | 1 | 1 | 1 | 55.56% | #NAME? | 2 | 4 | 1 | 5 | 4 | 3 | 63.33% | #NAME?
3 | 2 | 1 | 3 | 4 | 5 | 4 | 1 | 2 | 55.56% | #NAME? | 2 | 5 | 5 | 1 | 3 | 1 | 56.67% | #NAME?
1 | 1 | 1 | 1 | 5 | 5 | 3 | 1 | 3 | 46.67% | #NAME? | 1 | 2 | 1 | 1 | 2 | 2 | 30% | #NAME?
3 | 3 | 4 | 2 | 3 | 2 | 3 | 4 | 5 | 64.44% | #NAME? | 2 | 4 | 5 | 5 | 4 | 4 | 80% | #NAME?
2 | 2 | 1 | 1 | 5 | 1 | 4 | 1 | 3 | 44.44% | #NAME? | 4 | 4 | 5 | 5 | 1 | 3 | 73.33% | #NAME?
1 | 2 | 2 | 1 | 2 | 4 | 4 | 2 | 1 | 42.22% | #NAME? | 4 | 5 | 5 | 3 | 1 | 4 | 73.33% | #NAME?
5 | 1 | 5 | 4 | 5 | 5 | 2 | 1 | 5 | 73.33% | #NAME? | 3 | 1 | 1 | 4 | 2 | 2 | 43.33% | #NAME?
2 | 5 | 2 | 2 | 5 | 4 | 2 | 2 | 3 | 60% | #NAME? | 5 | 1 | 1 | 5 | 4 | 1 | 56.67% | #NAME?
4 | 2 | 1 | 2 | 3 | 5 | 4 | 2 | 4 | 60% | #NAME? | 5 | 3 | 1 | 5 | 4 | 3 | 70% | #NAME?
4 | 5 | 2 | 4 | 2 | 5 | 4 | 4 | 2 | 71.11% | #NAME? | 1 | 4 | 1 | 5 | 2 | 4 | 56.67% | #NAME?
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | #NAME? | 3 | 3 | 1 | 4 | 3 | 1 | 50% | #NAME?
3 | 5 | 5 | 5 | 1 | 2 | 1 | 4 | 4 | 66.67% | #NAME? | 4 | 4 | 1 | 3 | 2 | 1 | 50% | #NAME?
5 | 1 | 1 | 2 | 2 | 3 | 1 | 4 | 3 | 48.89% | #NAME? | 1 | 4 | 1 | 4 | 4 | 1 | 50% | #NAME?
1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 33.33% | #NAME? | 1 | 3 | 1 | 4 | 2 | 2 | 43.33% | #NAME?
5 | 4 | 3 | 2 | 4 | 5 | 4 | 2 | 4 | 73.33% | #NAME? | 4 | 2 | 1 | 3 | 2 | 3 | 50% | #NAME?
4 | 1 | 2 | 5 | 5 | 4 | 2 | 1 | 1 | 55.56% | #NAME? | 1 | 5 | 5 | 4 | 4 | 1 | 66.67% | #NAME?
2 | 5 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 53.33% | #NAME? | 4 | 4 | 5 | 5 | 3 | 2 | 76.67% | #NAME?
5 | 5 | 1 | 5 | 1 | 5 | 1 | 2 | 4 | 64.44% | #NAME? | 3 | 4 | 5 | 1 | 3 | 3 | 63.33% | #NAME?
2 | 2 | 1 | 3 | 1 | 2 | 5 | 1 | 4 | 46.67% | #NAME? | 3 | 4 | 1 | 1 | 1 | 4 | 46.67% | #NAME?
4 | 4 | 5 | 2 | 5 | 3 | 5 | 3 | 3 | 75.56% | #NAME? | 5 | 4 | 5 | 2 | 1 | 3 | 66.67% | #NAME?
1 | 1 | 2 | 1 | 3 | 2 | 4 | 3 | 3 | 44.44% | #NAME? | 5 | 4 | 5 | 4 | 2 | 1 | 70% | #NAME?
1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 33.33% | #NAME? | 3 | 2 | 1 | 1 | 2 | 1 | 33.33% | #NAME?
4 | 3 | 1 | 2 | 5 | 3 | 2 | 1 | 4 | 55.56% | #NAME? | 3 | 4 | 1 | 3 | 3 | 3 | 56.67% | #NAME?
3 | 1 | 3 | 2 | 4 | 4 | 4 | 3 | 4 | 62.22% | #NAME? | 5 | 2 | 1 | 2 | 1 | 3 | 46.67% | #NAME?
3 | 4 | 3 | 2 | 5 | 3 | 2 | 5 | 1 | 62.22% | #NAME? | 4 | 4 | 1 | 1 | 4 | 3 | 56.67% | #NAME?
4 | 5 | 5 | 2 | 3 | 3 | 1 | 4 | 3 | 66.67% | #NAME? | 3 | 3 | 1 | 1 | 1 | 3 | 40% | #NAME?
1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 28.89% | #NAME? | 4 | 3 | 1 | 5 | 5 | 3 | 70% | #NAME?
1 | 4 | 1 | 1 | 1 | 4 | 5 | 2 | 3 | 48.89% | #NAME? | 3 | 5 | 1 | 4 | 4 | 2 | 63.33% | #NAME?
4 | 1 | 5 | 3 | 1 | 2 | 5 | 3 | 4 | 62.22% | #NAME? | 5 | 4 | 5 | 5 | 3 | 4 | 86.67% | #NAME?
3 | 4 | 4 | 5 | 1 | 2 | 3 | 3 | 1 | 57.78% | #NAME? | 1 | 1 | 5 | 4 | 2 | 3 | 53.33% | #NAME?
4 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 53.33% | #NAME? | 3 | 5 | 5 | 1 | 5 | 4 | 76.67% | #NAME?
5 | 3 | 5 | 2 | 5 | 2 | 4 | 1 | 2 | 64.44% | #NAME? | 2 | 2 | 1 | 4 | 3 | 5 | 56.67% | #NAME?
3 | 3 | 5 | 3 | 4 | 5 | 2 | 2 | 5 | 71.11% | #NAME? | 5 | 3 | 1 | 1 | 2 | 4 | 53.33% | #NAME?
3 | 1 | 3 | 2 | 2 | 1 | 5 | 1 | 4 | 48.89% | #NAME? | 5 | 4 | 1 | 4 | 1 | 2 | 56.67% | #NAME?
2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 4 | 37.78% | #NAME? | 4 | 2 | 1 | 2 | 2 | 2 | 43.33% | #NAME?
3 | 2 | 2 | 3 | 5 | 4 | 2 | 1 | 3 | 55.56% | #NAME? | 4 | 4 | 1 | 3 | 5 | 4 | 70% | #NAME?
5 | 2 | 5 | 2 | 1 | 5 | 5 | 5 | 1 | 68.89% | #NAME? | 1 | 3 | 1 | 5 | 3 | 2 | 50% | #NAME?
1 | 1 | 1 | 1 | 5 | 4 | 5 | 1 | 1 | 44.44% | #NAME? | 1 | 1 | 1 | 1 | 1 | 2 | 23.33% | #NAME?
4 | 2 | 1 | 2 | 3 | 4 | 2 | 1 | 5 | 53.33% | #NAME? | 4 | 4 | 1 | 2 | 5 | 3 | 63.33% | #NAME?
2 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 5 | 44.44% | #NAME? | 1 | 3 | 1 | 4 | 3 | 4 | 53.33% | #NAME?
4 | 3 | 3 | 5 | 1 | 3 | 4 | 2 | 3 | 62.22% | #NAME? | 2 | 5 | 5 | 3 | 4 | 5 | 80% | #NAME?
5 | 1 | 1 | 4 | 3 | 3 | 3 | 3 | 2 | 55.56% | #NAME? | 1 | 3 | 1 | 3 | 5 | 5 | 60% | #NAME?
4 | 4 | 2 | 2 | 5 | 3 | 2 | 5 | 3 | 66.67% | #NAME? | 4 | 4 | 1 | 1 | 5 | 2 | 56.67% | #NAME?
3 | 1 | 4 | 5 | 5 | 1 | 1 | 5 | 2 | 60% | #NAME? | 1 | 5 | 5 | 4 | 1 | 3 | 63.33% | #NAME?
4 | 2 | 5 | 2 | 3 | 3 | 3 | 4 | 1 | 60% | #NAME? | 1 | 3 | 1 | 1 | 3 | 4 | 43.33% | #NAME?
5 | 5 | 1 | 4 | 5 | 5 | 4 | 4 | 4 | 82.22% | #NAME? | 3 | 1 | 1 | 4 | 3 | 5 | 56.67% | #NAME?
1 | 5 | 2 | 2 | 3 | 1 | 2 | 3 | 3 | 48.89% | #NAME? | 2 | 3 | 1 | 4 | 5 | 3 | 60% | #NAME?
4 | 5 | 1 | 4 | 2 | 1 | 1 | 1 | 5 | 53.33% | #NAME? | 4 | 3 | 1 | 1 | 5 | 1 | 50% | #NAME?
3 | 2 | 3 | 2 | 4 | 5 | 4 | 1 | 2 | 57.78% | #NAME? | 2 | 5 | 5 | 2 | 4 | 2 | 66.67% | #NAME?
5 | 5 | 5 | 4 | 5 | 1 | 5 | 3 | 3 | 80% | #NAME? | 3 | 2 | 1 | 4 | 3 | 2 | 50% | #NAME?
4 | 3 | 5 | 4 | 2 | 5 | 3 | 2 | 3 | 68.89% | #NAME? | 3 | 3 | 1 | 3 | 1 | 1 | 40% | #NAME?
5 | 1 | 5 | 3 | 4 | 2 | 4 | 1 | 4 | 64.44% | #NAME? | 5 | 3 | 1 | 5 | 2 | 4 | 66.67% | #NAME?
3 | 5 | 5 | 4 | 2 | 3 | 3 | 1 | 2 | 62.22% | #NAME? | 2 | 3 | 1 | 4 | 1 | 5 | 53.33% | #NAME?
2 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 5 | 51.11% | #NAME? | 4 | 2 | 1 | 5 | 3 | 1 | 53.33% | #NAME?
4 | 1 | 2 | 1 | 2 | 4 | 4 | 4 | 5 | 60% | #NAME? | 3 | 1 | 1 | 1 | 4 | 1 | 36.67% | #NAME?
2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22.22% | #NAME? | 5 | 3 | 1 | 5 | 1 | 1 | 53.33% | #NAME?
2 | 2 | 3 | 1 | 5 | 4 | 1 | 1 | 1 | 44.44% | #NAME? | 3 | 3 | 1 | 2 | 5 | 3 | 56.67% | #NAME?
2 | 4 | 2 | 2 | 3 | 1 | 5 | 1 | 4 | 53.33% | #NAME? | 5 | 1 | 1 | 1 | 1 | 2 | 36.67% | #NAME?
3 | 3 | 2 | 2 | 2 | 1 | 5 | 4 | 4 | 57.78% | #NAME? | 5 | 4 | 1 | 4 | 5 | 5 | 80% | #NAME?
5 | 3 | 4 | 5 | 2 | 3 | 5 | 1 | 1 | 64.44% | #NAME? | 4 | 3 | 1 | 4 | 1 | 5 | 60% | #NAME?
3 | 5 | 2 | 5 | 1 | 4 | 3 | 5 | 1 | 64.44% | #NAME? | 5 | 2 | 1 | 4 | 2 | 4 | 60% | #NAME?
4 | 5 | 2 | 2 | 3 | 3 | 5 | 3 | 3 | 66.67% | #NAME? | 2 | 4 | 1 | 5 | 4 | 2 | 60% | #NAME?
4 | 2 | 4 | 2 | 5 | 1 | 2 | 3 | 1 | 53.33% | #NAME? | 4 | 4 | 1 | 1 | 2 | 2 | 46.67% | #NAME?
4 | 3 | 3 | 5 | 4 | 4 | 4 | 1 | 3 | 68.89% | #NAME? | 2 | 5 | 1 | 3 | 2 | 1 | 46.67% | #NAME?
3 | 2 | 2 | 5 | 3 | 3 | 4 | 2 | 3 | 60% | #NAME? | 1 | 1 | 1 | 3 | 1 | 1 | 26.67% | #NAME?
5 | 4 | 3 | 3 | 4 | 5 | 5 | 5 | 4 | 84.44% | #NAME? | 1 | 3 | 1 | 3 | 3 | 2 | 43.33% | #NAME?
4 | 2 | 4 | 1 | 1 | 5 | 5 | 5 | 5 | 71.11% | #NAME? | 4 | 1 | 1 | 5 | 4 | 2 | 56.67% | #NAME?
4 | 1 | 1 | 3 | 2 | 5 | 2 | 1 | 5 | 53.33% | #NAME? | 4 | 4 | 1 | 4 | 4 | 5 | 73.33% | #NAME?
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | #NAME? | 5 | 4 | 1 | 3 | 5 | 4 | 73.33% | #NAME?
5 | 5 | 2 | 5 | 4 | 5 | 4 | 3 | 4 | 82.22% | #NAME? | 5 | 5 | 5 | 1 | 3 | 5 | 80% | #NAME?
2 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 4 | 44.44% | #NAME? | 3 | 4 | 1 | 5 | 1 | 1 | 50% | #NAME?
3 | 3 | 3 | 4 | 1 | 2 | 1 | 5 | 3 | 55.56% | #NAME? | 4 | 2 | 1 | 5 | 1 | 3 | 53.33% | #NAME?
2 | 3 | 1 | 3 | 2 | 5 | 3 | 1 | 4 | 53.33% | #NAME? | 5 | 4 | 1 | 1 | 1 | 2 | 46.67% | #NAME?
4 | 1 | 2 | 3 | 1 | 5 | 5 | 2 | 5 | 62.22% | #NAME? | 5 | 5 | 1 | 1 | 3 | 3 | 60% | #NAME?
2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 4 | 35.56% | #NAME? | 5 | 2 | 1 | 3 | 3 | 1 | 50% | #NAME?
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | #NAME? | 4 | 2 | 1 | 1 | 5 | 2 | 50% | #NAME?
1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 31.11% | #NAME? | 5 | 2 | 1 | 4 | 3 | 1 | 53.33% | #NAME?
1 | 3 | 1 | 2 | 3 | 5 | 5 | 1 | 5 | 57.78% | #NAME? | 2 | 2 | 1 | 5 | 2 | 2 | 46.67% | #NAME?
5 | 5 | 2 | 3 | 5 | 2 | 1 | 3 | 4 | 66.67% | #NAME? | 1 | 1 | 1 | 4 | 1 | 3 | 36.67% | #NAME?
2 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 5 | 48.89% | #NAME? | 1 | 2 | 1 | 2 | 1 | 2 | 30% | #NAME?
2 | 5 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 42.22% | #NAME? | 2 | 2 | 1 | 5 | 5 | 1 | 53.33% | #NAME?
5 | 1 | 4 | 4 | 5 | 3 | 3 | 5 | 4 | 75.56% | #NAME? | 3 | 1 | 1 | 3 | 3 | 3 | 46.67% | #NAME?
3 | 5 | 3 | 4 | 4 | 1 | 4 | 3 | 4 | 68.89% | #NAME? | 4 | 2 | 1 | 1 | 3 | 5 | 53.33% | #NAME?
4 | 4 | 1 | 1 | 3 | 1 | 4 | 4 | 3 | 55.56% | #NAME? | 5 | 2 | 1 | 1 | 1 | 3 | 43.33% | #NAME?
5 | 1 | 1 | 1 | 5 | 5 | 2 | 3 | 5 | 62.22% | #NAME? | 4 | 4 | 1 | 3 | 2 | 3 | 56.67% | #NAME?
5 | 2 | 5 | 3 | 2 | 4 | 3 | 4 | 3 | 68.89% | #NAME? | 5 | 4 | 1 | 2 | 5 | 3 | 66.67% | #NAME?
1 | 5 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 37.78% | #NAME? | 1 | 5 | 1 | 2 | 5 | 3 | 56.67% | #NAME?
4 | 1 | 2 | 1 | 5 | 3 | 4 | 2 | 5 | 60% | #NAME? | 1 | 1 | 1 | 3 | 2 | 2 | 33.33% | #NAME?
2 | 4 | 2 | 1 | 4 | 3 | 3 | 2 | 1 | 48.89% | #NAME? | 5 | 4 | 5 | 2 | 2 | 1 | 63.33% | #NAME?
4 | 3 | 5 | 3 | 2 | 4 | 1 | 3 | 4 | 64.44% | #NAME? | 1 | 4 | 5 | 1 | 5 | 3 | 63.33% | #NAME?
3 | 2 | 1 | 5 | 3 | 4 | 3 | 5 | 5 | 68.89% | #NAME? | 4 | 5 | 5 | 1 | 1 | 2 | 60% | #NAME?
4 | 2 | 5 | 3 | 2 | 2 | 4 | 3 | 1 | 57.78% | #NAME? | 2 | 2 | 1 | 5 | 1 | 5 | 53.33% | #NAME?
5 | 1 | 5 | 5 | 4 | 3 | 5 | 2 | 4 | 75.56% | #NAME? | 1 | 2 | 1 | 4 | 5 | 4 | 56.67% | #NAME?
1 | 2 | 1 | 3 | 2 | 5 | 1 | 1 | 4 | 44.44% | #NAME? | 1 | 4 | 1 | 5 | 5 | 5 | 70% | #NAME?
2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 31.11% | #NAME? | 5 | 4 | 1 | 5 | 3 | 1 | 63.33% | #NAME?
1 | 1 | 1 | 3 | 2 | 1 | 5 | 2 | 1 | 37.78% | #NAME? | 3 | 3 | 1 | 5 | 3 | 1 | 53.33% | #NAME?
2 | 4 | 1 | 3 | 2 | 5 | 2 | 2 | 3 | 53.33% | #NAME? | 4 | 4 | 1 | 2 | 5 | 5 | 70% | #NAME?
1 | 5 | 1 | 1 | 2 | 3 | 4 | 2 | 3 | 48.89% | #NAME? | 5 | 3 | 1 | 1 | 4 | 4 | 60% | #NAME?
5 | 3 | 1 | 4 | 4 | 4 | 4 | 3 | 1 | 64.44% | #NAME? | 5 | 3 | 1 | 5 | 1 | 4 | 63.33% | #NAME?
2 | 3 | 3 | 1 | 1 | 5 | 1 | 2 | 3 | 46.67% | #NAME? | 2 | 5 | 1 | 3 | 5 | 1 | 56.67% | #NAME?
1 | 5 | 3 | 2 | 1 | 5 | 4 | 2 | 1 | 53.33% | #NAME? | 3 | 2 | 1 | 2 | 3 | 1 | 40% | #NAME?
2 | 4 | 1 | 3 | 4 | 4 | 4 | 2 | 5 | 64.44% | #NAME? | 1 | 4 | 1 | 2 | 4 | 5 | 56.67% | #NAME?
3 | 4 | 2 | 4 | 3 | 3 | 3 | 3 | 4 | 64.44% | #NAME? | 1 | 3 | 1 | 1 | 3 | 2 | 36.67% | #NAME?
3 | 2 | 1 | 2 | 2 | 2 | 5 | 5 | 2 | 53.33% | #NAME? | 4 | 3 | 1 | 1 | 3 | 4 | 53.33% | #NAME?
3 | 5 | 2 | 3 | 3 | 3 | 5 | 4 | 3 | 68.89% | #NAME? | 5 | 1 | 1 | 4 | 1 | 1 | 43.33% | #NAME?
4 | 2 | 2 | 2 | 1 | 3 | 5 | 2 | 3 | 53.33% | #NAME? | 4 | 3 | 1 | 4 | 4 | 5 | 70% | #NAME?
1 | 5 | 2 | 2 | 2 | 1 | 1 | 2 | 4 | 44.44% | #NAME? | 4 | 4 | 1 | 4 | 4 | 5 | 73.33% | #NAME?
1 | 3 | 1 | 2 | 4 | 2 | 4 | 3 | 2 | 48.89% | #NAME? | 4 | 3 | 1 | 5 | 4 | 1 | 60% | #NAME?
2 | 3 | 2 | 2 | 3 | 2 | 3 | 2 | 5 | 53.33% | #NAME? | 5 | 3 | 1 | 4 | 4 | 4 | 70% | #NAME?
5 | 3 | 1 | 3 | 5 | 2 | 3 | 3 | 1 | 57.78% | #NAME? | 2 | 3 | 1 | 1 | 2 | 2 | 36.67% | #NAME?
5 | 1 | 3 | 2 | 3 | 1 | 2 | 4 | 3 | 53.33% | #NAME? | 1 | 4 | 1 | 1 | 2 | 1 | 33.33% | #NAME?
3 | 3 | 3 | 2 | 4 | 5 | 2 | 2 | 5 | 64.44% | #NAME? | 5 | 1 | 1 | 5 | 1 | 4 | 56.67% | #NAME?
4 | 3 | 4 | 5 | 1 | 2 | 1 | 2 | 3 | 55.56% | #NAME? | 3 | 2 | 1 | 5 | 4 | 4 | 63.33% | #NAME?
1 | 5 | 1 | 1 | 4 | 5 | 1 | 2 | 1 | 46.67% | #NAME? | 1 | 5 | 1 | 3 | 1 | 5 | 53.33% | #NAME?
3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 68.89% | #NAME? | 4 | 2 | 1 | 2 | 4 | 3 | 53.33% | #NAME?
5 | 5 | 3 | 2 | 5 | 5 | 4 | 3 | 5 | 82.22% | #NAME? | 3 | 5 | 5 | 1 | 2 | 5 | 70% | #NAME?
4 | 4 | 5 | 1 | 4 | 2 | 1 | 2 | 1 | 53.33% | #NAME? | 5 | 1 | 1 | 2 | 3 | 4 | 53.33% | #NAME?
2 | 1 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 33.33% | #NAME? | 2 | 1 | 1 | 3 | 4 | 2 | 43.33% | #NAME?
4 | 3 | 5 | 4 | 2 | 5 | 5 | 4 | 2 | 75.56% | #NAME? | 3 | 1 | 1 | 3 | 1 | 3 | 40% | #NAME?
4 | 2 | 4 | 5 | 2 | 4 | 2 | 3 | 5 | 68.89% | #NAME? | 5 | 2 | 5 | 4 | 4 | 3 | 76.67% | #NAME?
1 | 4 | 2 | 1 | 4 | 2 | 2 | 3 | 5 | 53.33% | #NAME? | 1 | 5 | 5 | 4 | 1 | 1 | 56.67% | #NAME?
1 | 5 | 3 | 1 | 3 | 3 | 2 | 2 | 2 | 48.89% | #NAME? | 5 | 4 | 5 | 5 | 1 | 2 | 73.33% | #NAME?
2 | 5 | 1 | 1 | 4 | 4 | 3 | 2 | 3 | 55.56% | #NAME? | 2 | 5 | 1 | 3 | 4 | 1 | 53.33% | #NAME?
2 | 3 | 1 | 2 | 2 | 5 | 3 | 1 | 3 | 48.89% | #NAME? | 3 | 3 | 1 | 5 | 2 | 3 | 56.67% | #NAME?
2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 42.22% | #NAME? | 4 | 5 | 5 | 2 | 2 | 3 | 70% | #NAME?
5 | 4 | 5 | 4 | 5 | 3 | 2 | 1 | 4 | 73.33% | #NAME? | 1 | 3 | 1 | 4 | 2 | 1 | 40% | #NAME?
5 | 4 | 1 | 3 | 5 | 5 | 5 | 4 | 5 | 82.22% | #NAME? | 1 | 3 | 1 | 3 | 3 | 3 | 46.67% | #NAME?
1 | 4 | 1 | 3 | 4 | 2 | 2 | 2 | 2 | 46.67% | #NAME? | 3 | 5 | 1 | 2 | 3 | 2 | 53.33% | #NAME?
3 | 1 | 3 | 4 | 4 | 2 | 4 | 3 | 3 | 60% | #NAME? | 3 | 5 | 5 | 3 | 3 | 3 | 73.33% | #NAME?
4 | 1 | 1 | 1 | 1 | 5 | 3 | 5 | 3 | 53.33% | #NAME? | 2 | 3 | 1 | 3 | 4 | 1 | 46.67% | #NAME?
2 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 5 | 40% | #NAME? | 3 | 1 | 1 | 2 | 1 | 4 | 40% | #NAME?
1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 33.33% | #NAME? | 1 | 1 | 1 | 2 | 4 | 1 | 33.33% | #NAME?
3 | 2 | 3 | 4 | 4 | 4 | 1 | 2 | 1 | 53.33% | #NAME? | 3 | 2 | 1 | 1 | 1 | 3 | 36.67% | #NAME?
1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 26.67% | #NAME? | 2 | 3 | 1 | 4 | 1 | 2 | 43.33% | #NAME?
4 | 5 | 2 | 4 | 1 | 3 | 4 | 3 | 5 | 68.89% | #NAME? | 4 | 1 | 1 | 5 | 1 | 2 | 46.67% | #NAME?
4 | 2 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 44.44% | #NAME? | 1 | 3 | 1 | 1 | 2 | 3 | 36.67% | #NAME?
2 | 3 | 2 | 3 | 2 | 1 | 3 | 2 | 5 | 51.11% | #NAME? | 4 | 5 | 5 | 4 | 2 | 5 | 83.33% | #NAME?
3 | 1 | 4 | 1 | 1 | 2 | 3 | 3 | 1 | 42.22% | #NAME? | 3 | 1 | 1 | 4 | 3 | 3 | 50% | #NAME?
1 | 2 | 2 | 1 | 2 | 4 | 5 | 2 | 3 | 48.89% | #NAME? | 2 | 2 | 1 | 2 | 4 | 1 | 40% | #NAME?
2 | 4 | 1 | 1 | 4 | 3 | 3 | 1 | 2 | 46.67% | #NAME? | 3 | 1 | 1 | 3 | 3 | 3 | 46.67% | #NAME?
3 | 3 | 2 | 1 | 2 | 4 | 4 | 1 | 2 | 48.89% | #NAME? | 3 | 3 | 1 | 3 | 3 | 5 | 60% | #NAME?
1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 28.89% | #NAME? | 3 | 2 | 1 | 4 | 3 | 4 | 56.67% | #NAME?
4 | 2 | 4 | 3 | 4 | 2 | 4 | 5 | 4 | 71.11% | #NAME? | 3 | 2 | 1 | 3 | 1 | 3 | 43.33% | #NAME?
2 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 4 | 44.44% | #NAME? | 5 | 5 | 5 | 3 | 4 | 2 | 80% | #NAME?
2 | 1 | 1 | 2 | 2 | 4 | 3 | 2 | 3 | 44.44% | #NAME? | 1 | 2 | 1 | 4 | 2 | 3 | 43.33% | #NAME?
4 | 3 | 4 | 3 | 4 | 5 | 3 | 2 | 5 | 73.33% | #NAME? | 1 | 1 | 1 | 2 | 4 | 4 | 43.33% | #NAME?
3 | 5 | 2 | 3 | 4 | 2 | 1 | 2 | 2 | 53.33% | #NAME? | 5 | 2 | 1 | 5 | 5 | 4 | 73.33% | #NAME?
2 | 1 | 2 | 1 | 2 | 4 | 3 | 1 | 5 | 46.67% | #NAME? | 5 | 1 | 1 | 4 | 2 | 3 | 53.33% | #NAME?
1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 3 | 35.56% | #NAME? | 1 | 1 | 1 | 1 | 3 | 1 | 26.67% | #NAME?
2 | 4 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 46.67% | #NAME? | 2 | 4 | 1 | 1 | 1 | 3 | 40% | #NAME?
5 | 1 | 2 | 5 | 2 | 2 | 4 | 2 | 2 | 55.56% | #NAME? | 4 | 5 | 5 | 3 | 3 | 1 | 70% | #NAME?
1 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 5 | 42.22% | #NAME? | 5 | 2 | 5 | 1 | 1 | 3 | 56.67% | #NAME?
4 | 3 | 3 | 5 | 4 | 2 | 2 | 5 | 2 | 66.67% | #NAME? | 3 | 1 | 1 | 1 | 1 | 2 | 30% | #NAME?
5 | 3 | 1 | 2 | 4 | 4 | 4 | 2 | 1 | 57.78% | #NAME? | 2 | 5 | 1 | 2 | 3 | 5 | 60% | #NAME?
3 | 2 | 1 | 2 | 3 | 2 | 2 | 3 | 4 | 48.89% | #NAME? | 1 | 4 | 1 | 3 | 5 | 4 | 60% | #NAME?
1 | 1 | 3 | 2 | 2 | 2 | 2 | 3 | 1 | 37.78% | #NAME? | 1 | 2 | 1 | 2 | 1 | 2 | 30% | #NAME?
4 | 1 | 4 | 2 | 3 | 3 | 1 | 5 | 3 | 57.78% | #NAME? | 2 | 4 | 1 | 3 | 1 | 2 | 43.33% | #NAME?
2 | 4 | 3 | 3 | 5 | 4 | 4 | 3 | 4 | 71.11% | #NAME? | 1 | 5 | 1 | 2 | 3 | 4 | 53.33% | #NAME?
1 | 5 | 1 | 3 | 2 | 1 | 4 | 2 | 3 | 48.89% | #NAME? | 3 | 3 | 1 | 1 | 1 | 3 | 40% | #NAME?
1 | 1 | 1 | 1 | 1 | 3 | 4 | 2 | 2 | 35.56% | #NAME? | 3 | 2 | 1 | 5 | 2 | 5 | 60% | #NAME?
1 | 5 | 1 | 3 | 1 | 5 | 2 | 2 | 1 | 46.67% | #NAME? | 4 | 3 | 1 | 4 | 2 | 5 | 63.33% | #NAME?
1 | 4 | 1 | 2 | 5 | 2 | 3 | 1 | 4 | 51.11% | #NAME? | 3 | 2 | 1 | 1 | 5 | 1 | 43.33% | #NAME?
3 | 2 | 4 | 4 | 5 | 5 | 1 | 2 | 4 | 66.67% | #NAME? | 3 | 4 | 1 | 2 | 2 | 3 | 50% | #NAME?
1 | 3 | 1 | 2 | 4 | 3 | 4 | 2 | 2 | 48.89% | #NAME? | 2 | 5 | 1 | 1 | 1 | 5 | 50% | #NAME?
2 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 2 | 35.56% | #NAME? | 2 | 2 | 1 | 4 | 3 | 3 | 50% | #NAME?
3 | 5 | 5 | 2 | 2 | 1 | 1 | 2 | 5 | 57.78% | #NAME? | 5 | 4 | 1 | 4 | 5 | 1 | 66.67% | #NAME?
4 | 5 | 2 | 2 | 3 | 5 | 3 | 1 | 1 | 57.78% | #NAME? | 3 | 2 | 1 | 4 | 5 | 1 | 53.33% | #NAME?
5 | 2 | 4 | 3 | 1 | 1 | 4 | 3 | 3 | 57.78% | #NAME? | 3 | 3 | 1 | 2 | 4 | 4 | 56.67% | #NAME?
2 | 2 | 1 | 1 | 2 | 2 | 4 | 3 | 5 | 48.89% | #NAME? | 3 | 3 | 1 | 4 | 1 | 5 | 56.67% | #NAME?
3 | 1 | 4 | 4 | 5 | 2 | 2 | 5 | 5 | 68.89% | #NAME? | 3 | 3 | 1 | 3 | 2 | 4 | 53.33% | #NAME?
2 | 1 | 1 | 2 | 3 | 4 | 2 | 3 | 3 | 46.67% | #NAME? | 2 | 4 | 1 | 5 | 4 | 1 | 56.67% | #NAME?
4 | 1 | 3 | 1 | 1 | 4 | 3 | 3 | 5 | 55.56% | #NAME? | 5 | 4 | 5 | 4 | 5 | 1 | 80% | #NAME?
2 | 3 | 1 | 1 | 5 | 3 | 2 | 2 | 5 | 53.33% | #NAME? | 2 | 4 | 5 | 2 | 4 | 5 | 73.33% | #NAME?
3 | 1 | 4 | 5 | 3 | 4 | 5 | 2 | 4 | 68.89% | #NAME? | 1 | 4 | 1 | 4 | 2 | 2 | 46.67% | #NAME?
5 | 4 | 2 | 2 | 5 | 4 | 5 | 5 | 4 | 80% | #NAME? | 4 | 1 | 1 | 1 | 1 | 3 | 36.67% | #NAME?
4 | 5 | 3 | 4 | 3 | 5 | 4 | 1 | 5 | 75.56% | #NAME? | 4 | 3 | 1 | 1 | 2 | 3 | 46.67% | #NAME?
3 | 3 | 3 | 1 | 3 | 3 | 3 | 5 | 1 | 55.56% | #NAME? | 5 | 4 | 1 | 2 | 2 | 5 | 63.33% | #NAME?
3 | 1 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 48.89% | #NAME? | 2 | 5 | 5 | 1 | 3 | 2 | 60% | #NAME?
2 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 35.56% | #NAME? | 2 | 5 | 5 | 2 | 1 | 3 | 60% | #NAME?
5 | 4 | 5 | 3 | 5 | 5 | 5 | 1 | 2 | 77.78% | #NAME? | 3 | 3 | 1 | 2 | 1 | 4 | 46.67% | #NAME?
2 | 5 | 3 | 2 | 4 | 4 | 3 | 2 | 1 | 57.78% | #NAME? | 1 | 3 | 1 | 3 | 1 | 5 | 46.67% | #NAME?
1 | 3 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 40% | #NAME? | 2 | 5 | 1 | 5 | 2 | 2 | 56.67% | #NAME?
4 | 4 | 5 | 3 | 5 | 1 | 5 | 1 | 5 | 73.33% | #NAME? | 2 | 2 | 1 | 4 | 3 | 5 | 56.67% | #NAME?
3 | 1 | 1 | 1 | 4 | 4 | 1 | 3 | 2 | 44.44% | #NAME? | 3 | 1 | 1 | 4 | 2 | 4 | 50% | #NAME?
2 | 4 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 40% | #NAME? | 1 | 4 | 1 | 5 | 1 | 5 | 56.67% | #NAME?
4 | 2 | 2 | 4 | 5 | 1 | 3 | 2 | 5 | 62.22% | #NAME? | 3 | 2 | 1 | 2 | 4 | 1 | 43.33% | #NAME?
3 | 4 | 1 | 2 | 3 | 2 | 2 | 3 | 4 | 53.33% | #NAME? | 3 | 5 | 1 | 1 | 2 | 4 | 53.33% | #NAME?
2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 5 | 46.67% | #NAME? | 5 | 5 | 5 | 2 | 4 | 5 | 86.67% | #NAME?
4 | 1 | 5 | 2 | 1 | 3 | 2 | 2 | 2 | 48.89% | #NAME? | 1 | 5 | 1 | 5 | 1 | 5 | 60% | #NAME?
3 | 4 | 1 | 1 | 3 | 3 | 3 | 5 | 2 | 55.56% | #NAME? | 3 | 3 | 1 | 1 | 1 | 1 | 33.33% | #NAME?
5 | 3 | 2 | 4 | 2 | 4 | 5 | 4 | 3 | 71.11% | #NAME? | 1 | 2 | 1 | 5 | 2 | 4 | 50% | #NAME?
3 | 2 | 3 | 3 | 5 | 1 | 2 | 5 | 4 | 62.22% | #NAME? | 4 | 4 | 5 | 1 | 2 | 1 | 56.67% | #NAME?
4 | 5 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 42.22% | #NAME? | 1 | 4 | 1 | 2 | 1 | 4 | 43.33% | #NAME?
4 | 3 | 4 | 5 | 1 | 2 | 4 | 3 | 4 | 66.67% | #NAME? | 3 | 1 | 1 | 5 | 5 | 4 | 63.33% | #NAME?
1 | 2 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 33.33% | #NAME? | 2 | 2 | 1 | 5 | 1 | 1 | 40% | #NAME?
4 | 2 | 2 | 3 | 3 | 2 | 3 | 5 | 2 | 57.78% | #NAME? | 2 | 2 | 1 | 3 | 4 | 4 | 53.33% | #NAME?
1 | 5 | 2 | 1 | 2 | 1 | 5 | 1 | 1 | 42.22% | #NAME? | 5 | 1 | 1 | 2 | 4 | 4 | 56.67% | #NAME?
4 | 1 | 4 | 3 | 3 | 3 | 3 | 2 | 4 | 60% | #NAME? | 2 | 5 | 1 | 5 | 3 | 2 | 60% | #NAME?
1 | 4 | 2 | 3 | 4 | 1 | 2 | 1 | 1 | 42.22% | #NAME? | 5 | 5 | 1 | 3 | 1 | 4 | 63.33% | #NAME?
4 | 5 | 1 | 4 | 5 | 2 | 5 | 4 | 1 | 68.89% | #NAME? | 1 | 3 | 1 | 2 | 4 | 2 | 43.33% | #NAME?
2 | 4 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 40% | #NAME? | 1 | 5 | 1 | 3 | 2 | 5 | 56.67% | #NAME?
2 | 5 | 3 | 2 | 3 | 1 | 5 | 3 | 3 | 60% | #NAME? | 2 | 3 | 1 | 3 | 3 | 1 | 43.33% | #NAME?
3 | 3 | 2 | 5 | 3 | 2 | 3 | 1 | 2 | 53.33% | #NAME? | 2 | 4 | 1 | 1 | 4 | 3 | 50% | #NAME?
5 | 3 | 2 | 2 | 5 | 3 | 4 | 1 | 3 | 62.22% | #NAME? | 2 | 3 | 1 | 2 | 2 | 1 | 36.67% | #NAME?
3 | 4 | 1 | 3 | 2 | 4 | 4 | 4 | 1 | 57.78% | #NAME? | 5 | 4 | 1 | 1 | 3 | 1 | 50% | #NAME?
4 | 5 | 2 | 4 | 4 | 1 | 5 | 2 | 4 | 68.89% | #NAME? | 3 | 2 | 1 | 1 | 4 | 1 | 40% | #NAME?
1 | 3 | 1 | 1 | 2 | 5 | 1 | 1 | 2 | 37.78% | #NAME? | 5 | 3 | 1 | 2 | 3 | 3 | 56.67% | #NAME?
2 | 3 | 3 | 1 | 3 | 2 | 3 | 3 | 3 | 51.11% | #NAME? | 1 | 3 | 1 | 1 | 2 | 4 | 40% | #NAME?
5 | 5 | 3 | 2 | 5 | 5 | 1 | 3 | 1 | 66.67% | #NAME? | 1 | 5 | 1 | 5 | 2 | 3 | 56.67% | #NAME?
4 | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 5 | 66.67% | #NAME? | 3 | 1 | 1 | 3 | 5 | 2 | 50% | #NAME?
2 | 2 | 2 | 2 | 5 | 5 | 2 | 1 | 3 | 53.33% | #NAME? | 1 | 5 | 1 | 4 | 5 | 5 | 70% | #NAME?
3 | 5 | 1 | 5 | 5 | 3 | 2 | 4 | 3 | 68.89% | #NAME? | 3 | 1 | 1 | 5 | 4 | 4 | 60% | #NAME?
1 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 3 | 33.33% | #NAME? | 5 | 3 | 1 | 1 | 2 | 5 | 56.67% | #NAME?
5 | 1 | 3 | 2 | 4 | 1 | 4 | 2 | 3 | 55.56% | #NAME? | 4 | 2 | 1 | 4 | 3 | 3 | 56.67% | #NAME?
1 | 3 | 3 | 1 | 1 | 5 | 2 | 1 | 2 | 42.22% | #NAME? | 1 | 1 | 5 | 3 | 2 | 5 | 56.67% | #NAME?
3 | 1 | 2 | 3 | 2 | 4 | 5 | 3 | 2 | 55.56% | #NAME? | 4 | 5 | 5 | 4 | 4 | 4 | 86.67% | #NAME?
4 | 3 | 4 | 4 | 2 | 2 | 5 | 5 | 1 | 66.67% | #NAME? | 4 | 5 | 5 | 2 | 3 | 3 | 73.33% | #NAME?
3 | 4 | 2 | 5 | 1 | 4 | 3 | 4 | 3 | 64.44% | #NAME? | 2 | 1 | 1 | 2 | 2 | 4 | 40% | #NAME?
5 | 2 | 1 | 2 | 5 | 5 | 2 | 5 | 1 | 62.22% | #NAME? | 1 | 3 | 1 | 4 | 2 | 3 | 46.67% | #NAME?
2 | 5 | 3 | 2 | 4 | 2 | 4 | 2 | 1 | 55.56% | #NAME? | 1 | 1 | 1 | 2 | 4 | 4 | 43.33% | #NAME?
5 | 5 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 53.33% | #NAME? | 5 | 4 | 1 | 3 | 3 | 1 | 56.67% | #NAME?
5 | 3 | 1 | 2 | 3 | 3 | 3 | 2 | 4 | 57.78% | #NAME? | 2 | 1 | 1 | 1 | 4 | 2 | 36.67% | #NAME?
3 | 1 | 4 | 2 | 2 | 2 | 3 | 2 | 3 | 48.89% | #NAME? | 3 | 1 | 1 | 3 | 2 | 5 | 50% | #NAME?
1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 28.89% | #NAME? | 2 | 1 | 1 | 1 | 1 | 3 | 30% | #NAME?
4 | 1 | 3 | 1 | 1 | 3 | 1 | 5 | 1 | 44.44% | #NAME? | 5 | 4 | 5 | 4 | 5 | 5 | 93.33% | #NAME?
4 | 3 | 2 | 4 | 1 | 3 | 5 | 5 | 2 | 64.44% | #NAME? | 5 | 1 | 1 | 4 | 2 | 2 | 50% | #NAME?
2 | 2 | 2 | 2 | 1 | 4 | 3 | 1 | 1 | 40% | #NAME? | 1 | 5 | 1 | 1 | 5 | 4 | 56.67% | #NAME?
3 | 2 | 1 | 1 | 2 | 4 | 5 | 4 | 5 | 60% | #NAME? | 1 | 4 | 1 | 3 | 5 | 2 | 53.33% | #NAME?
4 | 4 | 3 | 3 | 2 | 3 | 5 | 1 | 2 | 60% | #NAME? | 1 | 2 | 1 | 2 | 3 | 4 | 43.33% | #NAME?
1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 28.89% | #NAME? | 3 | 1 | 1 | 2 | 5 | 2 | 46.67% | #NAME?
3 | 5 | 4 | 1 | 1 | 4 | 1 | 2 | 5 | 57.78% | #NAME? | 4 | 5 | 1 | 3 | 4 | 3 | 66.67% | #NAME?
3 | 4 | 2 | 2 | 1 | 2 | 3 | 3 | 4 | 53.33% | #NAME? | 5 | 1 | 1 | 2 | 3 | 3 | 50% | #NAME?
5 | 2 | 4 | 5 | 2 | 4 | 2 | 1 | 3 | 62.22% | #NAME? | 3 | 2 | 1 | 1 | 1 | 3 | 36.67% | #NAME?
2 | 4 | 2 | 1 | 1 | 4 | 2 | 3 | 5 | 53.33% | #NAME? | 5 | 1 | 1 | 4 | 2 | 4 | 56.67% | #NAME?
5 | 4 | 1 | 2 | 2 | 5 | 1 | 2 | 2 | 53.33% | #NAME? | 3 | 3 | 1 | 4 | 3 | 2 | 53.33% | #NAME?
5 | 1 | 4 | 5 | 1 | 3 | 1 | 4 | 3 | 60% | #NAME? | 2 | 2 | 1 | 4 | 5 | 1 | 50% | #NAME?
2 | 5 | 2 | 3 | 4 | 5 | 5 | 1 | 1 | 62.22% | #NAME? | 3 | 2 | 1 | 4 | 4 | 4 | 60% | #NAME?
3 | 2 | 2 | 4 | 1 | 4 | 4 | 4 | 4 | 62.22% | #NAME? | 5 | 3 | 1 | 5 | 4 | 1 | 63.33% | #NAME?
4 | 5 | 3 | 4 | 1 | 5 | 3 | 5 | 3 | 73.33% | #NAME? | 4 | 1 | 1 | 3 | 3 | 3 | 50% | #NAME?
5 | 4 | 4 | 5 | 2 | 1 | 2 | 1 | 4 | 62.22% | #NAME? | 5 | 4 | 1 | 4 | 3 | 3 | 66.67% | #NAME?
1 | 2 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 35.56% | #NAME? | 1 | 3 | 1 | 1 | 2 | 4 | 40% | #NAME?
4 | 3 | 3 | 4 | 2 | 1 | 5 | 2 | 2 | 57.78% | #NAME? | 5 | 5 | 5 | 2 | 1 | 4 | 73.33% | #NAME?
5 | 1 | 3 | 4 | 2 | 2 | 5 | 1 | 4 | 60% | #NAME? | 2 | 1 | 1 | 3 | 4 | 1 | 40% | #NAME?
4 | 3 | 1 | 4 | 2 | 1 | 1 | 2 | 5 | 51.11% | #NAME? | 3 | 3 | 1 | 2 | 1 | 4 | 46.67% | #NAME?
2 | 4 | 1 | 2 | 1 | 5 | 3 | 1 | 5 | 53.33% | #NAME? | 2 | 5 | 1 | 1 | 3 | 1 | 43.33% | #NAME?
1 | 2 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 35.56% | #NAME? | 4 | 5 | 5 | 4 | 2 | 5 | 83.33% | #NAME?
4 | 2 | 3 | 5 | 1 | 3 | 1 | 5 | 1 | 55.56% | #NAME? | 3 | 2 | 1 | 5 | 1 | 2 | 46.67% | #NAME?
2 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 4 | 37.78% | #NAME? | 4 | 2 | 5 | 4 | 1 | 1 | 56.67% | #NAME?
5 | 5 | 3 | 2 | 5 | 5 | 5 | 2 | 4 | 80% | #NAME? | 1 | 5 | 5 | 5 | 4 | 3 | 76.67% | #NAME?
5 | 4 | 4 | 4 | 2 | 5 | 5 | 1 | 5 | 77.78% | #NAME? | 5 | 1 | 1 | 3 | 3 | 3 | 53.33% | #NAME?
4 | 4 | 1 | 1 | 4 | 2 | 1 | 2 | 2 | 46.67% | #NAME? | 3 | 3 | 1 | 2 | 5 | 4 | 60% | #NAME?
3 | 2 | 3 | 5 | 1 | 2 | 3 | 2 | 5 | 57.78% | #NAME? | 5 | 1 | 1 | 2 | 2 | 4 | 50% | #NAME?
1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 28.89% | #NAME? | 3 | 4 | 1 | 4 | 2 | 3 | 56.67% | #NAME?
2 | 4 | 2 | 3 | 5 | 2 | 1 | 2 | 5 | 57.78% | #NAME? | 4 | 5 | 1 | 2 | 1 | 4 | 56.67% | #NAME?
2 | 4 | 1 | 1 | 3 | 3 | 3 | 2 | 4 | 51.11% | #NAME? | 5 | 1 | 1 | 1 | 4 | 2 | 46.67% | #NAME?
2 | 1 | 1 | 1 | 2 | 5 | 3 | 3 | 5 | 51.11% | #NAME? | 4 | 1 | 1 | 3 | 4 | 1 | 46.67% | #NAME?
2 | 5 | 2 | 1 | 2 | 1 | 1 | 1 | 5 | 44.44% | #NAME? | 1 | 5 | 1 | 1 | 2 | 3 | 43.33% | #NAME?
3 | 3 | 1 | 5 | 2 | 5 | 1 | 4 | 1 | 55.56% | #NAME? | 4 | 1 | 1 | 4 | 2 | 5 | 56.67% | #NAME?
3 | 5 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 53.33% | #NAME? | 5 | 1 | 1 | 2 | 4 | 2 | 50% | #NAME?
5 | 1 | 1 | 3 | 2 | 5 | 1 | 5 | 3 | 57.78% | #NAME? | 1 | 2 | 1 | 3 | 1 | 2 | 33.33% | #NAME?
1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 28.89% | #NAME? | 3 | 1 | 1 | 3 | 4 | 1 | 43.33% | #NAME?
2 | 1 | 3 | 3 | 2 | 2 | 2 | 2 | 4 | 46.67% | #NAME? | 5 | 1 | 1 | 2 | 3 | 3 | 50% | #NAME?
3 | 2 | 4 | 3 | 4 | 2 | 4 | 1 | 1 | 53.33% | #NAME? | 2 | 4 | 1 | 5 | 5 | 5 | 73.33% | #NAME?
3 | 1 | 1 | 3 | 3 | 1 | 4 | 1 | 4 | 46.67% | #NAME? | 3 | 5 | 1 | 5 | 2 | 5 | 70% | #NAME?
4 | 4 | 3 | 4 | 1 | 2 | 5 | 2 | 2 | 60% | #NAME? | 1 | 2 | 1 | 1 | 1 | 5 | 36.67% | #NAME?
2 | 3 | 2 | 2 | 1 | 4 | 2 | 1 | 5 | 48.89% | #NAME? | 1 | 1 | 1 | 2 | 3 | 2 | 33.33% | #NAME?
3 | 1 | 1 | 4 | 3 | 5 | 3 | 1 | 1 | 48.89% | #NAME? | 2 | 4 | 1 | 1 | 1 | 4 | 43.33% | #NAME?
2 | 1 | 3 | 3 | 4 | 5 | 3 | 2 | 4 | 60% | #NAME? | 4 | 1 | 1 | 1 | 4 | 5 | 53.33% | #NAME?
1 | 2 | 3 | 1 | 2 | 2 | 2 | 2 | 2 | 37.78% | #NAME? | 2 | 3 | 1 | 1 | 1 | 2 | 33.33% | #NAME?
2 | 4 | 3 | 2 | 1 | 5 | 5 | 1 | 4 | 60% | #NAME? | 1 | 2 | 1 | 1 | 5 | 4 | 46.67% | #NAME?
4 | 3 | 2 | 5 | 2 | 2 | 5 | 2 | 1 | 57.78% | #NAME? | 4 | 1 | 1 | 4 | 4 | 4 | 60% | #NAME?
3 | 4 | 1 | 3 | 4 | 1 | 3 | 3 | 2 | 53.33% | #NAME? | 5 | 3 | 5 | 2 | 1 | 5 | 70% | #NAME?
5 | 4 | 1 | 4 | 3 | 1 | 1 | 3 | 3 | 55.56% | #NAME? | 5 | 1 | 1 | 4 | 1 | 1 | 43.33% | #NAME?
5 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 4 | 51.11% | #NAME? | 1 | 4 | 1 | 3 | 1 | 3 | 43.33% | #NAME?
3 | 5 | 1 | 1 | 5 | 1 | 5 | 4 | 3 | 62.22% | #NAME? | 2 | 1 | 1 | 5 | 1 | 1 | 36.67% | #NAME?
3 | 1 | 2 | 5 | 5 | 3 | 1 | 4 | 1 | 55.56% | #NAME? | 3 | 2 | 1 | 3 | 2 | 2 | 43.33% | #NAME?
3 | 1 | 4 | 5 | 1 | 2 | 2 | 5 | 5 | 62.22% | #NAME? | 2 | 3 | 1 | 5 | 4 | 1 | 53.33% | #NAME?
2 | 1 | 2 | 2 | 1 | 2 | 5 | 2 | 3 | 44.44% | #NAME? | 4 | 3 | 5 | 1 | 3 | 3 | 63.33% | #NAME?
2 | 4 | 1 | 1 | 1 | 5 | 5 | 3 | 1 | 51.11% | #NAME? | 5 | 1 | 1 | 3 | 1 | 4 | 50% | #NAME?
2 | 4 | 1 | 2 | 1 | 2 | 2 | 2 | 5 | 46.67% | #NAME? | 1 | 5 | 1 | 5 | 4 | 3 | 63.33% | #NAME?
1 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 4 | 44.44% | #NAME? | 1 | 3 | 1 | 1 | 2 | 2 | 33.33% | #NAME?
1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 26.67% | #NAME? | 5 | 1 | 1 | 3 | 4 | 1 | 50% | #NAME?
1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 26.67% | #NAME? | 2 | 1 | 1 | 1 | 3 | 2 | 33.33% | #NAME?
5 | 3 | 4 | 2 | 4 | 2 | 2 | 3 | 4 | 64.44% | #NAME? | 3 | 5 | 1 | 5 | 4 | 5 | 76.67% | #NAME?
3 | 2 | 3 | 2 | 5 | 1 | 2 | 2 | 4 | 53.33% | #NAME? | 1 | 2 | 1 | 4 | 1 | 4 | 43.33% | #NAME?
1 | 5 | 1 | 1 | 3 | 4 | 4 | 1 | 3 | 51.11% | #NAME? | 3 | 4 | 1 | 5 | 3 | 1 | 56.67% | #NAME?
4 | 5 | 4 | 2 | 1 | 5 | 4 | 3 | 2 | 66.67% | #NAME? | 3 | 4 | 5 | 4 | 1 | 5 | 73.33% | #NAME?
3 | 4 | 3 | 2 | 4 | 5 | 3 | 4 | 4 | 71.11% | #NAME? | 1 | 4 | 1 | 4 | 4 | 4 | 60% | #NAME?
1 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 28.89% | #NAME? | 5 | 4 | 5 | 1 | 5 | 4 | 80% | #NAME?
1 | 5 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 42.22% | #NAME? | 5 | 2 | 1 | 4 | 1 | 3 | 53.33% | #NAME?
3 | 4 | 2 | 1 | 5 | 1 | 1 | 3 | 3 | 51.11% | #NAME? | 4 | 5 | 5 | 2 | 5 | 5 | 86.67% | #NAME?
5 | 4 | 2 | 5 | 2 | 2 | 1 | 2 | 5 | 62.22% | #NAME? | 2 | 3 | 1 | 4 | 1 | 1 | 40% | #NAME?
2 | 3 | 1 | 1 | 2 | 4 | 1 | 3 | 5 | 48.89% | #NAME? | 2 | 3 | 1 | 3 | 5 | 5 | 63.33% | #NAME?
1 | 5 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 44.44% | #NAME? | 2 | 1 | 1 | 1 | 3 | 1 | 30% | #NAME?
4 | 4 | 2 | 2 | 3 | 5 | 4 | 2 | 4 | 66.67% | #NAME? | 1 | 2 | 1 | 5 | 1 | 2 | 40% | #NAME?
2 | 4 | 2 | 3 | 1 | 2 | 4 | 2 | 4 | 53.33% | #NAME? | 1 | 2 | 1 | 1 | 2 | 2 | 30% | #NAME?
1 | 2 | 1 | 1 | 3 | 2 | 3 | 2 | 3 | 40% | #NAME? | 5 | 5 | 1 | 4 | 3 | 3 | 70% | #NAME?
3 | 2 | 2 | 3 | 1 | 2 | 4 | 1 | 5 | 51.11% | #NAME? | 5 | 1 | 1 | 5 | 2 | 4 | 60% | #NAME?
4 | 3 | 4 | 4 | 3 | 3 | 5 | 1 | 2 | 64.44% | #NAME? | 3 | 1 | 1 | 4 | 3 | 5 | 56.67% | #NAME?
3 | 3 | 2 | 3 | 2 | 4 | 4 | 3 | 2 | 57.78% | #NAME? | 2 | 4 | 1 | 5 | 2 | 3 | 56.67% | #NAME?
2 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 46.67% | #NAME? | 3 | 3 | 1 | 1 | 4 | 5 | 56.67% | #NAME?
4 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 3 | 44.44% | #NAME? | 1 | 1 | 1 | 5 | 3 | 2 | 43.33% | #NAME?
3 | 4 | 1 | 1 | 2 | 5 | 4 | 3 | 1 | 53.33% | #NAME? | 2 | 1 | 1 | 3 | 1 | 2 | 33.33% | #NAME?
3 | 5 | 1 | 5 | 2 | 2 | 1 | 2 | 5 | 57.78% | #NAME? | 1 | 1 | 1 | 2 | 4 | 2 | 36.67% | #NAME?
3 | 1 | 3 | 1 | 4 | 1 | 2 | 1 | 3 | 42.22% | #NAME? | 2 | 2 | 1 | 4 | 2 | 3 | 46.67% | #NAME?
5 | 3 | 3 | 1 | 5 | 3 | 2 | 5 | 5 | 71.11% | #NAME? | 1 | 2 | 1 | 2 | 2 | 3 | 36.67% | #NAME?
5 | 2 | 1 | 2 | 5 | 4 | 4 | 5 | 5 | 73.33% | #NAME? | 5 | 4 | 1 | 5 | 3 | 5 | 76.67% | #NAME?
5 | 1 | 1 | 5 | 1 | 4 | 2 | 1 | 2 | 48.89% | #NAME? | 4 | 2 | 1 | 1 | 3 | 3 | 46.67% | #NAME?
3 | 2 | 3 | 1 | 5 | 4 | 3 | 1 | 2 | 53.33% | #NAME? | 3 | 3 | 5 | 4 | 1 | 2 | 60% | #NAME?
5 | 4 | 3 | 2 | 1 | 4 | 2 | 4 | 4 | 64.44% | #NAME? | 3 | 4 | 5 | 3 | 5 | 5 | 83.33% | #NAME?
4 | 5 | 2 | 4 | 2 | 3 | 5 | 5 | 3 | 73.33% | #NAME? | 4 | 3 | 5 | 4 | 1 | 2 | 63.33% | #NAME?
4 | 3 | 4 | 3 | 3 | 3 | 1 | 1 | 2 | 53.33% | #NAME? | 3 | 2 | 1 | 1 | 2 | 3 | 40% | #NAME?
4 | 1 | 1 | 3 | 1 | 1 | 2 | 5 | 2 | 44.44% | #NAME? | 2 | 4 | 1 | 1 | 2 | 2 | 40% | #NAME?
3 | 3 | 2 | 5 | 5 | 2 | 2 | 1 | 3 | 57.78% | #NAME? | 5 | 2 | 1 | 5 | 5 | 4 | 73.33% | #NAME?
1 | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 35.56% | #NAME? | 5 | 1 | 1 | 2 | 4 | 2 | 50% | #NAME?
1 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 40% | #NAME? | 3 | 3 | 1 | 3 | 1 | 4 | 50% | #NAME?
2 | 2 | 1 | 1 | 2 | 2 | 5 | 3 | 5 | 51.11% | #NAME? | 4 | 5 | 5 | 1 | 3 | 2 | 66.67% | #NAME?
4 | 2 | 2 | 2 | 5 | 3 | 3 | 5 | 4 | 66.67% | #NAME? | 1 | 2 | 1 | 4 | 5 | 4 | 56.67% | #NAME?
2 | 4 | 2 | 2 | 2 | 5 | 1 | 2 | 5 | 55.56% | #NAME? | 5 | 5 | 5 | 1 | 4 | 3 | 76.67% | #NAME?
1 | 5 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 37.78% | #NAME? | 4 | 5 | 5 | 1 | 4 | 5 | 80% | #NAME?
2 | 4 | 1 | 2 | 5 | 3 | 2 | 2 | 4 | 55.56% | #NAME? | 3 | 5 | 5 | 5 | 3 | 4 | 83.33% | #NAME?
2 | 1 | 3 | 2 | 5 | 2 | 3 | 2 | 1 | 46.67% | #NAME? | 2 | 3 | 1 | 2 | 1 | 2 | 36.67% | #NAME?
2 | 1 | 3 | 2 | 4 | 2 | 5 | 1 | 3 | 51.11% | #NAME? | 2 | 4 | 1 | 2 | 5 | 1 | 50% | #NAME?
5 | 5 | 3 | 1 | 3 | 4 | 1 | 1 | 1 | 53.33% | #NAME? | 2 | 2 | 1 | 5 | 5 | 2 | 56.67% | #NAME?
1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 24.44% | #NAME? | 2 | 2 | 1 | 5 | 4 | 3 | 56.67% | #NAME?
3 | 1 | 4 | 3 | 5 | 3 | 5 | 4 | 1 | 64.44% | #NAME? | 5 | 2 | 1 | 2 | 1 | 1 | 40% | #NAME?
1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 24.44% | #NAME? | 3 | 3 | 1 | 1 | 4 | 2 | 46.67% | #NAME?
5 | 5 | 4 | 3 | 5 | 2 | 3 | 4 | 1 | 71.11% | #NAME? | 1 | 3 | 1 | 1 | 3 | 1 | 33.33% | #NAME?
3 | 5 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 68.89% | #NAME? | 1 | 4 | 1 | 4 | 2 | 2 | 46.67% | #NAME?
2 | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 5 | 44.44% | #NAME? | 3 | 1 | 1 | 4 | 3 | 5 | 56.67% | #NAME?
4 | 2 | 2 | 4 | 3 | 5 | 3 | 5 | 3 | 68.89% | #NAME? | 4 | 1 | 1 | 5 | 5 | 1 | 56.67% | #NAME?
3 | 3 | 2 | 4 | 2 | 5 | 1 | 2 | 1 | 51.11% | #NAME? | 3 | 1 | 1 | 3 | 4 | 5 | 56.67% | #NAME?
2 | 5 | 3 | 3 | 4 | 1 | 2 | 3 | 4 | 60% | #NAME? | 3 | 3 | 1 | 4 | 3 | 2 | 53.33% | #NAME?
2 | 2 | 2 | 1 | 2 | 4 | 5 | 1 | 2 | 46.67% | #NAME? | 2 | 3 | 1 | 5 | 1 | 5 | 56.67% | #NAME?
5 | 1 | 3 | 4 | 3 | 2 | 2 | 1 | 2 | 51.11% | #NAME? | 4 | 3 | 1 | 4 | 1 | 2 | 50% | #NAME?
3 | 1 | 4 | 3 | 1 | 5 | 2 | 5 | 3 | 60% | #NAME? | 2 | 4 | 1 | 5 | 5 | 4 | 70% | #NAME?
5 | 5 | 3 | 2 | 4 | 5 | 4 | 4 | 4 | 80% | #NAME? | 2 | 1 | 1 | 1 | 5 | 2 | 40% | #NAME?
2 | 2 | 2 | 3 | 2 | 3 | 5 | 1 | 2 | 48.89% | #NAME? | 3 | 2 | 1 | 5 | 2 | 1 | 46.67% | #NAME?
2 | 3 | 3 | 2 | 3 | 1 | 3 | 1 | 1 | 42.22% | #NAME? | 4 | 5 | 1 | 4 | 1 | 5 | 66.67% | #NAME?
1 | 1 | 2 | 2 | 2 | 5 | 3 | 1 | 1 | 40% | #NAME? | 5 | 4 | 5 | 3 | 2 | 2 | 70% | #NAME?
3 | 2 | 1 | 1 | 2 | 1 | 4 | 3 | 4 | 46.67% | #NAME? | 4 | 2 | 1 | 2 | 4 | 2 | 50% | #NAME?
3 | 3 | 4 | 1 | 2 | 2 | 3 | 1 | 1 | 44.44% | #NAME? | 5 | 5 | 1 | 1 | 3 | 5 | 66.67% | #NAME?
2 | 4 | 2 | 5 | 2 | 1 | 2 | 2 | 2 | 48.89% | #NAME? | 4 | 2 | 5 | 1 | 3 | 1 | 53.33% | #NAME?
5 | 4 | 2 | 1 | 5 | 4 | 4 | 5 | 3 | 73.33% | #NAME? | 5 | 5 | 5 | 2 | 5 | 4 | 86.67% | #NAME?
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | #NAME? | 2 | 3 | 1 | 3 | 5 | 5 | 63.33% | #NAME?
2 | 1 | 2 | 1 | 4 | 2 | 3 | 1 | 5 | 46.67% | #NAME? | 3 | 1 | 1 | 3 | 4 | 4 | 53.33% | #NAME?
3 | 2 | 4 | 4 | 1 | 1 | 2 | 5 | 2 | 53.33% | #NAME? | 4 | 5 | 5 | 1 | 4 | 2 | 70% | #NAME?
3 | 1 | 2 | 1 | 5 | 2 | 1 | 2 | 2 | 42.22% | #NAME? | 2 | 4 | 1 | 3 | 3 | 4 | 56.67% | #NAME?
3 | 4 | 4 | 1 | 2 | 4 | 4 | 2 | 1 | 55.56% | #NAME? | 2 | 1 | 1 | 1 | 1 | 3 | 30% | #NAME?
4 | 3 | 2 | 4 | 5 | 2 | 1 | 2 | 5 | 62.22% | #NAME? | 5 | 2 | 1 | 1 | 4 | 4 | 56.67% | #NAME?
4 | 5 | 2 | 2 | 2 | 2 | 1 | 1 | 4 | 51.11% | #NAME? | 1 | 1 | 1 | 3 | 1 | 4 | 36.67% | #NAME?
2 | 1 | 2 | 2 | 5 | 4 | 4 | 3 | 4 | 60% | #NAME? | 5 | 3 | 1 | 2 | 1 | 2 | 46.67% | #NAME?
3 | 2 | 2 | 3 | 5 | 3 | 2 | 4 | 5 | 64.44% | #NAME? | 2 | 2 | 1 | 3 | 5 | 2 | 50% | #NAME?
4 | 5 | 1 | 4 | 5 | 4 | 5 | 1 | 2 | 68.89% | #NAME? | 2 | 3 | 1 | 4 | 1 | 4 | 50% | #NAME?
2 | 2 | 3 | 1 | 4 | 3 | 4 | 1 | 2 | 48.89% | #NAME? | 4 | 5 | 1 | 4 | 3 | 1 | 60% | #NAME?
3 | 5 | 3 | 1 | 4 | 1 | 5 | 4 | 5 | 68.89% | #NAME? | 5 | 5 | 1 | 2 | 5 | 4 | 73.33% | #NAME?
4 | 3 | 4 | 2 | 3 | 3 | 4 | 2 | 1 | 57.78% | #NAME? | 4 | 4 | 1 | 2 | 2 | 2 | 50% | #NAME?
3 | 2 | 1 | 2 | 5 | 5 | 3 | 1 | 4 | 57.78% | #NAME? | 3 | 5 | 1 | 5 | 4 | 1 | 63.33% | #NAME?
1 | 2 | 2 | 3 | 2 | 3 | 5 | 1 | 1 | 44.44% | #NAME? | 4 | 2 | 1 | 5 | 5 | 1 | 60% | #NAME?
4 | 1 | 3 | 3 | 4 | 3 | 4 | 3 | 3 | 62.22% | #NAME? | 3 | 5 | 1 | 2 | 1 | 5 | 56.67% | #NAME?
3 | 2 | 1 | 5 | 3 | 3 | 1 | 1 | 1 | 44.44% | #NAME? | 3 | 5 | 1 | 5 | 1 | 4 | 63.33% | #NAME?
5 | 2 | 1 | 4 | 4 | 2 | 1 | 3 | 5 | 60% | #NAME? | 2 | 5 | 1 | 2 | 3 | 5 | 60% | #NAME?
5 | 1 | 4 | 2 | 2 | 4 | 5 | 4 | 2 | 64.44% | #NAME? | 1 | 3 | 1 | 5 | 5 | 2 | 56.67% | #NAME?
5 | 2 | 2 | 5 | 5 | 2 | 5 | 2 | 2 | 66.67% | #NAME? | 2 | 3 | 1 | 2 | 1 | 4 | 43.33% | #NAME?
1 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 2 | 35.56% | #NAME? | 1 | 1 | 1 | 3 | 2 | 3 | 36.67% | #NAME?
4 | 4 | 3 | 5 | 4 | 2 | 1 | 4 | 4 | 68.89% | #NAME? | 3 | 2 | 1 | 1 | 3 | 3 | 43.33% | #NAME?
5 | 5 | 3 | 4 | 4 | 5 | 5 | 3 | 5 | 86.67% | #NAME? | 2 | 4 | 1 | 1 | 5 | 1 | 46.67% | #NAME?
5 | 3 | 4 | 1 | 1 | 4 | 4 | 3 | 1 | 57.78% | #NAME? | 5 | 2 | 1 | 5 | 4 | 5 | 73.33% | #NAME?
3 | 1 | 1 | 3 | 3 | 3 | 3 | 4 | 3 | 53.33% | #NAME? | 1 | 5 | 1 | 2 | 3 | 4 | 53.33% | #NAME?
3 | 1 | 3 | 2 | 5 | 5 | 5 | 4 | 5 | 73.33% | #NAME? | 4 | 3 | 1 | 1 | 2 | 1 | 40% | #NAME?
5 | 4 | 3 | 3 | 4 | 4 | 2 | 3 | 3 | 68.89% | #NAME? | 5 | 3 | 1 | 5 | 4 | 3 | 70% | #NAME?
2 | 1 | 1 | 1 | 3 | 5 | 2 | 1 | 3 | 42.22% | #NAME? | 5 | 4 | 5 | 4 | 2 | 1 | 70% | #NAME?
3 | 5 | 2 | 5 | 1 | 2 | 4 | 2 | 1 | 55.56% | #NAME? | 3 | 4 | 1 | 1 | 2 | 5 | 53.33% | #NAME?
2 | 5 | 2 | 2 | 2 | 1 | 4 | 1 | 5 | 53.33% | #NAME? | 4 | 2 | 1 | 1 | 2 | 3 | 43.33% | #NAME?
3 | 1 | 4 | 4 | 3 | 5 | 4 | 2 | 4 | 66.67% | #NAME? | 4 | 5 | 5 | 4 | 5 | 3 | 86.67% | #NAME?
2 | 4 | 2 | 1 | 4 | 2 | 5 | 1 | 5 | 57.78% | #NAME? | 3 | 1 | 1 | 3 | 5 | 5 | 60% | #NAME?
3 | 2 | 4 | 3 | 1 | 3 | 3 | 2 | 4 | 55.56% | #NAME? | 3 | 5 | 1 | 3 | 1 | 2 | 50% | #NAME?
3 | 5 | 2 | 5 | 4 | 4 | 1 | 2 | 5 | 68.89% | #NAME? | 3 | 5 | 1 | 4 | 5 | 5 | 76.67% | #NAME?
2 | 2 | 1 | 1 | 4 | 4 | 3 | 2 | 1 | 44.44% | #NAME? | 5 | 1 | 1 | 2 | 2 | 2 | 43.33% | #NAME?
5 | 5 | 2 | 1 | 5 | 2 | 5 | 2 | 4 | 68.89% | #NAME? | 4 | 4 | 5 | 5 | 5 | 1 | 80% | #NAME?
1 | 5 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 48.89% | #NAME? | 1 | 2 | 1 | 5 | 4 | 3 | 53.33% | #NAME?
3 | 5 | 3 | 3 | 2 | 4 | 2 | 3 | 2 | 60% | #NAME? | 4 | 1 | 1 | 1 | 5 | 1 | 43.33% | #NAME?
1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 28.89% | #NAME? | 2 | 3 | 1 | 1 | 1 | 2 | 33.33% | #NAME?
2 | 4 | 3 | 2 | 3 | 4 | 5 | 1 | 5 | 64.44% | #NAME? | 3 | 2 | 1 | 2 | 5 | 3 | 53.33% | #NAME?
2 | 4 | 3 | 1 | 4 | 5 | 5 | 2 | 4 | 66.67% | #NAME? | 5 | 4 | 1 | 5 | 1 | 3 | 63.33% | #NAME?
5 | 4 | 2 | 4 | 3 | 2 | 5 | 4 | 3 | 71.11% | #NAME? | 1 | 2 | 1 | 3 | 4 | 1 | 40% | #NAME?
5 | 3 | 3 | 3 | 4 | 5 | 3 | 3 | 1 | 66.67% | #NAME? | 2 | 4 | 1 | 1 | 2 | 3 | 43.33% | #NAME?
1 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 35.56% | #NAME? | 2 | 4 | 1 | 5 | 2 | 5 | 63.33% | #NAME?
2 | 1 | 3 | 1 | 4 | 2 | 3 | 2 | 5 | 51.11% | #NAME? | 5 | 3 | 1 | 3 | 5 | 5 | 73.33% | #NAME?
1 | 2 | 3 | 3 | 5 | 3 | 1 | 2 | 2 | 48.89% | #NAME? | 2 | 4 | 1 | 2 | 5 | 3 | 56.67% | #NAME?
3 | 3 | 1 | 4 | 2 | 5 | 1 | 4 | 4 | 60% | #NAME? | 2 | 3 | 1 | 5 | 1 | 3 | 50% | #NAME?
1 | 1 | 1 | 1 | 4 | 1 | 4 | 2 | 1 | 35.56% | #NAME? | 1 | 4 | 1 | 5 | 5 | 3 | 63.33% | #NAME?
5 | 4 | 2 | 5 | 3 | 3 | 3 | 3 | 2 | 66.67% | #NAME? | 2 | 2 | 1 | 4 | 2 | 1 | 40% | #NAME?
4 | 5 | 3 | 1 | 1 | 3 | 5 | 5 | 1 | 62.22% | #NAME? | 1 | 5 | 1 | 5 | 2 | 4 | 60% | #NAME?
4 | 1 | 1 | 4 | 3 | 3 | 4 | 1 | 2 | 51.11% | #NAME? | 5 | 2 | 1 | 5 | 3 | 4 | 66.67% | #NAME?
5 | 3 | 3 | 1 | 3 | 4 | 1 | 4 | 2 | 57.78% | #NAME? | 4 | 4 | 1 | 1 | 1 | 2 | 43.33% | #NAME?
1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 24.44% | #NAME? | 1 | 1 | 1 | 1 | 1 | 2 | 23.33% | #NAME?
2 | 4 | 1 | 3 | 2 | 1 | 4 | 2 | 3 | 48.89% | #NAME? | 1 | 4 | 1 | 5 | 3 | 3 | 56.67% | #NAME?
3 | 3 | 2 | 3 | 3 | 1 | 1 | 2 | 2 | 44.44% | #NAME? | 2 | 2 | 1 | 5 | 3 | 5 | 60% | #NAME?
4 | 3 | 3 | 3 | 2 | 5 | 2 | 5 | 1 | 62.22% | #NAME? | 1 | 4 | 1 | 5 | 4 | 3 | 60% | #NAME?
4 | 4 | 2 | 5 | 2 | 3 | 4 | 2 | 2 | 62.22% | #NAME? | 1 | 3 | 1 | 2 | 4 | 3 | 46.67% | #NAME?
2 | 2 | 1 | 1 | 4 | 1 | 2 | 3 | 5 | 46.67% | #NAME? | 1 | 1 | 1 | 2 | 1 | 1 | 23.33% | #NAME?
3 | 5 | 2 | 5 | 5 | 2 | 5 | 2 | 1 | 66.67% | #NAME? | 5 | 3 | 1 | 4 | 4 | 5 | 73.33% | #NAME?
1 | 3 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 40% | #NAME? | 5 | 5 | 5 | 1 | 2 | 3 | 70% | #NAME?
4 | 4 | 3 | 1 | 4 | 3 | 4 | 1 | 4 | 62.22% | #NAME? | 5 | 1 | 1 | 4 | 2 | 3 | 53.33% | #NAME?
5 | 5 | 3 | 1 | 5 | 5 | 4 | 5 | 5 | 84.44% | #NAME? | 4 | 2 | 1 | 5 | 3 | 4 | 63.33% | #NAME?
2 | 2 | 3 | 2 | 1 | 1 | 5 | 2 | 5 | 51.11% | #NAME? | 3 | 4 | 1 | 3 | 1 | 5 | 56.67% | #NAME?
3 | 5 | 4 | 2 | 1 | 3 | 5 | 4 | 1 | 62.22% | #NAME? | 4 | 2 | 1 | 3 | 3 | 5 | 60% | #NAME?
3 | 5 | 2 | 4 | 2 | 2 | 3 | 3 | 2 | 57.78% | #NAME? | 4 | 5 | 5 | 4 | 3 | 5 | 86.67% | #NAME?
5 | 5 | 3 | 2 | 4 | 3 | 4 | 1 | 3 | 66.67% | #NAME? | 2 | 1 | 1 | 5 | 4 | 5 | 60% | #NAME?
3 | 2 | 2 | 3 | 5 | 3 | 1 | 3 | 1 | 51.11% | #NAME? | 2 | 5 | 1 | 5 | 4 | 3 | 66.67% | #NAME?
5 | 1 | 4 | 4 | 4 | 5 | 4 | 3 | 5 | 77.78% | #NAME? | 4 | 1 | 1 | 1 | 1 | 1 | 30% | #NAME?
5 | 5 | 4 | 2 | 1 | 4 | 2 | 2 | 5 | 66.67% | #NAME? | 5 | 4 | 5 | 3 | 1 | 2 | 66.67% | #NAME?
1 | 2 | 2 | 1 | 1 | 5 | 1 | 2 | 2 | 37.78% | #NAME? | 2 | 3 | 1 | 4 | 2 | 1 | 43.33% | #NAME?
3 | 4 | 5 | 2 | 3 | 1 | 1 | 3 | 5 | 60% | #NAME? | 4 | 2 | 1 | 5 | 5 | 3 | 66.67% | #NAME?
5 | 5 | 3 | 3 | 4 | 5 | 1 | 4 | 3 | 73.33% | #NAME? | 2 | 4 | 1 | 1 | 5 | 2 | 50% | #NAME?
5 | 4 | 1 | 3 | 5 | 5 | 4 | 2 | 2 | 68.89% | #NAME? | 1 | 5 | 1 | 5 | 3 | 2 | 56.67% | #NAME?
1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 33.33% | #NAME? | 5 | 3 | 1 | 4 | 3 | 1 | 56.67% | #NAME?
1 | 1 | 3 | 1 | 5 | 1 | 3 | 1 | 3 | 42.22% | #NAME? | 2 | 4 | 1 | 4 | 5 | 4 | 66.67% | #NAME?
1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 31.11% | #NAME? | 4 | 2 | 1 | 3 | 1 | 1 | 40% | #NAME?
3 | 3 | 3 | 3 | 4 | 3 | 4 | 5 | 3 | 68.89% | #NAME? | 1 | 1 | 1 | 4 | 1 | 4 | 40% | #NAME?
2 | 2 | 1 | 2 | 4 | 2 | 2 | 2 | 2 | 42.22% | #NAME? | 2 | 5 | 1 | 2 | 2 | 5 | 56.67% | #NAME?
3 | 5 | 3 | 1 | 5 | 5 | 5 | 5 | 4 | 80% | #NAME? | 5 | 3 | 1 | 3 | 4 | 2 | 60% | #NAME?
4 | 4 | 2 | 1 | 1 | 2 | 5 | 5 | 5 | 64.44% | #NAME? | 2 | 3 | 1 | 2 | 5 | 3 | 53.33% | #NAME?
3 | 4 | 2 | 2 | 2 | 2 | 4 | 3 | 2 | 53.33% | #NAME? | 1 | 5 | 1 | 3 | 3 | 1 | 46.67% | #NAME?
1 | 3 | 1 | 3 | 3 | 2 | 5 | 2 | 1 | 46.67% | #NAME? | 1 | 5 | 1 | 4 | 2 | 1 | 46.67% | #NAME?
2 | 4 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 40% | #NAME? | 2 | 1 | 1 | 3 | 4 | 1 | 40% | #NAME?
2 | 4 | 1 | 1 | 2 | 2 | 2 | 2 | 5 | 46.67% | #NAME? | 5 | 1 | 1 | 5 | 3 | 5 | 66.67% | #NAME?
4 | 5 | 1 | 1 | 1 | 5 | 3 | 4 | 5 | 64.44% | #NAME? | 5 | 4 | 1 | 2 | 3 | 3 | 60% | #NAME?
3 | 5 | 4 | 1 | 2 | 2 | 3 | 2 | 5 | 60% | #NAME? | 4 | 5 | 5 | 3 | 4 | 5 | 86.67% | #NAME?
2 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 31.11% | #NAME? | 2 | 2 | 1 | 1 | 2 | 3 | 36.67% | #NAME?
1 | 4 | 2 | 2 | 1 | 2 | 4 | 2 | 2 | 44.44% | #NAME? | 4 | 4 | 1 | 5 | 3 | 3 | 66.67% | #NAME?
4 | 4 | 4 | 4 | 3 | 3 | 4 | 3 | 1 | 66.67% | #NAME? | 2 | 2 | 1 | 1 | 2 | 1 | 30% | #NAME?
2 | 2 | 1 | 3 | 2 | 4 | 3 | 2 | 5 | 53.33% | #NAME? | 5 | 5 | 1 | 3 | 3 | 2 | 63.33% | #NAME?
3 | 2 | 1 | 1 | 2 | 1 | 3 | 4 | 4 | 46.67% | #NAME? | 4 | 1 | 1 | 4 | 1 | 4 | 50% | #NAME?
2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 4 | 37.78% | #NAME? | 4 | 4 | 5 | 5 | 2 | 3 | 76.67% | #NAME?
3 | 4 | 2 | 2 | 4 | 3 | 4 | 3 | 2 | 60% | #NAME? | 3 | 1 | 1 | 1 | 4 | 1 | 36.67% | #NAME?
2 | 5 | 1 | 1 | 4 | 4 | 4 | 2 | 2 | 55.56% | #NAME? | 1 | 2 | 1 | 2 | 4 | 3 | 43.33% | #NAME?
4 | 1 | 1 | 5 | 4 | 5 | 3 | 2 | 4 | 64.44% | #NAME? | 1 | 5 | 1 | 1 | 2 | 4 | 46.67% | #NAME?
1 | 2 | 3 | 1 | 5 | 3 | 5 | 1 | 2 | 51.11% | #NAME? | 3 | 3 | 5 | 2 | 3 | 5 | 70% | #NAME?
5 | 5 | 2 | 5 | 3 | 2 | 4 | 4 | 1 | 68.89% | #NAME? | 1 | 2 | 5 | 2 | 4 | 4 | 60% | #NAME?
2 | 1 | 1 | 3 | 5 | 3 | 1 | 1 | 4 | 46.67% | #NAME? | 1 | 1 | 5 | 2 | 2 | 3 | 46.67% | #NAME?
2 | 5 | 3 | 1 | 4 | 4 | 5 | 2 | 2 | 62.22% | #NAME? | 5 | 2 | 5 | 3 | 4 | 1 | 66.67% | #NAME?
1 | 4 | 1 | 3 | 2 | 4 | 4 | 1 | 3 | 51.11% | #NAME? | 1 | 1 | 1 | 1 | 2 | 4 | 33.33% | #NAME?
4 | 5 | 2 | 3 | 2 | 4 | 5 | 3 | 4 | 71.11% | #NAME? | 3 | 5 | 1 | 3 | 5 | 5 | 73.33% | #NAME?
4 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 4 | 44.44% | #NAME? | 3 | 1 | 1 | 5 | 1 | 3 | 46.67% | #NAME?
5 | 1 | 4 | 5 | 2 | 2 | 3 | 1 | 4 | 60% | #NAME? | 1 | 3 | 1 | 5 | 3 | 2 | 50% | #NAME?
4 | 3 | 4 | 5 | 1 | 3 | 4 | 1 | 1 | 57.78% | #NAME? | 5 | 4 | 1 | 4 | 3 | 2 | 63.33% | #NAME?
5 | 5 | 4 | 3 | 4 | 4 | 1 | 2 | 3 | 68.89% | #NAME? | 3 | 1 | 1 | 2 | 3 | 3 | 43.33% | #NAME?
1 | 5 | 3 | 1 | 4 | 2 | 1 | 1 | 2 | 44.44% | #NAME? | 4 | 5 | 1 | 4 | 2 | 3 | 63.33% | #NAME?
1 | 5 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 35.56% | #NAME? | 2 | 5 | 1 | 5 | 5 | 2 | 66.67% | #NAME?
1 | 3 | 3 | 2 | 2 | 3 | 5 | 1 | 3 | 51.11% | #NAME? | 1 | 1 | 1 | 5 | 2 | 4 | 46.67% | #NAME?
3 | 5 | 2 | 3 | 2 | 2 | 2 | 4 | 2 | 55.56% | #NAME? | 1 | 5 | 1 | 3 | 4 | 2 | 53.33% | #NAME?
5 | 3 | 4 | 2 | 5 | 4 | 2 | 3 | 3 | 68.89% | #NAME? | 2 | 3 | 1 | 5 | 2 | 1 | 46.67% | #NAME?
4 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 37.78% | #NAME? | 4 | 3 | 1 | 3 | 3 | 2 | 53.33% | #NAME?
4 | 5 | 4 | 5 | 5 | 4 | 3 | 1 | 1 | 71.11% | #NAME? | 5 | 2 | 1 | 5 | 1 | 5 | 63.33% | #NAME?
4 | 4 | 2 | 4 | 4 | 3 | 3 | 5 | 3 | 71.11% | #NAME? | 5 | 5 | 1 | 1 | 1 | 2 | 50% | #NAME?
2 | 1 | 3 | 2 | 1 | 4 | 5 | 2 | 2 | 48.89% | #NAME? | 5 | 4 | 1 | 5 | 1 | 5 | 70% | #NAME?
1 | 5 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 35.56% | #NAME? | 5 | 5 | 5 | 4 | 3 | 1 | 76.67% | #NAME?
4 | 1 | 2 | 3 | 3 | 2 | 3 | 2 | 4 | 53.33% | #NAME? | 3 | 4 | 1 | 4 | 4 | 4 | 66.67% | #NAME?
4 | 2 | 1 | 2 | 2 | 5 | 5 | 2 | 2 | 55.56% | #NAME? | 2 | 3 | 1 | 3 | 1 | 2 | 40% | #NAME?
3 | 3 | 2 | 5 | 2 | 4 | 1 | 5 | 5 | 66.67% | #NAME? | 3 | 1 | 1 | 5 | 5 | 5 | 66.67% | #NAME?
1 | 2 | 1 | 1 | 1 | 4 | 3 | 3 | 3 | 42.22% | #NAME? | 3 | 3 | 1 | 2 | 1 | 3 | 43.33% | #NAME?
5 | 2 | 3 | 1 | 3 | 1 | 4 | 5 | 1 | 55.56% | #NAME? | 4 | 1 | 1 | 1 | 4 | 3 | 46.67% | #NAME?
5 | 3 | 1 | 2 | 3 | 2 | 1 | 4 | 1 | 48.89% | #NAME? | 2 | 1 | 1 | 1 | 5 | 4 | 46.67% | #NAME?
5 | 4 | 2 | 1 | 1 | 1 | 1 | 5 | 3 | 51.11% | #NAME? | 1 | 2 | 1 | 3 | 4 | 5 | 53.33% | #NAME?
5 | 3 | 4 | 5 | 1 | 2 | 2 | 1 | 2 | 55.56% | #NAME? | 1 | 5 | 1 | 4 | 3 | 1 | 50% | #NAME?
3 | 2 | 4 | 4 | 4 | 4 | 1 | 1 | 2 | 55.56% | #NAME? | 4 | 4 | 1 | 4 | 4 | 2 | 63.33% | #NAME?
3 | 3 | 4 | 3 | 1 | 1 | 2 | 3 | 5 | 55.56% | #NAME? | 1 | 2 | 1 | 5 | 4 | 3 | 53.33% | #NAME?
3 | 2 | 2 | 4 | 1 | 1 | 5 | 4 | 5 | 60% | #NAME? | 3 | 4 | 1 | 4 | 1 | 4 | 56.67% | #NAME?
4 | 5 | 3 | 2 | 2 | 1 | 4 | 1 | 2 | 53.33% | #NAME? | 4 | 1 | 1 | 1 | 4 | 5 | 53.33% | #NAME?
3 | 2 | 3 | 1 | 5 | 4 | 2 | 4 | 3 | 60% | #NAME? | 4 | 2 | 1 | 2 | 2 | 1 | 40% | #NAME?
3 | 4 | 1 | 4 | 4 | 3 | 4 | 2 | 4 | 64.44% | #NAME? | 3 | 4 | 1 | 2 | 5 | 5 | 66.67% | #NAME?
3 | 2 | 3 | 3 | 4 | 1 | 1 | 3 | 1 | 46.67% | #NAME? | 2 | 1 | 1 | 2 | 5 | 3 | 46.67% | #NAME?
3 | 5 | 1 | 4 | 3 | 2 | 2 | 1 | 2 | 51.11% | #NAME? | 1 | 5 | 1 | 1 | 5 | 5 | 60% | #NAME?
4 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 73.33% | #NAME? | 1 | 5 | 1 | 1 | 2 | 1 | 36.67% | #NAME?
5 | 3 | 2 | 2 | 3 | 1 | 5 | 5 | 2 | 62.22% | #NAME? | 3 | 1 | 1 | 1 | 4 | 4 | 46.67% | #NAME?
5 | 5 | 2 | 2 | 5 | 4 | 4 | 1 | 3 | 68.89% | #NAME? | 2 | 2 | 1 | 4 | 2 | 4 | 50% | #NAME?
1 | 1 | 2 | 2 | 1 | 1 | 4 | 1 | 1 | 31.11% | #NAME? | 1 | 1 | 3 | 1 | 1 | 4 | 36.67% | #NAME?
2 | 4 | 1 | 1 | 1 | 5 | 4 | 1 | 4 | 51.11% | #NAME? | 3 | 2 | 5 | 1 | 1 | 1 | 43.33% | #NAME?
4 | 2 | 4 | 3 | 5 | 3 | 1 | 2 | 1 | 55.56% | #NAME? | 3 | 3 | 5 | 4 | 4 | 2 | 70% | #NAME?
5 | 2 | 2 | 1 | 3 | 2 | 5 | 2 | 3 | 55.56% | #NAME? | 5 | 5 | 5 | 3 | 1 | 5 | 80% | #NAME?
1 | 5 | 2 | 1 | 3 | 3 | 5 | 1 | 3 | 53.33% | #NAME? | 1 | 5 | 5 | 1 | 5 | 1 | 60% | #NAME?
5 | 4 | 1 | 5 | 1 | 5 | 2 | 5 | 2 | 66.67% | #NAME? | 4 | 5 | 1 | 4 | 3 | 1 | 60% | #NAME?
4 | 2 | 2 | 5 | 3 | 5 | 3 | 3 | 3 | 66.67% | #NAME? | 1 | 4 | 1 | 1 | 4 | 4 | 50% | #NAME?
1 | 1 | 2 | 2 | 4 | 4 | 3 | 2 | 3 | 48.89% | #NAME? | 1 | 1 | 1 | 2 | 1 | 1 | 23.33% | #NAME?
4 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 40% | #NAME? | 5 | 2 | 1 | 3 | 3 | 3 | 56.67% | #NAME?
2 | 5 | 1 | 3 | 3 | 2 | 3 | 1 | 4 | 53.33% | #NAME? | 2 | 3 | 1 | 5 | 2 | 1 | 46.67% | #NAME?
1 | 3 | 1 | 1 | 4 | 2 | 5 | 2 | 2 | 46.67% | #NAME? | 3 | 5 | 1 | 4 | 1 | 2 | 53.33% | #NAME?
3 | 2 | 2 | 1 | 1 | 5 | 1 | 4 | 2 | 46.67% | #NAME? | 1 | 1 | 1 | 5 | 4 | 1 | 43.33% | #NAME?
4 | 5 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 86.67% | #NAME? | 1 | 1 | 1 | 1 | 1 | 2 | 23.33% | #NAME?
2 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 3 | 46.67% | #NAME? | 2 | 2 | 1 | 5 | 1 | 1 | 40% | #NAME?
4 | 5 | 3 | 1 | 1 | 5 | 3 | 2 | 5 | 64.44% | #NAME? | 4 | 1 | 1 | 5 | 3 | 3 | 56.67% | #NAME?
1 | 5 | 2 | 1 | 5 | 2 | 1 | 3 | 1 | 46.67% | #NAME? | 4 | 1 | 1 | 1 | 2 | 2 | 36.67% | #NAME?
4 | 3 | 4 | 5 | 2 | 5 | 3 | 2 | 5 | 73.33% | #NAME? | 2 | 1 | 1 | 4 | 1 | 3 | 40% | #NAME?
5 | 4 | 3 | 1 | 5 | 1 | 3 | 4 | 4 | 66.67% | #NAME? | 2 | 1 | 1 | 5 | 4 | 2 | 50% | #NAME?
4 | 2 | 1 | 5 | 2 | 5 | 3 | 5 | 4 | 68.89% | #NAME? | 4 | 4 | 1 | 5 | 4 | 4 | 73.33% | #NAME?
1 | 5 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 37.78% | #NAME? | 1 | 1 | 5 | 5 | 5 | 5 | 73.33% | #NAME?
1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 24.44% | #NAME? | 3 | 3 | 5 | 4 | 4 | 3 | 73.33% | #NAME?
4 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 42.22% | #NAME? | 3 | 2 | 5 | 3 | 5 | 2 | 66.67% | #NAME?
4 | 3 | 3 | 1 | 3 | 3 | 3 | 4 | 4 | 62.22% | #NAME? | 1 | 5 | 5 | 5 | 5 | 1 | 73.33% | #NAME?
4 | 5 | 3 | 4 | 3 | 2 | 1 | 2 | 5 | 64.44% | #NAME? | 5 | 3 | 5 | 4 | 5 | 5 | 90% | #NAME?
2 | 4 | 3 | 2 | 1 | 2 | 2 | 3 | 2 | 46.67% | #NAME? | 5 | 5 | 1 | 3 | 5 | 4 | 76.67% | #NAME?
3 | 4 | 2 | 3 | 1 | 1 | 2 | 5 | 2 | 51.11% | #NAME? | 5 | 4 | 1 | 5 | 5 | 4 | 80% | #NAME?
5 | 4 | 1 | 3 | 3 | 5 | 2 | 2 | 3 | 62.22% | #NAME? | 5 | 1 | 1 | 3 | 2 | 4 | 53.33% | #NAME?
1 | 5 | 3 | 2 | 3 | 4 | 2 | 1 | 1 | 48.89% | #NAME? | 2 | 2 | 1 | 5 | 3 | 1 | 46.67% | #NAME?
2 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 33.33% | #NAME? | 1 | 2 | 1 | 4 | 5 | 4 | 56.67% | #NAME?
2 | 5 | 2 | 2 | 5 | 4 | 5 | 3 | 3 | 68.89% | #NAME? | 5 | 4 | 1 | 5 | 1 | 3 | 63.33% | #NAME?
1 | 5 | 2 | 1 | 2 | 2 | 5 | 2 | 2 | 48.89% | #NAME? | 4 | 1 | 1 | 1 | 4 | 2 | 43.33% | #NAME?
1 | 3 | 2 | 2 | 1 | 5 | 4 | 3 | 1 | 48.89% | #NAME? | 5 | 4 | 5 | 4 | 3 | 4 | 83.33% | #NAME?
4 | 3 | 1 | 2 | 4 | 1 | 5 | 4 | 3 | 60% | #NAME? | 5 | 2 | 5 | 4 | 5 | 3 | 80% | #NAME?
4 | 3 | 2 | 4 | 4 | 3 | 5 | 1 | 1 | 60% | #NAME? | 1 | 3 | 5 | 4 | 3 | 4 | 66.67% | #NAME?
4 | 3 | 2 | 1 | 4 | 1 | 2 | 5 | 3 | 55.56% | #NAME? | 5 | 4 | 5 | 1 | 5 | 5 | 83.33% | #NAME?
5 | 4 | 2 | 3 | 3 | 5 | 5 | 4 | 5 | 80% | #NAME? | 5 | 2 | 5 | 3 | 1 | 4 | 66.67% | #NAME?
2 | 5 | 2 | 1 | 4 | 2 | 3 | 2 | 1 | 48.89% | #NAME? | 2 | 2 | 5 | 1 | 3 | 5 | 60% | #NAME?
4 | 2 | 2 | 3 | 3 | 5 | 2 | 5 | 1 | 60% | #NAME? | 2 | 3 | 5 | 5 | 2 | 2 | 63.33% | #NAME?
3 | 2 | 1 | 3 | 3 | 3 | 3 | 5 | 4 | 60% | #NAME? | 4 | 3 | 1 | 5 | 5 | 2 | 66.67% | #NAME?
1 | 5 | 1 | 3 | 3 | 5 | 2 | 1 | 1 | 48.89% | #NAME? | 2 | 5 | 1 | 3 | 1 | 4 | 53.33% | #NAME?
3 | 2 | 3 | 2 | 5 | 5 | 2 | 5 | 5 | 71.11% | #NAME? | 5 | 2 | 1 | 5 | 3 | 3 | 63.33% | #NAME?
3 | 2 | 1 | 5 | 5 | 3 | 3 | 2 | 3 | 60% | #NAME? | 2 | 2 | 1 | 4 | 3 | 1 | 43.33% | #NAME?
2 | 5 | 2 | 1 | 4 | 3 | 1 | 1 | 4 | 51.11% | #NAME? | 1 | 4 | 1 | 1 | 1 | 5 | 43.33% | #NAME?
1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 26.67% | #NAME? | 1 | 5 | 1 | 1 | 1 | 4 | 43.33% | #NAME?
3 | 1 | 4 | 2 | 1 | 2 | 2 | 5 | 5 | 55.56% | #NAME? | 3 | 1 | 1 | 4 | 5 | 1 | 50% | #NAME?
2 | 4 | 2 | 1 | 4 | 4 | 3 | 1 | 5 | 57.78% | #NAME? | 5 | 4 | 1 | 1 | 5 | 1 | 56.67% | #NAME?
4 | 4 | 4 | 4 | 5 | 1 | 5 | 3 | 1 | 68.89% | #NAME? | 5 | 2 | 1 | 3 | 3 | 3 | 56.67% | #NAME?
5 | 5 | 3 | 2 | 5 | 4 | 4 | 4 | 5 | 82.22% | #NAME? | 1 | 2 | 1 | 4 | 4 | 5 | 56.67% | #NAME?
4 | 5 | 2 | 4 | 4 | 3 | 5 | 3 | 3 | 73.33% | #NAME? | 5 | 3 | 1 | 4 | 2 | 4 | 63.33% | #NAME?
2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 35.56% | #NAME? | 1 | 2 | 1 | 5 | 2 | 4 | 50% | #NAME?
1 | 3 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 42.22% | #NAME? | 5 | 2 | 1 | 2 | 4 | 2 | 53.33% | #NAME?
2 | 2 | 1 | 1 | 4 | 1 | 3 | 2 | 1 | 37.78% | #NAME? | 4 | 2 | 1 | 3 | 1 | 3 | 46.67% | #NAME?
4 | 3 | 1 | 4 | 3 | 3 | 3 | 5 | 1 | 60% | #NAME? | 2 | 2 | 1 | 2 | 3 | 1 | 36.67% | #NAME?
3 | 2 | 1 | 1 | 3 | 5 | 2 | 1 | 4 | 48.89% | #NAME? | 1 | 2 | 1 | 3 | 5 | 3 | 50% | #NAME?
1 | 3 | 2 | 2 | 1 | 5 | 5 | 1 | 1 | 46.67% | #NAME? | 1 | 1 | 1 | 2 | 3 | 3 | 36.67% | #NAME?
3 | 4 | 2 | 3 | 4 | 3 | 5 | 4 | 4 | 71.11% | #NAME? | 5 | 4 | 1 | 1 | 2 | 1 | 46.67% | #NAME?
1 | 5 | 1 | 3 | 1 | 1 | 4 | 1 | 1 | 40% | #NAME? | 3 | 1 | 1 | 3 | 1 | 3 | 40% | #NAME?
5 | 1 | 4 | 2 | 5 | 4 | 5 | 2 | 2 | 66.67% | #NAME? | 3 | 3 | 1 | 4 | 4 | 2 | 56.67% | #NAME?
4 | 1 | 2 | 5 | 1 | 4 | 3 | 1 | 5 | 57.78% | #NAME? | 1 | 1 | 1 | 1 | 3 | 3 | 33.33% | #NAME?
3 | 3 | 1 | 2 | 3 | 1 | 3 | 4 | 4 | 53.33% | #NAME? | 1 | 5 | 1 | 1 | 2 | 3 | 43.33% | #NAME?
3 | 3 | 1 | 2 | 5 | 2 | 1 | 2 | 4 | 51.11% | #NAME? | 5 | 1 | 1 | 3 | 2 | 4 | 53.33% | #NAME?
2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 4 | 42.22% | #NAME? | 4 | 4 | 1 | 1 | 3 | 4 | 56.67% | #NAME?
4 | 1 | 1 | 4 | 3 | 2 | 4 | 4 | 4 | 60% | #NAME? | 3 | 1 | 1 | 3 | 4 | 3 | 50% | #NAME?
3 | 2 | 2 | 1 | 4 | 2 | 5 | 4 | 2 | 55.56% | #NAME? | 5 | 5 | 1 | 4 | 3 | 2 | 66.67% | #NAME?
1 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 37.78% | #NAME? | 3 | 4 | 1 | 2 | 5 | 4 | 63.33% | #NAME?
5 | 4 | 4 | 1 | 1 | 1 | 3 | 1 | 3 | 51.11% | #NAME? | 2 | 3 | 1 | 2 | 1 | 4 | 43.33% | #NAME?
2 | 3 | 2 | 1 | 5 | 3 | 1 | 1 | 5 | 51.11% | #NAME? | 4 | 4 | 1 | 5 | 5 | 3 | 73.33% | #NAME?
5 | 4 | 4 | 5 | 1 | 2 | 4 | 1 | 1 | 60% | #NAME? | 2 | 5 | 1 | 5 | 2 | 4 | 63.33% | #NAME?
2 | 5 | 1 | 3 | 4 | 1 | 2 | 1 | 2 | 46.67% | #NAME? | 2 | 2 | 1 | 5 | 3 | 4 | 56.67% | #NAME?
4 | 5 | 2 | 3 | 4 | 1 | 4 | 3 | 2 | 62.22% | #NAME? | 3 | 1 | 1 | 4 | 2 | 1 | 40% | #NAME?
5 | 1 | 1 | 1 | 3 | 4 | 1 | 3 | 1 | 44.44% | #NAME? | 4 | 1 | 1 | 1 | 3 | 1 | 36.67% | #NAME?
4 | 3 | 1 | 3 | 2 | 5 | 1 | 5 | 2 | 57.78% | #NAME? | 5 | 5 | 1 | 4 | 2 | 2 | 63.33% | #NAME?
5 | 5 | 3 | 4 | 5 | 2 | 5 | 2 | 1 | 71.11% | #NAME? | 5 | 5 | 1 | 4 | 3 | 4 | 73.33% | #NAME?
3 | 3 | 3 | 2 | 2 | 1 | 4 | 4 | 5 | 60% | #NAME? | 4 | 5 | 1 | 3 | 2 | 4 | 63.33% | #NAME?
1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 24.44% | #NAME? | 4 | 2 | 5 | 1 | 1 | 1 | 46.67% | #NAME?
4 | 3 | 2 | 2 | 1 | 3 | 4 | 1 | 1 | 46.67% | #NAME? | 3 | 3 | 1 | 3 | 4 | 1 | 50% | #NAME?
2 | 5 | 3 | 1 | 3 | 3 | 2 | 2 | 2 | 51.11% | #NAME? | 1 | 4 | 5 | 5 | 4 | 5 | 80% | #NAME?
3 | 2 | 3 | 1 | 1 | 4 | 4 | 4 | 2 | 53.33% | #NAME? | 2 | 5 | 5 | 4 | 2 | 1 | 63.33% | #NAME?
1 | 3 | 2 | 1 | 1 | 3 | 4 | 2 | 2 | 42.22% | #NAME? | 3 | 4 | 5 | 5 | 1 | 3 | 70% | #NAME?
1 | 4 | 3 | 3 | 2 | 5 | 2 | 1 | 2 | 51.11% | #NAME? | 5 | 3 | 1 | 5 | 5 | 2 | 70% | #NAME?
2 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 5 | 40% | #NAME? | 1 | 5 | 1 | 5 | 5 | 5 | 73.33% | #NAME?
1 | 1 | 1 | 1 | 1 | 2 | 5 | 2 | 1 | 33.33% | #NAME? | 5 | 1 | 1 | 3 | 1 | 2 | 43.33% | #NAME?
5 | 2 | 1 | 2 | 3 | 3 | 4 | 5 | 5 | 66.67% | #NAME? | 5 | 1 | 1 | 2 | 5 | 4 | 60% | #NAME?
2 | 3 | 1 | 2 | 3 | 5 | 2 | 2 | 3 | 51.11% | #NAME? | 1 | 3 | 1 | 2 | 5 | 3 | 50% | #NAME?
3 | 4 | 2 | 3 | 1 | 2 | 5 | 1 | 4 | 55.56% | #NAME? | 5 | 4 | 1 | 4 | 2 | 3 | 63.33% | #NAME?
4 | 1 | 1 | 1 | 5 | 1 | 4 | 4 | 3 | 53.33% | #NAME? | 5 | 4 | 1 | 1 | 3 | 1 | 50% | #NAME?
5 | 2 | 3 | 4 | 1 | 4 | 3 | 4 | 2 | 62.22% | #NAME? | 4 | 1 | 1 | 3 | 3 | 5 | 56.67% | #NAME?
2 | 2 | 2 | 3 | 1 | 3 | 4 | 1 | 4 | 48.89% | #NAME? | 2 | 4 | 1 | 5 | 2 | 3 | 56.67% | #NAME?
2 | 5 | 2 | 2 | 1 | 1 | 2 | 3 | 5 | 51.11% | #NAME? | 1 | 4 | 5 | 1 | 3 | 3 | 56.67% | #NAME?
3 | 1 | 1 | 1 | 4 | 4 | 4 | 3 | 2 | 51.11% | #NAME? | 5 | 2 | 5 | 1 | 2 | 1 | 53.33% | #NAME?
3 | 3 | 1 | 3 | 4 | 1 | 1 | 1 | 1 | 40% | #NAME? | 2 | 5 | 5 | 2 | 1 | 1 | 53.33% | #NAME?
5 | 2 | 4 | 5 | 4 | 4 | 1 | 1 | 3 | 64.44% | #NAME? | 2 | 5 | 1 | 5 | 2 | 2 | 56.67% | #NAME?
2 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 4 | 44.44% | #NAME? | 1 | 5 | 5 | 5 | 1 | 4 | 70% | #NAME?
3 | 5 | 2 | 5 | 5 | 3 | 4 | 2 | 1 | 66.67% | #NAME? | 1 | 3 | 5 | 4 | 2 | 2 | 56.67% | #NAME?
5 | 2 | 4 | 1 | 3 | 2 | 3 | 3 | 1 | 53.33% | #NAME? | 3 | 2 | 1 | 2 | 1 | 3 | 40% | #NAME?
3 | 5 | 2 | 2 | 4 | 4 | 5 | 5 | 4 | 75.56% | #NAME? | 1 | 4 | 1 | 1 | 5 | 5 | 56.67% | #NAME?
5 | 2 | 4 | 3 | 3 | 4 | 4 | 1 | 1 | 60% | #NAME? | 2 | 1 | 1 | 2 | 5 | 1 | 40% | #NAME?
2 | 2 | 1 | 1 | 5 | 3 | 2 | 2 | 3 | 46.67% | #NAME? | 1 | 1 | 1 | 2 | 5 | 4 | 46.67% | #NAME?
5 | 3 | 1 | 2 | 1 | 1 | 5 | 4 | 2 | 53.33% | #NAME? | 2 | 4 | 1 | 2 | 3 | 2 | 46.67% | #NAME?
1 | 2 | 3 | 2 | 4 | 5 | 3 | 1 | 1 | 48.89% | #NAME? | 4 | 4 | 1 | 1 | 1 | 3 | 46.67% | #NAME?
1 | 3 | 3 | 2 | 1 | 2 | 5 | 1 | 1 | 42.22% | #NAME? | 5 | 3 | 1 | 3 | 4 | 1 | 56.67% | #NAME?
3 | 5 | 2 | 1 | 2 | 5 | 2 | 3 | 5 | 62.22% | #NAME? | 4 | 2 | 5 | 3 | 3 | 4 | 70% | #NAME?
2 | 1 | 1 | 1 | 4 | 3 | 5 | 3 | 2 | 48.89% | #NAME? | 1 | 3 | 5 | 2 | 5 | 3 | 63.33% | #NAME?
4 | 1 | 4 | 3 | 1 | 4 | 4 | 4 | 4 | 64.44% | #NAME? | 2 | 2 | 5 | 3 | 5 | 5 | 73.33% | #NAME?
2 | 1 | 1 | 1 | 2 | 4 | 5 | 2 | 2 | 44.44% | #NAME? | 5 | 3 | 1 | 1 | 3 | 3 | 53.33% | #NAME?
4 | 2 | 3 | 3 | 3 | 4 | 1 | 4 | 1 | 55.56% | #NAME? | 5 | 1 | 1 | 3 | 3 | 1 | 46.67% | #NAME?
5 | 1 | 3 | 5 | 3 | 1 | 5 | 3 | 1 | 60% | #NAME? | 2 | 3 | 1 | 2 | 3 | 1 | 40% | #NAME?
1 | 3 | 2 | 1 | 4 | 5 | 2 | 3 | 3 | 53.33% | #NAME? | 4 | 1 | 1 | 5 | 5 | 5 | 70% | #NAME?
1 | 4 | 1 | 1 | 5 | 2 | 2 | 2 | 3 | 46.67% | #NAME? | 2 | 3 | 1 | 2 | 5 | 2 | 50% | #NAME?
3 | 1 | 1 | 1 | 5 | 1 | 4 | 2 | 3 | 46.67% | #NAME? | 2 | 2 | 1 | 4 | 3 | 4 | 53.33% | #NAME?
3 | 3 | 4 | 2 | 2 | 3 | 1 | 2 | 2 | 48.89% | #NAME? | 3 | 3 | 1 | 5 | 5 | 5 | 73.33% | #NAME?
5 | 2 | 4 | 1 | 5 | 2 | 5 | 5 | 2 | 68.89% | #NAME? | 3 | 3 | 1 | 2 | 2 | 4 | 50% | #NAME?
2 | 4 | 1 | 2 | 2 | 2 | 5 | 1 | 1 | 44.44% | #NAME? | 5 | 3 | 1 | 5 | 3 | 4 | 70% | #NAME?
5 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 44.44% | #NAME? | 3 | 5 | 5 | 1 | 5 | 3 | 73.33% | #NAME?
2 | 1 | 3 | 1 | 1 | 4 | 2 | 2 | 3 | 42.22% | #NAME? | 5 | 2 | 1 | 4 | 1 | 1 | 46.67% | #NAME?
1 | 5 | 1 | 1 | 5 | 1 | 1 | 3 | 3 | 46.67% | #NAME? | 4 | 4 | 1 | 1 | 5 | 1 | 53.33% | #NAME?
1 | 5 | 1 | 1 | 5 | 1 | 2 | 1 | 3 | 44.44% | #NAME? | 2 | 3 | 5 | 4 | 3 | 5 | 73.33% | #NAME?
4 | 1 | 1 | 2 | 3 | 4 | 5 | 3 | 3 | 57.78% | #NAME? | 5 | 2 | 1 | 4 | 2 | 2 | 53.33% | #NAME?
4 | 4 | 3 | 4 | 4 | 4 | 4 | 2 | 4 | 73.33% | #NAME? | 1 | 3 | 1 | 2 | 5 | 5 | 56.67% | #NAME?
2 | 2 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 35.56% | #NAME? | 3 | 4 | 1 | 4 | 2 | 3 | 56.67% | #NAME?
2 | 3 | 2 | 1 | 3 | 3 | 1 | 2 | 3 | 44.44% | #NAME? | 3 | 2 | 1 | 5 | 4 | 2 | 56.67% | #NAME?
3 | 2 | 1 | 5 | 5 | 5 | 4 | 4 | 5 | 75.56% | #NAME? | 1 | 3 | 5 | 4 | 4 | 4 | 70% | #NAME?
3 | 5 | 1 | 3 | 1 | 5 | 1 | 1 | 2 | 48.89% | #NAME? | 4 | 5 | 1 | 2 | 3 | 3 | 60% | #NAME?
3 | 5 | 2 | 2 | 4 | 2 | 4 | 2 | 3 | 60% | #NAME? | 3 | 1 | 1 | 5 | 2 | 3 | 50% | #NAME?
4 | 1 | 4 | 3 | 5 | 3 | 1 | 4 | 3 | 62.22% | #NAME? | 5 | 3 | 1 | 3 | 5 | 1 | 60% | #NAME?
1 | 3 | 1 | 1 | 4 | 3 | 2 | 1 | 1 | 37.78% | #NAME? | 1 | 5 | 1 | 4 | 4 | 1 | 53.33% | #NAME?
1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 28.89% | #NAME? | 4 | 5 | 1 | 5 | 3 | 1 | 63.33% | #NAME?
3 | 5 | 3 | 2 | 2 | 2 | 4 | 1 | 3 | 55.56% | #NAME? | 2 | 5 | 1 | 2 | 5 | 5 | 66.67% | #NAME?
3 | 5 | 1 | 5 | 3 | 2 | 2 | 3 | 4 | 62.22% | #NAME? | 1 | 5 | 1 | 1 | 1 | 3 | 40% | #NAME?
3 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 5 | 44.44% | #NAME? | 3 | 4 | 1 | 2 | 4 | 2 | 53.33% | #NAME?
1 | 4 | 3 | 2 | 4 | 3 | 5 | 1 | 1 | 53.33% | #NAME? | 2 | 2 | 1 | 2 | 2 | 2 | 36.67% | #NAME?
3 | 1 | 3 | 3 | 5 | 1 | 5 | 3 | 5 | 64.44% | #NAME? | 3 | 2 | 1 | 4 | 5 | 5 | 66.67% | #NAME?
3 | 4 | 3 | 3 | 2 | 5 | 4 | 2 | 5 | 68.89% | #NAME? | 4 | 3 | 1 | 1 | 4 | 5 | 60% | #NAME?
5 | 5 | 3 | 1 | 2 | 2 | 4 | 5 | 4 | 68.89% | #NAME? | 1 | 5 | 1 | 3 | 1 | 1 | 40% | #NAME?
3 | 1 | 1 | 5 | 5 | 4 | 1 | 5 | 1 | 57.78% | #NAME? | 3 | 2 | 1 | 4 | 5 | 2 | 56.67% | #NAME?
1 | 4 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 35.56% | #NAME? | 2 | 1 | 1 | 1 | 1 | 5 | 36.67% | #NAME?
1 | 4 | 1 | 2 | 3 | 1 | 3 | 1 | 2 | 40% | #NAME? | 3 | 3 | 1 | 1 | 2 | 2 | 40% | #NAME?
1 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 2 | 35.56% | #NAME? | 1 | 1 | 1 | 1 | 5 | 3 | 40% | #NAME?
3 | 2 | 3 | 3 | 4 | 4 | 4 | 1 | 5 | 64.44% | #NAME? | 4 | 2 | 1 | 4 | 1 | 3 | 50% | #NAME?
5 | 3 | 3 | 1 | 2 | 2 | 1 | 5 | 5 | 60% | #NAME? | 1 | 2 | 1 | 2 | 2 | 3 | 36.67% | #NAME?
1 | 1 | 2 | 1 | 5 | 3 | 2 | 1 | 2 | 40% | #NAME? | 4 | 3 | 1 | 1 | 4 | 3 | 53.33% | #NAME?
3 | 5 | 1 | 2 | 3 | 2 | 4 | 3 | 5 | 62.22% | #NAME? | 3 | 4 | 1 | 3 | 1 | 3 | 50% | #NAME?
1 | 3 | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 35.56% | #NAME? | 4 | 5 | 5 | 5 | 1 | 2 | 73.33% | #NAME?
2 | 5 | 3 | 2 | 4 | 4 | 5 | 1 | 1 | 60% | #NAME? | 5 | 3 | 1 | 1 | 2 | 4 | 53.33% | #NAME?
4 | 5 | 4 | 1 | 5 | 3 | 4 | 2 | 4 | 71.11% | #NAME? | 1 | 4 | 1 | 4 | 1 | 4 | 50% | #NAME?
2 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 5 | 44.44% | #NAME? | 2 | 5 | 1 | 1 | 3 | 1 | 43.33% | #NAME?
1 | 2 | 2 | 3 | 5 | 2 | 5 | 3 | 1 | 53.33% | #NAME? | 2 | 3 | 1 | 5 | 5 | 5 | 70% | #NAME?
2 | 4 | 2 | 2 | 1 | 4 | 4 | 2 | 1 | 48.89% | #NAME? | 2 | 5 | 1 | 2 | 1 | 3 | 46.67% | #NAME?
1 | 5 | 2 | 2 | 3 | 5 | 3 | 1 | 2 | 53.33% | #NAME? | 4 | 3 | 1 | 3 | 4 | 2 | 56.67% | #NAME?
4 | 4 | 4 | 4 | 2 | 1 | 2 | 4 | 4 | 64.44% | #NAME? | 2 | 5 | 1 | 2 | 1 | 3 | 46.67% | #NAME?
5 | 5 | 2 | 1 | 5 | 2 | 5 | 5 | 3 | 73.33% | #NAME? | 3 | 3 | 1 | 5 | 1 | 2 | 50% | #NAME?
2 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 33.33% | #NAME? | 4 | 5 | 1 | 3 | 2 | 3 | 60% | #NAME?
2 | 2 | 1 | 1 | 1 | 2 | 5 | 2 | 3 | 42.22% | #NAME? | 4 | 4 | 1 | 1 | 5 | 2 | 56.67% | #NAME?
4 | 1 | 3 | 1 | 3 | 3 | 4 | 5 | 5 | 64.44% | #NAME? | 4 | 2 | 1 | 4 | 2 | 4 | 56.67% | #NAME?
3 | 1 | 1 | 1 | 3 | 5 | 3 | 5 | 1 | 51.11% | #NAME? | 1 | 1 | 1 | 4 | 3 | 4 | 46.67% | #NAME?
4 | 3 | 2 | 3 | 2 | 3 | 3 | 4 | 1 | 55.56% | #NAME? | 1 | 1 | 1 | 1 | 3 | 1 | 26.67% | #NAME?
2 | 5 | 1 | 2 | 5 | 4 | 4 | 3 | 4 | 66.67% | #NAME? | 4 | 4 | 1 | 3 | 4 | 1 | 56.67% | #NAME?
1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 35.56% | #NAME? | 1 | 3 | 1 | 1 | 4 | 1 | 36.67% | #NAME?
1 | 2 | 2 | 1 | 2 | 4 | 4 | 1 | 3 | 44.44% | #NAME? | 4 | 1 | 1 | 2 | 1 | 2 | 36.67% | #NAME?
5 | 4 | 4 | 5 | 1 | 5 | 1 | 3 | 2 | 66.67% | #NAME? | 1 | 5 | 1 | 2 | 1 | 1 | 36.67% | #NAME?
1 | 3 | 3 | 1 | 5 | 3 | 4 | 1 | 1 | 48.89% | #NAME? | 4 | 1 | 1 | 5 | 1 | 2 | 46.67% | #NAME?
4 | 4 | 3 | 2 | 4 | 2 | 1 | 5 | 2 | 60% | #NAME? | 5 | 5 | 5 | 2 | 2 | 4 | 76.67% | #NAME?
5 | 5 | 1 | 1 | 1 | 4 | 5 | 1 | 3 | 57.78% | #NAME? | 1 | 2 | 5 | 5 | 3 | 5 | 70% | #NAME?
4 | 2 | 3 | 2 | 5 | 3 | 4 | 5 | 3 | 68.89% | #NAME? | 4 | 4 | 5 | 5 | 1 | 1 | 66.67% | #NAME?
2 | 3 | 2 | 1 | 4 | 5 | 4 | 1 | 3 | 55.56% | #NAME? | 4 | 2 | 1 | 2 | 3 | 5 | 56.67% | #NAME?
3 | 4 | 1 | 2 | 3 | 1 | 4 | 2 | 1 | 46.67% | #NAME? | 5 | 5 | 1 | 4 | 3 | 5 | 76.67% | #NAME?
3 | 4 | 2 | 4 | 3 | 2 | 1 | 4 | 2 | 55.56% | #NAME? | 4 | 4 | 1 | 4 | 2 | 1 | 53.33% | #NAME?
5 | 5 | 3 | 1 | 4 | 1 | 3 | 2 | 3 | 60% | #NAME? | 4 | 4 | 1 | 5 | 2 | 5 | 70% | #NAME?
5 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 84.44% | #NAME? | 1 | 2 | 1 | 3 | 5 | 4 | 53.33% | #NAME?
5 | 3 | 2 | 2 | 1 | 2 | 5 | 4 | 1 | 55.56% | #NAME? | 4 | 5 | 1 | 3 | 5 | 4 | 73.33% | #NAME?
3 | 4 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 42.22% | #NAME? | 2 | 5 | 1 | 2 | 5 | 2 | 56.67% | #NAME?
4 | 4 | 3 | 5 | 3 | 5 | 5 | 4 | 3 | 80% | #NAME? | 2 | 3 | 1 | 3 | 3 | 3 | 50% | #NAME?
5 | 5 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 51.11% | #NAME? | 3 | 5 | 1 | 5 | 3 | 1 | 60% | #NAME?
4 | 4 | 2 | 4 | 5 | 5 | 3 | 1 | 1 | 64.44% | #NAME? | 5 | 4 | 1 | 1 | 1 | 4 | 53.33% | #NAME?
1 | 4 | 1 | 1 | 2 | 5 | 5 | 2 | 2 | 51.11% | #NAME? | 4 | 4 | 1 | 1 | 2 | 4 | 53.33% | #NAME?
2 | 5 | 2 | 3 | 4 | 5 | 5 | 1 | 5 | 71.11% | #NAME? | 1 | 2 | 1 | 3 | 1 | 4 | 40% | #NAME?
5 | 1 | 3 | 3 | 2 | 1 | 4 | 3 | 3 | 55.56% | #NAME? | 4 | 1 | 1 | 2 | 2 | 1 | 36.67% | #NAME?
5 | 5 | 3 | 1 | 5 | 2 | 1 | 5 | 5 | 71.11% | #NAME? | 1 | 5 | 1 | 2 | 1 | 3 | 43.33% | #NAME?
1 | 1 | 3 | 3 | 4 | 1 | 4 | 1 | 1 | 42.22% | #NAME? | 4 | 1 | 1 | 1 | 5 | 1 | 43.33% | #NAME?
4 | 4 | 4 | 1 | 1 | 5 | 4 | 3 | 5 | 68.89% | #NAME? | 4 | 4 | 1 | 2 | 2 | 1 | 46.67% | #NAME?
5 | 3 | 3 | 3 | 1 | 5 | 4 | 4 | 3 | 68.89% | #NAME? | 1 | 1 | 1 | 1 | 2 | 5 | 36.67% | #NAME?
4 | 1 | 1 | 4 | 3 | 2 | 3 | 5 | 2 | 55.56% | #NAME? | 3 | 4 | 1 | 1 | 1 | 2 | 40% | #NAME?
2 | 5 | 2 | 3 | 5 | 4 | 4 | 1 | 5 | 68.89% | #NAME? | 4 | 3 | 1 | 2 | 5 | 3 | 60% | #NAME?
4 | 2 | 4 | 1 | 3 | 2 | 2 | 5 | 4 | 60% | #NAME? | 3 | 2 | 1 | 2 | 1 | 3 | 40% | #NAME?
2 | 5 | 1 | 2 | 2 | 3 | 2 | 1 | 4 | 48.89% | #NAME? | 4 | 5 | 1 | 1 | 1 | 2 | 46.67% | #NAME?
2 | 3 | 3 | 2 | 4 | 3 | 1 | 1 | 2 | 46.67% | #NAME? | 4 | 2 | 1 | 5 | 2 | 3 | 56.67% | #NAME?
5 | 5 | 3 | 2 | 4 | 4 | 2 | 3 | 5 | 73.33% | #NAME? | 5 | 2 | 1 | 5 | 2 | 5 | 66.67% | #NAME?
4 | 3 | 4 | 1 | 5 | 4 | 4 | 3 | 3 | 68.89% | #NAME? | 4 | 3 | 1 | 4 | 1 | 5 | 60% | #NAME?
5 | 3 | 3 | 4 | 2 | 2 | 2 | 4 | 3 | 62.22% | #NAME? | 5 | 4 | 5 | 1 | 2 | 1 | 60% | #NAME?
5 | 3 | 3 | 3 | 3 | 5 | 2 | 4 | 3 | 68.89% | #NAME? | 5 | 3 | 1 | 3 | 3 | 3 | 60% | #NAME?
2 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 5 | 40% | #NAME? | 3 | 5 | 1 | 4 | 1 | 3 | 56.67% | #NAME?
5 | 5 | 1 | 3 | 5 | 4 | 5 | 3 | 2 | 73.33% | #NAME? | 1 | 3 | 1 | 3 | 4 | 2 | 46.67% | #NAME?
1 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 4 | 42.22% | #NAME? | 2 | 1 | 5 | 1 | 3 | 5 | 56.67% | #NAME?
3 | 1 | 1 | 1 | 4 | 2 | 1 | 2 | 3 | 40% | #NAME? | 5 | 5 | 5 | 4 | 4 | 2 | 83.33% | #NAME?
1 | 1 | 1 | 2 | 5 | 2 | 2 | 3 | 2 | 42.22% | #NAME? | 1 | 5 | 5 | 2 | 1 | 4 | 60% | #NAME?
3 | 3 | 2 | 4 | 4 | 3 | 4 | 2 | 2 | 60% | #NAME? | 5 | 3 | 1 | 2 | 5 | 4 | 66.67% | #NAME?
1 | 3 | 1 | 1 | 4 | 3 | 2 | 3 | 1 | 42.22% | #NAME? | 2 | 4 | 1 | 1 | 2 | 2 | 40% | #NAME?
5 | 3 | 2 | 4 | 2 | 5 | 5 | 3 | 3 | 71.11% | #NAME? | 4 | 1 | 5 | 5 | 4 | 3 | 73.33% | #NAME?
2 | 3 | 2 | 3 | 3 | 4 | 5 | 1 | 2 | 55.56% | #NAME? | 3 | 5 | 1 | 3 | 1 | 1 | 46.67% | #NAME?
1 | 4 | 1 | 2 | 2 | 2 | 5 | 1 | 2 | 44.44% | #NAME? | 5 | 4 | 1 | 5 | 3 | 5 | 76.67% | #NAME?
4 | 4 | 3 | 1 | 4 | 4 | 1 | 2 | 3 | 57.78% | #NAME? | 3 | 1 | 1 | 1 | 5 | 2 | 43.33% | #NAME?
3 | 4 | 3 | 1 | 4 | 2 | 5 | 1 | 1 | 53.33% | #NAME? | 2 | 2 | 5 | 5 | 1 | 3 | 60% | #NAME?
2 | 2 | 1 | 1 | 4 | 1 | 2 | 1 | 5 | 42.22% | #NAME? | 5 | 4 | 1 | 3 | 4 | 1 | 60% | #NAME?
3 | 4 | 1 | 3 | 1 | 5 | 5 | 3 | 3 | 62.22% | #NAME? | 1 | 1 | 1 | 4 | 1 | 5 | 43.33% | #NAME?
5 | 2 | 1 | 3 | 1 | 4 | 1 | 1 | 1 | 42.22% | #NAME? | 1 | 5 | 1 | 3 | 3 | 2 | 50% | #NAME?
4 | 5 | 2 | 2 | 3 | 2 | 4 | 2 | 4 | 62.22% | #NAME? | 3 | 4 | 1 | 5 | 5 | 4 | 73.33% | #NAME?
3 | 1 | 2 | 2 | 4 | 4 | 4 | 2 | 4 | 57.78% | #NAME? | 1 | 1 | 1 | 4 | 4 | 3 | 46.67% | #NAME?
2 | 4 | 2 | 3 | 5 | 2 | 4 | 1 | 4 | 60% | #NAME? | 2 | 4 | 1 | 2 | 4 | 5 | 60% | #NAME?
4 | 2 | 3 | 2 | 2 | 3 | 5 | 2 | 5 | 62.22% | #NAME? | 5 | 1 | 1 | 3 | 4 | 1 | 50% | #NAME?
1 | 2 | 3 | 3 | 1 | 1 | 4 | 1 | 3 | 42.22% | #NAME? | 4 | 5 | 5 | 3 | 4 | 4 | 83.33% | #NAME?
4 | 1 | 4 | 4 | 1 | 4 | 3 | 3 | 3 | 60% | #NAME? | 2 | 4 | 1 | 3 | 5 | 4 | 63.33% | #NAME?
3 | 1 | 4 | 5 | 4 | 2 | 4 | 2 | 5 | 66.67% | #NAME? | 2 | 2 | 1 | 2 | 1 | 5 | 43.33% | #NAME?
2 | 2 | 1 | 1 | 2 | 2 | 4 | 2 | 2 | 40% | #NAME? | 1 | 4 | 1 | 2 | 1 | 2 | 36.67% | #NAME?
2 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 4 | 44.44% | #NAME? | 4 | 4 | 1 | 2 | 2 | 5 | 60% | #NAME?
2 | 5 | 1 | 2 | 2 | 4 | 2 | 1 | 5 | 53.33% | #NAME? | 2 | 5 | 1 | 2 | 1 | 4 | 50% | #NAME?
1 | 1 | 1 | 1 | 4 | 1 | 5 | 1 | 4 | 42.22% | #NAME? | 2 | 2 | 1 | 5 | 3 | 5 | 60% | #NAME?
2 | 2 | 2 | 2 | 3 | 1 | 5 | 1 | 2 | 44.44% | #NAME? | 3 | 3 | 5 | 2 | 2 | 3 | 60% | #NAME?
1 | 1 | 1 | 1 | 4 | 5 | 4 | 2 | 3 | 48.89% | #NAME? | 2 | 4 | 1 | 4 | 1 | 5 | 56.67% | #NAME?
1 | 3 | 1 | 1 | 4 | 1 | 4 | 3 | 3 | 46.67% | #NAME? | 3 | 3 | 1 | 3 | 1 | 2 | 43.33% | #NAME?
5 | 4 | 1 | 5 | 3 | 2 | 3 | 1 | 3 | 60% | #NAME? | 2 | 3 | 1 | 5 | 4 | 1 | 53.33% | #NAME?
4 | 2 | 1 | 2 | 5 | 4 | 2 | 3 | 4 | 60% | #NAME? | 1 | 2 | 1 | 3 | 4 | 1 | 40% | #NAME?
5 | 5 | 3 | 4 | 1 | 3 | 1 | 2 | 2 | 57.78% | #NAME? | 4 | 5 | 1 | 2 | 3 | 2 | 56.67% | #NAME?
2 | 4 | 1 | 1 | 4 | 3 | 2 | 2 | 3 | 48.89% | #NAME? | 5 | 2 | 1 | 5 | 3 | 4 | 66.67% | #NAME?
2 | 4 | 1 | 2 | 3 | 5 | 1 | 2 | 2 | 48.89% | #NAME? | 5 | 4 | 5 | 3 | 4 | 3 | 80% | #NAME?
5 | 5 | 2 | 4 | 1 | 3 | 2 | 2 | 3 | 60% | #NAME? | 1 | 4 | 5 | 1 | 1 | 3 | 50% | #NAME?
5 | 5 | 3 | 4 | 5 | 4 | 4 | 1 | 3 | 75.56% | #NAME? | 1 | 4 | 1 | 3 | 4 | 5 | 60% | #NAME?
2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 31.11% | #NAME? | 5 | 5 | 1 | 1 | 4 | 3 | 63.33% | #NAME?
5 | 1 | 4 | 1 | 3 | 5 | 4 | 5 | 3 | 68.89% | #NAME? | 4 | 3 | 1 | 2 | 3 | 4 | 56.67% | #NAME?
5 | 3 | 3 | 3 | 3 | 2 | 5 | 3 | 4 | 68.89% | #NAME? | 4 | 3 | 1 | 1 | 5 | 1 | 50% | #NAME?
5 | 1 | 1 | 2 | 5 | 3 | 1 | 5 | 2 | 55.56% | #NAME? | 4 | 3 | 1 | 3 | 1 | 4 | 53.33% | #NAME?
5 | 1 | 2 | 5 | 4 | 1 | 2 | 2 | 4 | 57.78% | #NAME? | 5 | 4 | 1 | 1 | 4 | 2 | 56.67% | #NAME?
1 | 5 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 40% | #NAME? | 3 | 2 | 1 | 3 | 2 | 5 | 53.33% | #NAME?
4 | 3 | 3 | 5 | 3 | 1 | 4 | 4 | 5 | 71.11% | #NAME? | 4 | 5 | 1 | 5 | 2 | 2 | 63.33% | #NAME?
4 | 1 | 3 | 1 | 3 | 4 | 2 | 2 | 5 | 55.56% | #NAME? | 3 | 2 | 1 | 4 | 5 | 1 | 53.33% | #NAME?
4 | 3 | 3 | 4 | 2 | 2 | 3 | 4 | 1 | 57.78% | #NAME? | 4 | 2 | 1 | 2 | 5 | 5 | 63.33% | #NAME?
1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 2 | 35.56% | #NAME? | 1 | 1 | 1 | 1 | 1 | 4 | 30% | #NAME?
2 | 3 | 2 | 2 | 5 | 1 | 5 | 1 | 5 | 57.78% | #NAME? | 1 | 2 | 1 | 2 | 2 | 4 | 40% | #NAME?
3 | 3 | 1 | 4 | 2 | 2 | 4 | 2 | 2 | 51.11% | #NAME? | 3 | 3 | 1 | 2 | 1 | 5 | 50% | #NAME?
1 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 35.56% | #NAME? | 1 | 1 | 1 | 5 | 3 | 5 | 53.33% | #NAME?
1 | 4 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 33.33% | #NAME? | 2 | 2 | 1 | 1 | 1 | 5 | 40% | #NAME?
2 | 2 | 2 | 2 | 5 | 3 | 4 | 1 | 1 | 48.89% | #NAME? | 3 | 1 | 1 | 5 | 1 | 3 | 46.67% | #NAME?
5 | 4 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | 53.33% | #NAME? | 1 | 5 | 1 | 1 | 4 | 4 | 53.33% | #NAME?
5 | 4 | 1 | 1 | 3 | 5 | 5 | 2 | 2 | 62.22% | #NAME? | 3 | 1 | 1 | 3 | 4 | 5 | 56.67% | #NAME?
5 | 3 | 2 | 3 | 1 | 5 | 4 | 1 | 3 | 60% | #NAME? | 3 | 3 | 1 | 3 | 1 | 3 | 46.67% | #NAME?
3 | 4 | 1 | 4 | 1 | 1 | 2 | 4 | 1 | 46.67% | #NAME? | 2 | 5 | 5 | 5 | 1 | 4 | 73.33% | #NAME?
5 | 2 | 3 | 2 | 5 | 3 | 3 | 1 | 1 | 55.56% | #NAME? | 3 | 1 | 5 | 2 | 1 | 4 | 53.33% | #NAME?
4 | 5 | 3 | 1 | 4 | 5 | 1 | 1 | 2 | 57.78% | #NAME? | 4 | 4 | 1 | 3 | 4 | 3 | 63.33% | #NAME?
2 | 3 | 2 | 1 | 3 | 3 | 5 | 2 | 5 | 57.78% | #NAME? | 4 | 4 | 1 | 1 | 1 | 2 | 43.33% | #NAME?
4 | 3 | 3 | 3 | 5 | 2 | 1 | 4 | 4 | 64.44% | #NAME? | 4 | 3 | 1 | 2 | 5 | 4 | 63.33% | #NAME?
1 | 2 | 2 | 1 | 1 | 2 | 4 | 2 | 1 | 35.56% | #NAME? | 4 | 1 | 1 | 2 | 1 | 2 | 36.67% | #NAME?
1 | 4 | 2 | 1 | 2 | 2 | 4 | 2 | 3 | 46.67% | #NAME? | 3 | 5 | 5 | 2 | 5 | 5 | 83.33% | #NAME?
4 | 5 | 3 | 3 | 4 | 1 | 3 | 1 | 1 | 55.56% | #NAME? | 1 | 5 | 5 | 1 | 3 | 3 | 60% | #NAME?
5 | 4 | 1 | 3 | 1 | 2 | 4 | 1 | 5 | 57.78% | #NAME? | 4 | 5 | 1 | 3 | 3 | 5 | 70% | #NAME?
2 | 3 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 42.22% | #NAME? | 4 | 3 | 1 | 2 | 5 | 2 | 56.67% | #NAME?
4 | 5 | 3 | 2 | 5 | 2 | 2 | 1 | 3 | 60% | #NAME? | 2 | 2 | 1 | 4 | 2 | 2 | 43.33% | #NAME?
5 | 3 | 3 | 5 | 2 | 4 | 2 | 5 | 4 | 73.33% | #NAME? | 1 | 4 | 1 | 4 | 4 | 3 | 56.67% | #NAME?
5 | 4 | 2 | 2 | 1 | 2 | 3 | 3 | 5 | 60% | #NAME? | 4 | 2 | 1 | 4 | 1 | 5 | 56.67% | #NAME?
3 | 1 | 1 | 2 | 4 | 3 | 2 | 4 | 1 | 46.67% | #NAME? | 4 | 1 | 1 | 2 | 2 | 3 | 43.33% | #NAME?
5 | 5 | 1 | 1 | 1 | 1 | 2 | 2 | 5 | 51.11% | #NAME? | 4 | 4 | 1 | 5 | 3 | 2 | 63.33% | #NAME?
2 | 2 | 1 | 1 | 5 | 2 | 1 | 2 | 3 | 42.22% | #NAME? | 1 | 2 | 1 | 1 | 1 | 3 | 30% | #NAME?
1 | 3 | 2 | 1 | 4 | 3 | 4 | 2 | 1 | 46.67% | #NAME? | 2 | 1 | 5 | 3 | 5 | 1 | 56.67% | #NAME?
2 | 1 | 3 | 1 | 2 | 2 | 4 | 2 | 2 | 42.22% | #NAME? | 4 | 4 | 1 | 1 | 1 | 5 | 53.33% | #NAME?
5 | 3 | 1 | 4 | 1 | 1 | 5 | 1 | 3 | 53.33% | #NAME? | 3 | 3 | 1 | 4 | 5 | 4 | 66.67% | #NAME?
5 | 5 | 3 | 5 | 3 | 5 | 2 | 5 | 3 | 80% | #NAME? | 3 | 5 | 1 | 5 | 4 | 4 | 73.33% | #NAME?
1 | 4 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 33.33% | #NAME? | 2 | 2 | 5 | 2 | 4 | 5 | 66.67% | #NAME?
3 | 1 | 2 | 5 | 3 | 1 | 3 | 3 | 5 | 57.78% | #NAME? | 1 | 1 | 1 | 4 | 3 | 4 | 46.67% | #NAME?
3 | 5 | 2 | 4 | 3 | 5 | 4 | 2 | 3 | 68.89% | #NAME? | 1 | 2 | 1 | 5 | 3 | 3 | 50% | #NAME?
2 | 4 | 1 | 1 | 3 | 4 | 4 | 3 | 4 | 57.78% | #NAME? | 5 | 3 | 1 | 2 | 1 | 4 | 53.33% | #NAME?
3 | 4 | 2 | 5 | 4 | 1 | 3 | 2 | 5 | 64.44% | #NAME? | 5 | 5 | 1 | 3 | 5 | 2 | 70% | #NAME?
2 | 4 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 44.44% | #NAME? | 5 | 5 | 1 | 2 | 3 | 3 | 63.33% | #NAME?
5 | 4 | 2 | 3 | 2 | 5 | 2 | 1 | 3 | 60% | #NAME? | 5 | 1 | 1 | 1 | 5 | 3 | 53.33% | #NAME?
5 | 3 | 2 | 1 | 5 | 3 | 1 | 4 | 3 | 60% | #NAME? | 4 | 3 | 1 | 5 | 5 | 5 | 76.67% | #NAME?
4 | 1 | 3 | 1 | 5 | 3 | 3 | 2 | 1 | 51.11% | #NAME? | 1 | 4 | 1 | 4 | 1 | 3 | 46.67% | #NAME?
4 | 1 | 2 | 2 | 3 | 4 | 4 | 3 | 3 | 57.78% | #NAME? | 5 | 3 | 1 | 2 | 3 | 4 | 60% | #NAME?
3 | 1 | 4 | 2 | 5 | 2 | 1 | 5 | 5 | 62.22% | #NAME? | 5 | 5 | 1 | 3 | 5 | 1 | 66.67% | #NAME?
3 | 5 | 2 | 3 | 3 | 2 | 4 | 5 | 5 | 71.11% | #NAME? | 1 | 4 | 1 | 2 | 1 | 3 | 40% | #NAME?
1 | 2 | 3 | 1 | 3 | 3 | 4 | 2 | 1 | 44.44% | #NAME? | 1 | 4 | 1 | 3 | 2 | 2 | 43.33% | #NAME?
3 | 5 | 2 | 5 | 2 | 2 | 1 | 1 | 3 | 53.33% | #NAME? | 5 | 2 | 1 | 5 | 3 | 3 | 63.33% | #NAME?
2 | 3 | 2 | 2 | 5 | 3 | 1 | 2 | 4 | 53.33% | #NAME? | 2 | 4 | 1 | 4 | 5 | 3 | 63.33% | #NAME?
1 | 4 | 2 | 2 | 3 | 5 | 3 | 3 | 2 | 55.56% | #NAME? | 3 | 3 | 1 | 2 | 1 | 3 | 43.33% | #NAME?
4 | 3 | 1 | 4 | 5 | 4 | 2 | 4 | 2 | 64.44% | #NAME? | 5 | 3 | 1 | 5 | 1 | 2 | 56.67% | #NAME?
5 | 1 | 1 | 5 | 2 | 2 | 2 | 3 | 4 | 55.56% | #NAME? | 1 | 5 | 1 | 5 | 2 | 1 | 50% | #NAME?
2 | 4 | 2 | 3 | 4 | 2 | 5 | 3 | 3 | 62.22% | #NAME? | 4 | 1 | 1 | 3 | 3 | 2 | 46.67% | #NAME?
2 | 2 | 1 | 2 | 2 | 5 | 5 | 3 | 3 | 55.56% | #NAME? | 3 | 5 | 1 | 2 | 4 | 4 | 63.33% | #NAME?
1 | 1 | 1 | 3 | 1 | 4 | 3 | 1 | 2 | 37.78% | #NAME? | 4 | 5 | 1 | 2 | 1 | 1 | 46.67% | #NAME?
2 | 3 | 1 | 3 | 3 | 1 | 4 | 3 | 3 | 51.11% | #NAME? | 2 | 5 | 1 | 2 | 2 | 3 | 50% | #NAME?
1 | 3 | 3 | 3 | 5 | 4 | 4 | 1 | 5 | 64.44% | #NAME? | 5 | 4 | 1 | 2 | 1 | 2 | 50% | #NAME?
3 | 3 | 3 | 4 | 5 | 5 | 5 | 2 | 4 | 75.56% | #NAME? | 4 | 2 | 5 | 1 | 1 | 2 | 50% | #NAME?
4 | 3 | 4 | 4 | 2 | 3 | 1 | 3 | 3 | 60% | #NAME? | 3 | 4 | 5 | 5 | 1 | 4 | 73.33% | #NAME?
1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 35.56% | #NAME? | 1 | 1 | 5 | 5 | 4 | 3 | 63.33% | #NAME?
1 | 2 | 3 | 1 | 3 | 5 | 3 | 1 | 2 | 46.67% | #NAME? | 1 | 2 | 1 | 1 | 3 | 2 | 33.33% | #NAME?
5 | 5 | 3 | 4 | 4 | 5 | 4 | 5 | 3 | 84.44% | #NAME? | 2 | 5 | 1 | 4 | 5 | 3 | 66.67% | #NAME?
5 | 2 | 5 | 1 | 3 | 5 | 3 | 2 | 4 | 66.67% | #NAME? | 2 | 4 | 1 | 4 | 3 | 1 | 50% | #NAME?
2 | 2 | 1 | 3 | 4 | 1 | 2 | 1 | 2 | 40% | #NAME? | 2 | 2 | 1 | 1 | 2 | 4 | 40% | #NAME?
2 | 2 | 1 | 2 | 1 | 3 | 3 | 3 | 5 | 48.89% | #NAME? | 2 | 4 | 1 | 1 | 1 | 5 | 46.67% | #NAME?
3 | 3 | 2 | 3 | 5 | 2 | 1 | 3 | 2 | 53.33% | #NAME? | 3 | 3 | 1 | 4 | 4 | 4 | 63.33% | #NAME?
2 | 4 | 3 | 1 | 1 | 4 | 3 | 2 | 2 | 48.89% | #NAME? | 5 | 3 | 1 | 5 | 5 | 1 | 66.67% | #NAME?
4 | 4 | 2 | 2 | 2 | 5 | 1 | 4 | 5 | 64.44% | #NAME? | 3 | 1 | 5 | 2 | 1 | 4 | 53.33% | #NAME?
4 | 4 | 2 | 2 | 5 | 5 | 4 | 3 | 1 | 66.67% | #NAME? | 5 | 5 | 1 | 1 | 5 | 5 | 73.33% | #NAME?
2 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 33.33% | #NAME? | 4 | 4 | 1 | 2 | 5 | 1 | 56.67% | #NAME?
1 | 4 | 1 | 3 | 4 | 3 | 2 | 1 | 1 | 44.44% | #NAME? | 3 | 2 | 1 | 1 | 4 | 4 | 50% | #NAME?
1 | 1 | 3 | 1 | 3 | 4 | 4 | 2 | 2 | 46.67% | #NAME? | 2 | 1 | 1 | 4 | 4 | 1 | 43.33% | #NAME?
5 | 4 | 2 | 4 | 3 | 3 | 1 | 3 | 4 | 64.44% | #NAME? | 5 | 4 | 1 | 2 | 2 | 4 | 60% | #NAME?
2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 4 | 37.78% | #NAME? | 2 | 5 | 1 | 4 | 4 | 4 | 66.67% | #NAME?
2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 40% | #NAME? | 5 | 4 | 1 | 1 | 2 | 2 | 50% | #NAME?
2 | 1 | 1 | 1 | 2 | 5 | 3 | 3 | 3 | 46.67% | #NAME? | 2 | 5 | 1 | 2 | 3 | 4 | 56.67% | #NAME?
1 | 3 | 1 | 1 | 3 | 5 | 1 | 2 | 2 | 42.22% | #NAME? | 2 | 5 | 1 | 2 | 2 | 5 | 56.67% | #NAME?
4 | 2 | 3 | 3 | 2 | 1 | 4 | 5 | 5 | 64.44% | #NAME? | 4 | 1 | 1 | 3 | 3 | 3 | 50% | #NAME?
1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 35.56% | #NAME? | 1 | 2 | 1 | 1 | 3 | 1 | 30% | #NAME?
3 | 4 | 3 | 2 | 4 | 4 | 1 | 5 | 5 | 68.89% | #NAME? | 5 | 3 | 1 | 4 | 4 | 1 | 60% | #NAME?
1 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 37.78% | #NAME? | 5 | 5 | 1 | 3 | 3 | 3 | 66.67% | #NAME?
4 | 2 | 2 | 2 | 2 | 4 | 2 | 5 | 2 | 55.56% | #NAME? | 5 | 3 | 1 | 2 | 2 | 4 | 56.67% | #NAME?
4 | 2 | 2 | 2 | 4 | 5 | 3 | 2 | 3 | 60% | #NAME? | 2 | 1 | 1 | 3 | 1 | 3 | 36.67% | #NAME?
5 | 3 | 4 | 4 | 3 | 5 | 4 | 5 | 2 | 77.78% | #NAME? | 5 | 3 | 1 | 3 | 2 | 5 | 63.33% | #NAME?
5 | 3 | 3 | 4 | 1 | 3 | 5 | 4 | 2 | 66.67% | #NAME? | 1 | 1 | 5 | 5 | 3 | 5 | 66.67% | #NAME?
2 | 3 | 1 | 1 | 4 | 2 | 2 | 3 | 2 | 44.44% | #NAME? | 5 | 5 | 1 | 1 | 2 | 2 | 53.33% | #NAME?
3 | 1 | 2 | 2 | 2 | 4 | 2 | 5 | 2 | 51.11% | #NAME? | 1 | 5 | 1 | 4 | 3 | 2 | 53.33% | #NAME?
4 | 3 | 1 | 3 | 4 | 1 | 4 | 2 | 3 | 55.56% | #NAME? | 5 | 5 | 1 | 3 | 3 | 4 | 70% | #NAME?
1 | 2 | 3 | 3 | 5 | 5 | 2 | 3 | 4 | 62.22% | #NAME? | 5 | 4 | 5 | 3 | 1 | 1 | 63.33% | #NAME?
2 | 2 | 2 | 2 | 4 | 4 | 4 | 3 | 2 | 55.56% | #NAME? | 1 | 2 | 1 | 5 | 2 | 1 | 40% | #NAME?
4 | 3 | 1 | 1 | 2 | 4 | 5 | 1 | 3 | 53.33% | #NAME? | 1 | 2 | 5 | 2 | 2 | 3 | 50% | #NAME?
4 | 4 | 3 | 4 | 4 | 4 | 5 | 5 | 2 | 77.78% | #NAME? | 3 | 4 | 5 | 1 | 5 | 3 | 70% | #NAME?
5 | 2 | 2 | 4 | 2 | 5 | 4 | 4 | 4 | 71.11% | #NAME? | 3 | 5 | 1 | 1 | 1 | 3 | 46.67% | #NAME?
5 | 4 | 2 | 1 | 2 | 5 | 1 | 3 | 3 | 57.78% | #NAME? | 5 | 1 | 1 | 1 | 2 | 2 | 40% | #NAME?
2 | 4 | 2 | 1 | 5 | 3 | 5 | 1 | 4 | 60% | #NAME? | 2 | 5 | 1 | 1 | 4 | 2 | 50% | #NAME?
2 | 2 | 3 | 2 | 3 | 3 | 3 | 2 | 5 | 55.56% | #NAME? | 1 | 4 | 1 | 2 | 2 | 3 | 43.33% | #NAME?
3 | 3 | 3 | 3 | 5 | 1 | 5 | 5 | 4 | 71.11% | #NAME? | 4 | 2 | 1 | 2 | 5 | 5 | 63.33% | #NAME?
4 | 2 | 2 | 3 | 3 | 1 | 3 | 2 | 2 | 48.89% | #NAME? | 3 | 5 | 1 | 5 | 2 | 5 | 70% | #NAME?
2 | 1 | 3 | 1 | 1 | 1 | 5 | 3 | 1 | 40% | #NAME? | 2 | 2 | 1 | 5 | 1 | 3 | 46.67% | #NAME?
5 | 2 | 1 | 3 | 2 | 4 | 1 | 3 | 3 | 53.33% | #NAME? | 2 | 5 | 1 | 3 | 4 | 2 | 56.67% | #NAME?
1 | 3 | 2 | 2 | 4 | 5 | 2 | 1 | 4 | 53.33% | #NAME? | 2 | 5 | 1 | 4 | 1 | 4 | 56.67% | #NAME?
2 | 4 | 2 | 2 | 5 | 2 | 2 | 1 | 4 | 53.33% | #NAME? | 3 | 4 | 1 | 5 | 2 | 2 | 56.67% | #NAME?
3 | 3 | 3 | 3 | 4 | 1 | 5 | 5 | 5 | 71.11% | #NAME? | 5 | 2 | 1 | 2 | 2 | 2 | 46.67% | #NAME?
4 | 1 | 4 | 1 | 2 | 4 | 2 | 5 | 5 | 62.22% | #NAME? | 4 | 1 | 1 | 5 | 4 | 4 | 63.33% | #NAME?
3 | 2 | 4 | 3 | 3 | 5 | 1 | 3 | 4 | 62.22% | #NAME? | 2 | 5 | 1 | 1 | 2 | 2 | 43.33% | #NAME?
2 | 3 | 3 | 2 | 4 | 4 | 3 | 3 | 2 | 57.78% | #NAME? | 3 | 3 | 1 | 4 | 2 | 3 | 53.33% | #NAME?
5 | 4 | 1 | 3 | 3 | 3 | 1 | 5 | 1 | 57.78% | #NAME? | 3 | 4 | 1 | 1 | 3 | 4 | 53.33% | #NAME?
5 | 3 | 3 | 3 | 1 | 4 | 4 | 1 | 4 | 62.22% | #NAME? | 1 | 4 | 1 | 2 | 4 | 1 | 43.33% | #NAME?
3 | 3 | 3 | 3 | 4 | 2 | 4 | 3 | 3 | 62.22% | #NAME? | 1 | 1 | 1 | 4 | 5 | 1 | 43.33% | #NAME?
2 | 4 | 2 | 1 | 1 | 5 | 3 | 3 | 3 | 53.33% | #NAME? | 2 | 3 | 1 | 2 | 2 | 3 | 43.33% | #NAME?
4 | 4 | 2 | 4 | 1 | 3 | 5 | 3 | 3 | 64.44% | #NAME? | 4 | 4 | 1 | 1 | 4 | 4 | 60% | #NAME?
5 | 3 | 2 | 1 | 2 | 1 | 4 | 5 | 4 | 60% | #NAME? | 2 | 5 | 1 | 5 | 4 | 5 | 73.33% | #NAME?
2 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 35.56% | #NAME? | 2 | 3 | 1 | 1 | 5 | 3 | 50% | #NAME?
3 | 1 | 1 | 3 | 1 | 1 | 5 | 2 | 2 | 42.22% | #NAME? | 5 | 1 | 1 | 5 | 5 | 1 | 60% | #NAME?
2 | 2 | 3 | 2 | 2 | 2 | 1 | 3 | 4 | 46.67% | #NAME? | 3 | 5 | 5 | 2 | 4 | 4 | 76.67% | #NAME?
2 | 5 | 1 | 3 | 2 | 5 | 4 | 2 | 1 | 55.56% | #NAME? | 1 | 3 | 1 | 2 | 1 | 5 | 43.33% | #NAME?
2 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 3 | 42.22% | #NAME? | 1 | 5 | 1 | 4 | 1 | 3 | 50% | #NAME?
2 | 5 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 46.67% | #NAME? | 4 | 3 | 1 | 2 | 1 | 5 | 53.33% | #NAME?
4 | 3 | 2 | 5 | 1 | 5 | 5 | 4 | 1 | 66.67% | #NAME? | 4 | 4 | 1 | 3 | 4 | 1 | 56.67% | #NAME?
4 | 5 | 4 | 2 | 2 | 2 | 2 | 1 | 4 | 57.78% | #NAME? | 1 | 1 | 1 | 5 | 5 | 2 | 50% | #NAME?
2 | 2 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 40% | #NAME? | 1 | 2 | 5 | 2 | 5 | 4 | 63.33% | #NAME?
5 | 3 | 4 | 3 | 1 | 5 | 1 | 5 | 5 | 71.11% | #NAME? | 5 | 3 | 1 | 1 | 2 | 1 | 43.33% | #NAME?
1 | 2 | 2 | 3 | 3 | 4 | 3 | 1 | 2 | 46.67% | #NAME? | 2 | 5 | 1 | 2 | 5 | 3 | 60% | #NAME?
2 | 1 | 1 | 1 | 4 | 4 | 3 | 2 | 4 | 48.89% | #NAME? | 2 | 4 | 1 | 2 | 2 | 3 | 46.67% | #NAME?
4 | 3 | 4 | 2 | 4 | 5 | 1 | 4 | 3 | 66.67% | #NAME? | 1 | 2 | 1 | 3 | 4 | 3 | 46.67% | #NAME?
4 | 2 | 3 | 2 | 5 | 5 | 4 | 3 | 5 | 73.33% | #NAME? | 2 | 5 | 1 | 4 | 5 | 1 | 60% | #NAME?
1 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 3 | 35.56% | #NAME? | 3 | 2 | 1 | 5 | 4 | 5 | 66.67% | #NAME?
1 | 5 | 1 | 2 | 2 | 3 | 3 | 2 | 4 | 51.11% | #NAME? | 4 | 3 | 1 | 4 | 1 | 3 | 53.33% | #NAME?
5 | 5 | 1 | 2 | 2 | 1 | 1 | 5 | 4 | 57.78% | #NAME? | 1 | 4 | 1 | 3 | 3 | 5 | 56.67% | #NAME?
2 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 31.11% | #NAME? | 4 | 2 | 5 | 4 | 5 | 1 | 70% | #NAME?
1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 26.67% | #NAME? | 5 | 4 | 1 | 4 | 4 | 4 | 73.33% | #NAME?
5 | 5 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 48.89% | #NAME? | 4 | 3 | 5 | 1 | 2 | 4 | 63.33% | #NAME?
5 | 5 | 4 | 3 | 5 | 1 | 5 | 5 | 1 | 75.56% | #NAME? | 3 | 5 | 1 | 3 | 5 | 2 | 63.33% | #NAME?
2 | 2 | 2 | 2 | 1 | 2 | 4 | 2 | 4 | 46.67% | #NAME? | 1 | 1 | 5 | 4 | 5 | 5 | 70% | #NAME?
1 | 5 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 40% | #NAME? | 2 | 3 | 1 | 1 | 1 | 4 | 40% | #NAME?
5 | 5 | 4 | 3 | 1 | 3 | 4 | 4 | 1 | 66.67% | #NAME? | 3 | 2 | 1 | 2 | 5 | 3 | 53.33% | #NAME?
1 | 4 | 1 | 1 | 4 | 5 | 1 | 1 | 4 | 48.89% | #NAME? | 5 | 5 | 1 | 5 | 2 | 1 | 63.33% | #NAME?
5 | 2 | 1 | 1 | 4 | 3 | 4 | 3 | 2 | 55.56% | #NAME? | 3 | 2 | 1 | 5 | 1 | 2 | 46.67% | #NAME?
5 | 5 | 1 | 2 | 1 | 1 | 4 | 1 | 5 | 55.56% | #NAME? | 2 | 5 | 1 | 4 | 4 | 4 | 66.67% | #NAME?
1 | 4 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 40% | #NAME? | 3 | 3 | 1 | 5 | 5 | 3 | 66.67% | #NAME?
5 | 5 | 3 | 4 | 3 | 3 | 2 | 5 | 1 | 68.89% | #NAME? | 1 | 2 | 1 | 1 | 5 | 1 | 36.67% | #NAME?
4 | 5 | 2 | 3 | 1 | 4 | 2 | 3 | 3 | 60% | #NAME? | 3 | 1 | 1 | 1 | 5 | 4 | 50% | #NAME?
4 | 5 | 4 | 3 | 2 | 1 | 1 | 3 | 1 | 53.33% | #NAME? | 5 | 5 | 1 | 1 | 1 | 4 | 56.67% | #NAME?
5 | 1 | 4 | 3 | 3 | 4 | 2 | 5 | 3 | 66.67% | #NAME? | 2 | 5 | 1 | 4 | 2 | 5 | 63.33% | #NAME?
5 | 4 | 2 | 5 | 1 | 3 | 3 | 4 | 2 | 64.44% | #NAME? | 1 | 3 | 1 | 2 | 2 | 5 | 46.67% | #NAME?
3 | 3 | 1 | 2 | 3 | 2 | 5 | 3 | 3 | 55.56% | #NAME? | 4 | 5 | 1 | 5 | 4 | 5 | 80% | #NAME?
5 | 2 | 3 | 3 | 5 | 2 | 3 | 3 | 5 | 68.89% | #NAME? | 5 | 5 | 1 | 2 | 2 | 1 | 53.33% | #NAME?
5 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 3 | 46.67% | #NAME? | 3 | 4 | 1 | 5 | 4 | 3 | 66.67% | #NAME?
1 | 5 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 42.22% | #NAME? | 2 | 5 | 1 | 1 | 4 | 3 | 53.33% | #NAME?
3 | 5 | 4 | 1 | 4 | 1 | 2 | 5 | 5 | 66.67% | #NAME? | 4 | 2 | 1 | 1 | 1 | 2 | 36.67% | #NAME?
4 | 4 | 4 | 5 | 1 | 1 | 3 | 2 | 5 | 64.44% | #NAME? | 2 | 1 | 1 | 4 | 3 | 5 | 53.33% | #NAME?
4 | 1 | 4 | 4 | 3 | 2 | 5 | 2 | 3 | 62.22% | #NAME? | 2 | 1 | 5 | 1 | 4 | 1 | 46.67% | #NAME?
1 | 1 | 1 | 1 | 5 | 5 | 3 | 2 | 3 | 48.89% | #NAME? | 5 | 1 | 5 | 4 | 4 | 5 | 80% | #NAME?
2 | 5 | 1 | 3 | 2 | 2 | 3 | 3 | 2 | 51.11% | #NAME? | 3 | 4 | 5 | 1 | 5 | 1 | 63.33% | #NAME?
5 | 5 | 1 | 2 | 4 | 2 | 2 | 2 | 1 | 53.33% | #NAME? | 1 | 5 | 1 | 5 | 1 | 4 | 56.67% | #NAME?
1 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 1 | 40% | #NAME? | 1 | 3 | 1 | 4 | 3 | 3 | 50% | #NAME?
5 | 5 | 1 | 4 | 3 | 3 | 3 | 1 | 1 | 57.78% | #NAME? | 1 | 5 | 1 | 3 | 4 | 4 | 60% | #NAME?
2 | 5 | 1 | 1 | 4 | 1 | 5 | 2 | 5 | 57.78% | #NAME? | 1 | 3 | 1 | 2 | 4 | 5 | 53.33% | #NAME?
1 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 35.56% | #NAME? | 3 | 3 | 1 | 1 | 3 | 4 | 50% | #NAME?
5 | 2 | 4 | 1 | 3 | 2 | 4 | 3 | 4 | 62.22% | #NAME? | 4 | 1 | 5 | 3 | 2 | 4 | 63.33% | #NAME?
3 | 1 | 2 | 1 | 5 | 3 | 2 | 1 | 5 | 51.11% | #NAME? | 1 | 1 | 1 | 4 | 2 | 3 | 40% | #NAME?
2 | 1 | 3 | 3 | 1 | 4 | 5 | 2 | 5 | 57.78% | #NAME? | 5 | 2 | 5 | 2 | 1 | 4 | 63.33% | #NAME?
2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 35.56% | #NAME? | 2 | 5 | 5 | 2 | 1 | 1 | 53.33% | #NAME?
1 | 2 | 2 | 1 | 1 | 4 | 2 | 3 | 3 | 42.22% | #NAME? | 3 | 2 | 5 | 4 | 4 | 1 | 63.33% | #NAME?
3 | 2 | 1 | 5 | 1 | 3 | 1 | 3 | 4 | 51.11% | #NAME? | 5 | 3 | 1 | 3 | 4 | 5 | 70% | #NAME?
1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 22.22% | #NAME? | 2 | 1 | 1 | 5 | 2 | 5 | 53.33% | #NAME?
2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 31.11% | #NAME? | 1 | 1 | 1 | 1 | 3 | 3 | 33.33% | #NAME?
1 | 1 | 2 | 1 | 4 | 3 | 2 | 3 | 1 | 40% | #NAME? | 1 | 1 | 1 | 1 | 1 | 3 | 26.67% | #NAME?
3 | 3 | 3 | 2 | 5 | 4 | 3 | 1 | 2 | 57.78% | #NAME? | 1 | 5 | 1 | 4 | 4 | 4 | 63.33% | #NAME?
3 | 5 | 3 | 3 | 3 | 4 | 2 | 1 | 5 | 64.44% | #NAME? | 3 | 1 | 1 | 5 | 4 | 1 | 50% | #NAME?
3 | 1 | 3 | 4 | 2 | 3 | 2 | 1 | 4 | 51.11% | #NAME? | 4 | 2 | 1 | 1 | 5 | 3 | 53.33% | #NAME?
5 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 4 | 44.44% | #NAME? | 2 | 1 | 1 | 3 | 1 | 5 | 43.33% | #NAME?
3 | 5 | 2 | 3 | 5 | 5 | 4 | 1 | 3 | 68.89% | #NAME? | 4 | 1 | 1 | 4 | 4 | 1 | 50% | #NAME?
5 | 1 | 1 | 5 | 4 | 4 | 4 | 5 | 1 | 66.67% | #NAME? | 4 | 3 | 1 | 4 | 5 | 3 | 66.67% | #NAME?
4 | 2 | 4 | 3 | 2 | 2 | 4 | 2 | 2 | 55.56% | #NAME? | 5 | 1 | 1 | 4 | 1 | 1 | 43.33% | #NAME?
1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 28.89% | #NAME? | 5 | 2 | 1 | 3 | 3 | 4 | 60% | #NAME?
5 | 1 | 4 | 5 | 4 | 4 | 5 | 5 | 4 | 82.22% | #NAME? | 4 | 1 | 1 | 2 | 2 | 2 | 40% | #NAME?
5 | 5 | 3 | 2 | 5 | 2 | 2 | 5 | 3 | 71.11% | #NAME? | 3 | 5 | 1 | 4 | 1 | 1 | 50% | #NAME?
5 | 5 | 3 | 4 | 1 | 4 | 4 | 4 | 4 | 75.56% | #NAME? | 5 | 5 | 1 | 2 | 2 | 4 | 63.33% | #NAME?
3 | 1 | 1 | 3 | 5 | 5 | 3 | 1 | 1 | 51.11% | #NAME? | 5 | 2 | 1 | 2 | 3 | 3 | 53.33% | #NAME?
2 | 2 | 2 | 3 | 3 | 4 | 5 | 3 | 4 | 62.22% | #NAME? | 1 | 5 | 1 | 4 | 4 | 1 | 53.33% | #NAME?
3 | 4 | 1 | 4 | 5 | 2 | 4 | 4 | 1 | 62.22% | #NAME? | 2 | 1 | 1 | 1 | 5 | 5 | 50% | #NAME?
5 | 4 | 2 | 2 | 2 | 2 | 5 | 2 | 1 | 55.56% | #NAME? | 2 | 2 | 5 | 3 | 1 | 4 | 56.67% | #NAME?
4 | 1 | 2 | 5 | 4 | 1 | 1 | 4 | 4 | 57.78% | #NAME? | 1 | 4 | 1 | 3 | 5 | 5 | 63.33% | #NAME?
3 | 1 | 1 | 1 | 3 | 1 | 5 | 4 | 1 | 44.44% | #NAME? | 4 | 4 | 1 | 5 | 2 | 2 | 60% | #NAME?
4 | 1 | 3 | 1 | 3 | 1 | 3 | 5 | 1 | 48.89% | #NAME? | 4 | 2 | 5 | 4 | 1 | 4 | 66.67% | #NAME?
1 | 4 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 37.78% | #NAME? | 2 | 3 | 5 | 5 | 4 | 5 | 80% | #NAME?
2 | 2 | 1 | 1 | 4 | 4 | 1 | 2 | 1 | 40% | #NAME? | 2 | 5 | 1 | 4 | 3 | 1 | 53.33% | #NAME?
1 | 5 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 44.44% | #NAME? | 3 | 1 | 1 | 4 | 3 | 5 | 56.67% | #NAME?
3 | 2 | 3 | 3 | 3 | 4 | 1 | 4 | 1 | 53.33% | #NAME? | 1 | 5 | 5 | 2 | 2 | 4 | 63.33% | #NAME?
1 | 4 | 3 | 1 | 1 | 4 | 2 | 3 | 2 | 46.67% | #NAME? | 2 | 5 | 1 | 4 | 5 | 3 | 66.67% | #NAME?
1 | 5 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 42.22% | #NAME? | 4 | 5 | 1 | 1 | 2 | 1 | 46.67% | #NAME?
1 | 5 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 33.33% | #NAME? | 1 | 1 | 1 | 1 | 3 | 5 | 40% | #NAME?
1 | 4 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 40% | #NAME? | 3 | 1 | 1 | 2 | 4 | 1 | 40% | #NAME?

## PI list
Work ID | workrequest | Line of Business | PROGRAMCLASSIFICATION | ProgramNAME | RepairType | Location | Required Work Completion Date | PlannedYear | PROJECT DURATION (days) | OutageDuration (days) | ProjectStartDate | Driver Safety | DriverOperational | DriverEnvironment | DriverRegulatory | DiverCompliance | StandardCost | ProjectedCost | ActualCost | BurnRate | FinancialBudgetType | FullyScoped | OUTAGE TYPE (UNIT, PLANT, STATION, PIPELINE) | OutageConfirmed | OutagePlanned | outageRequired | detailsScoped | designCompleted | longLeadMaterialsOrdered | resourcesIdentified | transferCompressor | permitsReceived | siteVisitsPerformed | stakeholdersEngaged | stakeholdersSupport | projectReimburseable | projectPlanEst | ProjectReadinessScope | ProjectEngDesign | ProjectFunding | ProjectPermits | ProjectStkholdrEngagmnt | ProjectProcurementScm | ProjectResourceMgmt | ProjectExeqtnSched | ProjectReadinessPerct | ProjectReadinessRank | PriorityScopeClarity | PriorityImpact Assessmt | PrioritySafetyReqmt | PriorityCommCapacityReliabiilty | PriorityOutageImpacts | PriorityRank (RISK) | PriorityReadinessPerct | FLOW IMPACT (M^3/DAY) | COST IMPACT /DAY
997 | 997 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | Nov30,2027 | Oct 31, 2026 | 59 | 4 | 2025-09-02 | med | high | low | low | low | 1800000 | 1864493 | 1802540 | 87.159 | EXPENSE | yes | Derate/low flow Pipe segment | x | x | x | x | x | NR | x | x | x | x | x |  | No | Yes | 5 | 1 | 1 | 4 | 2 | 5 | 1 | 4 | 57.5% | 6 | 4 | 4 | 1 | 3 | 3 | 60% | 6 |  | 8429.71
998 | 998 | L2 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Montreal | Dec 31, 2030 | Dec 31, 2026 | 201 | 2 | 2025-01-11 | med | high | high | med | high | 190000 | 175087 | 174680 | 40.7081 | EXPENSE | no | Derate/low flow Pipe segment |  |  | x | x | x | no | x | x | x | [5 empty] | 3 | 1 | 4 | 3 | 1 | 4 | 1 | 4 | 52.5% | 6 | 1 | 3 | 1 | 4 | 4 | 52% | 6 |  | 8756
999 | 999 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | May 31, 2026 | Jul 31, 2027 | 327 | 5 | 2024-12-08 | low | high | med | high | med | 400000 | 611769 | 669250 | 85.7283 | EXPENSE | yes | Pipeline segment | x | x | x | x | x | Yes | x | NR | NR | NR | NR | NR | No | Yes | 4 | 5 | 2 | 3 | 1 | 4 | 5 | 3 | 67.5% | 6 | 5 | 5 | 1 | 5 | 1 | 68% | 7 |  | 52
1000 | 1000 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Aug 31,2029 | Oct 31, 2025 | 315 | 4 | 2024-02-20 | high | med | med | high | low | 650000 | 778878 | 779764 | 65.902 | EXPENSE | yes | Derate/low flow Pipe segment | x | x | x | x | x | Yes | x | x | Yes | Yes | Yes |  | No | No | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 85% | 9 | 3 | 1 | 1 | 1 | 1 | 28% | 3 |  | 4526
1001 | 1001 | L2 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Ottawa | June 30, 2025 | Jul 31, 2026 | 263 | 5 | 2025-02-10 | low | high | high | low | low | 300000 | 306500 | 310745 | 27.2404 | CAPITAL | no | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | Yes | Yes | 2 | 3 | 2 | 5 | 3 | 1 | 5 | 3 | 60% | 6 | 4 | 5 | 1 | 4 | 2 | 64% | 7 |  | 258
1002 | 1002 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | March 31, 2026 | Jul 31, 2025 | 72 | 5 | 2025-08-20 | med | med | low | low | med | 400000 | 465754 | 469856 | 159.1014 | CAPITAL | no | Pipeline segment | X | X |  |  |  | Yes | Yes | Yes | no | Yes | no | Yes | Yes | no | 4 | 5 | 3 | 4 | 5 | 3 | 4 | 4 | 80% | 8 | 2 | 5 | 1 | 2 | 1 | 44% | 5 |  | 842.9817
1003 | 1003 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Calgary | Nov 30, 2025 | Oct 31, 2027 | 361 | 8 | 2024-04-04 | high | med | med | high | low | 450000 | 958642 | 975845 | 83.0189 | CAPITAL | no | Pipeline segment |  | X |  | X |  | Yes | Yes | no | Yes | Yes | no | no | Yes | Yes | 2 | 3 | 2 | 3 | 4 | 3 | 4 | 2 | 57.5% | 6 | 1 | 4 | 1 | 3 | 2 | 44% | 5 |  | 842.9817
1004 | 1004 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | March 31, 2026 | Oct 31, 2027 | 312 | 5 | 2024-05-23 | high | med | high | low | low | 450000 | 505744 | 505000 | 32.772 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | Yes | no | no | no | Yes | Yes | no | 1 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 37.5% | 4 | 3 | 4 | 1 | 1 | 3 | 48% | 5 |  | 13420.4072
1005 | 1005 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Montreal | Aug 31,2027 | Oct 31, 2027 | 202 | 5 | 2024-06-12 | low | low | med | med | med | 500000 | 534470 | 533637 | 147.3292 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | no | Yes | no | no | Yes | 5 | 1 | 1 | 4 | 4 | 4 | 1 | 2 | 55% | 6 | 1 | 1 | 1 | 5 | 5 | 52% | 6 |  | 1727.2647
1006 | 1006 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Toronto | April 30,2029 | Dec 31, 2026 | 175 | 8 | 2025-05-09 | med | high | high | low | med | 300000 | 387000 | 435200 | 180.0007 | CAPITAL | Yes | Pipeline segment | X |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 37.5% | 4 | 2 | 4 | 1 | 5 | 2 | 56% | 6 |  | 1578
1007 | 1007 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | April 30,2027 | Jul 31, 2025 | 183 | 4 | 2025-07-01 | low | high | high | high | low | 2000000 | 2085890 | 2014691 | 488.9487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | no | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 35% | 4 | 1 | 4 | 1 | 1 | 3 | 40% | 4 |  | 3506.8708
1008 | 1008 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Nov30,2027 | Oct 31, 2025 | 260 | 4 | 2024-07-14 | low | low | low | low | low | 2100000 | 2520000 | 2454250 | 40.3349 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | no | no | no | no | no | Yes | no | 3 | 5 | 2 | 4 | 4 | 4 | 4 | 3 | 72.5% | 8 | 2 | 5 | 1 | 2 | 3 | 52% | 6 |  | 3981.0002
1009 | 1009 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | April 30,2028 | Dec 31, 2026 | 342 | 2 | 2024-01-24 | high | low | med | low | low | 650000 | 689531 | 725189 | 242.8512 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X | X | X | no | no | no | Yes | no | Yes | Yes | Yes | no | 2 | 2 | 1 | 3 | 1 | 4 | 2 | 2 | 42.5% | 5 | 3 | 1 | 1 | 2 | 2 | 36% | 4 |  | 20815.3255
1010 | 1010 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Sept 30, 2025 | Jul 31, 2025 | 248 | 4 | 2024-07-26 | med | high | high | high | high | 2000000 | 2473474 | 2450004 | 25.7224 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | no | Yes | no | no | no | Yes | Yes | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 5 | 70% | 6 | 2 | 5 | 5 | 1 | 2 | 60% | 6 |  | 278.7236
1011 | 1011 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Nov 30,2029 | Jul 31, 2025 | 32 | 3 | 2025-06-29 | low | high | low | med | low | 400000 | 450563 | 409107 | 135.4595 | EXPENSE | no | Pipeline segment |  | X |  |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 4 | 4 | 4 | 1 | 3 | 4 | 1 | 3 | 60% | 6 | 1 | 5 | 5 | 4 | 1 | 64% | 7 |  | 278.7236
1012 | 1012 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Aug 31,2027 | Jul 31, 2027 | 195 | 3 | 2025-04-19 | low | high | low | med | high | 400000 | 450041 | 489250 | 122.5032 | EXPENSE | Yes | Pipeline segment | X |  |  | X |  | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 3 | 2 | 4 | 4 | 3 | 5 | 5 | 70% | 6 | 5 | 4 | 5 | 4 | 4 | 88% | 9 |  | 203.1281
1013 | 1013 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Sept 30,2026 | Dec 31, 2025 | 240 | 3 | 2024-12-03 | high | med | high | med | med | 500000 | 509283 | 509602 | 148.1189 | EXPENSE | Yes | Pipeline segment | X |  | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 5 | 5 | 1 | 5 | 4 | 5 | 5 | 4 | 85% | 9 | 5 | 3 | 5 | 3 | 2 | 72% | 8 |  | 203.1281
1014 | 1014 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Dec 31,2028 | Oct 31, 2027 | 42 | 15 | 2025-09-19 | low | low | low | low | med | 450000 | 715279 | 728240 | 184.0435 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | Yes | no | no | no | no | no | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 35% | 4 | 4 | 5 | 1 | 2 | 3 | 60% | 6 |  | 853.1382
1015 | 1015 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Saskatoon | Dec 31,2026 | Dec 31, 2025 | 124 | 4 | 2025-06-29 | med | med | med | high | high | 450000 | 419931 | 446058 | 34.5922 | CAPITAL | no | derate/low flow Pipe segment | X | X |  |  | X | Yes | no | no | no | Yes | no | no | Yes | Yes | 3 | 1 | 2 | 4 | 3 | 2 | 4 | 2 | 52.5% | 6 | 4 | 5 | 1 | 1 | 5 | 64% | 7 |  | 23717.2367
1016 | 1016 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Montreal | June 30, 2025 | Jul 31, 2027 | 355 | 8 | 2024-08-10 | high | high | low | low | high | 500000 | 520373 | 521000 | 16.0911 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 4 | 2 | 5 | 1 | 3 | 3 | 1 | 2 | 52.5% | 6 | 2 | 3 | 1 | 3 | 3 | 48% | 5 |  | 746.1723
1017 | 1017 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | March 31, 2026 | Oct 31, 2026 | 255 | 5 | 2024-04-20 | low | high | high | low | low | 450000 | 515075 | 534568 | 23.9593 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | Yes | no | no | Yes | Yes | no | Yes | 3 | 3 | 2 | 1 | 4 | 3 | 5 | 1 | 55% | 6 | 1 | 2 | 1 | 2 | 3 | 36% | 4 |  | 13677.1818
1018 | 1018 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | Sept 30,2026 | Oct 31, 2025 | 360 | 15 | 2025-01-05 | high | low | high | med | med | 450000 | 529718 | 528784 | 270.4653 | CAPITAL | no | Pipeline segment |  | X |  |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 2 | 45% | 5 | 1 | 4 | 1 | 4 | 3 | 52% | 6 |  | 16021.8416
1019 | 1019 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Sept 30, 2025 | Oct 31, 2026 | 275 | 7 | 2025-01-29 | low | med | low | high | low | 450000 | 542580 | 545780 | 104.3547 | EXPENSE | no | Derate/low flow Pipe segment | X |  | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 4 | 2 | 4 | 2 | 4 | 5 | 2 | 4 | 67.5% | 6 | 1 | 5 | 1 | 2 | 4 | 52% | 6 |  | 7007.9205
1020 | 1020 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Dec 31,2026 | Oct 31, 2025 | 99 | 4 | 2024-12-22 | high | low | high | high | med | 650000 | 789531 | 768189 | 48.6768 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | no | no | Yes | no | Yes | Yes | Yes | Yes | no | 4 | 2 | 4 | 3 | 2 | 3 | 4 | 5 | 67.5% | 6 | 2 | 1 | 1 | 5 | 2 | 44% | 5 |  | 7007.9205
1021 | 1021 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Aug 31,2029 | Dec 31, 2027 | 101 | 5 | 2025-07-22 | high | low | low | med | med | 400000 | 550000 | 559415 | 194.4749 | EXPENSE | Yes | Pipeline segment |  |  |  | X | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 1 | 2 | 3 | 2 | 1 | 5 | 4 | 4 | 55% | 6 | 1 | 1 | 1 | 4 | 3 | 40% | 4 |  | 1685.9635
1022 | 1022 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | April 30,2029 | Dec 31, 2026 | 346 | 3 | 2025-01-19 | low | low | low | low | low | 650000 | 620531 | 625189 | 26.0956 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 1 | 5 | 5 | 5 | 4 | 2 | 3 | 67.5% | 6 | 2 | 1 | 1 | 1 | 3 | 32% | 4 |  | 1685.9635
1023 | 1023 | L2 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Quebec City | Nov 30, 2025 | Dec 31, 2027 | 146 | 2 | 2025-06-07 | high | med | low | med | low | 75000 | 85254 | 95452 | 156.8587 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 1 | 1 | 5 | 5 | 2 | 1 | 2 | 4 | 52.5% | 6 | 1 | 1 | 1 | 1 | 2 | 24% | 3 |  | 778.6578
1024 | 1024 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Dec 31,2026 | Dec 31, 2027 | 170 | 4 | 2024-07-14 | med | high | high | med | high | 450000 | 852538 | 857775 | 35.5286 | CAPITAL | no | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | Yes | Yes | Yes | Yes | no | 2 | 4 | 2 | 2 | 4 | 1 | 2 | 2 | 47.5% | 5 | 1 | 4 | 1 | 5 | 2 | 52% | 6 |  | 121.8769
1025 | 1025 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Sept 30, 2025 | Oct 31, 2025 | 251 | 8 | 2024-11-22 | med | high | med | high | med | 450000 | 452014 | 454644 | 26.015 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | Yes | Yes | 1 | 4 | 2 | 4 | 2 | 1 | 4 | 2 | 50% | 5 | 3 | 5 | 5 | 3 | 5 | 84% | 9 |  | 267.7598
1026 | 1026 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Sept 30,2028 | Dec 31, 2027 | 243 | 4 | 2024-05-02 | high | high | high | high | med | 400000 | 449044 | 455180 | 18.1227 | CAPITAL | no | Pipeline segment | X | X |  |  |  | no | Yes | no | Yes | no | no | no | Yes | no | 1 | 5 | 1 | 4 | 5 | 3 | 3 | 1 | 57.5% | 6 | 2 | 1 | 5 | 3 | 1 | 48% | 5 |  | 267.7598
1027 | 1027 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Mar 31,2030 | Dec 31, 2026 | 239 | 2 | 2025-05-06 | low | high | high | high | low | 350000 | 534618 | 575616 | 502.8679 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | no | Yes | no | no | no | no | Yes | no | no | 3 | 4 | 2 | 5 | 5 | 3 | 1 | 1 | 60% | 6 | 2 | 2 | 5 | 3 | 1 | 52% | 6 |  | 267.7598
1028 | 1028 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANNUAL SURVEY | Calgary | Sept 30,2026 | Jul 31, 2027 | 331 | 5 | 2024-02-04 | high | med | high | high | low | 780000 | 1376437 | 1313514 | 98.0993 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 3 | 4 | 1 | 5 | 4 | 5 | 4 | 1 | 67.5% | 6 | 1 | 3 | 5 | 5 | 3 | 68% | 7 |  | 17599.3754
1029 | 1029 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP-REMEDITION | Montreal | Sept 30,2028 | Jul 31, 2026 | 348 | 5 | 2024-11-17 | high | med | med | med | low | 850000 | 850026 | 8543747 | 76.5526 | CAPITAL | no | Pipeline segment | X | X |  |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 3 | 2 | 1 | 5 | 3 | 4 | 3 | 3 | 60% | 6 | 4 | 2 | 1 | 4 | 2 | 52% | 6 |  | 6832.4917
1030 | 1030 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Sept 30,2028 | Dec 31, 2026 | 55 | 5 | 2025-02-04 | med | low | high | low | low | 400000 | 495918 | 472825 | 414.8802 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | Yes | 3 | 3 | 1 | 5 | 2 | 1 | 1 | 5 | 52.5% | 6 | 1 | 5 | 1 | 4 | 5 | 64% | 7 |  | 330
1031 | 1031 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | April 30,2029 | Oct 31, 2026 | 77 | 4 | 2024-10-15 | low | low | med | high | low | 400000 | 491000 | 485000 | 1266.3815 | EXPENSE | no | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 2 | 4 | 1 | 2 | 1 | 3 | 4 | 1 | 45% | 5 | 4 | 2 | 1 | 2 | 4 | 52% | 6 |  | 5845
1032 | 1032 | L1 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Calgary | Nov30,2027 | Oct 31, 2026 | 190 | 4 | 2025-04-24 | med | high | high | low | high | 125000 | 110410 | 107380 | 565.0045 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | Yes | no | Yes | no | Yes | 1 | 4 | 2 | 5 | 4 | 5 | 1 | 3 | 62.5% | 6 | 1 | 1 | 1 | 2 | 4 | 36% | 4 |  | 3077.9635
1033 | 1033 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | North Bay | Sept 30,2026 | Oct 31, 2025 | 149 | 4 | 2024-11-02 | med | high | low | high | med | 1250000 | 1281952 | 1285422 | 72.2212 | EXPENSE | no | Derate/low flow Pipe segment | X | X |  |  | X | no | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 3 | 1 | 2 | 3 | 5 | 2 | 1 | 1 | 45% | 5 | 5 | 3 | 1 | 2 | 4 | 60% | 6 |  | 5097.2605
1034 | 1034 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | Sept 30,2030 | Dec 31, 2025 | 214 | 15 | 2025-05-31 | low | high | low | low | low | 450000 | 986403 | 1000404 | 103.1048 | CAPITAL | no | Pipeline segment | X |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 5 | 5 | 1 | 3 | 5 | 5 | 5 | 4 | 82.5% | 9 | 4 | 5 | 5 | 2 | 2 | 72% | 8 |  | 13582.277
1035 | 1035 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Nov30,2027 | Jul 31, 2027 | 247 | 3 | 2024-11-26 | low | high | high | med | low | 500000 | 534135 | 576815 | 91.6522 | CAPITAL | Yes | PIpeline segment | X |  |  | X |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 5 | 1 | 2 | 4 | 3 | 1 | 5 | 5 | 65% | 6 | 3 | 4 | 5 | 5 | 2 | 76% | 8 |  | 4391.6369
1036 | 1036 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Montreal | Nov 30, 2025 | Dec 31, 2027 | 109 | 4 | 2025-09-13 | high | high | low | high | high | 300000 | 505538 | 508025 | 98.783 | EXPENSE | Yes | Pipeline segment | X |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 2 | 5 | 1 | 2 | 1 | 4 | 2 | 3 | 50% | 5 | 1 | 1 | 5 | 5 | 2 | 56% | 6 |  | 4314.1949
1037 | 1037 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Ottawa | June 30, 2025 | Jul 31, 2025 | 21 | 8 | 2025-10-10 | med | high | high | high | med | 750000 | 838059 | 852793 | 279.986 | EXPENSE | no | Pipeline segment |  | X | X |  |  | no | Yes | no | Yes | Yes | no | Yes | no | no | 2 | 5 | 4 | 2 | 4 | 2 | 2 | 4 | 62.5% | 6 | 5 | 4 | 5 | 5 | 1 | 80% | 8 |  | 4858.8867
1038 | 1038 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | WINNIPEG | Aug 31,2027 | Jul 31, 2026 | 146 | 8 | 2025-08-07 | low | med | low | high | high | 450000 | 428864 | 428750 | 56.9979 | CAPITAL | Yes | Pipeline segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | no | no | no | 2 | 1 | 2 | 2 | 2 | 4 | 1 | 2 | 40% | 4 | 1 | 5 | 5 | 2 | 5 | 72% | 8 |  | 2178.0735
1039 | 1039 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | WINNIPEG | April 30,2029 | Dec 31, 2025 | 179 | 8 | 2025-02-02 | med | low | med | med | med | 450000 | 816716 | 810460 | 30.4676 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | Yes | Yes | Yes | no | Yes | no | Yes | no | Yes | 5 | 5 | 1 | 3 | 3 | 5 | 5 | 3 | 75% | 8 | 1 | 4 | 1 | 4 | 3 | 52% | 6 |  | 1090.5382
1040 | 1040 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | Dec 31, 2030 | Oct 31, 2025 | 364 | 8 | 2024-04-01 | high | low | high | med | med | 350000 | 310639 | 310032 | 4.3752 | CAPITAL | no | Pipeline segment | X | X | X |  | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 4 | 47.5% | 5 | 2 | 1 | 1 | 3 | 4 | 44% | 5 |  | 4052.0846
1041 | 1041 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Nov 30, 2025 | Jul 31, 2025 | 180 | 5 | 2025-02-01 | med | med | low | high | low | 350000 | 451173 | 453222 | 22.175 | EXPENSE | Yes | Pipeline segment | X | X | X |  |  | Yes | no | no | no | Yes | no | no | Yes | no | 4 | 1 | 5 | 4 | 4 | 5 | 1 | 2 | 65% | 6 | 3 | 4 | 1 | 4 | 5 | 68% | 7 |  | 4995.3897
1042 | 1042 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Mar 31,2030 | Jul 31, 2026 | 264 | 15 | 2024-04-11 | low | low | low | high | high | 450000 | 680678 | 686152 | 22.4512 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | no | Yes | no | no | 3 | 5 | 4 | 2 | 2 | 1 | 5 | 5 | 67.5% | 6 | 5 | 3 | 1 | 2 | 5 | 64% | 7 |  | 646
1043 | 1043 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | April 30,2029 | Oct 31, 2027 | 20 | 4 | 2025-03-11 | med | med | high | med | low | 500000 | 608924 | 630832 | 93.0837 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | Yes | Yes | no | no | 4 | 4 | 3 | 4 | 1 | 2 | 4 | 1 | 57.5% | 6 | 2 | 3 | 1 | 3 | 1 | 40% | 4 |  | 347
1044 | 1044 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Aug 31,2027 | Dec 31, 2026 | 192 | 4 | 2025-06-22 | low | high | low | low | low | 350000 | 379330 | 377636 | 415.9262 | EXPENSE | no | Pipeline segment |  | X | X |  |  | no | no | no | no | Yes | Yes | Yes | no | Yes | 4 | 2 | 4 | 3 | 3 | 5 | 2 | 5 | 70% | 6 | 4 | 3 | 1 | 5 | 5 | 72% | 8 |  | 158885
1045 | 1045 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | April 30,2028 | Jul 31, 2027 | 363 | 5 | 2024-08-02 | med | low | high | med | low | 1800000 | 1855522 | 1845724 | 87.5976 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 5 | 5 | 2 | 3 | 1 | 3 | 4 | 65% | 6 | 3 | 5 | 1 | 2 | 2 | 52% | 6 |  | 1207.7993
1046 | 1046 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | March 31, 2026 | Dec 31, 2025 | 170 | 5 | 2024-10-12 | high | high | high | high | med | 650000 | 788878 | 779764 | 27.6329 | EXPENSE | no | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 5 | 4 | 3 | 2 | 1 | 1 | 5 | 4 | 62.5% | 6 | 1 | 3 | 1 | 1 | 5 | 44% | 5 |  | 1785
1047 | 1047 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | Nov30,2027 | Oct 31, 2027 | 312 | 5 | 2025-02-22 | low | high | high | high | med | 300000 | 295522 | 295724 | 110.9054 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | no | no | Yes | no | no | Yes | Yes | Yes | 4 | 1 | 3 | 4 | 4 | 2 | 3 | 4 | 62.5% | 6 | 1 | 1 | 1 | 2 | 3 | 32% | 4 |  | 172.2548
1048 | 1048 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | April 30,2028 | Oct 31, 2026 | 317 | 5 | 2024-12-18 | low | high | med | med | low | 1250000 | 1350000 | 1450000 | 96.934 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 2 | 3 | 5 | 1 | 3 | 1 | 2 | 5 | 55% | 6 | 2 | 1 | 1 | 5 | 4 | 52% | 6 |  | 172.2548
1049 | 1049 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Nov 30,2029 | Oct 31, 2027 | 94 | 15 | 2024-09-28 | low | low | med | high | med | 450000 | 453975 | 454237 | 29.298 | CAPITAL | no | Pipeline segment | X |  |  | X | X | no | Yes | no | Yes | no | no | no | no | Yes | 1 | 4 | 2 | 2 | 2 | 2 | 3 | 5 | 52.5% | 6 | 2 | 3 | 1 | 4 | 4 | 56% | 6 |  | 191.3942
1050 | 1050 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Quebec City | Nov 30, 2025 | Dec 31, 2027 | 268 | 7 | 2024-07-06 | high | med | low | high | low | 450000 | 1514932 | 1512774 | 7.2499 | CAPITAL | no | pipeline segment | X | X | X |  | X | no | no | no | no | no | no | no | Yes | Yes | 5 | 4 | 2 | 1 | 5 | 2 | 1 | 1 | 52.5% | 6 | 2 | 1 | 1 | 4 | 4 | 48% | 5 |  | 173.2929
1051 | 1051 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | April 30,2028 | Jul 31, 2026 | 92 | 4 | 2024-09-30 | med | low | low | high | low | 750000 | 789882 | 779817 | 4.1819 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | no | no | no | no | no | Yes | Yes | no | no | 2 | 1 | 5 | 4 | 2 | 3 | 4 | 5 | 65% | 6 | 2 | 1 | 1 | 1 | 3 | 32% | 4 |  | 749.7244
1052 | 1052 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Aug 31,2029 | Oct 31, 2025 | 270 | 7 | 2024-07-04 | low | med | low | high | med | 650000 | 698448 | 697296 | 28.5018 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | no | Yes | no | no | Yes | 1 | 1 | 3 | 5 | 5 | 2 | 2 | 4 | 57.5% | 6 | 1 | 2 | 1 | 1 | 1 | 24% | 3 |  | 32.5005
1053 | 1053 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | June 30, 2025 | Dec 31, 2027 | 196 | 7 | 2025-04-18 | high | low | low | med | med | 350000 | 370016 | 378399 | 96.1798 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | no | no | no | Yes | Yes | 5 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 47.5% | 5 | 2 | 3 | 1 | 5 | 4 | 60% | 6 |  | 1022.4116
1054 | 1054 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | Aug 31,2029 | Dec 31, 2026 | 309 | 8 | 2024-05-26 | high | low | med | med | high | 450000 | 480343 | 480758 | 89.4674 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 5 | 4 | 5 | 5 | 1 | 3 | 2 | 3 | 70% | 6 | 4 | 1 | 1 | 2 | 3 | 44% | 5 |  | 458
1055 | 1055 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | May 31, 2026 | Dec 31, 2026 | 156 | 6 | 2024-07-28 | med | med | low | med | high | 350000 | 677837 | 682856 | 68.0307 | CAPITAL | no | Pipeline segment | X |  |  | X |  | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 2 | 1 | 2 | 4 | 5 | 4 | 4 | 1 | 57.5% | 6 | 1 | 1 | 1 | 2 | 2 | 28% | 3 |  | 20000
1056 | 1056 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | Dec 31,2026 | Dec 31, 2026 | 44 | 8 | 2025-11-17 | med | med | low | med | high | 650000 | 686027 | 682144 | 108.8597 | CAPITAL | no | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | no | Yes | Yes | 1 | 4 | 5 | 4 | 2 | 4 | 3 | 3 | 65% | 6 | 1 | 1 | 1 | 3 | 1 | 28% | 3 |  | 2078
1057 | 1057 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | June 30, 2025 | Oct 31, 2026 | 205 | 7 | 2025-06-09 | high | low | low | med | med | 1800000 | 1964493 | 1902540 | 55.4393 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 5 | 4 | 4 | 2 | 1 | 2 | 4 | 4 | 65% | 6 | 5 | 1 | 1 | 1 | 4 | 48% | 5 |  | 1875
1058 | 1058 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Sept 30, 2025 | Jul 31, 2025 | 282 | 4 | 2024-03-24 | med | low | med | low | med | 450000 | 856958 | 888680 | 64.1787 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 3 | 2 | 1 | 3 | 4 | 5 | 4 | 2 | 60% | 6 | 2 | 5 | 5 | 1 | 3 | 64% | 7 |  | 7718.869
1059 | 1059 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Dec 31,2026 | Jul 31, 2026 | 244 | 4 | 2025-05-01 | high | low | low | high | high | 400000 | 445632 | 446927 | 93.8623 | EXPENSE | no | Pipeline segment |  | X |  | X | X | no | no | no | no | Yes | no | Yes | no | no | 1 | 2 | 2 | 5 | 2 | 4 | 4 | 5 | 62.5% | 6 | 4 | 5 | 5 | 3 | 1 | 72% | 8 |  | 25393.3666
1060 | 1060 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Dec 31,2026 | Jul 31, 2027 | 25 | 4 | 2025-03-06 | low | med | med | high | high | 650000 | 666455 | 695432 | 12.1249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 4 | 2 | 1 | 2 | 3 | 5 | 4 | 4 | 62.5% | 6 | 5 | 3 | 1 | 5 | 4 | 72% | 8 |  | 3138.8656
1061 | 1061 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | April 30,2027 | Oct 31, 2025 | 357 | 4 | 2025-01-08 | low | low | med | high | high | 450000 | 743098 | 791931 | 94.2513 | CAPITAL | Yes | Pipeline segment |  |  | X |  | X | Yes | no | no | Yes | Yes | Yes | Yes | Yes | no | 5 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 45% | 5 | 1 | 4 | 1 | 4 | 4 | 56% | 6 |  | 4487
1062 | 1062 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Toronto | Mar 31,2030 | Dec 31, 2027 | 112 | 8 | 2024-09-10 | med | high | high | med | high | 1000000 | 1821878 | 1824096 | 99.9422 | EXPENSE | Yes | Pipeline segment |  | X | X | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | Yes | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 30% | 3 | 1 | 3 | 1 | 4 | 2 | 44% | 5 |  | 211.3988
1063 | 1063 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | June 30, 2025 | Oct 31, 2027 | 291 | 8 | 2025-03-15 | low | high | low | med | low | 350000 | 669911 | 695057 | 54.5821 | EXPENSE | no | Pipeline segment | X |  |  |  | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 5 | 5 | 1 | 5 | 1 | 5 | 1 | 4 | 67.5% | 6 | 3 | 4 | 5 | 1 | 3 | 64% | 7 |  | 1486.7011
1064 | 1064 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Aug 31,2029 | Oct 31, 2025 | 70 | 8 | 2024-10-22 | med | high | high | low | med | 350000 | 344031 | 340632 | 122.8607 | CAPITAL | no | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | no | Yes | no | Yes | Yes | 2 | 2 | 4 | 3 | 1 | 2 | 5 | 4 | 57.5% | 6 | 3 | 4 | 1 | 1 | 1 | 40% | 4 |  | 2679.5194
1065 | 1065 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | May 31, 2026 | Oct 31, 2026 | 23 | 8 | 2024-12-08 | med | med | low | high | med | 350000 | 339702 | 391874 | 109.8564 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | no | no | no | no | no | no | no | Yes | Yes | 4 | 4 | 5 | 2 | 5 | 3 | 5 | 3 | 77.5% | 8 | 5 | 4 | 5 | 2 | 1 | 68% | 7 |  | 2679.5194
1066 | 1066 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Toronto | Nov30,2027 | Oct 31, 2027 | 207 | 8 | 2024-06-07 | high | low | high | low | high | 550000 | 661009 | 682588 | 111.3269 | EXPENSE | Yes | Pipeline segment | X |  | X | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 1 | 1 | 2 | 1 | 3 | 2 | 4 | 3 | 42.5% | 5 | 5 | 4 | 5 | 4 | 2 | 80% | 8 |  | 1072.7658
1067 | 1067 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Saskatoon | Aug 31,2027 | Dec 31, 2027 | 144 | 8 | 2024-08-09 | high | high | high | low | low | 550000 | 623179 | 603094 | 59.7386 | EXPENSE | no | Pipeline segment |  | X |  | X | X | Yes | no | no | no | no | no | no | no | Yes | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 35% | 4 | 3 | 2 | 1 | 1 | 2 | 36% | 4 |  | 3333.1342
1068 | 1068 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Montreal | Nov30,2027 | Dec 31, 2026 | 170 | 8 | 2025-02-11 | low | med | low | low | high | 550000 | 590681 | 591056 | 280 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | Yes | 3 | 1 | 3 | 2 | 4 | 4 | 4 | 4 | 62.5% | 6 | 5 | 2 | 1 | 2 | 1 | 44% | 5 |  | 1117.2047
1069 | 1069 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Dec 31,2026 | Oct 31, 2027 | 66 | 5 | 2024-10-26 | high | low | low | high | low | 400000 | 391992 | 396981 | 279.7384 | EXPENSE | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 4 | 5 | 5 | 2 | 3 | 3 | 1 | 3 | 65% | 6 | 3 | 3 | 1 | 1 | 1 | 36% | 4 |  | 1300.7103
1070 | 1070 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Aug 31,2027 | Jul 31, 2026 | 153 | 2 | 2025-05-31 | med | low | high | high | med | 500000 | 550475 | 595557 | 117.2576 | EXPENSE | no | Pipeline segment |  | X | X |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 4 | 1 | 5 | 3 | 1 | 2 | 5 | 4 | 62.5% | 6 | 5 | 4 | 5 | 5 | 3 | 88% | 9 |  | 14995.8254
1071 | 1071 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Dec 31,2026 | Oct 31, 2027 | 122 | 5 | 2025-07-01 | med | low | med | low | low | 350000 | 340105 | 340380 | 81.2986 | CAPITAL | no | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | no | no | 3 | 4 | 4 | 5 | 1 | 2 | 3 | 1 | 57.5% | 6 | 1 | 1 | 5 | 4 | 2 | 52% | 6 |  | 76225.6763
1072 | 1072 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | April 30,2029 | Oct 31, 2026 | 279 | 5 | 2024-03-27 | med | high | high | high | high | 500000 | 724601 | 722346 | 98.531 | CAPITAL | no | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | no | no | no | Yes | 4 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 47.5% | 5 | 3 | 5 | 5 | 1 | 5 | 76% | 8 |  | 16.9273
1073 | 1073 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | May 31, 2026 | Oct 31, 2026 | 176 | 8 | 2025-07-08 | low | high | med | med | low | 350000 | 332474 | 335000 | 37.7222 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | Yes | 5 | 3 | 5 | 5 | 5 | 2 | 4 | 2 | 77.5% | 8 | 2 | 2 | 1 | 4 | 3 | 48% | 5 |  | 16.9273
1074 | 1074 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Sept 30,2026 | Oct 31, 2026 | 191 | 15 | 2025-06-23 | low | med | low | low | low | 350000 | 499124 | 498275 | 77.5311 | EXPENSE | no | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | no | Yes | no | Yes | 3 | 3 | 5 | 3 | 4 | 5 | 2 | 5 | 75% | 8 | 5 | 3 | 1 | 1 | 2 | 48% | 5 |  | 560.1412
1075 | 1075 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Nov 30,2029 | Jul 31, 2025 | 314 | 4 | 2024-09-20 | med | low | high | low | high | 400000 | 350785 | 393433 | 109.3207 | EXPENSE | no | Pipeline segment | X | X |  | X | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 3 | 1 | 3 | 2 | 2 | 1 | 5 | 4 | 52.5% | 6 | 5 | 4 | 1 | 4 | 1 | 60% | 6 |  | 560.1412
1076 | 1076 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | WINNIPEG | Sept 30,2026 | Jul 31, 2027 | 134 | 8 | 2025-08-19 | high | high | high | low | med | 350000 | 522998 | 520888 | 74.8121 | CAPITAL | no | Pipeline segment | X | X |  | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 2 | 2 | 3 | 5 | 4 | 2 | 3 | 60% | 6 | 4 | 4 | 1 | 3 | 5 | 68% | 7 |  | 16059.7772
1077 | 1077 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | April 30,2028 | Oct 31, 2027 | 341 | 8 | 2024-04-24 | high | med | med | med | high | 350000 | 411473 | 413108 | 142.0502 | CAPITAL | no | Pipeline segment | X | X | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 1 | 1 | 5 | 5 | 5 | 4 | 5 | 1 | 67.5% | 6 | 1 | 1 | 1 | 1 | 1 | 20% | 2 |  | 2310.5725
1078 | 1078 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30,2028 | Jul 31, 2025 | 359 | 8 | 2024-08-06 | med | med | low | med | low | 350000 | 466242 | 460097 | 82.7364 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 5 | 1 | 1 | 4 | 3 | 3 | 3 | 2 | 55% | 6 | 1 | 3 | 1 | 3 | 5 | 52% | 6 |  | 2480.6254
1079 | 1079 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Sept 30,2030 | Dec 31, 2026 | 187 | 7 | 2025-06-27 | low | med | med | low | high | 450000 | 531429 | 533699 | 69.7306 | CAPITAL | no | Pipeline segment | X | X |  | X | X | Yes | Yes | Yes | no | Yes | Yes | Yes | no | no | 4 | 4 | 2 | 2 | 5 | 3 | 2 | 3 | 62.5% | 6 | 4 | 4 | 1 | 1 | 5 | 60% | 6 |  | 2480.6254
1080 | 1080 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | May 31, 2026 | Oct 31, 2026 | 260 | 8 | 2025-04-15 | low | med | low | high | high | 450000 | 465673 | 462884 | 110.153 | CAPITAL | no | Pipeline segment | X | X | X |  | X | no | no | Yes | Yes | Yes | no | no | no | no | 5 | 5 | 1 | 4 | 5 | 5 | 4 | 4 | 82.5% | 9 | 3 | 1 | 1 | 4 | 3 | 48% | 5 |  | 495.1227
1081 | 1081 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Winnipeg | May 31, 2026 | Oct 31, 2025 | 181 | 8 | 2025-07-03 | low | med | med | med | low | 450000 | 400384 | 400364 | 36.7014 | CAPITAL | no | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 4 | 5 | 1 | 4 | 2 | 1 | 1 | 5 | 57.5% | 6 | 4 | 3 | 1 | 1 | 5 | 56% | 6 |  | 3220.812
1082 | 1082 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | Sept 30,2030 | Jul 31, 2026 | 90 | 5 | 2024-12-31 | high | low | low | med | low | 400000 | 424413 | 424247 | 13.6895 | CAPITAL | no | Pipeline segment | X | X |  | X | X | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 5 | 1 | 5 | 3 | 4 | 2 | 4 | 4 | 70% | 6 | 5 | 3 | 1 | 5 | 2 | 64% | 7 |  | 17906.9371
1083 | 1083 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Aug 31,2029 | Jul 31, 2025 | 80 | 4 | 2025-01-10 | med | low | high | low | med | 400000 | 487955 | 487622 | 81.7758 | EXPENSE | no | Pipeline segment | X | X | X |  |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 3 | 5 | 5 | 4 | 2 | 3 | 3 | 2 | 67.5% | 6 | 2 | 3 | 1 | 4 | 1 | 44% | 5 |  | 21537.8368
1084 | 1084 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | Aug 31,2027 | Dec 31, 2025 | 314 | 15 | 2024-09-20 | med | low | high | high | high | 450000 | 994397 | 956898 | 61.6448 | CAPITAL | Yes | Pipeline segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | no | Yes | Yes | 2 | 2 | 4 | 3 | 1 | 3 | 3 | 5 | 57.5% | 6 | 4 | 2 | 1 | 5 | 3 | 60% | 6 |  | 2973.4021
1085 | 1085 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Nov 30, 2025 | Jul 31, 2026 | 293 | 8 | 2025-01-11 | low | med | med | med | low | 450000 | 495726 | 469706 | 19.694 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 2 | 4 | 2 | 2 | 3 | 1 | 5 | 4 | 57.5% | 6 | 5 | 1 | 1 | 1 | 1 | 36% | 4 |  | 6487.5816
1086 | 1086 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | May 31, 2026 | Oct 31, 2025 | 287 | 7 | 2025-01-17 | low | med | high | high | low | 1800000 | 2095522 | 2095724 | 35.0188 | EXPENSE | no | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | no | no | no | 3 | 3 | 2 | 2 | 2 | 1 | 5 | 4 | 55% | 6 | 5 | 4 | 1 | 4 | 5 | 76% | 8 |  | 1083.35
1087 | 1087 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Sept 30,2026 | Dec 31, 2027 | 216 | 7 | 2024-05-29 | low | low | med | low | med | 2100000 | 2089588 | 2100050 | 1745.308 | EXPENSE | no | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | Yes | no | no | no | no | no | Yes | 5 | 3 | 4 | 5 | 2 | 3 | 5 | 1 | 70% | 6 | 4 | 3 | 1 | 4 | 1 | 52% | 6 |  | 1184.9141
1088 | 1088 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | May 31, 2026 | Oct 31, 2026 | 45 | 4 | 2025-11-16 | high | high | high | high | med | 400000 | 453423 | 450247 | 167.1303 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 5 | 2 | 5 | 1 | 4 | 3 | 1 | 60% | 6 | 5 | 2 | 1 | 4 | 2 | 56% | 6 |  | 1846.6194
1089 | 1089 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | April 30,2027 | Jul 31, 2026 | 258 | 8 | 2025-02-15 | high | high | low | low | low | 450000 | 434113 | 437206 | 51.5723 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 4 | 5 | 2 | 2 | 3 | 3 | 5 | 3 | 67.5% | 6 | 2 | 4 | 1 | 5 | 4 | 64% | 7 |  | 1846.6194
1090 | 1090 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Calgary | Dec 31,2026 | Jul 31, 2025 | 339 | 8 | 2024-08-26 | low | low | med | med | high | 450000 | 510412 | 516874 | 19.5924 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | no | no | no | no | no | no | Yes | 4 | 2 | 4 | 2 | 5 | 1 | 2 | 1 | 52.5% | 6 | 4 | 4 | 1 | 1 | 2 | 48% | 5 |  | 9580.8769
1091 | 1091 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | March 31, 2026 | Dec 31, 2025 | 316 | 8 | 2025-02-18 | high | med | low | high | low | 400000 | 827809 | 927128 | 245.1045 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | no | no | 4 | 3 | 3 | 5 | 4 | 4 | 4 | 3 | 75% | 8 | 2 | 5 | 1 | 3 | 2 | 52% | 6 |  | 8429.71
1092 | 1092 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | Aug 31,2027 | Oct 31, 2027 | 125 | 8 | 2025-03-28 | high | high | low | med | med | 650000 | 808987 | 803329 | 57.38 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 2 | 2 | 5 | 3 | 3 | 4 | 3 | 62.5% | 6 | 1 | 1 | 1 | 3 | 1 | 28% | 3 |  | 425
1093 | 1093 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | Dec 31,2026 | Oct 31, 2026 | 21 | 8 | 2024-12-10 | low | med | med | high | low | 450000 | 857877 | 866522 | 121.3811 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | no | no | Yes | no | no | Yes | no | no | Yes | 5 | 4 | 3 | 3 | 4 | 5 | 5 | 4 | 82.5% | 9 | 1 | 3 | 1 | 3 | 3 | 44% | 5 |  | 5875
1094 | 1094 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Nov 30, 2025 | Oct 31, 2026 | 282 | 7 | 2024-10-22 | high | low | med | med | med | 450000 | 428727 | 466800 | 526.2579 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 4 | 2 | 4 | 1 | 1 | 5 | 5 | 5 | 67.5% | 6 | 4 | 1 | 1 | 5 | 4 | 60% | 6 |  | 48755
1095 | 1095 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Aug 31,2027 | Oct 31, 2025 | 289 | 8 | 2024-06-15 | low | med | med | high | med | 350000 | 374581 | 382853 | 166.8084 | CAPITAL | Yes | Pipeline segment |  | X |  | X |  | no | no | no | Yes | Yes | Yes | no | no | no | 1 | 2 | 1 | 3 | 2 | 3 | 4 | 3 | 47.5% | 5 | 5 | 4 | 1 | 3 | 5 | 72% | 8 |  | 5522
1096 | 1096 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Edmonton | Dec 31, 2030 | Oct 31, 2027 | 33 | 8 | 2024-11-28 | low | high | high | low | high | 750000 | 861410 | 860656 | 15.3529 | EXPENSE | no | Derate/low flow Pipe segment |  | X | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | no | 5 | 5 | 2 | 5 | 4 | 5 | 4 | 4 | 85% | 9 | 5 | 5 | 5 | 1 | 3 | 76% | 8 |  | 4101.0339
1097 | 1097 | L1 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Regina | Dec 31,2026 | Jul 31, 2026 | 93 | 4 | 2025-04-29 | high | high | high | high | low | 1800000 | 1807733 | 1857547 | 102.2668 | EXPENSE | no | Pipeline segment | X |  | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 4 | 47.5% | 5 | 3 | 4 | 1 | 5 | 1 | 56% | 6 |  | 22170.3266
1098 | 1098 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | May 31, 2026 | Oct 31, 2025 | 346 | 7 | 2024-04-19 | high | low | high | low | high | 400000 | 555442 | 55668 | 71.2228 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | no | Yes | Yes | Yes | no | 2 | 2 | 1 | 5 | 1 | 5 | 1 | 4 | 52.5% | 6 | 5 | 2 | 1 | 3 | 3 | 56% | 6 |  | 1727.2647
1099 | 1099 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | Nov30,2027 | Oct 31, 2025 | 79 | 7 | 2025-01-11 | high | med | high | low | med | 450000 | 525700 | 525468 | 53.7439 | CAPITAL | no | Pipeline segment | X |  |  |  |  | Yes | Yes | no | no | no | Yes | Yes | no | Yes | 1 | 3 | 1 | 2 | 3 | 5 | 5 | 5 | 62.5% | 6 | 2 | 2 | 1 | 5 | 2 | 48% | 5 |  | 18109.7232
1100 | 1100 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Sept 30,2028 | Dec 31, 2027 | 198 | 8 | 2025-01-14 | med | high | low | low | low | 350000 | 780645 | 788090 | 117.9206 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | no | 5 | 5 | 2 | 5 | 5 | 2 | 1 | 4 | 72.5% | 8 | 1 | 1 | 1 | 4 | 1 | 32% | 4 |  | 3981.0002
1101 | 1101 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | March 31, 2026 | Oct 31, 2027 | 117 | 8 | 2024-12-04 | high | high | low | high | low | 500000 | 685306 | 681669 | 68.6381 | CAPITAL | Yes | Pipeline segment | X |  | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 2 | 3 | 4 | 1 | 1 | 3 | 2 | 5 | 52.5% | 6 | 1 | 2 | 1 | 2 | 1 | 28% | 3 |  | 20815.3255
1102 | 1102 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Mar 31,2030 | Dec 31, 2026 | 142 | 4 | 2025-08-11 | med | low | med | low | med | 500000 | 509915 | 513929 | 72.3249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | no | no | no | no | Yes | no | no | 2 | 5 | 3 | 1 | 1 | 1 | 2 | 3 | 45% | 5 | 2 | 2 | 1 | 5 | 5 | 60% | 6 |  | 48955
1103 | 1103 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Winnipeg | Dec 31,2026 | Dec 31, 2026 | 144 | 8 | 2025-03-09 | high | high | low | low | low | 450000 | 806609 | 803956 | 84.9423 | CAPITAL | no | pipeline segment | X | X | X | X |  | no | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 5 | 3 | 4 | 4 | 1 | 4 | 4 | 70% | 6 | 4 | 2 | 1 | 1 | 3 | 44% | 5 |  | 278.7236
1104 | 1104 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | Dec 31,2028 | Dec 31, 2026 | 257 | 7 | 2024-04-18 | med | low | high | high | low | 1500000 | 1506928 | 1495675 | 33.796 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | Yes | no | no | Yes | no | no | Yes | no | no | 5 | 1 | 1 | 1 | 5 | 5 | 2 | 5 | 62.5% | 6 | 4 | 4 | 1 | 3 | 2 | 56% | 6 |  | 203.1281
1105 | 1105 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP-REMEDITION | Calgary | Nov30,2027 | Dec 31, 2026 | 305 | 8 | 2024-03-01 | high | low | low | low | med | 850000 | 951968 | 9054634 | 41.9164 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | Yes | no | Yes | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 1 | 4 | 1 | 2 | 2 | 3 | 47.5% | 5 | 1 | 5 | 1 | 2 | 5 | 56% | 6 |  | 203.1281
1106 | 1106 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Mar 31,2030 | Jul 31, 2027 | 193 | 5 | 2024-06-21 | low | med | high | high | low | 350000 | 320570 | 315873 | 375.5287 | EXPENSE | no | Pipeline segment |  |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | Yes | 4 | 1 | 2 | 1 | 5 | 3 | 4 | 5 | 62.5% | 6 | 1 | 1 | 1 | 3 | 2 | 32% | 4 |  | 853.1382
1107 | 1107 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | March 31, 2026 | Dec 31, 2026 | 279 | 8 | 2024-10-25 | high | med | high | low | med | 350000 | 449452 | 496903 | 34.9002 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 2 | 4 | 2 | 5 | 4 | 3 | 3 | 1 | 60% | 6 | 5 | 4 | 5 | 2 | 2 | 72% | 8 |  | 23717.2367
1108 | 1108 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Dec 31,2028 | Jul 31, 2027 | 361 | 8 | 2024-11-04 | med | med | low | low | low | 450000 | 424655 | 452754 | 95.8703 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | no | no | Yes | no | no | no | no | Yes | 4 | 3 | 5 | 3 | 2 | 4 | 1 | 4 | 65% | 6 | 1 | 4 | 5 | 1 | 5 | 64% | 7 |  | 746.1723
1109 | 1109 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30,2028 | Jul 31, 2026 | 200 | 4 | 2025-04-14 | med | high | med | low | med | 350000 | 354302 | 387376 | 71.1665 | EXPENSE | no | Pipeline segment |  | X |  |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | 3 | 2 | 1 | 5 | 3 | 4 | 3 | 5 | 65% | 6 | 4 | 5 | 5 | 1 | 1 | 64% | 7 |  | 1174.9707
1110 | 1110 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | April 30,2027 | Oct 31, 2025 | 215 | 8 | 2024-05-30 | high | med | med | low | low | 450000 | 531419 | 534750 | 76.4614 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | no | no | 5 | 1 | 5 | 5 | 4 | 3 | 5 | 4 | 80% | 8 | 1 | 2 | 1 | 4 | 5 | 52% | 6 |  | 16021.8416
1111 | 1111 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANNUAL SURVEY | Regina | Nov 30,2029 | Oct 31, 2027 | 284 | 8 | 2024-10-20 | med | med | low | low | high | 780000 | 737705 | 703302 | 228.8332 | EXPENSE | Yes | Pipeline segment | X | X |  | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | no | 1 | 1 | 1 | 3 | 2 | 1 | 5 | 1 | 37.5% | 4 | 3 | 3 | 1 | 5 | 3 | 60% | 6 |  | 18.4662
1112 | 1112 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Winnipeg | Nov30,2027 | Oct 31, 2025 | 44 | 8 | 2025-09-17 | med | low | med | med | high | 550000 | 585478 | 580917 | 28.2991 | EXPENSE | no | Pipeline segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 2 | 3 | 3 | 5 | 1 | 5 | 1 | 3 | 57.5% | 6 | 2 | 5 | 1 | 3 | 5 | 64% | 7 |  | 121.8769
1113 | 1113 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | April 30,2027 | Jul 31, 2027 | 61 | 8 | 2025-10-31 | low | low | high | med | low | 450000 | 448450 | 489906 | 134.4344 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | no | no | Yes | Yes | Yes | no | no | Yes | 1 | 5 | 3 | 4 | 1 | 5 | 4 | 1 | 60% | 6 | 3 | 2 | 1 | 2 | 3 | 44% | 5 |  | 643.2391
1114 | 1114 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Mar 31,2030 | Jul 31, 2026 | 121 | 15 | 2025-09-01 | high | high | high | low | high | 450000 | 692798 | 634137 | 890.1864 | CAPITAL | no | Pipeline segment |  | X | X | X | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 2 | 4 | 1 | 3 | 4 | 4 | 4 | 5 | 67.5% | 6 | 1 | 4 | 1 | 2 | 4 | 48% | 5 |  | 267.7598
1115 | 1115 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Sept 30,2030 | Oct 31, 2027 | 100 | 4 | 2024-09-22 | high | med | low | high | med | 1500000 | 1550829 | 1550305 | 143.1102 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 3 | 2 | 1 | 2 | 2 | 2 | 5 | 2 | 47.5% | 5 | 4 | 3 | 1 | 1 | 3 | 48% | 5 |  | 267.7598
1116 | 1116 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Montreal | Mar 31,2030 | Oct 31, 2026 | 125 | 8 | 2025-06-28 | med | high | high | high | low | 550000 | 551865 | 564621 | 86.0466 | EXPENSE | Yes | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 4 | 2 | 2 | 2 | 1 | 3 | 5 | 3 | 55% | 6 | 4 | 3 | 1 | 4 | 4 | 64% | 7 |  | 7024.2246
1117 | 1117 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Quebec City | Nov30,2027 | Dec 31, 2027 | 356 | 5 | 2024-08-09 | low | med | low | med | low | 300000 | 385848 | 388631 | 71.0178 | EXPENSE | Yes | Pipeline segment |  |  |  | X |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 5 | 2 | 4 | 2 | 1 | 1 | 4 | 50% | 5 | 4 | 4 | 1 | 4 | 4 | 68% | 7 |  | 1591.1704
1118 | 1118 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | June 30, 2025 | Oct 31, 2027 | 204 | 15 | 2025-01-08 | high | high | high | med | med | 450000 | 489758 | 489076 | 56.3678 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | Yes | no | no | no | no | no | no | no | no | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 5 | 55% | 6 | 5 | 3 | 1 | 4 | 4 | 68% | 7 |  | 4785
1119 | 1119 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Edmonton | Nov30,2027 | Dec 31, 2025 | 121 | 10 | 2024-09-01 | low | high | high | low | high | 300000 | 373417 | 385508 | 204.7502 | EXPENSE | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 5 | 3 | 1 | 3 | 5 | 2 | 3 | 1 | 57.5% | 6 | 2 | 3 | 1 | 1 | 2 | 36% | 4 |  | 3358
1120 | 1120 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Saskatoon | Dec 31,2028 | Dec 31, 2026 | 235 | 8 | 2024-05-10 | high | high | med | med | med | 300000 | 384800 | 409516 | 193.3484 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | no | Yes | Yes | no | no | Yes | Yes | Yes | 5 | 1 | 3 | 2 | 3 | 1 | 2 | 3 | 50% | 5 | 1 | 4 | 1 | 1 | 2 | 36% | 4 |  | 5732.8906
1121 | 1121 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | April 30,2027 | Dec 31, 2025 | 274 | 8 | 2025-04-01 | high | med | high | low | low | 650000 | 1109127 | 1023937 | 53.022 | CAPITAL | no | Pipeline segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 3 | 3 | 3 | 2 | 4 | 5 | 2 | 5 | 67.5% | 6 | 5 | 1 | 1 | 5 | 1 | 52% | 6 |  | 3077.9635
1122 | 1122 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | Aug 31,2027 | Dec 31, 2025 | 181 | 4 | 2025-05-03 | high | low | low | low | med | 1800000 | 1789522 | 1832500 | 2.6813 | EXPENSE | no | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 1 | 5 | 4 | 5 | 4 | 5 | 1 | 1 | 65% | 6 | 1 | 5 | 1 | 3 | 1 | 44% | 5 |  | 13582.277
1123 | 1123 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | March 31, 2026 | Oct 31, 2026 | 217 | 7 | 2024-12-26 | med | high | low | high | high | 2000000 | 2020848 | 2089578 | 304.5368 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X | X | X | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 65% | 6 | 4 | 2 | 1 | 2 | 4 | 52% | 6 |  | 7709.8457
1124 | 1124 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Toronto | Nov30,2027 | Dec 31, 2027 | 32 | 15 | 2025-06-29 | med | med | low | high | high | 550000 | 899341 | 906308 | 44.7596 | EXPENSE | no | Pipeline segment | X | X |  | X | X | no | no | Yes | Yes | Yes | Yes | no | Yes | no | 5 | 5 | 3 | 5 | 5 | 5 | 4 | 5 | 92.5% | 10 | 3 | 5 | 5 | 1 | 2 | 64% | 7 |  | 7110.0938
1125 | 1125 | L2 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Ottawa | Nov 30, 2025 | Dec 31, 2027 | 43 | 10 | 2025-06-18 | med | med | low | low | low | 300000 | 323560 | 360010 | 86.1551 | EXPENSE | no | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | Yes | Yes | Yes | no | no | 2 | 1 | 4 | 4 | 1 | 2 | 5 | 1 | 50% | 5 | 2 | 1 | 1 | 3 | 4 | 44% | 5 |  | 4314.1949
1126 | 1126 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Saskatoon | April 30,2029 | Jul 31, 2025 | 307 | 10 | 2024-12-28 | med | low | high | low | med | 450000 | 452055 | 421982 | 100.5902 | CAPITAL | no | pipeline segment outage |  | X | X |  | X | no | Yes | no | no | no | Yes | no | no | Yes | 2 | 3 | 5 | 2 | 2 | 5 | 3 | 3 | 62.5% | 6 | 3 | 3 | 1 | 5 | 2 | 56% | 6 |  | 6062.6028
1127 | 1127 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Montreal | Sept 30,2030 | Dec 31, 2025 | 229 | 10 | 2024-05-16 | high | high | med | high | high | 300000 | 275080 | 295529 | 32.563 | EXPENSE | no | Pipeline segment |  |  | X | X | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 5 | 4 | 5 | 4 | 5 | 3 | 2 | 4 | 80% | 8 | 1 | 3 | 1 | 4 | 2 | 44% | 5 |  | 2898
1128 | 1128 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Winnipeg | May 31, 2026 | Oct 31, 2025 | 218 | 15 | 2025-05-27 | med | low | low | low | high | 450000 | 466475 | 465002 | 13.0596 | CAPITAL | no | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 5 | 4 | 1 | 3 | 5 | 5 | 5 | 5 | 82.5% | 9 | 1 | 3 | 1 | 3 | 3 | 44% | 5 |  | 4522
1129 | 1129 | L2 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Quebec City | April 30,2028 | Jul 31, 2026 | 286 | 8 | 2024-03-20 | low | med | low | high | med | 550000 | 478617 | 519000 | 3.8339 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 1 | 3 | 4 | 4 | 2 | 4 | 3 | 60% | 6 | 3 | 5 | 5 | 3 | 3 | 76% | 8 |  | 8429.71
1130 | 1130 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | March 31, 2026 | Jul 31, 2026 | 140 | 8 | 2024-08-13 | med | high | low | med | high | 500000 | 986111 | 989500 | 89.8531 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 5 | 40% | 4 | 3 | 1 | 1 | 2 | 1 | 32% | 4 |  | 5875
1131 | 1131 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | April 30,2027 | Dec 31, 2026 | 215 | 10 | 2024-12-28 | med | high | high | low | high | 350000 | 362980 | 373520 | 1124.6434 | EXPENSE | no | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 3 | 2 | 3 | 4 | 4 | 4 | 1 | 1 | 55% | 6 | 3 | 2 | 1 | 1 | 1 | 32% | 4 |  | 258
1132 | 1132 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | Dec 31,2028 | Jul 31, 2025 | 269 | 8 | 2025-02-04 | med | high | high | high | high | 350000 | 1071481 | 1076796 | 137.4312 | CAPITAL | no | Pipeline segment |  |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 2 | 3 | 1 | 4 | 1 | 44% | 5 |  | 4785
1133 | 1133 | L2 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Calgary | April 30,2027 | Oct 31, 2027 | 184 | 8 | 2025-01-28 | high | high | high | med | high | 250000 | 257881 | 301469 | 14.7788 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X |  | no | no | Yes | Yes | no | no | Yes | no | Yes | 1 | 2 | 2 | 4 | 2 | 4 | 5 | 3 | 57.5% | 6 | 2 | 2 | 1 | 2 | 4 | 44% | 5 |  | 13420.41
1134 | 1134 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Nov 30, 2025 | Jul 31, 2026 | 301 | 8 | 2024-03-05 | high | med | high | high | low | 350000 | 359833 | 352678 | 78.3491 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 2 | 4 | 1 | 5 | 4 | 3 | 3 | 2 | 60% | 6 | 3 | 1 | 1 | 3 | 3 | 44% | 5 |  | 1727.265
1135 | 1135 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | May 31, 2026 | Dec 31, 2025 | 37 | 8 | 2025-06-24 | med | high | high | med | low | 400000 | 836064 | 996142 | 188.6819 | EXPENSE | Yes | Pipeline segment |  | X |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 4 | 2 | 4 | 3 | 4 | 2 | 4 | 4 | 67.5% | 6 | 3 | 2 | 1 | 3 | 1 | 40% | 4 |  | 18109.72
1136 | 1136 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | April 30,2028 | Jul 31, 2027 | 205 | 4 | 2024-06-09 | low | low | low | high | med | 950000 | 951400 | 9573713 | 165.7118 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | no | no | no | Yes | 2 | 1 | 1 | 2 | 2 | 4 | 3 | 3 | 45% | 5 | 1 | 2 | 1 | 4 | 2 | 40% | 4 |  | 20815.33
1137 | 1137 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Dec 31,2026 | Dec 31, 2025 | 240 | 4 | 2024-12-03 | high | low | low | low | high | 650000 | 720531 | 725189 | 732.8044 | EXPENSE | no | Derate/low flow Pipe segment | X | X |  |  |  | no | Yes | Yes | Yes | Yes | no | no | no | no | 4 | 3 | 4 | 3 | 4 | 5 | 3 | 5 | 77.5% | 8 | 1 | 1 | 1 | 2 | 4 | 36% | 4 |  | 425
1138 | 1138 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Quebec City | April 30,2029 | Jul 31, 2027 | 56 | 4 | 2024-11-05 | low | high | med | low | med | 650000 | 680531 | 685189 | 146.1537 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | no | no | Yes | Yes | no | Yes | no | Yes | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 3 | 42.5% | 5 | 1 | 1 | 1 | 1 | 3 | 28% | 3 |  | 2789
1139 | 1139 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | April 30,2027 | Oct 31, 2025 | 265 | 7 | 2024-11-08 | low | high | low | low | med | 2100000 | 2124910 | 2128330 | 12.9047 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | no | no | no | no | Yes | no | 2 | 4 | 3 | 2 | 3 | 2 | 1 | 1 | 45% | 5 | 2 | 4 | 1 | 1 | 1 | 36% | 4 |  | 5666
1140 | 1140 | L2 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Winnipeg | Aug 31,2027 | Dec 31, 2026 | 84 | 4 | 2025-01-06 | high | high | low | med | med | 1300000 | 1324785 | 1350260 | 119.9716 | EXPENSE | no | Pipeline segment | X |  |  |  | X | Yes | no | no | Yes | Yes | no | no | Yes | no | 5 | 1 | 2 | 5 | 2 | 2 | 4 | 2 | 57.5% | 6 | 4 | 5 | 5 | 3 | 3 | 80% | 8 |  | 2789
1141 | 1141 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Sept 30,2026 | Oct 31, 2025 | 188 | 4 | 2025-06-26 | high | med | med | high | med | 400000 | 393878 | 395581 | 318.2127 | EXPENSE | no | Pipeline segment | X |  |  | X | X | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 5 | 3 | 1 | 2 | 4 | 4 | 4 | 1 | 60% | 6 | 2 | 5 | 1 | 2 | 3 | 52% | 6 |  | 23717.24
1142 | 1142 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | Nov 30,2029 | Jul 31, 2025 | 162 | 8 | 2024-10-20 | high | low | med | med | low | 500000 | 879950 | 872100 | 59.654 | CAPITAL | no | Pipeline segment |  | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 4 | 1 | 4 | 2 | 3 | 3 | 1 | 3 | 52.5% | 6 | 2 | 4 | 1 | 3 | 1 | 44% | 5 |  | 13677.18
1143 | 1143 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Dec 31,2028 | Dec 31, 2027 | 153 | 8 | 2025-07-31 | low | med | med | low | low | 350000 | 350821 | 350947 | 250.7139 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | no | no | no | Yes | 2 | 4 | 3 | 3 | 5 | 4 | 4 | 4 | 72.5% | 8 | 1 | 5 | 1 | 2 | 3 | 48% | 5 |  | 16021.84
1144 | 1144 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Aug 31,2027 | Oct 31, 2025 | 72 | 5 | 2025-08-20 | low | low | high | med | med | 400000 | 527515 | 518701 | 129.2729 | EXPENSE | no | Pipeline segment | X | X |  | X |  | no | Yes | Yes | Yes | no | no | no | Yes | no | 1 | 5 | 1 | 3 | 2 | 1 | 4 | 3 | 50% | 5 | 3 | 3 | 1 | 1 | 1 | 36% | 4 |  | 7007.921
1145 | 1145 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Nov 30,2029 | Dec 31, 2026 | 16 | 8 | 2025-10-15 | med | low | high | med | high | 350000 | 364592 | 366431 | 134.8065 | EXPENSE | no | Pipeline segment | X | X |  |  | X | Yes | no | Yes | Yes | no | no | no | no | no | 1 | 1 | 5 | 4 | 1 | 3 | 4 | 2 | 52.5% | 6 | 3 | 2 | 1 | 5 | 2 | 52% | 6 |  | 7007.921
1146 | 1146 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP-RECTIFIER | Quebec City | Dec 31,2028 | Dec 31, 2026 | 182 | 8 | 2024-07-02 | high | high | high | low | med | 600000 | 670309 | 670000 | 28.6028 | CAPITAL | no | pipeline segment outage |  |  | X |  | X | Yes | no | no | no | no | Yes | no | Yes | Yes | 2 | 1 | 5 | 1 | 5 | 1 | 2 | 2 | 47.5% | 5 | 2 | 2 | 1 | 4 | 3 | 48% | 5 |  | 121.8769
1147 | 1147 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Winnipeg | Mar 31,2030 | Jul 31, 2027 | 227 | 8 | 2025-05-18 | low | low | high | high | high | 450000 | 401590 | 401803 | 118.806 | CAPITAL | no | pipeline segment outage | X | X |  |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 2 | 2 | 1 | 1 | 2 | 2 | 4 | 5 | 47.5% | 5 | 3 | 3 | 1 | 4 | 1 | 48% | 5 |  | 267.7598
1148 | 1148 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | May 31, 2026 | Jul 31, 2025 | 280 | 4 | 2024-03-26 | high | high | low | high | low | 2100000 | 2014910 | 2018330 | 61.0855 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 2 | 3 | 5 | 5 | 5 | 3 | 2 | 5 | 75% | 8 | 2 | 4 | 5 | 2 | 4 | 68% | 7 |  | 6832.492
1149 | 1149 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | May 31, 2026 | Oct 31, 2025 | 94 | 8 | 2025-04-28 | low | low | low | low | low | 500000 | 677573 | 672660 | 11.9354 | EXPENSE | no | Pipeline segment |  |  | X |  |  | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 3 | 1 | 4 | 5 | 3 | 4 | 5 | 4 | 72.5% | 8 | 1 | 4 | 1 | 4 | 2 | 48% | 5 |  | 25885
1150 | 1150 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | Nov30,2027 | Oct 31, 2026 | 139 | 5 | 2025-03-14 | med | med | med | med | low | 400000 | 425230 | 434107 | 383.2311 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | no | Yes | no | Yes | no | no | Yes | no | 4 | 5 | 3 | 4 | 3 | 5 | 4 | 5 | 82.5% | 9 | 4 | 3 | 1 | 1 | 2 | 44% | 5 |  | 5732.891
1151 | 1151 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | June 30, 2025 | Dec 31, 2025 | 74 | 4 | 2025-01-16 | low | low | high | low | low | 1000000 | 995898 | 947471 | 78.2163 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X | X | Yes | no | no | no | no | no | Yes | no | Yes | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 1 | 50% | 5 | 5 | 4 | 1 | 2 | 2 | 56% | 6 |  | 3077.963
1152 | 1152 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | June 30, 2025 | Oct 31, 2026 | 87 | 5 | 2025-01-03 | high | high | high | low | high | 400000 | 493729 | 468570 | 162.7571 | EXPENSE | no | Pipeline segment | X | X |  |  | X | no | Yes | Yes | Yes | no | no | Yes | no | Yes | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 2 | 47.5% | 5 | 2 | 5 | 5 | 1 | 3 | 64% | 7 |  | 5097.261
1153 | 1153 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Calgary | Sept 30,2026 | Dec 31, 2026 | 236 | 8 | 2025-03-09 | low | low | low | med | low | 450000 | 444446 | 445417 | 145.3755 | CAPITAL | no | Pipeline segment |  |  | X | X | X | Yes | no | Yes | Yes | Yes | no | Yes | Yes | Yes | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 2 | 90% | 9 | 3 | 3 | 1 | 2 | 1 | 40% | 4 |  | 7709.846
1154 | 1154 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Calgary | Dec 31,2026 | Oct 31, 2026 | 176 | 8 | 2024-07-08 | high | low | med | high | high | 450000 | 858949 | 899364 | 44.4078 | CAPITAL | Yes | pipeline segment | X | X |  |  | X | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 2 | 5 | 3 | 2 | 4 | 4 | 3 | 1 | 60% | 6 | 1 | 3 | 1 | 3 | 1 | 36% | 4 |  | 7110.094
1155 | 1155 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | Mar 31,2030 | Oct 31, 2027 | 265 | 2 | 2024-11-08 | med | low | low | med | high | 850000 | 795426 | 800000 | 287.411 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 3 | 2 | 1 | 2 | 3 | 3 | 2 | 42.5% | 5 | 2 | 5 | 1 | 5 | 2 | 60% | 6 |  | 4391.637
1156 | 1156 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | April 30,2029 | Oct 31, 2026 | 45 | 4 | 2025-06-16 | low | med | med | low | high | 1000000 | 1135786 | 1204048 | 336.0415 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 1 | 1 | 1 | 4 | 4 | 1 | 2 | 42.5% | 5 | 3 | 1 | 1 | 4 | 2 | 44% | 5 |  | 4858.887
1157 | 1157 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | May 31, 2026 | Oct 31, 2026 | 101 | 8 | 2024-12-20 | med | high | med | med | high | 500000 | 567194 | 567060 | 49.109 | EXPENSE | no | Pipeline segment | X | X |  |  |  | Yes | Yes | no | no | Yes | no | no | Yes | Yes | 4 | 2 | 2 | 4 | 5 | 1 | 3 | 5 | 65% | 6 | 3 | 2 | 1 | 2 | 4 | 48% | 5 |  | 1090.538
1158 | 1158 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | Aug 31,2027 | Oct 31, 2027 | 57 | 8 | 2025-06-04 | med | med | med | high | med | 350000 | 306367 | 304154 | 56.2148 | CAPITAL | Yes | Pipeline segment |  | X | X |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 2 | 2 | 5 | 3 | 2 | 2 | 2 | 5 | 57.5% | 6 | 5 | 5 | 5 | 2 | 4 | 84% | 9 |  | 4052.085
1159 | 1159 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Nov30,2027 | Jul 31, 2027 | 63 | 8 | 2025-01-27 | low | high | med | low | med | 350000 | 306322 | 304238 | 104.2124 | CAPITAL | no | Pipeline segment | X | X | X |  | X | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 1 | 5 | 2 | 1 | 3 | 2 | 2 | 50% | 5 | 1 | 5 | 1 | 5 | 1 | 52% | 6 |  | 6062.603
1160 | 1160 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | May 31, 2026 | Oct 31, 2026 | 153 | 2 | 2025-07-31 | med | med | high | high | low | 300000 | 351489 | 352567 | 256.8876 | EXPENSE | no | Derate/low flow Pipe segment |  | X |  | X | X | Yes | Yes | no | Yes | Yes | no | no | no | no | 3 | 4 | 1 | 1 | 3 | 3 | 3 | 2 | 50% | 5 | 3 | 3 | 1 | 1 | 1 | 36% | 4 |  | 2610.39
1161 | 1161 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | June 30, 2025 | Oct 31, 2026 | 67 | 8 | 2025-10-25 | med | low | med | low | med | 350000 | 393527 | 393520 | 21.7053 | EXPENSE | no | Pipeline segment | X |  |  |  |  | no | no | no | Yes | no | no | Yes | no | Yes | 5 | 3 | 2 | 4 | 2 | 4 | 5 | 3 | 70% | 6 | 1 | 2 | 1 | 5 | 2 | 44% | 5 |  | 241.5599
1162 | 1162 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30,2028 | Oct 31, 2026 | 265 | 8 | 2024-04-10 | high | low | med | med | high | 400000 | 857316 | 863023 | 42.7227 | CAPITAL | no | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 2 | 3 | 3 | 5 | 1 | 2 | 4 | 57.5% | 6 | 4 | 4 | 5 | 1 | 2 | 64% | 7 |  | 4995.39
1163 | 1163 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Sept 30,2030 | Jul 31, 2027 | 291 | 8 | 2024-06-13 | low | med | low | low | low | 350000 | 420028 | 448094 | 90.2519 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | no | 4 | 5 | 1 | 3 | 1 | 1 | 2 | 1 | 45% | 5 | 1 | 4 | 1 | 2 | 1 | 36% | 4 |  | 6993.546
1164 | 1164 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Sept 30,2026 | Dec 31, 2026 | 36 | 8 | 2025-11-25 | low | high | med | low | low | 350000 | 354238 | 347119 | 61.5753 | EXPENSE | no | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 4 | 3 | 4 | 5 | 1 | 2 | 4 | 4 | 67.5% | 6 | 3 | 1 | 1 | 5 | 5 | 60% | 6 |  | 222.8052
1165 | 1165 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Aug 31,2029 | Jul 31, 2026 | 216 | 4 | 2025-05-29 | med | low | low | high | low | 1900000 | 1959945 | 1963759 | 28.0968 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | Yes | 4 | 2 | 2 | 3 | 3 | 2 | 3 | 2 | 52.5% | 6 | 2 | 2 | 1 | 3 | 4 | 48% | 5 |  | 5000
1166 | 1166 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Dec 31,2028 | Oct 31, 2027 | 355 | 8 | 2024-04-10 | low | low | high | high | low | 350000 | 401605 | 407547 | 7.1499 | CAPITAL | no | Pipeline segment | X |  |  | X |  | no | no | Yes | no | no | no | Yes | no | Yes | 1 | 4 | 4 | 3 | 4 | 1 | 2 | 1 | 50% | 5 | 5 | 5 | 1 | 3 | 1 | 60% | 6 |  | 347
1167 | 1167 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | June 30, 2025 | Jul 31, 2027 | 208 | 15 | 2025-06-06 | med | low | low | low | low | 450000 | 505184 | 505568 | 15.392 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | no | no | Yes | 2 | 5 | 3 | 4 | 3 | 1 | 5 | 3 | 65% | 6 | 2 | 3 | 1 | 3 | 3 | 48% | 5 |  | 1785
1168 | 1168 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Calgary | Aug 31,2027 | Dec 31, 2027 | 26 | 8 | 2024-12-05 | low | med | low | med | med | 750000 | 900542 | 936801 | 120.5022 | EXPENSE | Yes | Pipeline segment | X | X | X |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 5 | 3 | 2 | 2 | 5 | 3 | 4 | 3 | 67.5% | 6 | 2 | 3 | 1 | 2 | 2 | 40% | 4 |  | 172.2548
1169 | 1169 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Ottawa | April 30,2029 | Oct 31, 2026 | 99 | 5 | 2025-07-24 | high | low | high | med | high | 450000 | 679319 | 635544 | 35.2892 | CAPITAL | no | pipeline segment outage | X |  | X | X | X | Yes | Yes | Yes | no | no | Yes | no | no | no | 4 | 5 | 2 | 4 | 4 | 1 | 5 | 4 | 72.5% | 8 | 3 | 2 | 1 | 1 | 4 | 44% | 5 |  | 191.3942
1170 | 1170 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Nov 30, 2025 | Oct 31, 2027 | 36 | 4 | 2024-11-25 | med | med | med | low | low | 500000 | 544088 | 579248 | 152.364 | CAPITAL | no | Pipeline segment | X |  |  |  | X | Yes | no | Yes | no | Yes | Yes | no | Yes | Yes | 1 | 3 | 4 | 1 | 2 | 5 | 1 | 2 | 47.5% | 5 | 5 | 3 | 1 | 2 | 3 | 56% | 6 |  | 382.7885
1171 | 1171 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Nov 30,2029 | Oct 31, 2025 | 264 | 8 | 2025-04-11 | low | med | med | med | low | 450000 | 360834 | 399482 | 177.3607 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | Yes | no | no | Yes | no | Yes | no | no | 2 | 3 | 3 | 4 | 3 | 2 | 3 | 3 | 57.5% | 6 | 1 | 3 | 1 | 1 | 2 | 32% | 4 |  | 173.2929
1172 | 1172 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | April 30,2027 | Dec 31, 2026 | 61 | 8 | 2025-10-31 | high | low | high | med | med | 500000 | 498707 | 498210 | 152.9866 | EXPENSE | no | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | Yes | no | no | no | no | 4 | 2 | 2 | 2 | 3 | 5 | 5 | 5 | 70% | 6 | 3 | 1 | 1 | 3 | 5 | 52% | 6 |  | 749.7244
1173 | 1173 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | Sept 30,2026 | Jul 31, 2025 | 327 | 4 | 2024-05-08 | high | high | med | high | med | 1500000 | 1812742 | 1842116 | 34.0888 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 2 | 2 | 4 | 5 | 5 | 5 | 2 | 3 | 70% | 6 | 1 | 5 | 1 | 4 | 5 | 64% | 7 |  | 41798.52
1174 | 1174 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-RECTIFIER | Edmonton | April 30,2028 | Oct 31, 2026 | 199 | 2 | 2024-09-13 | high | low | low | low | high | 600000 | 598833 | 611085 | 218.6029 | EXPENSE | no | pipeline segment outage | X |  | X | X |  | no | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 1 | 2 | 3 | 2 | 4 | 5 | 2 | 55% | 6 | 4 | 5 | 5 | 4 | 4 | 88% | 9 |  | 425
1175 | 1175 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Aug 31,2029 | Oct 31, 2026 | 46 | 5 | 2024-11-15 | high | low | high | high | low | 400000 | 522720 | 529911 | 242.1342 | CAPITAL | no | Pipeline segment |  |  |  | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 4 | 2 | 5 | 1 | 4 | 3 | 3 | 62.5% | 6 | 2 | 1 | 1 | 2 | 2 | 32% | 4 |  | 20000
1176 | 1176 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Nov 30, 2025 | Jul 31, 2027 | 160 | 5 | 2025-05-24 | med | high | low | med | low | 400000 | 408000 | 425000 | 218.7171 | EXPENSE | Yes | pipeline segment |  |  | X | X | X | no | no | no | no | no | Yes | Yes | Yes | no | 5 | 2 | 1 | 2 | 5 | 5 | 2 | 1 | 57.5% | 6 | 1 | 3 | 1 | 4 | 2 | 44% | 5 |  | 2078
1177 | 1177 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | May 31, 2026 | Dec 31, 2026 | 172 | 5 | 2024-07-12 | low | high | med | med | high | 500000 | 586296 | 558571 | 163.365 | CAPITAL | no | Pipeline segment |  | X | X | X | X | no | no | Yes | no | no | no | Yes | no | no | 2 | 5 | 3 | 4 | 4 | 2 | 4 | 1 | 62.5% | 6 | 1 | 1 | 1 | 2 | 4 | 36% | 4 |  | 1875
1178 | 1178 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Sept 30,2030 | Dec 31, 2026 | 106 | 4 | 2025-09-16 | high | high | med | high | high | 500000 | 501652 | 545736 | 41.1751 | EXPENSE | no | Pipeline segment |  | X | X |  |  | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 5 | 5 | 1 | 3 | 2 | 3 | 1 | 3 | 57.5% | 6 | 5 | 4 | 1 | 3 | 3 | 64% | 7 |  | 7718.869
1179 | 1179 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Dec 31, 2030 | Oct 31, 2025 | 18 | 8 | 2025-12-13 | low | med | med | med | low | 500000 | 513241 | 519365 | 5.9556 | CAPITAL | no | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | no | 5 | 3 | 1 | 2 | 3 | 3 | 3 | 4 | 60% | 6 | 2 | 1 | 1 | 1 | 4 | 36% | 4 |  | 7718.869
1180 | 1180 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Mar 31,2030 | Jul 31, 2025 | 330 | 4 | 2024-09-04 | low | high | high | high | high | 750000 | 1804556 | 813074 | 83.977 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  | X | Yes | Yes | no | no | Yes | no | no | no | no | 3 | 1 | 4 | 2 | 2 | 2 | 3 | 3 | 50% | 5 | 3 | 1 | 1 | 3 | 2 | 40% | 4 |  | 6993.546
1181 | 1181 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Aug 31,2027 | Jul 31, 2027 | 343 | 4 | 2024-08-22 | low | high | low | med | high | 750000 | 853330 | 827797 | 200.4576 | EXPENSE | no | Derate/low flow Pipe segment | [5 empty] | no | no | no | no | Yes | Yes | no | no | Yes | 1 | 2 | 4 | 5 | 4 | 4 | 3 | 3 | 65% | 6 | 2 | 1 | 1 | 1 | 1 | 24% | 3 |  | 1475
1182 | 1182 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Aug 31,2027 | Oct 31, 2027 | 61 | 8 | 2025-01-29 | med | high | low | high | med | 400000 | 582895 | 585540 | 199.4572 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 3 | 2 | 1 | 1 | 2 | 4 | 5 | 5 | 57.5% | 6 | 1 | 4 | 1 | 3 | 5 | 56% | 6 |  | 2369.828
1183 | 1183 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | Dec 31, 2030 | Dec 31, 2027 | 298 | 2 | 2025-01-06 | high | low | med | high | high | 450000 | 422239 | 452847 | 172.7549 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 4 | 3 | 3 | 2 | 3 | 5 | 2 | 65% | 6 | 1 | 2 | 1 | 2 | 3 | 36% | 4 |  | 3138.866
1184 | 1184 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Montreal | Aug 31,2029 | Oct 31, 2026 | 74 | 8 | 2024-10-18 | high | low | med | high | high | 500000 | 949928 | 991050 | 59.9299 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | Yes | Yes | no | no | no | Yes | no | Yes | 1 | 2 | 3 | 5 | 4 | 3 | 1 | 3 | 55% | 6 | 3 | 1 | 1 | 2 | 5 | 48% | 5 |  | 3138.866
1185 | 1185 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | Aug 31,2027 | Jul 31, 2026 | 267 | 8 | 2024-07-07 | med | high | med | high | high | 450000 | 929329 | 985745 | 24.4952 | CAPITAL | no | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 3 | 5 | 4 | 1 | 1 | 4 | 1 | 5 | 60% | 6 | 4 | 5 | 1 | 3 | 4 | 68% | 7 |  | 14928.99
1186 | 1186 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | April 30,2029 | Jul 31, 2027 | 36 | 4 | 2025-11-25 | high | high | med | med | med | 1500000 | 1517309 | 1577293 | 56.1178 | EXPENSE | no | Derate/low flow Pipe segment |  | X |  |  | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | no | 3 | 4 | 2 | 2 | 1 | 2 | 3 | 4 | 52.5% | 6 | 5 | 1 | 1 | 2 | 3 | 48% | 5 |  | 4785
1187 | 1187 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Edmonton | Sept 30,2026 | Jul 31, 2027 | 151 | 8 | 2024-10-31 | med | med | low | high | med | 550000 | 583881 | 573876 | 11.6418 | EXPENSE | no | Pipeline segment |  | X |  | X | X | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 2 | 5 | 2 | 3 | 4 | 5 | 5 | 1 | 67.5% | 6 | 3 | 2 | 1 | 4 | 4 | 56% | 6 |  | 4542.743
1188 | 1188 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | Dec 31,2028 | Oct 31, 2026 | 267 | 15 | 2025-04-08 | low | med | low | low | high | 500000 | 554230 | 580197 | 6.3304 | CAPITAL | no | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | no | no | no | 4 | 3 | 3 | 4 | 2 | 1 | 5 | 2 | 60% | 6 | 5 | 5 | 5 | 2 | 1 | 72% | 8 |  | 3333.134
1189 | 1189 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Saskatoon | Dec 31,2026 | Dec 31, 2026 | 246 | 10 | 2024-04-29 | low | low | med | high | low | 450000 | 562796 | 571191 | 107.4224 | CAPITAL | no | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | no | no | no | no | Yes | Yes | 4 | 3 | 1 | 4 | 2 | 1 | 1 | 5 | 52.5% | 6 | 3 | 3 | 1 | 2 | 1 | 40% | 4 |  | 1117.205
1190 | 1190 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Edmonton | April 30,2027 | Dec 31, 2027 | 274 | 10 | 2024-10-30 | med | med | low | med | low | 550000 | 480203 | 490541 | 101.2735 | EXPENSE | Yes | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 2 | 4 | 1 | 4 | 1 | 5 | 3 | 5 | 62.5% | 6 | 2 | 5 | 1 | 1 | 3 | 48% | 5 |  | 45.3112
1191 | 1191 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Sept 30,2030 | Dec 31, 2026 | 170 | 4 | 2024-10-12 | high | low | high | med | high | 400000 | 488222 | 477827 | 202.8834 | CAPITAL | Yes | Pipeline segment |  | X |  | X | X | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 1 | 2 | 1 | 3 | 3 | 2 | 2 | 5 | 47.5% | 5 | 4 | 5 | 5 | 4 | 2 | 80% | 8 |  | 1300.71
1192 | 1192 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | WINNIPEG | Sept 30,2030 | Jul 31, 2025 | 142 | 15 | 2024-08-11 | med | med | high | med | low | 450000 | 481653 | 480764 | 90.3714 | CAPITAL | no | Pipeline segment | X | X | X |  |  | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 4 | 2 | 3 | 5 | 1 | 3 | 1 | 1 | 50% | 5 | 3 | 2 | 1 | 5 | 1 | 48% | 5 |  | 263.7275
1193 | 1193 | L2 | PIPE INTEGRITY | EXCAVATION | VALIDATION | North Bay | Dec 31,2028 | Dec 31, 2025 | 108 | 8 | 2025-09-14 | med | med | high | low | med | 250000 | 200338 | 234729 | 167.215 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 4 | 92.5% | 10 | 1 | 5 | 5 | 5 | 4 | 80% | 8 |  | 14995.83
1194 | 1194 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Aug 31,2029 | Oct 31, 2027 | 67 | 4 | 2025-10-25 | high | low | high | med | high | 1500000 | 1450980 | 1458652 | 118.0594 | EXPENSE | no | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 5 | 4 | 4 | 4 | 2 | 5 | 5 | 5 | 85% | 9 | 5 | 1 | 1 | 3 | 3 | 52% | 6 |  | 76225.68
1195 | 1195 | L3 | PIPE INTEGRITY | L&R | LAUNCHER RECEIVER INSTALL | Quebec City | Aug 31,2027 | Jul 31, 2025 | 53 | 8 | 2025-09-08 | med | low | med | high | high | 4585000 | 4680012 | 4700046 | 91.5834 | CAPITAL | Yes | Station outage |  |  | X |  |  | no | Yes | Yes | no | Yes | no | no | no | Yes | 4 | 4 | 1 | 1 | 4 | 2 | 1 | 2 | 47.5% | 5 | 3 | 3 | 1 | 2 | 5 | 56% | 6 |  | 16.9273
1196 | 1196 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Dec 31,2028 | Oct 31, 2027 | 17 | 4 | 2025-07-14 | high | low | low | low | med | 750000 | 710189 | 719044 | 61.5579 | EXPENSE | no | Derate/low flow Pipe segment | X |  |  | X | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 2 | 3 | 5 | 1 | 2 | 3 | 5 | 60% | 6 | 5 | 1 | 1 | 2 | 2 | 44% | 5 |  | 16.9273
1197 | 1197 | L2 | PIPE INTEGRITY | L&R | TETHER | Winnipeg | Nov 30, 2025 | Jul 31, 2027 | 259 | 7 | 2025-04-16 | med | low | low | med | low | 850000 | 892844 | 905260 | 1023.831 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | Yes | no | Yes | no | Yes | no | 2 | 4 | 4 | 3 | 5 | 2 | 1 | 5 | 65% | 6 | 4 | 5 | 1 | 2 | 1 | 52% | 6 |  | 560.1412
1198 | 1198 | L2 | PIPE INTEGRITY | L&R | TETHER | Quebec City | April 30,2028 | Oct 31, 2026 | 329 | 4 | 2024-02-06 | low | low | low | high | high | 450000 | 447194 | 557595 | 159.9953 | EXPENSE | Yes | Unit outage | X | X |  | X |  | no | Yes | no | Yes | Yes | Yes | no | no | Yes | 2 | 4 | 1 | 5 | 3 | 3 | 3 | 4 | 62.5% | 6 | 5 | 1 | 1 | 1 | 4 | 48% | 5 |  | 10535.75
1199 | 1199 | L1 | PIPE INTEGRITY | L&R | LAUNCHER RECEIVER INSTALL | Saskatoon | Aug 31,2027 | Dec 31, 2025 | 160 | 4 | 2024-10-22 | med | high | low | high | high | 6620000 | 6515868 | 6632189 | 33.0673 | CAPITAL | no | Station outage |  | X |  | X |  | no | no | Yes | Yes | no | Yes | no | Yes | Yes | 2 | 1 | 1 | 5 | 2 | 5 | 3 | 5 | 60% | 6 | 4 | 1 | 1 | 3 | 4 | 52% | 6 |  | 16059.78
1200 | 1200 | L3 | PIPE INTEGRITY | L&R | TETHER | North Bay | Aug 31,2029 | Oct 31, 2025 | 236 | 8 | 2024-08-07 | med | med | med | low | high | 850000 | 792844 | 805260 | 190.1713 | EXPENSE | no | Pipeline segment |  |  |  | X | X | Yes | no | no | no | no | Yes | no | no | no | 2 | 5 | 2 | 4 | 2 | 1 | 1 | 5 | 55% | 6 | 1 | 5 | 1 | 1 | 2 | 40% | 4 |  | 10182.17
1201 | 1201 | L3 | PIPE INTEGRITY | L&R | LAUNCHER RECEIVER INSTALL | Montreal | Dec 31,2026 | Jul 31, 2027 | 44 | 8 | 2025-06-17 | med | med | high | low | high | 3500000 | 3705220 | 3754725 | 42.5944 | CAPITAL | no | Station outage | X | X | X | X |  | Yes | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 3 | 1 | 5 | 2 | 5 | 1 | 1 | 52.5% | 6 | 4 | 1 | 1 | 4 | 2 | 48% | 5 |  | 2310.573
1202 | 1202 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Sept 30, 2025 | Oct 31, 2026 | 13 | 4 | 2025-07-18 | med | high | low | low | high | 400000 | 405834 | 452505 | 98.3964 | EXPENSE | no | pipeline segment outage |  |  |  |  | X | no | Yes | Yes | Yes | no | no | no | Yes | no | 3 | 5 | 2 | 1 | 2 | 2 | 3 | 3 | 52.5% | 6 | 5 | 1 | 1 | 2 | 4 | 52% | 6 |  | 2369.828
1203 | 1203 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | June 30, 2025 | Oct 31, 2025 | 346 | 8 | 2024-08-19 | low | high | low | high | high | 350000 | 327934 | 382673 | 32.9463 | CAPITAL | no | pipeline segment outage | X | X |  |  |  | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 4 | 47.5% | 5 | 5 | 1 | 1 | 2 | 3 | 48% | 5 |  | 2480.625
1204 | 1204 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Dec 31,2026 | Oct 31, 2025 | 248 | 7 | 2024-07-26 | med | low | high | high | high | 1900000 | 1977581 | 1989278 | 94.5144 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | no | no | Yes | Yes | Yes | Yes | Yes | no | 3 | 2 | 4 | 3 | 4 | 2 | 4 | 1 | 57.5% | 6 | 2 | 4 | 1 | 5 | 5 | 68% | 7 |  | 2480.625
1205 | 1205 | L2 | PIPE INTEGRITY | EXCAVATION | VALIDATION | North Bay | Sept 30,2028 | Jul 31, 2025 | 266 | 4 | 2024-04-09 | med | high | low | low | med | 250000 | 252651 | 244871 | 56.4922 | EXPENSE | no | NO |  |  | X | X |  | no | Yes | no | Yes | no | no | Yes | no | no | 3 | 1 | 1 | 3 | 3 | 1 | 4 | 4 | 50% | 5 | 3 | 5 | 1 | 5 | 2 | 64% | 7 |  | 31873.29
1206 | 1206 | L1 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Winnipeg | Sept 30,2028 | Jul 31, 2027 | 36 | 4 | 2025-09-25 | med | low | med | high | low | 250000 | 260869 | 306879 | 692.039 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X |  | no | Yes | Yes | Yes | Yes | Yes | no | no | no | 3 | 1 | 1 | 4 | 3 | 5 | 3 | 1 | 52.5% | 6 | 2 | 4 | 1 | 1 | 1 | 36% | 4 |  | 5521.373
1207 | 1207 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Sept 30, 2025 | Oct 31, 2026 | 75 | 4 | 2025-10-17 | high | high | med | med | med | 850000 | 850944 | 820000 | 24.4354 | EXPENSE | no | Derate/low flow Pipe segment |  | X | X |  | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 1 | 3 | 3 | 4 | 5 | 3 | 4 | 62.5% | 6 | 4 | 1 | 1 | 1 | 4 | 44% | 5 |  | 3220.812
1208 | 1208 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Nov 30, 2025 | Oct 31, 2026 | 36 | 15 | 2025-02-23 | low | high | med | high | high | 500000 | 530563 | 545236 | 60.5912 | CAPITAL | no | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 4 | 3 | 2 | 5 | 2 | 2 | 5 | 1 | 60% | 6 | 4 | 1 | 1 | 4 | 4 | 56% | 6 |  | 13659.19
1209 | 1209 | L3 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Winnipeg | Sept 30,2030 | Oct 31, 2025 | 224 | 5 | 2024-05-21 | med | med | med | low | low | 250000 | 276609 | 286072 | 96.9233 | EXPENSE | Yes | NO | [5 empty] | Yes | no | Yes | Yes | Yes | no | no | Yes | no | 3 | 5 | 1 | 1 | 5 | 1 | 5 | 3 | 60% | 6 | 2 | 1 | 1 | 5 | 1 | 40% | 4 |  | 19639.87
1210 | 1210 | L2 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Winnipeg | June 30, 2025 | Jul 31, 2027 | 232 | 8 | 2024-08-11 | high | low | high | med | med | 300000 | 469283 | 461267 | 143.1483 | EXPENSE | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 3 | 1 | 4 | 5 | 1 | 2 | 2 | 5 | 57.5% | 6 | 2 | 3 | 1 | 5 | 4 | 60% | 6 |  | 2166.583
1211 | 1211 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Dec 31, 2030 | Jul 31, 2026 | 202 | 8 | 2025-04-12 | high | med | high | med | high | 300000 | 296541 | 294310 | 86.2445 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | Yes | no | Yes | no | Yes | Yes | no | Yes | 2 | 4 | 1 | 2 | 1 | 2 | 2 | 5 | 47.5% | 5 | 1 | 5 | 1 | 5 | 4 | 64% | 7 |  | 1184.914
1212 | 1212 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Sept 30, 2025 | Jul 31, 2025 | 223 | 7 | 2024-12-20 | med | low | high | med | high | 2000000 | 2451951 | 2464009 | 287.5273 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 4 | 50% | 5 | 1 | 3 | 1 | 1 | 2 | 32% | 4 |  | 1846.619
1213 | 1213 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Aug 31,2029 | Oct 31, 2025 | 206 | 2 | 2025-01-06 | med | med | low | med | med | 350000 | 387958 | 348402 | 338.5852 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 5 | 3 | 4 | 2 | 4 | 2 | 2 | 4 | 65% | 6 | 3 | 5 | 1 | 5 | 4 | 72% | 8 |  | 4522
1214 | 1214 | L2 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Saskatoon | Nov 30,2029 | Jul 31, 2027 | 18 | 8 | 2025-10-13 | low | high | high | low | low | 300000 | 303443 | 304754 | 122.9237 | EXPENSE | no | Pipeline segment |  |  | X |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 5 | 1 | 5 | 3 | 4 | 4 | 3 | 65% | 6 | 3 | 4 | 1 | 5 | 3 | 64% | 7 |  | 8429.71
1215 | 1215 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | Dec 31,2026 | Jul 31, 2026 | 360 | 8 | 2024-04-05 | low | high | med | low | high | 1750000 | 1822372 | 1853987 | 87.2637 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X | X | X | no | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 4 | 5 | 4 | 2 | 1 | 5 | 4 | 2 | 67.5% | 6 | 3 | 4 | 5 | 4 | 1 | 68% | 7 |  | 8756
1216 | 1216 | L1 | PIPE INTEGRITY | Excavation | RECOAT | Winnipeg | Sept 30, 2025 | Jul 31, 2026 | 135 | 4 | 2024-11-16 | low | low | low | low | high | 350000 | 424886 | 436808 | 9.937 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | Yes | no | no | Yes | Yes | Yes | Yes | no | 3 | 4 | 3 | 2 | 4 | 5 | 3 | 4 | 70% | 6 | 1 | 4 | 1 | 4 | 4 | 56% | 6 |  | 52
1217 | 1217 | L2 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Edmonton | Sept 30,2030 | Jul 31, 2025 | 101 | 8 | 2024-12-20 | low | low | med | low | med | 300000 | 340748 | 344971 | 7.9241 | EXPENSE | no | Pipeline segment |  | X | X |  | X | no | no | no | Yes | no | no | no | Yes | no | 1 | 5 | 2 | 1 | 2 | 1 | 5 | 3 | 50% | 5 | 5 | 2 | 1 | 4 | 1 | 52% | 6 |  | 258
1218 | 1218 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Quebec City | March 31, 2026 | Oct 31, 2025 | 131 | 4 | 2024-08-22 | low | med | high | high | med | 750000 | 741959 | 741361 | 122.5762 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 5 | 4 | 2 | 5 | 2 | 2 | 1 | 5 | 65% | 6 | 2 | 3 | 1 | 4 | 1 | 44% | 5 |  | 4101.0339
1219 | 1219 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | North Bay | March 31, 2026 | Dec 31, 2025 | 204 | 4 | 2024-09-08 | high | med | high | med | med | 350000 | 377958 | 378402 | 60.2487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | Yes | Yes | no | Yes | 4 | 4 | 2 | 2 | 3 | 5 | 4 | 4 | 70% | 6 | 1 | 2 | 1 | 5 | 1 | 40% | 4 |  | 842.9817
1220 | 1220 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | Dec 31, 2030 | Jul 31, 2025 | 133 | 2 | 2025-03-20 | low | med | low | low | med | 520000 | 520076 | 517552 | 339.8771 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 2 | 4 | 2 | 3 | 1 | 2 | 4 | 4 | 55% | 6 | 1 | 2 | 1 | 1 | 2 | 28% | 3 |  | 13420.4072
1221 | 1221 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Sept 30,2026 | Dec 31, 2025 | 158 | 4 | 2025-02-23 | med | low | low | low | med | 750000 | 800359 | 808385 | 201.382 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X |  | X | Yes | no | no | no | no | no | Yes | no | no | 3 | 2 | 2 | 3 | 1 | 2 | 4 | 5 | 55% | 6 | 5 | 1 | 1 | 5 | 2 | 56% | 6 |  | 1578
1222 | 1222 | L1 | PIPE INTEGRITY | Excavation | RECOAT | Montreal | Sept 30,2030 | Dec 31, 2027 | 237 | 5 | 2024-08-06 | high | med | low | high | med | 500000 | 580071 | 583077 | 339.2298 | EXPENSE | no | pipeline segment outage |  | X | X |  |  | no | Yes | no | Yes | no | Yes | no | no | no | 3 | 1 | 3 | 1 | 4 | 1 | 2 | 3 | 45% | 5 | 2 | 2 | 1 | 4 | 2 | 44% | 5 |  | 278.7236
1223 | 1223 | L1 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Quebec City | April 30,2029 | Dec 31, 2025 | 284 | 4 | 2024-10-20 | low | high | high | low | med | 125000 | 137635 | 149404 | 946.0832 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 5 | 3 | 3 | 1 | 5 | 3 | 2 | 5 | 67.5% | 6 | 1 | 2 | 1 | 2 | 2 | 32% | 4 |  | 278.7236
1224 | 1224 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Nov 30,2029 | Dec 31, 2025 | 131 | 8 | 2024-08-22 | med | med | high | med | low | 450000 | 522096 | 523817 | 101.141 | CAPITAL | no | Pipeline segment |  | X |  | X |  | no | Yes | no | no | Yes | Yes | Yes | no | no | 5 | 2 | 1 | 5 | 5 | 4 | 4 | 5 | 77.5% | 8 | 5 | 4 | 1 | 5 | 3 | 72% | 8 |  | 203.1281
1225 | 1225 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Toronto | May 31, 2026 | Dec 31, 2027 | 103 | 4 | 2024-12-18 | low | low | high | low | med | 550000 | 957635 | 1018992 | 105.7103 | EXPENSE | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 5 | 1 | 1 | 5 | 1 | 4 | 2 | 2 | 52.5% | 6 | 4 | 2 | 1 | 1 | 3 | 44% | 5 |  | 203.1281
1226 | 1226 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | June 30, 2025 | Oct 31, 2025 | 29 | 8 | 2025-03-02 | high | low | low | low | low | 450000 | 407875 | 435270 | 80.7138 | CAPITAL | no | pipeline segment outage | X | X |  | X |  | no | Yes | no | Yes | no | Yes | no | Yes | no | 3 | 2 | 3 | 1 | 5 | 4 | 3 | 2 | 57.5% | 6 | 3 | 3 | 5 | 4 | 1 | 64% | 7 |  | 203.1281
1227 | 1227 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | March 31, 2026 | Jul 31, 2025 | 34 | 4 | 2025-02-25 | med | low | med | med | med | 1000000 | 1021505 | 1092551 | 56.5076 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | no | no | no | no | no | no | no | no | Yes | 5 | 4 | 3 | 5 | 1 | 4 | 2 | 4 | 70% | 6 | 3 | 4 | 5 | 3 | 5 | 80% | 8 |  | 853.1382
1228 | 1228 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Nov 30,2029 | Dec 31, 2026 | 113 | 8 | 2025-09-09 | high | high | high | high | high | 350000 | 404631 | 406242 | 26.1799 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | Yes | no | no | no | Yes | no | Yes | Yes | 4 | 3 | 4 | 3 | 3 | 3 | 1 | 2 | 57.5% | 6 | 3 | 2 | 1 | 1 | 2 | 36% | 4 |  | 746.1723
1229 | 1229 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Montreal | Dec 31, 2030 | Jul 31, 2026 | 291 | 4 | 2025-01-13 | med | med | med | low | low | 500000 | 571069 | 578420 | 20.7067 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | no | no | no | no | Yes | Yes | Yes | 4 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 37.5% | 4 | 2 | 4 | 1 | 1 | 2 | 40% | 4 |  | 1174.9707
1230 | 1230 | L3 | PIPE INTEGRITY | Excavation | RECOAT | Ottawa | March 31, 2026 | Dec 31, 2026 | 356 | 4 | 2024-08-09 | low | high | low | high | low | 400000 | 574072 | 556987 | 133.3009 | EXPENSE | no | Station outage | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | Yes | no | Yes | 1 | 3 | 1 | 4 | 5 | 3 | 2 | 1 | 50% | 5 | 5 | 1 | 1 | 2 | 4 | 52% | 6 |  | 16021.8416
1231 | 1231 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Aug 31,2027 | Jul 31, 2026 | 333 | 15 | 2024-05-02 | high | med | med | low | low | 450000 | 836197 | 864086 | 65.7764 | CAPITAL | no | Pipeline segment | X | X | X |  | X | Yes | Yes | no | no | no | no | Yes | Yes | Yes | 2 | 2 | 4 | 4 | 2 | 2 | 5 | 5 | 65% | 6 | 4 | 5 | 5 | 1 | 3 | 72% | 8 |  | 7007.9205
1232 | 1232 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Dec 31,2026 | Dec 31, 2026 | 86 | 2 | 2025-10-06 | med | med | high | med | low | 350000 | 331626 | 366466 | 618.2189 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | Yes | no | Yes | Yes | Yes | no | no | no | Yes | 2 | 4 | 4 | 4 | 2 | 5 | 1 | 5 | 67.5% | 6 | 5 | 5 | 5 | 1 | 4 | 80% | 8 |  | 1685.9635
1233 | 1233 | L1 | PIPE INTEGRITY | EXCAVATION | VALIDATION | North Bay | April 30,2028 | Oct 31, 2027 | 11 | 2 | 2025-07-20 | high | med | high | med | high | 125000 | 205456 | 208103 | 713.9495 | EXPENSE | Yes | NO |  | X |  |  |  | Yes | Yes | no | no | Yes | Yes | no | Yes | no | 2 | 1 | 3 | 2 | 5 | 2 | 3 | 1 | 47.5% | 5 | 2 | 3 | 1 | 2 | 1 | 36% | 4 |  | 121.8769
1234 | 1234 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Aug 31,2029 | Dec 31, 2027 | 292 | 7 | 2024-03-14 | low | med | med | high | high | 1500000 | 1460980 | 1558652 | 152.9836 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | Yes | no | Yes | Yes | Yes | no | 5 | 5 | 3 | 1 | 3 | 4 | 1 | 1 | 57.5% | 6 | 2 | 2 | 1 | 5 | 5 | 60% | 6 |  | 267.7598
1235 | 1235 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | Aug 31,2027 | Dec 31, 2026 | 184 | 2 | 2025-01-28 | high | med | low | med | high | 520000 | 590076 | 591552 | 500.6594 | EXPENSE | no | Derate/low flow Pipe segment | X | X |  | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 1 | 1 | 4 | 2 | 5 | 4 | 4 | 1 | 55% | 6 | 2 | 2 | 1 | 5 | 4 | 56% | 6 |  | 267.7598
1236 | 1236 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Montreal | Nov 30, 2025 | Oct 31, 2026 | 227 | 5 | 2024-12-16 | low | high | med | low | low | 800000 | 817249 | 857404 | 116.0893 | EXPENSE | Yes | pipeline segment outage |  | X |  | X | X | no | no | no | no | Yes | Yes | no | Yes | Yes | 3 | 1 | 4 | 3 | 5 | 3 | 5 | 1 | 62.5% | 6 | 5 | 2 | 1 | 2 | 1 | 44% | 5 |  | 267.7598
1237 | 1237 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Nov30,2027 | Dec 31, 2027 | 170 | 5 | 2024-07-14 | med | low | low | med | med | 400000 | 406220 | 406135 | 33.5343 | CAPITAL | Yes | Pipeline segment | X | X | X | X |  | no | no | Yes | no | Yes | no | Yes | no | Yes | 1 | 2 | 4 | 4 | 4 | 4 | 2 | 5 | 65% | 6 | 3 | 3 | 1 | 1 | 4 | 48% | 5 |  | 17599.3754
1238 | 1238 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Winnipeg | Sept 30,2026 | Oct 31, 2027 | 197 | 15 | 2024-09-15 | med | low | low | high | med | 500000 | 513676 | 518168 | 511.7996 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 5 | 5 | 4 | 3 | 5 | 2 | 3 | 1 | 70% | 6 | 1 | 3 | 1 | 1 | 3 | 36% | 4 |  | 7024.2246
1239 | 1239 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Dec 31, 2030 | Oct 31, 2025 | 234 | 8 | 2025-03-11 | low | low | med | med | med | 500000 | 501921 | 501943 | 47.5442 | EXPENSE | no | Pipeline segment | X |  |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 5 | 2 | 3 | 3 | 3 | 4 | 4 | 67.5% | 6 | 1 | 4 | 1 | 4 | 2 | 48% | 5 |  | 1591.1704
1240 | 1240 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Dec 31,2028 | Oct 31, 2026 | 41 | 7 | 2025-02-18 | low | high | low | low | high | 1900000 | 1900004 | 1908751 | 44.5632 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  | X |  | Yes | Yes | no | no | no | no | no | no | Yes | 2 | 3 | 2 | 4 | 2 | 1 | 1 | 5 | 50% | 5 | 3 | 1 | 1 | 4 | 3 | 48% | 5 |  | 6832.4917
1241 | 1241 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Sept 30,2028 | Dec 31, 2026 | 194 | 10 | 2025-06-20 | low | high | low | med | low | 350000 | 835683 | 830953 | 55.3744 | CAPITAL | no | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | Yes | no | Yes | no | 4 | 2 | 2 | 4 | 3 | 5 | 3 | 3 | 65% | 6 | 4 | 1 | 1 | 5 | 5 | 64% | 7 |  | 330
1242 | 1242 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Aug 31,2029 | Oct 31, 2026 | 237 | 8 | 2024-08-06 | high | med | high | high | low | 450000 | 479835 | 487417 | 412.8922 | CAPITAL | no | pipeline segment outage | X |  |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 3 | 3 | 2 | 4 | 2 | 5 | 1 | 1 | 52.5% | 6 | 3 | 1 | 1 | 3 | 4 | 48% | 5 |  | 5845
1243 | 1243 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | April 30,2029 | Dec 31, 2027 | 174 | 5 | 2025-02-07 | low | med | low | high | med | 350000 | 406595 | 482491 | 284.7276 | EXPENSE | no | Pipeline segment | X | X |  | X | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 2 | 2 | 2 | 5 | 2 | 4 | 5 | 2 | 60% | 6 | 2 | 3 | 1 | 5 | 1 | 48% | 5 |  | 3077.9635
1244 | 1244 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Dec 31,2028 | Jul 31, 2026 | 191 | 10 | 2025-01-21 | high | med | low | high | high | 350000 | 379453 | 378408 | 58.7845 | CAPITAL | no | Pipeline segment |  |  | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 1 | 4 | 3 | 1 | 5 | 2 | 3 | 55% | 6 | 2 | 4 | 1 | 5 | 5 | 68% | 7 |  | 13582.277
1245 | 1245 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Aug 31,2027 | Oct 31, 2027 | 211 | 8 | 2025-06-03 | low | low | low | high | high | 500000 | 682395 | 696748 | 22.5065 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | no | no | no | Yes | no | no | no | Yes | 5 | 5 | 3 | 5 | 4 | 5 | 4 | 4 | 87.5% | 9 | 2 | 1 | 1 | 1 | 5 | 40% | 4 |  | 7709.8457
1246 | 1246 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Aug 31,2029 | Dec 31, 2025 | 323 | 8 | 2024-09-11 | high | med | med | high | med | 350000 | 318965 | 339197 | 71.4985 | CAPITAL | no | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 2 | 2 | 2 | 3 | 2 | 3 | 5 | 2 | 52.5% | 6 | 3 | 2 | 1 | 5 | 2 | 52% | 6 |  | 7110.0938
1247 | 1247 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Saskatoon | April 30,2029 | Jul 31, 2027 | 32 | 8 | 2024-11-29 | high | low | med | med | high | 300000 | 805802 | 891083 | 36.3611 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | no | Yes | no | no | Yes | no | no | Yes | no | 1 | 1 | 2 | 5 | 2 | 5 | 3 | 4 | 57.5% | 6 | 5 | 4 | 5 | 3 | 2 | 76% | 8 |  | 4314.1949
1248 | 1248 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Sept 30,2028 | Jul 31, 2025 | 165 | 2 | 2025-02-16 | low | low | low | high | low | 350000 | 482300 | 486971 | 593.4244 | EXPENSE | no | Pipeline segment | X | X | X |  | X | no | no | Yes | no | no | no | Yes | Yes | Yes | 3 | 2 | 1 | 1 | 2 | 1 | 4 | 4 | 45% | 5 | 4 | 2 | 1 | 2 | 4 | 52% | 6 |  | 4858.8867
1249 | 1249 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Sept 30,2030 | Dec 31, 2026 | 272 | 8 | 2024-04-03 | med | med | med | low | med | 350000 | 444414 | 440670 | 101.6158 | CAPITAL | no | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 3 | 3 | 4 | 1 | 2 | 2 | 3 | 1 | 47.5% | 5 | 5 | 5 | 1 | 1 | 3 | 60% | 6 |  | 2178.0735
1250 | 1250 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Dec 31,2026 | Oct 31, 2026 | 81 | 7 | 2025-08-11 | high | low | high | low | high | 750000 | 875896 | 878514 | 24.8857 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  |  | no | Yes | no | Yes | no | no | no | no | Yes | 2 | 4 | 2 | 5 | 2 | 1 | 2 | 2 | 50% | 5 | 4 | 2 | 5 | 1 | 3 | 60% | 6 |  | 1090.5382
1251 | 1251 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Nov30,2027 | Jul 31, 2027 | 156 | 15 | 2025-05-28 | high | high | med | high | high | 450000 | 428046 | 421693 | 82.8772 | CAPITAL | no | Pipeline segment |  | X |  | X | X | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 1 | 1 | 1 | 5 | 3 | 3 | 4 | 5 | 57.5% | 6 | 2 | 3 | 1 | 3 | 5 | 56% | 6 |  | 4052.0846
1252 | 1252 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | Nov30,2027 | Jul 31, 2025 | 75 | 7 | 2025-10-17 | med | med | med | low | low | 2000000 | 2054742 | 2048761 | 57.9714 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 3 | 2 | 4 | 4 | 1 | 1 | 2 | 2 | 47.5% | 5 | 4 | 5 | 5 | 1 | 4 | 76% | 8 |  | 2610.3898
1253 | 1253 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | June 30, 2025 | Dec 31, 2027 | 24 | 10 | 2025-10-07 | high | med | low | low | low | 350000 | 379854 | 356546 | 25.9626 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 3 | 1 | 2 | 1 | 5 | 2 | 1 | 2 | 42.5% | 5 | 2 | 4 | 1 | 3 | 3 | 52% | 6 |  | 241.5599
1254 | 1254 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Nov 30,2029 | Jul 31, 2027 | 98 | 8 | 2025-09-24 | med | med | low | med | med | 350000 | 410000 | 410045 | 183.6307 | EXPENSE | Yes | Pipeline segment |  |  | X |  |  | no | no | Yes | Yes | no | Yes | no | Yes | no | 3 | 4 | 4 | 1 | 2 | 4 | 4 | 1 | 57.5% | 6 | 2 | 1 | 1 | 1 | 1 | 24% | 3 |  | 4995.3897
1255 | 1255 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | WINNIPEG | Sept 30,2026 | Oct 31, 2026 | 141 | 8 | 2024-08-12 | low | med | high | med | low | 350000 | 818560 | 807036 | 31.5417 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 4 | 3 | 2 | 4 | 5 | 2 | 1 | 5 | 65% | 6 | 5 | 2 | 1 | 1 | 4 | 52% | 6 |  | 6993.5456
1256 | 1256 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Regina | Dec 31, 2030 | Dec 31, 2027 | 250 | 10 | 2024-11-23 | high | high | med | low | high | 750000 | 745189 | 786550 | 57.545 | EXPENSE | no | pipeline segment outage | X |  | X |  | X | Yes | Yes | Yes | no | no | no | no | no | no | 2 | 1 | 2 | 2 | 5 | 4 | 4 | 4 | 60% | 6 | 5 | 3 | 1 | 2 | 1 | 48% | 5 |  | 840.2082
1257 | 1257 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | Aug 31,2029 | Jul 31, 2026 | 85 | 7 | 2024-10-07 | low | med | high | med | med | 2000000 | 1758655 | 1869566 | 383.6846 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | no | no | Yes | Yes | Yes | no | 3 | 2 | 2 | 3 | 5 | 3 | 2 | 5 | 62.5% | 6 | 2 | 2 | 1 | 3 | 5 | 52% | 6 |  | 5000
1258 | 1258 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | April 30,2028 | Dec 31, 2027 | 159 | 2 | 2025-07-25 | high | med | med | med | high | 350000 | 441828 | 446179 | 16.1628 | EXPENSE | no | Derate/low flow Pipe segment |  | X | X | X | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 4 | 5 | 1 | 4 | 5 | 4 | 5 | 2 | 75% | 8 | 2 | 3 | 1 | 4 | 1 | 44% | 5 |  | 646
1259 | 1259 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Sept 30,2028 | Jul 31, 2025 | 197 | 4 | 2025-06-17 | med | high | high | med | low | 1800000 | 1909884 | 1937687 | 97.7988 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | no | no | Yes | no | no | no | no | no | Yes | 2 | 2 | 3 | 4 | 4 | 3 | 4 | 2 | 60% | 6 | 4 | 5 | 1 | 4 | 3 | 68% | 7 |  | 289
1260 | 1260 | L1 | PIPE INTEGRITY | CLASS | CLASS UPGRADE | Quebec City | Aug 31,2029 | Dec 31, 2026 | 245 | 20 | 2025-04-30 | med | low | low | med | med | 28550000 | 28506803 | 28740397 | 96.8203 | CAPITAL | no | pipeline segment outage | X |  | X | X | X | Yes | no | no | no | Yes | Yes | Yes | Yes | no | 3 | 5 | 3 | 1 | 4 | 1 | 5 | 5 | 67.5% | 6 | 5 | 5 | 1 | 2 | 5 | 72% | 8 |  | 347
1261 | 1261 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | June 30, 2025 | Oct 31, 2027 | 335 | 4 | 2024-11-30 | med | med | low | high | low | 1500000 | 1871375 | 1900437 | 20.7353 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X | X | Yes | no | Yes | Yes | no | Yes | Yes | no | Yes | 4 | 3 | 4 | 2 | 3 | 3 | 4 | 1 | 60% | 6 | 4 | 4 | 1 | 2 | 2 | 52% | 6 |  | 158885
1262 | 1262 | L3 | PIPE INTEGRITY | CLASS | CLASS UPGRADE | North Bay | Sept 30,2026 | Dec 31, 2027 | 117 | 25 | 2025-04-05 | med | high | med | high | med | 1405000 | 15158244 | 15509480 | 80.1164 | CAPITAL | Yes | pipeline segment outage | X |  |  | X | X | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 1 | 2 | 2 | 3 | 2 | 3 | 5 | 4 | 55% | 6 | 4 | 2 | 1 | 5 | 5 | 68% | 7 |  | 1785
1263 | 1263 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Montreal | Dec 31,2028 | Dec 31, 2027 | 208 | 15 | 2024-09-04 | med | low | low | high | high | 750000 | 1164753 | 1662254 | 91.2063 | EXPENSE | no | Pipeline segment |  |  | X |  |  | no | Yes | Yes | no | Yes | no | Yes | no | no | 4 | 1 | 3 | 3 | 4 | 3 | 4 | 3 | 62.5% | 6 | 3 | 5 | 1 | 2 | 1 | 48% | 5 |  | 898
1264 | 1264 | L3 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Edmonton | Sept 30,2026 | Jul 31, 2025 | 60 | 15 | 2025-06-01 | high | high | low | med | med | 850000 | 827077 | 841856 | 80.7922 | EXPENSE | Yes | pipeline segment outage |  |  | X |  | X | no | Yes | Yes | no | Yes | Yes | Yes | no | Yes | 3 | 2 | 1 | 5 | 3 | 3 | 1 | 1 | 47.5% | 5 | 3 | 5 | 1 | 5 | 1 | 60% | 6 |  | 172.2548
1265 | 1265 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Montreal | Sept 30,2028 | Oct 31, 2027 | 161 | 8 | 2025-05-23 | med | med | high | low | med | 1000000 | 1022203 | 1280954 | 44.865 | EXPENSE | no | pipeline segment outage |  | X | X | X |  | Yes | Yes | no | no | Yes | no | no | no | no | 5 | 2 | 1 | 4 | 4 | 2 | 1 | 5 | 60% | 6 | 2 | 5 | 1 | 2 | 3 | 52% | 6 |  | 172.2548
1266 | 1266 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | April 30,2027 | Jul 31, 2027 | 118 | 5 | 2025-07-05 | med | high | high | high | high | 400000 | 434790 | 444911 | 114.2737 | EXPENSE | no | Pipeline segment | X |  |  |  |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 5 | 2 | 2 | 5 | 5 | 2 | 5 | 2 | 70% | 6 | 2 | 3 | 1 | 2 | 1 | 36% | 4 |  | 382.7885
1267 | 1267 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Mar 31,2030 | Oct 31, 2026 | 201 | 2 | 2025-01-11 | med | med | med | high | med | 650000 | 655557 | 668033 | 224.9398 | EXPENSE | no | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | Yes | no | 1 | 1 | 3 | 2 | 5 | 3 | 1 | 5 | 52.5% | 6 | 1 | 1 | 1 | 3 | 2 | 32% | 4 |  | 173.2929
1268 | 1268 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | North Bay | Aug 31,2027 | Oct 31, 2025 | 233 | 2 | 2024-12-10 | low | med | high | high | med | 950000 | 1089229 | 1080770 | 128.235 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | Yes | no | Yes | Yes | Yes | 4 | 4 | 3 | 5 | 4 | 2 | 1 | 4 | 67.5% | 6 | 3 | 2 | 1 | 1 | 3 | 40% | 4 |  | 900.2043
1269 | 1269 | L2 | PIPE INTEGRITY | CLASS | CLASS UPGRADE | Winnipeg | March 31, 2026 | Jul 31, 2027 | 21 | 15 | 2025-03-10 | low | med | high | med | high | 6870000 | 6877100 | 7401079 | 369.6154 | CAPITAL | Yes | pipeline segment outage | X | X |  |  | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 5 | 5 | 3 | 4 | 4 | 5 | 5 | 5 | 90% | 9 | 2 | 4 | 1 | 1 | 5 | 52% | 6 |  | 749.7244
1270 | 1270 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30,2028 | Oct 31, 2027 | 18 | 4 | 2024-12-13 | med | high | high | low | high | 400000 | 458461 | 454334 | 125.3264 | EXPENSE | no | Pipeline segment | X |  | X |  | X | no | Yes | no | Yes | no | Yes | no | Yes | no | 5 | 4 | 3 | 3 | 4 | 4 | 2 | 3 | 70% | 6 | 5 | 3 | 1 | 5 | 4 | 72% | 8 |  | 1022.4116
1271 | 1271 | L3 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Montreal | April 30,2027 | Oct 31, 2025 | 226 | 4 | 2024-05-19 | med | high | high | high | high | 250000 | 285616 | 285266 | 68.1605 | EXPENSE | no | NO |  |  | X |  | X | no | no | no | Yes | no | Yes | Yes | no | no | 2 | 1 | 4 | 5 | 3 | 5 | 2 | 3 | 62.5% | 6 | 5 | 4 | 5 | 4 | 2 | 80% | 8 |  | 458
1272 | 1272 | L1 | PIPE INTEGRITY | CLASS | CLASS UPGRADE | Ottawa | April 30,2027 | Dec 31, 2027 | 226 | 15 | 2024-08-17 | low | low | high | med | low | 9400000 | 19427475 | 9354713 | 89.0006 | CAPITAL | no | pipeline segment outage | X |  | X | X |  | Yes | Yes | Yes | no | Yes | no | no | no | no | 3 | 5 | 2 | 5 | 1 | 2 | 4 | 1 | 57.5% | 6 | 3 | 4 | 1 | 1 | 2 | 44% | 5 |  | 425
1273 | 1273 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP-RECTIFIER | Quebec City | Dec 31, 2030 | Oct 31, 2025 | 244 | 4 | 2025-03-01 | med | med | med | high | low | 600000 | 757099 | 785103 | 484.7808 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  | X |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 2 | 5 | 2 | 2 | 2 | 1 | 4 | 5 | 57.5% | 6 | 4 | 2 | 1 | 1 | 2 | 40% | 4 |  | 4447
1274 | 1274 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Sept 30,2030 | Oct 31, 2026 | 238 | 6 | 2024-12-05 | high | high | med | high | low | 1750000 | 1770877 | 1780700 | 91.2089 | EXPENSE | no | Derate/low flow Pipe segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | no | 3 | 1 | 4 | 4 | 3 | 5 | 4 | 4 | 70% | 6 | 4 | 5 | 5 | 4 | 5 | 92% | 10 |  | 20000
1275 | 1275 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Quebec City | June 30, 2025 | Jul 31, 2025 | 320 | 4 | 2024-05-15 | med | high | med | high | high | 1500000 | 1500982 | 1500604 | 7.9794 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | Yes | Yes | no | no | Yes | no | 2 | 4 | 2 | 1 | 4 | 2 | 5 | 5 | 62.5% | 6 | 3 | 1 | 1 | 3 | 5 | 52% | 6 |  | 2078
1276 | 1276 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | April 30,2029 | Oct 31, 2026 | 288 | 10 | 2024-10-16 | med | low | med | low | med | 350000 | 363583 | 359590 | 32.0854 | CAPITAL | no | Pipeline segment |  |  | X | X |  | no | Yes | no | no | Yes | no | Yes | no | no | 3 | 2 | 4 | 3 | 1 | 3 | 3 | 4 | 57.5% | 6 | 3 | 5 | 1 | 3 | 1 | 52% | 6 |  | 1875
1277 | 1277 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Aug 31,2029 | Jul 31, 2027 | 253 | 8 | 2024-11-20 | low | med | high | high | high | 450000 | 483200 | 482753 | 123.3918 | CAPITAL | no | Pipeline segment |  | X |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 3 | 5 | 2 | 5 | 4 | 4 | 1 | 5 | 72.5% | 8 | 3 | 5 | 1 | 4 | 5 | 72% | 8 |  | 7718.869
1278 | 1278 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | April 30,2028 | Dec 31, 2027 | 355 | 4 | 2024-11-10 | high | high | low | low | high | 1750000 | 1708182 | 1716547 | 45.4478 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 2 | 2 | 4 | 5 | 4 | 4 | 3 | 1 | 62.5% | 6 | 5 | 1 | 1 | 2 | 2 | 44% | 5 |  | 7718.869
1279 | 1279 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Nov30,2027 | Oct 31, 2027 | 71 | 2 | 2025-10-21 | high | high | high | low | high | 300000 | 378545 | 398478 | 311.1133 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X | X | X | no | no | no | Yes | Yes | no | no | Yes | no | 5 | 5 | 2 | 5 | 5 | 2 | 5 | 4 | 82.5% | 9 | 4 | 4 | 5 | 5 | 5 | 92% | 10 |  | 6993.5456
1280 | 1280 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Saskatoon | May 31, 2026 | Dec 31, 2025 | 288 | 8 | 2025-01-16 | high | low | high | low | high | 750000 | 855692 | 855145 | 139.156 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  | X | Yes | Yes | no | no | no | Yes | no | no | Yes | 3 | 5 | 3 | 3 | 2 | 4 | 2 | 2 | 60% | 6 | 4 | 1 | 1 | 1 | 5 | 48% | 5 |  | 636.4681
1281 | 1281 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | Nov30,2027 | Dec 31, 2025 | 46 | 4 | 2024-11-15 | med | low | high | low | med | 400000 | 560984 | 561355 | 83.4126 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | no | no | no | Yes | Yes | Yes | Yes | no | Yes | 1 | 2 | 4 | 4 | 2 | 2 | 5 | 5 | 62.5% | 6 | 2 | 3 | 1 | 1 | 1 | 32% | 4 |  | 25393.3666
1282 | 1282 | L2 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Regina | Nov30,2027 | Oct 31, 2027 | 206 | 15 | 2024-06-08 | med | low | low | low | med | 1800000 | 1825733 | 1857547 | 76.4961 | EXPENSE | no | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 2 | 4 | 3 | 2 | 3 | 4 | 5 | 5 | 70% | 6 | 3 | 2 | 1 | 2 | 5 | 52% | 6 |  | 2369.8282
1283 | 1283 | L2 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Saskatoon | Nov30,2027 | Oct 31, 2027 | 12 | 4 | 2024-12-19 | high | high | med | med | high | 425000 | 662668 | 637944 | 32.9243 | EXPENSE | Yes | pipeline segment outage | X | X | X |  | X | no | Yes | Yes | no | Yes | no | no | no | no | 2 | 4 | 3 | 4 | 4 | 5 | 5 | 4 | 77.5% | 8 | 5 | 4 | 1 | 5 | 1 | 64% | 7 |  | 2369.8282
1284 | 1284 | L2 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Saskatoon | June 30, 2025 | Oct 31, 2025 | 64 | 8 | 2025-05-28 | low | low | med | high | med | 1800000 | 1875000 | 1830883 | 49.4725 | EXPENSE | no | pipeline segment outage |  |  |  | X |  | no | no | no | Yes | Yes | Yes | Yes | no | no | 5 | 4 | 2 | 4 | 3 | 2 | 5 | 3 | 70% | 6 | 1 | 2 | 1 | 3 | 4 | 44% | 5 |  | 3138.8656
1285 | 1285 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Quebec City | Mar 31,2030 | Oct 31, 2027 | 52 | 2 | 2025-09-09 | med | med | high | med | high | 520000 | 686253 | 671492 | 34.7089 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X | X |  | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 3 | 3 | 3 | 4 | 5 | 3 | 1 | 67.5% | 6 | 2 | 4 | 1 | 1 | 2 | 40% | 4 |  | 3138.8656
1286 | 1286 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Nov30,2027 | Oct 31, 2027 | 41 | 4 | 2025-06-20 | med | med | high | med | high | 1000000 | 1649706 | 1663088 | 96.0767 | EXPENSE | no | Derate/low flow Pipe segment | X |  | X | X | X | no | Yes | no | no | Yes | Yes | no | no | no | 1 | 2 | 1 | 5 | 3 | 4 | 3 | 2 | 52.5% | 6 | 2 | 4 | 1 | 5 | 2 | 56% | 6 |  | 14928.9944
1287 | 1287 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | May 31, 2026 | Jul 31, 2026 | 213 | 5 | 2024-12-30 | med | low | med | med | low | 400000 | 850000 | 895000 | 24.5147 | EXPENSE | no | Pipeline segment |  | X |  | X |  | no | no | no | no | no | no | Yes | Yes | no | 1 | 2 | 3 | 3 | 5 | 3 | 5 | 4 | 65% | 6 | 2 | 4 | 1 | 2 | 5 | 56% | 6 |  | 4487
1288 | 1288 | L2 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Edmonton | Aug 31,2029 | Oct 31, 2027 | 184 | 8 | 2025-01-28 | low | high | med | high | low | 3200000 | 3281295 | 3570817 | 714.4143 | EXPENSE | no | pipeline segment outage | X |  | X |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 1 | 1 | 1 | 1 | 4 | 1 | 4 | 1 | 35% | 4 | 1 | 4 | 1 | 5 | 5 | 64% | 7 |  | 477.3811
1289 | 1289 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | April 30,2027 | Oct 31, 2027 | 296 | 2 | 2024-06-08 | high | low | low | low | med | 350000 | 378827 | 442990 | 523.2809 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | no | 5 | 4 | 2 | 5 | 3 | 3 | 3 | 2 | 67.5% | 6 | 2 | 2 | 1 | 4 | 2 | 44% | 5 |  | 5347.325
1290 | 1290 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Mar 31,2030 | Jul 31, 2026 | 214 | 6 | 2024-12-29 | med | low | high | high | high | 1000000 | 1200000 | 1281639 | 8.2654 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  |  | X | no | no | no | Yes | no | Yes | Yes | no | Yes | 5 | 3 | 3 | 1 | 3 | 4 | 1 | 2 | 55% | 6 | 4 | 4 | 1 | 1 | 1 | 44% | 5 |  | 2679.5194
1291 | 1291 | L2 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Winnipeg | Aug 31,2027 | Dec 31, 2027 | 250 | 8 | 2024-11-23 | high | high | med | med | low | 1300000 | 1324785 | 1350260 | 2123.4281 | EXPENSE | Yes | pipeline segment outage | X |  |  |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | no | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 1 | 1 | 1 | 1 | 1 | 20% | 2 |  | 2679.5194
1292 | 1292 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Nov30,2027 | Oct 31, 2026 | 114 | 6 | 2024-12-07 | med | high | med | med | low | 1800000 | 1817708 | 1891840 | 73.0943 | EXPENSE | no | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 4 | 1 | 3 | 2 | 1 | 4 | 3 | 50% | 5 | 1 | 4 | 1 | 5 | 3 | 56% | 6 |  | 1072.7658
1293 | 1293 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | March 31, 2026 | Oct 31, 2027 | 186 | 8 | 2025-01-26 | low | low | low | low | high | 350000 | 371048 | 377414 | 41.8408 | CAPITAL | no | Pipeline segment | X |  | X | X | X | no | Yes | Yes | Yes | Yes | no | no | no | no | 3 | 3 | 2 | 3 | 3 | 1 | 1 | 2 | 45% | 5 | 2 | 2 | 1 | 5 | 3 | 52% | 6 |  | 3333.1342
1294 | 1294 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Dec 31, 2030 | Jul 31, 2025 | 137 | 4 | 2024-08-16 | high | low | low | high | low | 350000 | 901807 | 925115 | 243.4001 | EXPENSE | no | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 3 | 5 | 2 | 5 | 5 | 2 | 5 | 1 | 70% | 6 | 5 | 3 | 1 | 4 | 4 | 68% | 7 |  | 1300.7103
1295 | 1295 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | June 30, 2025 | Oct 31, 2026 | 59 | 8 | 2027-09-02 | med | high | low | low | low | 2000000 | 2534662 | 2571775 | 87.159 | EXPENSE | yes | Derate/low flow Pipe segment | x | x | x | x | x | NR | x | x | x | x | x |  | No | Yes | 2 | 2 | 3 | 2 | 1 | 1 | 5 | 5 | 52.5% | 6 | 3 | 4 | 1 | 3 | 1 | 48% | 5 |  | 76225.6763
1296 | 1296 | L1 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Montreal | Nov 30,2029 | 2027-12-31 | 201 | 2 | 2027-01-11 | med | high | high | med | high | 190000 | 196187 | 197468 | 40.7081 | EXPENSE | no | NO |  |  | x | x | x |  | x | x | x | [5 empty] | 3 | 5 | 4 | 2 | 1 | 3 | 5 | 1 | 60% | 6 | 4 | 2 | 1 | 3 | 3 | 52% | 6 |  | 16.9273
1297 | 1297 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | North Bay | Dec 31, 2030 | Jul 31, 2027 | 327 | 8 | 2025-12-08 | low | high | med | high | med | 750000 | 611769 | 669250 | 85.7283 | EXPENSE | yes | Pipeline segment | x | x | x | x | x | Yes | x | NR | NR | NR | NR | NR | No | Yes | 3 | 5 | 2 | 4 | 2 | 2 | 3 | 2 | 57.5% | 6 | 4 | 5 | 5 | 4 | 3 | 84% | 9 |  | 16.9273
1298 | 1298 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | April 30,2028 | 2027-10-31 | 315 | 4 | 2027-02-19 | high | med | med | high | low | 650000 | 888878 | 879764 | 65.902 | EXPENSE | yes | Derate/low flow Pipe segment | x | x | x | x | x | Yes | x | x | Yes | Yes | Yes |  | No | No | 5 | 5 | 3 | 2 | 4 | 3 | 4 | 3 | 72.5% | 8 | 2 | 1 | 1 | 5 | 4 | 52% | 6 |  | 560.1412
1299 | 1299 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | June 30, 2025 | 2027-07-31 | 263 | 8 | 2026-02-10 | low | high | high | low | low | 350000 | 332894 | 386745 | 27.2404 | CAPITAL | no | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | Yes | Yes | 3 | 2 | 2 | 3 | 5 | 3 | 1 | 1 | 50% | 5 | 2 | 5 | 1 | 5 | 4 | 68% | 7 |  | 560.1412
1300 | 1300 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Nov30,2027 | 2027-07-31 | 72 | 8 | 2027-08-20 | med | med | low | low | med | 420000 | 465754 | 449856 | 159.1014 | CAPITAL | no | Pipeline segment | X | X |  |  |  | Yes | Yes | Yes | no | Yes | no | Yes | Yes | no | 3 | 4 | 5 | 2 | 3 | 1 | 1 | 5 | 60% | 6 | 4 | 2 | 1 | 5 | 5 | 68% | 7 |  | 2310.5725
1301 | 1301 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | June 30, 2025 | 2026-10-31 | 361 | 8 | 2025-04-04 | high | med | med | high | low | 350000 | 358642 | 375845 | 83.0189 | CAPITAL | no | Pipeline segment |  | X |  | X |  | Yes | Yes | no | Yes | Yes | no | no | Yes | Yes | 5 | 5 | 3 | 3 | 4 | 5 | 1 | 3 | 72.5% | 8 | 2 | 4 | 1 | 1 | 5 | 52% | 6 |  | 2369.8282
1302 | 1302 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Nov30,2027 | 2028-10-31 | 312 | 8 | 2027-05-24 | high | med | high | low | low | 550000 | 555744 | 590000 | 32.772 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | Yes | no | no | no | Yes | Yes | no | 5 | 4 | 1 | 3 | 5 | 5 | 4 | 2 | 72.5% | 8 | 1 | 5 | 1 | 5 | 3 | 60% | 6 |  | 2491.953
1303 | 1303 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Montreal | March 31, 2026 | 2029-10-31 | 202 | 8 | 2029-06-12 | low | low | med | med | med | 650000 | 634470 | 663637 | 147.3292 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | no | Yes | no | no | Yes | 1 | 2 | 3 | 1 | 2 | 3 | 5 | 5 | 55% | 6 | 5 | 3 | 1 | 4 | 3 | 64% | 7 |  | 16593.6851
1304 | 1304 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Sept 30,2028 | 2027-12-31 | 175 | 15 | 2027-05-09 | med | high | high | low | med | 500000 | 478589 | 470244 | 180.0007 | CAPITAL | Yes | Pipeline segment | X |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 1 | 3 | 5 | 5 | 3 | 3 | 3 | 60% | 6 | 2 | 4 | 1 | 4 | 5 | 64% | 7 |  | 2480.6254
1305 | 1305 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Sept 30, 2025 | 2026-12-31 | 183 | 8 | 2026-07-01 | low | high | high | high | low | 2000000 | 2058655 | 2014691 | 488.9487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | no | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 5 | 37.5% | 4 | 4 | 2 | 1 | 3 | 1 | 44% | 5 |  | 2480.6254
1306 | 1306 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Aug 31,2029 | 2027-10-31 | 260 | 8 | 2026-07-14 | low | low | low | low | low | 2100000 | 2120000 | 2154250 | 40.3349 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | no | no | no | no | no | Yes | no | 2 | 2 | 1 | 2 | 4 | 2 | 2 | 2 | 42.5% | 5 | 2 | 5 | 1 | 2 | 2 | 48% | 5 |  | 728.1385
1307 | 1307 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Dec 31, 2030 | 2028-12-31 | 342 | 2 | 2028-01-24 | high | low | med | low | low | 650000 | 609531 | 605189 | 242.8512 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X | X | X | no | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 5 | 3 | 1 | 5 | 5 | 5 | 4 | 77.5% | 8 | 5 | 3 | 1 | 3 | 4 | 64% | 7 |  | 495.1227
1308 | 1308 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Sept 30,2030 | 2026-07-31 | 248 | 4 | 2025-07-26 | med | high | high | high | high | 2000000 | 2373474 | 2320004 | 25.7224 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | no | Yes | no | no | no | Yes | Yes | 1 | 3 | 1 | 3 | 3 | 3 | 5 | 1 | 50% | 5 | 1 | 5 | 1 | 4 | 2 | 52% | 6 |  | 6039.0018
1309 | 1309 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | April 30,2028 | 2026-07-31 | 32 | 5 | 2026-06-29 | low | high | low | med | low | 400000 | 450563 | 459107 | 135.4595 | EXPENSE | no | Pipeline segment |  | X |  |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 2 | 4 | 1 | 4 | 3 | 2 | 2 | 2 | 50% | 5 | 2 | 1 | 1 | 3 | 4 | 44% | 5 |  | 13659.1884
1310 | 1310 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | April 30,2029 | 2026-07-31 | 195 | 5 | 2027-04-19 | low | high | low | med | high | 420000 | 850041 | 889250 | 122.5032 | EXPENSE | Yes | Pipeline segment | X |  |  | X |  | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 2 | 4 | 4 | 1 | 2 | 5 | 2 | 5 | 62.5% | 6 | 5 | 1 | 1 | 5 | 3 | 60% | 6 |  | 13659.1884
1311 | 1311 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Dec 31,2026 | 2025-12-31 | 240 | 5 | 2025-12-03 | high | med | high | med | med | 420000 | 419283 | 410602 | 148.1189 | EXPENSE | Yes | Pipeline segment | X |  | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 3 | 5 | 4 | 1 | 2 | 2 | 3 | 5 | 62.5% | 6 | 4 | 5 | 5 | 3 | 4 | 84% | 9 |  | 21537.8368
1312 | 1312 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Aug 31,2027 | 2028-10-31 | 42 | 15 | 2028-09-19 | low | low | low | low | med | 550000 | 615279 | 618240 | 184.0435 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | Yes | no | no | no | no | no | 2 | 2 | 4 | 4 | 2 | 2 | 4 | 2 | 55% | 6 | 2 | 2 | 1 | 1 | 2 | 32% | 4 |  | 2973.4021
1313 | 1313 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Saskatoon | Dec 31, 2030 | 2026-12-31 | 124 | 10 | 2026-06-29 | med | med | med | high | high | 750000 | 701993 | 706058 | 34.5922 | EXPENSE | no | derate/low flow Pipe segment | X | X |  |  | X | Yes | no | no | no | Yes | no | no | Yes | Yes | 1 | 4 | 2 | 2 | 1 | 3 | 4 | 5 | 55% | 6 | 4 | 4 | 1 | 5 | 3 | 68% | 7 |  | 19639.8665
1314 | 1314 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Montreal | Sept 30,2028 | Jul 31, 2027 | 355 | 10 | 2026-08-10 | high | high | low | low | high | 550000 | 620373 | 628500 | 16.0911 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 1 | 67.5% | 6 | 2 | 2 | 1 | 1 | 2 | 32% | 4 |  | 5776.4313
1315 | 1315 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Mar 31,2030 | 2028-10-31 | 255 | 10 | 2028-04-20 | low | high | high | low | low | 550000 | 897555 | 933585 | 23.9593 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | Yes | no | no | Yes | Yes | no | Yes | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 4 | 42.5% | 5 | 4 | 1 | 1 | 4 | 1 | 44% | 5 |  | 6487.5816
1316 | 1316 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | Nov30,2027 | 2026-10-31 | 360 | 10 | 2027-01-05 | high | low | high | med | med | 500000 | 582971 | 589878 | 270.4653 | CAPITAL | no | Pipeline segment |  | X |  |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 2 | 3 | 4 | 5 | 1 | 1 | 2 | 4 | 55% | 6 | 4 | 4 | 5 | 5 | 2 | 80% | 8 |  | 1083.35
1317 | 1317 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Mar 31,2030 | 2027-10-31 | 275 | 4 | 2027-01-29 | low | med | low | high | low | 2000000 | 2242580 | 2285780 | 104.3547 | EXPENSE | no | Derate/low flow Pipe segment | X |  | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 3 | 4 | 2 | 2 | 4 | 3 | 4 | 2 | 60% | 6 | 3 | 1 | 1 | 1 | 4 | 40% | 4 |  | 1184.9141
1318 | 1318 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Dec 31, 2030 | 2026-10-31 | 99 | 2 | 2026-12-22 | high | low | high | high | med | 1500000 | 2469351 | 704714 | 48.6768 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | no | no | Yes | no | Yes | Yes | Yes | Yes | no | 2 | 5 | 1 | 4 | 4 | 4 | 4 | 2 | 65% | 6 | 1 | 2 | 1 | 2 | 4 | 40% | 4 |  | 1846.6194
1319 | 1319 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Dec 31,2026 | Dec 31, 2027 | 101 | 10 | 2027-07-22 | high | low | low | med | med | 400000 | 500000 | 489415 | 194.4749 | EXPENSE | Yes | Pipeline segment |  |  |  | X | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 1 | 2 | 3 | 1 | 5 | 3 | 5 | 4 | 60% | 6 | 3 | 3 | 5 | 2 | 3 | 64% | 7 |  | 9580.8769
1320 | 1320 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Dec 31,2026 | 2028-12-31 | 346 | 2 | 2028-01-20 | low | low | low | low | low | 850000 | 852000 | 900000 | 26.0956 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | Yes | Yes | Yes | 5 | 5 | 2 | 5 | 3 | 2 | 4 | 1 | 67.5% | 6 | 1 | 2 | 5 | 2 | 4 | 56% | 6 |  | 8429.71
1321 | 1321 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Nov30,2027 | Dec 31, 2027 | 146 | 10 | 2027-06-07 | high | med | low | med | low | 500000 | 385254 | 395452 | 156.8587 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | no | 2 | 1 | 4 | 3 | 5 | 3 | 5 | 4 | 67.5% | 6 | 1 | 1 | 5 | 2 | 2 | 44% | 5 |  | 425
1322 | 1322 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Sept 30,2026 | 2029-12-31 | 170 | 10 | 2029-07-14 | med | high | high | med | high | 550000 | 852979 | 857775 | 35.5286 | CAPITAL | no | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | Yes | Yes | Yes | Yes | no | 2 | 5 | 3 | 5 | 4 | 4 | 5 | 2 | 75% | 8 | 5 | 2 | 5 | 3 | 4 | 76% | 8 |  | 5875
1323 | 1323 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Nov 30, 2025 | 2029-10-31 | 251 | 15 | 2029-11-22 | med | high | med | high | med | 550000 | 542014 | 546441 | 26.015 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | Yes | Yes | 4 | 5 | 2 | 3 | 2 | 4 | 5 | 4 | 72.5% | 8 | 3 | 5 | 1 | 3 | 5 | 68% | 7 |  | 25777
1324 | 1324 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Dec 31, 2030 | 2029-12-31 | 243 | 4 | 2029-05-02 | high | high | high | high | med | 420000 | 449044 | 455180 | 18.1227 | CAPITAL | no | Pipeline segment | X | X |  |  |  | no | Yes | no | Yes | no | no | no | Yes | no | 4 | 1 | 2 | 1 | 1 | 3 | 1 | 4 | 42.5% | 5 | 3 | 1 | 1 | 5 | 1 | 44% | 5 |  | 5522
1325 | 1325 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Nov 30,2029 | 2028-12-31 | 239 | 4 | 2027-05-06 | low | high | high | high | low | 350000 | 534618 | 575616 | 502.8679 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | no | Yes | no | no | no | no | Yes | no | no | 5 | 1 | 4 | 5 | 2 | 2 | 3 | 4 | 65% | 6 | 1 | 3 | 1 | 5 | 3 | 52% | 6 |  | 4101.0339
1326 | 1326 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Calgary | Nov30,2027 | 2029-07-31 | 331 | 5 | 2029-02-03 | high | med | high | high | low | 450000 | 476437 | 473514 | 98.0993 | CAPITAL | Yes | Derate/low flow Pipe segment | X | X | X | X | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | Yes | 4 | 3 | 4 | 5 | 1 | 3 | 4 | 1 | 62.5% | 6 | 5 | 4 | 1 | 4 | 3 | 68% | 7 |  | 22170.3266
1327 | 1327 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Montreal | Aug 31,2027 | 2029-07-31 | 348 | 5 | 2028-11-17 | high | med | med | med | low | 1000000 | 1550026 | 1443747 | 76.5526 | EXPENSE | no | Pipeline segment | X | X |  |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 1 | 5 | 4 | 5 | 1 | 3 | 5 | 1 | 62.5% | 6 | 2 | 5 | 1 | 5 | 5 | 72% | 8 |  | 13420.4072
1328 | 1328 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | April 30,2029 | 2028-12-31 | 55 | 5 | 2028-02-05 | med | low | high | low | low | 400000 | 495918 | 472825 | 414.8802 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | Yes | 1 | 3 | 3 | 5 | 2 | 3 | 5 | 3 | 62.5% | 6 | 1 | 1 | 1 | 5 | 2 | 40% | 4 |  | 1727.2647
1329 | 1329 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Sept 30,2030 | 2027-10-31 | 77 | 5 | 2027-10-15 | low | low | med | high | low | 420000 | 491000 | 485000 | 1266.3815 | EXPENSE | no | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 3 | 5 | 2 | 3 | 2 | 2 | 2 | 2 | 52.5% | 6 | 1 | 5 | 1 | 3 | 4 | 56% | 6 |  | 2588
1330 | 1330 | L2 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Calgary | Sept 30, 2025 | 2027-10-31 | 190 | 2 | 2027-04-24 | med | high | high | low | high | 125000 | 110410 | 117380 | 565.0045 | EXPENSE | Yes | NO | X |  |  |  | X | no | Yes | Yes | no | Yes | no | Yes | no | Yes | 4 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 35% | 4 | 4 | 3 | 1 | 3 | 3 | 56% | 6 |  | 18109.7232
1331 | 1331 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | North Bay | Nov 30,2029 | 2027-10-31 | 149 | 2 | 2027-11-03 | med | high | low | high | med | 1250000 | 1381952 | 1385422 | 72.2212 | EXPENSE | no | Derate/low flow Pipe segment | X | X |  |  | X | no | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 4 | 5 | 4 | 5 | 5 | 4 | 3 | 1 | 77.5% | 8 | 5 | 2 | 1 | 5 | 1 | 56% | 6 |  | 3981.0002
1332 | 1332 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | Dec 31, 2030 | 2028-12-31 | 214 | 15 | 2028-05-31 | low | high | low | low | low | 550000 | 986403 | 1000025 | 103.1048 | CAPITAL | no | Pipeline segment | X |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 4 | 4 | 2 | 4 | 4 | 3 | 3 | 3 | 67.5% | 6 | 5 | 5 | 1 | 1 | 1 | 52% | 6 |  | 20815.3255
1333 | 1333 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Aug 31,2027 | 2026-07-31 | 247 | 4 | 2025-11-26 | low | high | high | med | low | 500000 | 514135 | 576815 | 91.6522 | CAPITAL | Yes | PIpeline segment | X |  |  | X |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 4 | 1 | 2 | 3 | 3 | 2 | 3 | 4 | 55% | 6 | 3 | 4 | 1 | 4 | 4 | 64% | 7 |  | 278.7236
1334 | 1334 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Nov 30, 2025 | Dec 31, 2027 | 109 | 8 | 2027-09-13 | high | high | low | high | high | 500000 | 1505538 | 1480254 | 98.783 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 4 | 2 | 1 | 2 | 2 | 5 | 5 | 2 | 57.5% | 6 | 2 | 3 | 1 | 3 | 1 | 40% | 4 |  | 278.7236
1335 | 1335 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | March 31, 2026 | 2026-07-31 | 21 | 8 | 2026-10-10 | med | high | high | high | med | 350000 | 438059 | 432793 | 279.986 | CAPITAL | no | Pipeline segment |  | X | X |  |  | no | Yes | no | Yes | Yes | no | Yes | no | no | 3 | 3 | 2 | 5 | 2 | 4 | 1 | 5 | 62.5% | 6 | 3 | 1 | 1 | 5 | 5 | 60% | 6 |  | 203.1281
1336 | 1336 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | WINNIPEG | Sept 30,2028 | 2026-12-31 | 146 | 10 | 2028-08-07 | low | med | low | high | high | 550000 | 528864 | 528750 | 56.9979 | CAPITAL | Yes | Pipeline segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | no | no | no | 1 | 2 | 4 | 5 | 1 | 4 | 3 | 3 | 57.5% | 6 | 3 | 3 | 1 | 2 | 1 | 40% | 4 |  | 203.1281
1337 | 1337 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | WINNIPEG | Dec 31,2028 | 2026-12-31 | 179 | 10 | 2026-02-02 | med | low | med | med | med | 450000 | 516716 | 510460 | 30.4676 | CAPITAL | Yes | Pipeline segment |  | X | X | X |  | Yes | Yes | Yes | no | Yes | no | Yes | no | Yes | 5 | 2 | 3 | 1 | 3 | 1 | 4 | 1 | 50% | 5 | 4 | 1 | 1 | 1 | 4 | 44% | 5 |  | 203.1281
1338 | 1338 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | May 31, 2026 | 2027-10-31 | 364 | 10 | 2026-04-01 | high | low | high | med | med | 400000 | 410639 | 410032 | 4.3752 | CAPITAL | no | Pipeline segment | X | X | X |  | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 5 | 4 | 2 | 1 | 1 | 1 | 1 | 3 | 45% | 5 | 1 | 2 | 1 | 3 | 4 | 44% | 5 |  | 23717.2367
1339 | 1339 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | April 30,2028 | 2028-07-31 | 180 | 10 | 2028-02-02 | med | med | low | high | low | 400000 | 451173 | 453222 | 22.175 | EXPENSE | Yes | Pipeline segment | X | X | X |  |  | Yes | no | no | no | Yes | no | no | Yes | no | 3 | 2 | 2 | 4 | 1 | 1 | 5 | 5 | 57.5% | 6 | 3 | 4 | 1 | 4 | 1 | 52% | 6 |  | 16021.8416
1340 | 1340 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Sept 30,2026 | 2029-03-31 | 264 | 8 | 2029-04-11 | high | high | low | high | high | 550000 | 680678 | 686152 | 22.4512 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | no | Yes | no | no | 3 | 5 | 1 | 4 | 3 | 2 | 2 | 2 | 55% | 6 | 1 | 5 | 1 | 1 | 5 | 52% | 6 |  | 1685.9635
1341 | 1341 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Nov30,2027 | 2026-10-31 | 20 | 2 | 2027-03-11 | med | med | high | med | low | 500000 | 608924 | 630832 | 93.0837 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | Yes | Yes | no | no | 5 | 3 | 2 | 2 | 3 | 1 | 5 | 2 | 57.5% | 6 | 3 | 1 | 1 | 1 | 4 | 40% | 4 |  | 121.8769
1342 | 1342 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30,2026 | 2026-12-31 | 192 | 4 | 2026-06-22 | low | high | low | low | low | 350000 | 539330 | 577636 | 415.9262 | EXPENSE | no | Pipeline segment |  | X | X |  |  | no | no | no | no | Yes | Yes | Yes | no | Yes | 5 | 5 | 2 | 2 | 5 | 4 | 4 | 3 | 75% | 8 | 2 | 2 | 1 | 4 | 2 | 44% | 5 |  | 643.2391
1343 | 1343 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | May 31, 2026 | 2028-07-31 | 363 | 4 | 2027-08-03 | med | low | high | med | low | 300000 | 295522 | 290724 | 87.5976 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | no | no | 1 | 1 | 2 | 2 | 1 | 1 | 4 | 5 | 42.5% | 5 | 1 | 1 | 3 | 1 | 1 | 28% | 3 |  | 267.7598
1344 | 1344 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Aug 31,2029 | 2026-12-31 | 170 | 4 | 2026-10-12 | high | high | high | high | med | 1500000 | 1557641 | 1550000 | 27.6329 | EXPENSE | no | Derate/low flow Pipe segment | X |  |  |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 2 | 4 | 1 | 1 | 1 | 5 | 4 | 4 | 55% | 6 | 3 | 2 | 5 | 1 | 1 | 48% | 5 |  | 267.7598
1345 | 1345 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | Dec 31,2026 | 2028-10-31 | 312 | 4 | 2028-02-23 | low | high | high | high | med | 1500000 | 1583805 | 1580197 | 110.9054 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | no | no | Yes | no | no | Yes | Yes | Yes | 5 | 2 | 2 | 1 | 3 | 2 | 5 | 3 | 57.5% | 6 | 5 | 5 | 5 | 3 | 1 | 76% | 8 |  | 17599.3754
1346 | 1346 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Aug 31,2029 | 2029-10-31 | 317 | 4 | 2028-12-18 | low | high | med | med | low | 1250000 | 1350000 | 1450000 | 96.934 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 4 | 5 | 3 | 3 | 5 | 3 | 72.5% | 8 | 1 | 5 | 5 | 1 | 5 | 68% | 7 |  | 7024.2246
1347 | 1347 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | April 30,2029 | 2028-10-31 | 94 | 15 | 2028-09-28 | low | low | med | high | med | 550000 | 583975 | 578458 | 29.298 | CAPITAL | no | Pipeline segment | X |  |  | X | X | no | Yes | no | Yes | no | no | no | no | Yes | 5 | 4 | 1 | 5 | 1 | 5 | 2 | 2 | 62.5% | 6 | 4 | 5 | 1 | 4 | 3 | 68% | 7 |  | 1591.1704
1348 | 1348 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Quebec City | May 31, 2026 | 2027-12-31 | 268 | 8 | 2026-07-06 | high | med | low | high | low | 1000000 | 1514932 | 1512774 | 7.2499 | EXPENSE | no | pipeline segment | X | X | X |  | X | no | no | no | no | no | no | no | Yes | Yes | 1 | 1 | 2 | 2 | 4 | 4 | 3 | 3 | 50% | 5 | 1 | 1 | 1 | 2 | 1 | 24% | 3 |  | 4785
1349 | 1349 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Sept 30,2030 | 2030-07-31 | 92 | 4 | 2030-09-30 | med | low | low | high | low | 1750000 | 1789882 | 1779817 | 4.1819 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | no | no | no | no | no | Yes | Yes | no | no | 2 | 5 | 1 | 3 | 3 | 2 | 3 | 4 | 57.5% | 6 | 2 | 3 | 1 | 5 | 2 | 52% | 6 |  | 5732.8906
1350 | 1350 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Aug 31,2029 | 2027-10-31 | 270 | 15 | 2027-07-05 | low | med | low | high | med | 550000 | 575844 | 575478 | 28.5018 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | no | Yes | no | no | Yes | 3 | 2 | 2 | 1 | 1 | 5 | 1 | 2 | 42.5% | 5 | 1 | 1 | 1 | 5 | 4 | 48% | 5 |  | 5097.2605
1351 | 1351 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Dec 31, 2030 | 2025-12-31 | 196 | 10 | 2026-04-18 | high | low | low | med | med | 350000 | 370016 | 378399 | 96.1798 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | Yes | no | Yes | no | no | no | no | Yes | Yes | 4 | 5 | 3 | 3 | 4 | 5 | 5 | 5 | 85% | 9 | 1 | 1 | 1 | 1 | 1 | 20% | 2 |  | 13582.277
1352 | 1352 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | April 30,2028 | 2028-12-31 | 309 | 10 | 2027-05-27 | high | low | med | med | high | 550000 | 1480343 | 1480758 | 89.4674 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 4 | 5 | 3 | 1 | 1 | 5 | 3 | 5 | 67.5% | 6 | 4 | 1 | 1 | 5 | 3 | 56% | 6 |  | 7110.0938
1353 | 1353 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | June 30, 2025 | 2029-12-31 | 156 | 10 | 2029-07-28 | med | med | low | med | high | 400000 | 477837 | 478567 | 68.0307 | CAPITAL | no | Pipeline segment | X |  |  | X |  | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 5 | 4 | 3 | 1 | 5 | 1 | 3 | 4 | 65% | 6 | 2 | 1 | 1 | 5 | 4 | 52% | 6 |  | 4858.8867
1354 | 1354 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | Mar 31,2030 | 2028-12-31 | 44 | 8 | 2028-11-17 | med | med | low | med | high | 650000 | 662027 | 682144 | 108.8597 | CAPITAL | no | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | no | Yes | Yes | 4 | 2 | 1 | 5 | 2 | 5 | 3 | 4 | 65% | 6 | 4 | 4 | 1 | 5 | 4 | 72% | 8 |  | 2178.0735
1355 | 1355 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | Sept 30,2028 | 2028-10-31 | 205 | 4 | 2028-06-09 | high | low | low | med | med | 1800000 | 1964493 | 1902540 | 55.4393 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 1 | 5 | 4 | 5 | 1 | 2 | 2 | 1 | 52.5% | 6 | 1 | 1 | 5 | 5 | 5 | 68% | 7 |  | 1090.5382
1356 | 1356 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | April 30,2027 | 2026-07-31 | 282 | 8 | 2026-03-24 | med | low | med | low | med | 500000 | 786958 | 789562 | 64.1787 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 4 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 45% | 5 | 3 | 2 | 5 | 3 | 5 | 72% | 8 |  | 4052.0846
1357 | 1357 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Sept 30, 2025 | 2027-07-31 | 244 | 4 | 2027-05-01 | high | low | low | high | high | 400000 | 545632 | 516927 | 93.8623 | EXPENSE | no | Pipeline segment |  | X |  | X | X | no | no | no | no | Yes | no | Yes | no | no | 3 | 4 | 2 | 3 | 1 | 1 | 2 | 2 | 45% | 5 | 5 | 4 | 1 | 5 | 5 | 80% | 8 |  | 4522
1358 | 1358 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Nov 30, 2025 | 2026-07-31 | 25 | 8 | 2026-03-06 | low | med | med | high | high | 500000 | 666455 | 685432 | 12.1249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 3 | 1 | 5 | 2 | 1 | 1 | 2 | 42.5% | 5 | 1 | 2 | 1 | 4 | 5 | 52% | 6 |  | 8756
1359 | 1359 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Nov 30, 2025 | 2027-10-31 | 357 | 8 | 2027-01-08 | low | low | med | high | high | 500000 | 483098 | 491931 | 94.2513 | CAPITAL | Yes | Pipeline segment |  |  | X |  | X | Yes | no | no | Yes | Yes | Yes | Yes | Yes | no | 4 | 3 | 1 | 2 | 4 | 1 | 5 | 3 | 57.5% | 6 | 5 | 2 | 5 | 4 | 5 | 84% | 9 |  | 4785
1360 | 1360 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Toronto | Sept 30, 2025 | 2028-12-31 | 112 | 10 | 2028-09-10 | med | high | high | med | high | 450000 | 821878 | 824096 | 99.9422 | CAPITAL | Yes | Pipeline segment |  | X | X | X | X | no | no | Yes | Yes | Yes | Yes | Yes | no | Yes | 4 | 3 | 2 | 4 | 4 | 3 | 5 | 1 | 65% | 6 | 1 | 3 | 5 | 4 | 3 | 64% | 7 |  | 4101.034
1361 | 1361 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Aug 31,2027 | 2029-10-31 | 291 | 10 | 2029-03-15 | low | high | low | med | low | 400000 | 669911 | 715057 | 54.5821 | EXPENSE | no | Pipeline segment | X |  |  |  | X | no | no | Yes | no | Yes | Yes | no | no | Yes | 4 | 2 | 2 | 3 | 3 | 5 | 2 | 1 | 55% | 6 | 2 | 3 | 5 | 5 | 2 | 68% | 7 |  | 13420.41
1362 | 1362 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Sept 30,2030 | 2030-10-31 | 70 | 10 | 2030-10-22 | med | high | high | low | med | 400000 | 344031 | 340632 | 122.8607 | CAPITAL | no | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | no | Yes | no | Yes | Yes | 3 | 2 | 1 | 3 | 3 | 3 | 3 | 4 | 55% | 6 | 4 | 3 | 1 | 5 | 5 | 72% | 8 |  | 1727.265
1363 | 1363 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Sept 30,2028 | Oct 31, 2026 | 23 | 10 | 2026-12-08 | med | med | low | high | med | 350000 | 439702 | 481874 | 109.8564 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | no | no | no | no | no | no | no | Yes | Yes | 1 | 5 | 1 | 3 | 3 | 5 | 2 | 5 | 62.5% | 6 | 2 | 5 | 1 | 3 | 1 | 48% | 5 |  | 1578
1364 | 1364 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Aug 31,2027 | 2026-10-31 | 207 | 10 | 2026-06-07 | high | low | high | low | high | 350000 | 661009 | 682588 | 111.3269 | EXPENSE | Yes | Pipeline segment | X |  | X | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | Yes | 3 | 2 | 3 | 2 | 5 | 5 | 2 | 5 | 67.5% | 6 | 5 | 2 | 1 | 5 | 3 | 64% | 7 |  | 3506.871
1365 | 1365 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30,2026 | 2026-12-31 | 144 | 10 | 2026-08-09 | high | high | high | low | low | 350000 | 323179 | 320094 | 59.7386 | CAPITAL | no | Pipeline segment |  | X |  | X | X | Yes | no | no | no | no | no | no | no | Yes | 3 | 2 | 1 | 5 | 5 | 3 | 3 | 3 | 62.5% | 6 | 2 | 2 | 1 | 4 | 3 | 48% | 5 |  | 18109.72
1366 | 1366 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Aug 31,2027 | 2027-12-31 | 170 | 10 | 2028-02-12 | low | med | low | low | high | 500000 | 590681 | 590005 | 24.542 | EXPENSE | Yes | Pipeline segment |  | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | Yes | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 27.5% | 3 | 1 | 5 | 1 | 1 | 1 | 36% | 4 |  | 20815.33
1367 | 1367 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Sept 30,2026 | 2025-10-31 | 66 | 8 | 2025-10-26 | high | low | low | high | low | 400000 | 801992 | 806981 | 279.7384 | EXPENSE | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 2 | 4 | 2 | 5 | 4 | 4 | 3 | 5 | 72.5% | 8 | 5 | 4 | 1 | 1 | 5 | 64% | 7 |  | 2789
1368 | 1368 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Sept 30,2026 | 2028-07-31 | 153 | 8 | 2027-05-31 | med | low | high | high | med | 500000 | 550475 | 595557 | 117.2576 | EXPENSE | no | Pipeline segment |  | X | X |  |  | no | Yes | Yes | no | Yes | no | no | Yes | Yes | 4 | 5 | 2 | 4 | 4 | 3 | 5 | 3 | 75% | 8 | 5 | 3 | 1 | 4 | 2 | 60% | 6 |  | 5666
1369 | 1369 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Dec 31, 2030 | 2026-10-31 | 122 | 10 | 2026-07-01 | med | low | med | low | low | 350000 | 540105 | 540380 | 81.2986 | CAPITAL | no | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | no | Yes | no | no | no | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 32.5% | 4 | 1 | 2 | 1 | 5 | 2 | 44% | 5 |  | 2789
1370 | 1370 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | April 30,2027 | 2029-10-31 | 279 | 10 | 2029-03-27 | med | high | high | high | high | 500000 | 724601 | 723464 | 98.531 | CAPITAL | no | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | no | no | no | Yes | 1 | 3 | 1 | 2 | 3 | 3 | 2 | 5 | 50% | 5 | 5 | 2 | 1 | 2 | 4 | 56% | 6 |  | 2588
1371 | 1371 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Sept 30, 2025 | 2026-10-31 | 176 | 10 | 2026-07-08 | low | high | med | med | low | 350000 | 352474 | 355000 | 37.7222 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | Yes | 2 | 2 | 1 | 4 | 4 | 1 | 3 | 1 | 45% | 5 | 4 | 2 | 1 | 3 | 1 | 44% | 5 |  | 8792
1372 | 1372 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Quebec City | May 31, 2026 | 2028-10-31 | 191 | 15 | 2028-06-23 | low | med | low | low | low | 550000 | 499129 | 513827 | 77.5311 | EXPENSE | no | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | no | Yes | no | Yes | 4 | 3 | 1 | 4 | 3 | 3 | 3 | 1 | 55% | 6 | 2 | 2 | 1 | 2 | 3 | 40% | 4 |  | 23717.24
1373 | 1373 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Sept 30, 2025 | 2029-07-31 | 314 | 4 | 2028-09-20 | med | low | high | low | high | 400000 | 350785 | 393433 | 109.3207 | EXPENSE | no | Pipeline segment | X | X |  | X | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 3 | 2 | 1 | 1 | 3 | 5 | 2 | 4 | 52.5% | 6 | 1 | 2 | 1 | 3 | 5 | 48% | 5 |  | 746.1723
1374 | 1374 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | WINNIPEG | April 30,2029 | 2029-07-31 | 134 | 8 | 2029-08-19 | high | high | high | low | med | 400000 | 422998 | 420888 | 74.8121 | CAPITAL | no | Pipeline segment | X | X |  | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 4 | 2 | 3 | 4 | 3 | 5 | 4 | 70% | 6 | 5 | 4 | 1 | 1 | 2 | 52% | 6 |  | 13677.18
1375 | 1375 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Sept 30,2028 | 2029-10-31 | 341 | 8 | 2029-04-24 | high | med | med | med | high | 400000 | 381473 | 383108 | 142.0502 | CAPITAL | no | Pipeline segment | X | X | X | X | X | Yes | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 1 | 4 | 2 | 5 | 4 | 5 | 2 | 70% | 6 | 3 | 3 | 1 | 4 | 4 | 60% | 6 |  | 7007.921
1376 | 1376 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Dec 31, 2030 | 2025-07-31 | 359 | 8 | 2024-08-06 | med | med | low | med | low | 350000 | 362424 | 362097 | 82.7364 | CAPITAL | Yes | Pipeline segment |  |  | X | X | X | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 4 | 55% | 6 | 4 | 4 | 1 | 1 | 3 | 52% | 6 |  | 1685.963
1377 | 1377 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Nov 30,2029 | 2029-12-31 | 187 | 8 | 2029-06-27 | low | med | med | low | high | 550000 | 531429 | 533699 | 69.7306 | CAPITAL | no | Pipeline segment | X | X |  | X | X | Yes | Yes | Yes | no | Yes | Yes | Yes | no | no | 4 | 1 | 1 | 4 | 3 | 2 | 4 | 4 | 57.5% | 6 | 3 | 1 | 1 | 3 | 4 | 48% | 5 |  | 778.6578
1378 | 1378 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | June 30, 2025 | 2028-10-31 | 260 | 8 | 2028-04-15 | low | med | low | high | high | 550000 | 565673 | 562884 | 110.153 | CAPITAL | no | Pipeline segment | X | X | X |  | X | no | no | Yes | Yes | Yes | no | no | no | no | 5 | 4 | 4 | 1 | 1 | 1 | 3 | 3 | 55% | 6 | 2 | 3 | 1 | 2 | 1 | 36% | 4 |  | 267.7598
1379 | 1379 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Winnipeg | Sept 30, 2025 | 2026-10-31 | 181 | 8 | 2026-07-03 | low | med | med | med | low | 500000 | 780384 | 780364 | 36.7014 | CAPITAL | no | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 5 | 4 | 4 | 5 | 1 | 2 | 4 | 1 | 65% | 6 | 2 | 5 | 1 | 5 | 2 | 60% | 6 |  | 267.7598
1380 | 1380 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | May 31, 2026 | 2029-03-31 | 90 | 8 | 2028-12-31 | high | low | low | med | low | 400000 | 474413 | 474247 | 13.6895 | CAPITAL | no | Pipeline segment | X | X |  | X | X | Yes | no | no | Yes | no | Yes | Yes | Yes | Yes | 4 | 3 | 1 | 3 | 2 | 5 | 1 | 2 | 52.5% | 6 | 5 | 5 | 1 | 4 | 2 | 68% | 7 |  | 6832.492
1381 | 1381 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30, 2025 | 2027-07-31 | 80 | 4 | 2027-01-10 | med | low | high | low | med | 400000 | 487955 | 487622 | 81.7758 | EXPENSE | no | Pipeline segment | X | X | X |  |  | no | no | Yes | Yes | no | no | Yes | Yes | no | 5 | 5 | 3 | 4 | 5 | 2 | 5 | 1 | 75% | 8 | 5 | 5 | 1 | 4 | 3 | 72% | 8 |  | 25885
1382 | 1382 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | Nov30,2027 | 2028-12-31 | 314 | 15 | 2027-09-21 | med | low | high | high | high | 550000 | 864397 | 866898 | 61.6448 | CAPITAL | Yes | Pipeline segment | X | X | X |  | X | Yes | Yes | no | Yes | no | Yes | no | Yes | Yes | 3 | 3 | 3 | 2 | 2 | 1 | 4 | 5 | 57.5% | 6 | 4 | 5 | 1 | 3 | 2 | 60% | 6 |  | 5845
1383 | 1383 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Dec 31,2028 | 2027-07-31 | 293 | 4 | 2026-01-11 | low | med | med | med | low | 500000 | 595726 | 599706 | 19.694 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 3 | 2 | 3 | 1 | 1 | 4 | 4 | 2 | 50% | 5 | 2 | 5 | 5 | 4 | 2 | 72% | 8 |  | 13582.28
1384 | 1384 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | June 30, 2025 | 2027-10-31 | 287 | 8 | 2027-01-17 | low | med | high | high | low | 2000000 | 2063711 | 2060699 | 35.0188 | EXPENSE | no | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | no | no | no | 1 | 3 | 4 | 5 | 1 | 3 | 4 | 5 | 65% | 6 | 3 | 4 | 5 | 5 | 1 | 72% | 8 |  | 7709.846
1385 | 1385 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Aug 31,2029 | 2029-12-31 | 216 | 8 | 2029-05-29 | low | low | med | low | med | 2100000 | 2089588 | 2100050 | 1745.308 | EXPENSE | no | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | Yes | no | no | no | no | no | Yes | 1 | 4 | 3 | 3 | 2 | 5 | 2 | 2 | 55% | 6 | 5 | 3 | 1 | 5 | 5 | 76% | 8 |  | 7110.094
1386 | 1386 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | Aug 31,2027 | 2026-10-31 | 45 | 10 | 2026-11-16 | high | high | high | high | med | 400000 | 443423 | 420247 | 167.1303 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 2 | 1 | 4 | 5 | 2 | 2 | 2 | 5 | 57.5% | 6 | 1 | 5 | 1 | 5 | 5 | 68% | 7 |  | 4391.637
1387 | 1387 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | Dec 31,2028 | 2028-07-31 | 258 | 10 | 2028-02-16 | high | high | low | low | low | 550000 | 464113 | 471206 | 51.5723 | CAPITAL | Yes | Pipeline segment |  |  |  | X | X | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 1 | 1 | 1 | 5 | 1 | 2 | 5 | 5 | 52.5% | 6 | 5 | 1 | 1 | 3 | 1 | 44% | 5 |  | 4314.195
1388 | 1388 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Calgary | Aug 31,2029 | 2026-07-31 | 339 | 10 | 2025-08-26 | low | low | med | med | high | 500000 | 490412 | 496874 | 19.5924 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | no | no | no | no | no | no | no | Yes | 5 | 2 | 1 | 5 | 3 | 3 | 4 | 5 | 70% | 6 | 5 | 1 | 1 | 2 | 5 | 56% | 6 |  | 4858.887
1389 | 1389 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Nov 30, 2025 | 2025-12-31 | 316 | 8 | 2025-02-18 | high | med | low | high | low | 400000 | 827809 | 927128 | 245.1045 | CAPITAL | Yes | Pipeline segment |  |  |  | X |  | Yes | Yes | no | no | no | Yes | no | no | no | 2 | 3 | 1 | 2 | 3 | 5 | 2 | 3 | 52.5% | 6 | 1 | 3 | 1 | 2 | 5 | 48% | 5 |  | 2178.073
1390 | 1390 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | April 30,2027 | 2028-10-31 | 125 | 10 | 2029-03-28 | high | high | low | med | med | 550000 | 489598 | 483329 | 57.38 | CAPITAL | Yes | Pipeline segment | X | X |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 4 | 2 | 3 | 1 | 2 | 5 | 4 | 60% | 6 | 5 | 4 | 1 | 4 | 2 | 64% | 7 |  | 1090.538
1391 | 1391 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Saskatoon | April 30,2029 | 2026-10-31 | 21 | 10 | 2027-12-10 | low | med | med | high | low | 500000 | 487877 | 486522 | 121.3811 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | no | no | Yes | no | no | Yes | no | no | Yes | 4 | 1 | 1 | 1 | 5 | 1 | 4 | 3 | 50% | 5 | 5 | 4 | 1 | 1 | 3 | 56% | 6 |  | 8501.429
1392 | 1392 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Mar 31,2030 | 2029-10-31 | 282 | 8 | 2028-10-22 | high | low | med | med | med | 2000000 | 1987275 | 1896800 | 526.2579 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | Yes | Yes | no | Yes | Yes | 5 | 2 | 3 | 4 | 1 | 4 | 3 | 2 | 60% | 6 | 4 | 1 | 1 | 3 | 3 | 48% | 5 |  | 4052.085
1393 | 1393 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Nov 30, 2025 | 2026-10-31 | 289 | 10 | 2025-06-15 | low | med | med | high | med | 350000 | 474581 | 482853 | 166.8084 | CAPITAL | Yes | Pipeline segment |  | X |  | X |  | no | no | no | Yes | Yes | Yes | no | no | no | 2 | 5 | 2 | 2 | 1 | 1 | 2 | 5 | 50% | 5 | 1 | 4 | 5 | 1 | 3 | 56% | 6 |  | 2610.39
1394 | 1394 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Edmonton | April 30,2029 | 2029-10-31 | 33 | 8 | 2029-11-28 | low | high | high | low | high | 750000 | 861410 | 860656 | 15.3529 | EXPENSE | no | Derate/low flow Pipe segment |  | X | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | no | 3 | 1 | 1 | 1 | 4 | 4 | 4 | 2 | 50% | 5 | 5 | 2 | 5 | 1 | 2 | 60% | 6 |  | 241.5599
1395 | 1395 | L1 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Regina | Nov30,2027 | 2027-07-31 | 93 | 8 | 2027-04-29 | high | high | high | high | low | 1800000 | 1807733 | 1857547 | 102.2668 | EXPENSE | no | Pipeline segment | X |  | X | X |  | Yes | Yes | no | Yes | Yes | no | Yes | Yes | Yes | 3 | 3 | 1 | 3 | 4 | 1 | 1 | 1 | 42.5% | 5 | 2 | 5 | 5 | 2 | 1 | 60% | 6 |  | 4995.39
1396 | 1396 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Dec 31, 2030 | Oct 31, 2025 | 346 | 8 | 2025-04-19 | high | low | high | low | high | 400000 | 555442 | 543668 | 71.2228 | EXPENSE | Yes | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | no | Yes | Yes | Yes | no | 5 | 2 | 4 | 1 | 3 | 2 | 3 | 1 | 52.5% | 6 | 3 | 2 | 1 | 2 | 1 | 36% | 4 |  | 5000
1397 | 1397 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | Aug 31,2029 | Oct 31, 2025 | 79 | 8 | 2026-01-11 | high | med | high | low | med | 500000 | 827580 | 888541 | 53.7439 | CAPITAL | no | Pipeline segment | X |  |  |  |  | Yes | Yes | no | no | no | Yes | Yes | no | Yes | 2 | 2 | 1 | 5 | 5 | 3 | 2 | 3 | 57.5% | 6 | 1 | 1 | 1 | 2 | 5 | 40% | 4 |  | 347
1398 | 1398 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Sept 30,2028 | 2025-12-31 | 198 | 8 | 2026-01-14 | med | high | low | low | low | 350000 | 380645 | 388809 | 117.9206 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | no | 5 | 3 | 1 | 2 | 1 | 1 | 5 | 2 | 50% | 5 | 2 | 4 | 1 | 2 | 3 | 48% | 5 |  | 158885
1399 | 1399 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | Sept 30,2030 | 2026-10-31 | 117 | 8 | 2026-12-04 | high | high | low | high | low | 550000 | 1575306 | 1571669 | 68.6381 | CAPITAL | Yes | Pipeline segment | X |  | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | Yes | 1 | 2 | 3 | 2 | 4 | 5 | 3 | 4 | 60% | 6 | 4 | 4 | 1 | 1 | 1 | 44% | 5 |  | 1207.799
1400 | 1400 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | June 30, 2025 | 2029-12-31 | 142 | 10 | 2029-08-11 | med | low | med | low | med | 500000 | 509915 | 513929 | 72.3249 | CAPITAL | Yes | Pipeline segment | X |  | X |  |  | Yes | Yes | no | no | no | no | Yes | no | no | 1 | 3 | 3 | 2 | 1 | 2 | 5 | 1 | 45% | 5 | 5 | 3 | 1 | 3 | 4 | 64% | 7 |  | 1785
1401 | 1401 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Winnipeg | Sept 30,2028 | 2028-12-31 | 144 | 10 | 2027-03-09 | high | high | low | low | low | 500000 | 488609 | 483956 | 84.9423 | CAPITAL | no | pipeline segment | X | X | X | X |  | no | no | Yes | Yes | no | no | no | Yes | Yes | 2 | 1 | 1 | 1 | 4 | 3 | 5 | 2 | 47.5% | 5 | 1 | 3 | 5 | 2 | 5 | 64% | 7 |  | 172.2548
1402 | 1402 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | April 30,2027 | Dec 31, 2026 | 257 | 4 | 2026-04-18 | med | low | high | high | low | 1500000 | 1506928 | 1495675 | 33.796 | MAINT. CAP | Yes | Derate/low flow Pipe segment | X |  | X |  | X | Yes | no | no | Yes | no | no | Yes | no | no | 2 | 1 | 4 | 5 | 2 | 4 | 5 | 2 | 62.5% | 6 | 5 | 3 | 1 | 1 | 3 | 52% | 6 |  | 191.3942
1403 | 1403 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Calgary | March 31, 2026 | 2027-12-31 | 305 | 10 | 2027-03-01 | high | low | low | low | med | 750000 | 751968 | 754634 | 41.9164 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | Yes | no | Yes | Yes | no | Yes | Yes | Yes | no | 5 | 1 | 3 | 5 | 3 | 1 | 5 | 1 | 60% | 6 | 2 | 3 | 1 | 2 | 3 | 44% | 5 |  | 173.2929
1404 | 1404 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Sept 30,2028 | 2027-07-31 | 193 | 5 | 2026-06-21 | low | med | high | high | low | 350000 | 320570 | 415873 | 375.5287 | EXPENSE | no | Pipeline segment |  |  |  | X |  | Yes | Yes | Yes | Yes | Yes | no | no | Yes | Yes | 1 | 3 | 2 | 1 | 4 | 5 | 2 | 3 | 52.5% | 6 | 4 | 1 | 1 | 5 | 5 | 64% | 7 |  | 900.2043
1405 | 1405 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Mar 31,2030 | 2028-07-31 | 279 | 10 | 2027-10-26 | high | med | high | low | med | 400000 | 709452 | 706903 | 34.9002 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 1 | 4 | 1 | 1 | 5 | 2 | 2 | 3 | 47.5% | 5 | 2 | 3 | 1 | 2 | 5 | 52% | 6 |  | 749.7244
1406 | 1406 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | April 30,2029 | 2026-07-31 | 361 | 10 | 2025-11-04 | med | med | low | low | low | 500000 | 624655 | 652754 | 95.8703 | CAPITAL | Yes | Pipeline segment | X |  |  | X |  | no | no | no | Yes | no | no | no | no | Yes | 3 | 1 | 1 | 1 | 5 | 1 | 4 | 3 | 47.5% | 5 | 2 | 2 | 1 | 4 | 3 | 48% | 5 |  | 41798.52
1407 | 1407 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Dec 31,2028 | 2026-07-31 | 200 | 4 | 2026-04-14 | med | high | med | low | med | 400000 | 454302 | 487376 | 71.1665 | EXPENSE | no | Pipeline segment |  | X |  |  | X | Yes | Yes | Yes | Yes | Yes | no | Yes | Yes | Yes | 3 | 3 | 4 | 2 | 2 | 3 | 1 | 2 | 50% | 5 | 3 | 3 | 1 | 5 | 5 | 68% | 7 |  | 32.5005
1408 | 1408 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | April 30,2027 | 2029-10-31 | 215 | 8 | 2029-05-30 | high | med | med | low | low | 550000 | 931419 | 934750 | 76.4614 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | no | Yes | Yes | no | no | 2 | 4 | 1 | 2 | 2 | 2 | 5 | 1 | 47.5% | 5 | 5 | 3 | 1 | 5 | 3 | 68% | 7 |  | 1022.412
1409 | 1409 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-RECTIFIER | Regina | Nov30,2027 | 2027-10-31 | 284 | 8 | 2026-10-20 | med | med | low | low | high | 700000 | 437705 | 443302 | 228.8332 | EXPENSE | Yes | Pipeline segment | X | X |  | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | no | 1 | 5 | 4 | 4 | 5 | 1 | 1 | 3 | 60% | 6 | 4 | 4 | 1 | 1 | 5 | 60% | 6 |  | 4447
1410 | 1410 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | Dec 31,2026 | 2026-10-31 | 44 | 8 | 2026-09-17 | med | low | med | med | high | 400000 | 485478 | 480917 | 28.2991 | EXPENSE | no | Pipeline segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 2 | 2 | 1 | 2 | 5 | 1 | 1 | 1 | 37.5% | 4 | 3 | 4 | 1 | 4 | 2 | 56% | 6 |  | 7718.869
1411 | 1411 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Aug 31,2029 | 2028-07-31 | 61 | 8 | 2028-10-31 | low | low | high | med | low | 550000 | 558450 | 559906 | 134.4344 | CAPITAL | Yes | Pipeline segment |  | X | X |  |  | Yes | no | no | Yes | Yes | Yes | no | no | Yes | 2 | 3 | 2 | 4 | 3 | 3 | 1 | 3 | 52.5% | 6 | 3 | 2 | 1 | 5 | 4 | 60% | 6 |  | 7718.869
1412 | 1412 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Dec 31,2026 | 2029-07-31 | 121 | 10 | 2029-09-01 | high | high | high | low | high | 550000 | 792798 | 734137 | 890.1864 | CAPITAL | no | Pipeline segment |  | X | X | X | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 3 | 2 | 1 | 5 | 5 | 5 | 4 | 5 | 75% | 8 | 1 | 3 | 5 | 4 | 4 | 68% | 7 |  | 6993.546
1413 | 1413 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Aug 31,2029 | 2026-10-31 | 100 | 4 | 2026-09-22 | high | med | low | high | med | 1500000 | 1580829 | 1584305 | 143.1102 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | no | Yes | no | no | no | Yes | 3 | 5 | 2 | 2 | 4 | 2 | 4 | 3 | 62.5% | 6 | 3 | 1 | 1 | 5 | 2 | 48% | 5 |  | 636.4681
1414 | 1414 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Nov30,2027 | 2026-10-31 | 125 | 10 | 2025-06-28 | med | high | high | high | low | 500000 | 351865 | 354621 | 86.0466 | CAPITAL | Yes | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | no | Yes | Yes | no | 1 | 3 | 4 | 4 | 4 | 3 | 2 | 1 | 55% | 6 | 1 | 5 | 1 | 4 | 4 | 60% | 6 |  | 2369.828
1415 | 1415 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | April 30,2027 | 2026-12-31 | 356 | 10 | 2025-08-09 | low | med | low | med | low | 500000 | 985848 | 988631 | 71.0178 | EXPENSE | Yes | Pipeline segment |  |  |  | X |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 3 | 3 | 1 | 5 | 2 | 1 | 3 | 47.5% | 5 | 4 | 5 | 1 | 5 | 3 | 72% | 8 |  | 2369.828
1416 | 1416 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Dec 31,2026 | 2026-10-31 | 204 | 15 | 2027-01-08 | high | high | high | med | med | 500000 | 897582 | 890760 | 56.3678 | CAPITAL | Yes | Pipeline segment |  |  | X | X |  | Yes | no | no | no | no | no | no | no | no | 3 | 5 | 1 | 5 | 3 | 2 | 2 | 4 | 62.5% | 6 | 1 | 5 | 1 | 1 | 1 | 36% | 4 |  | 3138.866
1417 | 1417 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | April 30,2027 | 2028-12-31 | 121 | 15 | 2028-09-01 | low | high | high | low | high | 400000 | 623417 | 635508 | 204.7502 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | Yes | Yes | no | Yes | Yes | no | no | Yes | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 5 | 45% | 5 | 3 | 4 | 1 | 2 | 4 | 56% | 6 |  | 14928.99
1418 | 1418 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30, 2025 | 2029-12-31 | 235 | 5 | 2029-05-10 | high | high | med | med | med | 420000 | 384800 | 395163 | 193.3484 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | no | Yes | Yes | no | no | Yes | Yes | Yes | 1 | 4 | 3 | 4 | 4 | 3 | 5 | 1 | 62.5% | 6 | 2 | 2 | 1 | 2 | 2 | 36% | 4 |  | 4785
1419 | 1419 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | Dec 31,2026 | 2028-12-31 | 274 | 10 | 2028-04-01 | high | med | high | low | low | 650000 | 769127 | 763937 | 53.022 | CAPITAL | no | Pipeline segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | no | Yes | Yes | 3 | 1 | 3 | 3 | 5 | 1 | 5 | 5 | 65% | 6 | 3 | 2 | 1 | 4 | 5 | 60% | 6 |  | 4487
1420 | 1420 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | Nov 30, 2025 | 2027-12-31 | 181 | 4 | 2027-05-03 | high | low | low | low | med | 1800000 | 1789522 | 1832500 | 2.6813 | EXPENSE | no | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | no | no | Yes | Yes | no | Yes | Yes | 5 | 5 | 3 | 5 | 2 | 2 | 4 | 4 | 75% | 8 | 1 | 5 | 1 | 3 | 1 | 44% | 5 |  | 477.3811
1421 | 1421 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | Mar 31,2030 | 2029-10-31 | 217 | 8 | 2027-12-27 | med | high | low | high | high | 2000000 | 1920848 | 1689578 | 304.5368 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X | X | X | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 3 | 1 | 1 | 5 | 5 | 4 | 1 | 1 | 52.5% | 6 | 3 | 2 | 1 | 4 | 5 | 60% | 6 |  | 5347.325
1422 | 1422 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | April 30,2027 | 2028-12-31 | 32 | 10 | 2028-06-29 | med | med | low | high | high | 400000 | 499341 | 496308 | 44.7596 | CAPITAL | no | Pipeline segment | X | X |  | X | X | no | no | Yes | Yes | Yes | Yes | no | Yes | no | 1 | 4 | 2 | 1 | 2 | 1 | 3 | 5 | 47.5% | 5 | 2 | 1 | 1 | 1 | 1 | 24% | 3 |  | 4542.743
1423 | 1423 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | April 30,2028 | 2028-12-31 | 43 | 8 | 2028-06-18 | med | med | low | low | low | 400000 | 423560 | 460010 | 86.1551 | EXPENSE | no | Pipeline segment | X |  |  | X |  | Yes | no | Yes | Yes | Yes | Yes | Yes | no | no | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 35% | 4 | 1 | 1 | 1 | 1 | 5 | 36% | 4 |  | 2679.519
1424 | 1424 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Saskatoon | Sept 30,2030 | 2027-07-31 | 307 | 10 | 2026-12-28 | med | low | high | low | med | 750000 | 752055 | 721982 | 100.5902 | EXPENSE | no | pipeline segment outage |  | X | X |  | X | no | Yes | no | no | no | Yes | no | no | Yes | 2 | 5 | 3 | 2 | 4 | 4 | 5 | 1 | 65% | 6 | 5 | 3 | 1 | 1 | 2 | 48% | 5 |  | 45.3112
1425 | 1425 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Sept 30,2030 | 2027-12-31 | 229 | 8 | 2027-05-16 | high | high | med | high | high | 500000 | 725080 | 725529 | 32.563 | EXPENSE | no | Pipeline segment |  |  | X | X | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 2 | 1 | 4 | 2 | 1 | 3 | 2 | 5 | 50% | 5 | 2 | 5 | 1 | 1 | 3 | 48% | 5 |  | 263.7275
1426 | 1426 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Winnipeg | Nov 30,2029 | 2026-10-31 | 218 | 10 | 2026-05-27 | med | low | low | low | high | 500000 | 496475 | 495002 | 13.0596 | CAPITAL | no | Pipeline segment | [5 empty] | Yes | Yes | Yes | no | no | Yes | Yes | no | Yes | 1 | 2 | 2 | 3 | 5 | 2 | 5 | 1 | 52.5% | 6 | 2 | 3 | 1 | 5 | 5 | 64% | 7 |  | 18394.3
1427 | 1427 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Mar 31,2030 | 2029-07-31 | 286 | 8 | 2028-03-20 | low | med | low | high | med | 500000 | 478617 | 519000 | 3.8339 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 5 | 2 | 2 | 3 | 5 | 3 | 5 | 65% | 6 | 4 | 3 | 1 | 3 | 4 | 60% | 6 |  | 76225.68
1428 | 1428 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Dec 31, 2030 | 2027-07-31 | 140 | 8 | 2027-08-13 | med | high | low | med | high | 520000 | 986111 | 1100500 | 89.8531 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 5 | 5 | 2 | 1 | 5 | 2 | 5 | 3 | 70% | 6 | 3 | 3 | 1 | 5 | 1 | 52% | 6 |  | 16.9273
1429 | 1429 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Toronto | Sept 30,2030 | 2026-12-31 | 215 | 12 | 2025-12-28 | med | high | high | low | high | 300000 | 362980 | 335201 | 1124.6434 | EXPENSE | no | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 2 | 2 | 1 | 4 | 1 | 2 | 5 | 3 | 50% | 5 | 4 | 4 | 1 | 1 | 5 | 60% | 6 |  | 560.1412
1430 | 1430 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | March 31, 2026 | 2027-07-31 | 269 | 8 | 2027-02-04 | med | high | high | high | high | 400000 | 371481 | 367796 | 137.4312 | CAPITAL | no | Pipeline segment |  |  | X | X | X | Yes | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 4 | 1 | 3 | 1 | 3 | 3 | 4 | 5 | 60% | 6 | 4 | 2 | 1 | 4 | 2 | 52% | 6 |  | 10535.75
1431 | 1431 | L2 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Calgary | Mar 31,2030 | 2026-10-31 | 184 | 8 | 2026-06-30 | high | high | high | med | high | 250000 | 298807 | 298469 | 14.7788 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X |  | no | no | Yes | Yes | no | no | Yes | no | Yes | 1 | 2 | 2 | 5 | 2 | 4 | 4 | 3 | 57.5% | 6 | 4 | 1 | 1 | 2 | 1 | 36% | 4 |  | 2491.953
1432 | 1432 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | North Bay | Mar 31,2030 | 2028-07-31 | 301 | 8 | 2028-03-05 | high | med | high | high | low | 550000 | 529833 | 522678 | 78.3491 | EXPENSE | Yes | Pipeline segment |  |  |  | X | X | no | Yes | no | no | no | Yes | no | Yes | no | 5 | 4 | 4 | 5 | 1 | 5 | 1 | 2 | 67.5% | 6 | 1 | 5 | 1 | 2 | 1 | 40% | 4 |  | 16593.69
1433 | 1433 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Nov 30, 2025 | 2029-12-31 | 37 | 8 | 2029-06-24 | med | high | high | med | low | 400000 | 636064 | 696142 | 188.6819 | EXPENSE | Yes | Pipeline segment |  | X |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 5 | 5 | 1 | 1 | 1 | 4 | 5 | 3 | 62.5% | 6 | 1 | 2 | 5 | 5 | 3 | 64% | 7 |  | 31873.29
1434 | 1434 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | April 30,2028 | 2030-07-31 | 205 | 4 | 2030-06-09 | low | low | low | high | med | 950000 | 951400 | 1073713 | 165.7118 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | no | no | no | Yes | 2 | 3 | 2 | 1 | 4 | 5 | 4 | 3 | 60% | 6 | 4 | 2 | 1 | 2 | 3 | 48% | 5 |  | 495.1227
1435 | 1435 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Dec 31, 2030 | 2027-12-31 | 240 | 4 | 2027-12-04 | high | low | low | low | high | 1250000 | 1201124 | 1215797 | 732.8044 | EXPENSE | no | Derate/low flow Pipe segment | X | X |  |  |  | no | Yes | Yes | Yes | Yes | no | no | no | no | 3 | 4 | 1 | 2 | 3 | 1 | 4 | 1 | 47.5% | 5 | 5 | 5 | 1 | 4 | 3 | 72% | 8 |  | 5521.373
1436 | 1436 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Quebec City | Mar 31,2030 | 2028-07-31 | 56 | 2 | 2028-11-05 | low | high | med | low | med | 450000 | 493301 | 555422 | 146.1537 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | no | no | Yes | Yes | no | Yes | no | Yes | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 85% | 9 | 1 | 2 | 1 | 3 | 5 | 48% | 5 |  | 13659.19
1437 | 1437 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | April 30,2027 | 2027-10-31 | 265 | 7 | 2026-11-08 | low | high | low | low | med | 2000000 | 2222026 | 2251913 | 12.9047 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | no | no | no | no | Yes | no | 5 | 3 | 2 | 2 | 1 | 2 | 5 | 1 | 52.5% | 6 | 4 | 5 | 1 | 3 | 5 | 72% | 8 |  | 13659.19
1438 | 1438 | L3 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Winnipeg | Nov 30,2029 | 2028-12-31 | 84 | 10 | 2029-01-06 | high | high | low | med | med | 1300000 | 1324785 | 1350260 | 119.9716 | EXPENSE | no | Pipeline segment | X |  |  |  | X | Yes | no | no | Yes | Yes | no | no | Yes | no | 3 | 4 | 2 | 3 | 1 | 2 | 2 | 1 | 45% | 5 | 2 | 5 | 1 | 2 | 5 | 60% | 6 |  | 17906.94
1439 | 1439 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Dec 31, 2030 | 2026-10-31 | 188 | 5 | 2026-06-26 | high | med | med | high | med | 400000 | 393878 | 395581 | 318.2127 | EXPENSE | no | Pipeline segment | X |  |  | X | X | no | no | Yes | Yes | Yes | no | no | Yes | Yes | 4 | 4 | 2 | 4 | 5 | 5 | 3 | 1 | 70% | 6 | 5 | 4 | 1 | 1 | 1 | 48% | 5 |  | 19639.87
1440 | 1440 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | Aug 31,2027 | 2025-07-31 | 162 | 10 | 2025-10-20 | high | low | med | med | low | 550000 | 875950 | 888752 | 59.654 | CAPITAL | no | Pipeline segment |  | X | X | X | X | Yes | no | no | no | Yes | Yes | no | Yes | no | 5 | 1 | 3 | 3 | 2 | 1 | 4 | 3 | 55% | 6 | 4 | 1 | 1 | 2 | 2 | 40% | 4 |  | 6487.582
1441 | 1441 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Toronto | Sept 30, 2025 | Dec 31, 2027 | 153 | 10 | 2025-07-31 | low | med | med | low | low | 550000 | 870821 | 874947 | 250.7139 | EXPENSE | Yes | Pipeline segment | X | X |  |  | X | Yes | no | no | Yes | no | no | no | no | Yes | 5 | 5 | 3 | 1 | 5 | 2 | 1 | 5 | 67.5% | 6 | 1 | 5 | 1 | 2 | 1 | 40% | 4 |  | 1083.35
1442 | 1442 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Dec 31,2026 | Oct 31, 2025 | 72 | 8 | 2025-08-20 | low | low | high | med | med | 400000 | 617515 | 618701 | 129.2729 | EXPENSE | no | Pipeline segment | X | X |  | X |  | no | Yes | Yes | Yes | no | no | no | Yes | no | 1 | 1 | 3 | 3 | 4 | 1 | 4 | 1 | 45% | 5 | 4 | 1 | 1 | 1 | 5 | 48% | 5 |  | 1184.914
1443 | 1443 | L2 | PIPE INTEGRITY | EXCAVATION | SLEEVE | North Bay | April 30,2028 | 2027-12-31 | 16 | 10 | 2027-10-15 | med | low | high | med | high | 300000 | 314592 | 316431 | 134.8065 | EXPENSE | no | Pipeline segment | X | X |  |  | X | Yes | no | Yes | Yes | no | no | no | no | no | 4 | 4 | 4 | 1 | 1 | 5 | 4 | 5 | 70% | 6 | 4 | 4 | 1 | 2 | 2 | 52% | 6 |  | 1846.619
1444 | 1444 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-RECTIFIER | Quebec City | Mar 31,2030 | 2026-10-31 | 182 | 8 | 2027-07-02 | high | high | high | low | med | 700000 | 770309 | 770000 | 28.6028 | CAPITAL | no | pipeline segment outage |  |  | X |  | X | Yes | no | no | no | no | Yes | no | Yes | Yes | 2 | 5 | 4 | 2 | 2 | 3 | 2 | 4 | 60% | 6 | 4 | 5 | 1 | 1 | 1 | 48% | 5 |  | 8429.71
1445 | 1445 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Winnipeg | April 30,2027 | 2031-07-31 | 227 | 10 | 2030-05-18 | low | low | high | high | high | 750000 | 701590 | 708037 | 118.806 | EXPENSE | no | pipeline segment outage | X | X |  |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 5 | 3 | 3 | 4 | 2 | 2 | 2 | 3 | 60% | 6 | 5 | 4 | 5 | 1 | 2 | 68% | 7 |  | 258
1446 | 1446 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Dec 31,2028 | 2026-07-31 | 280 | 4 | 2026-03-26 | high | high | low | high | low | 1000000 | 1024910 | 1058330 | 61.0855 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | no | no | Yes | Yes | no | Yes | Yes | 1 | 1 | 4 | 2 | 2 | 3 | 2 | 4 | 47.5% | 5 | 2 | 1 | 5 | 1 | 3 | 48% | 5 |  | 842.9817
1447 | 1447 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | March 31, 2026 | 2027-10-31 | 94 | 10 | 2027-04-28 | low | low | low | low | low | 500000 | 677573 | 672660 | 11.9354 | EXPENSE | no | Pipeline segment |  |  | X |  |  | Yes | no | Yes | no | Yes | Yes | no | Yes | no | 3 | 1 | 1 | 1 | 4 | 2 | 1 | 3 | 40% | 4 | 5 | 5 | 5 | 4 | 4 | 92% | 10 |  | 842.9817
1448 | 1448 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | Dec 31,2028 | 2027-10-31 | 139 | 8 | 2027-03-14 | med | med | med | med | low | 400000 | 425230 | 434107 | 383.2311 | CAPITAL | Yes | Pipeline segment |  | X |  |  |  | no | no | Yes | no | Yes | no | no | Yes | no | 3 | 3 | 2 | 4 | 4 | 3 | 4 | 2 | 62.5% | 6 | 5 | 3 | 1 | 2 | 5 | 64% | 7 |  | 1727.2647
1449 | 1449 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | April 30,2029 | 2026-12-31 | 74 | 4 | 2026-01-16 | low | low | high | low | low | 1000000 | 1295898 | 1247471 | 78.2163 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X | X | X | Yes | no | no | no | no | no | Yes | no | Yes | 1 | 3 | 1 | 1 | 4 | 3 | 2 | 5 | 50% | 5 | 2 | 4 | 1 | 1 | 2 | 40% | 4 |  | 1578
1450 | 1450 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | Sept 30,2030 | 2027-10-31 | 87 | 8 | 2028-01-04 | high | high | high | low | high | 400000 | 493729 | 468570 | 162.7571 | EXPENSE | no | Pipeline segment | X | X |  |  | X | no | Yes | Yes | Yes | no | no | Yes | no | Yes | 5 | 3 | 2 | 4 | 2 | 5 | 5 | 3 | 72.5% | 8 | 4 | 1 | 5 | 5 | 4 | 76% | 8 |  | 3506.8708
1451 | 1451 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Calgary | Sept 30, 2025 | 2028-12-31 | 236 | 5 | 2028-03-09 | low | low | low | med | low | 550000 | 544446 | 575417 | 145.3755 | CAPITAL | no | Pipeline segment |  |  | X | X | X | Yes | no | Yes | Yes | Yes | no | Yes | Yes | Yes | 1 | 4 | 1 | 2 | 2 | 2 | 5 | 2 | 47.5% | 5 | 5 | 4 | 1 | 5 | 3 | 72% | 8 |  | 3981.0002
1452 | 1452 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Calgary | Dec 31, 2030 | 2027-10-31 | 176 | 8 | 2027-07-08 | high | low | med | high | high | 500000 | 458949 | 459364 | 44.4078 | CAPITAL | Yes | pipeline segment | X | X |  |  | X | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 4 | 4 | 3 | 1 | 4 | 4 | 1 | 3 | 60% | 6 | 3 | 1 | 1 | 1 | 5 | 44% | 5 |  | 20815.3255
1453 | 1453 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | WINNIPEG | June 30, 2025 | 2029-10-31 | 265 | 4 | 2029-11-08 | med | low | low | med | high | 850000 | 795426 | 800000 | 287.411 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  | X | X | Yes | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 3 | 4 | 3 | 1 | 4 | 2 | 5 | 1 | 57.5% | 6 | 2 | 2 | 5 | 5 | 1 | 60% | 6 |  | 425
1454 | 1454 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | Nov30,2027 | 2030-10-31 | 45 | 4 | 2029-06-16 | low | med | med | low | high | 1000000 | 1035786 | 1004048 | 336.0415 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 4 | 1 | 3 | 1 | 5 | 5 | 3 | 62.5% | 6 | 1 | 1 | 1 | 4 | 1 | 32% | 4 |  | 278.7236
1455 | 1455 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Montreal | Aug 31,2027 | 2030-10-31 | 101 | 8 | 2029-12-20 | med | high | med | med | high | 550000 | 467194 | 477060 | 49.109 | EXPENSE | no | Pipeline segment | X | X |  |  |  | Yes | Yes | no | no | Yes | no | no | Yes | Yes | 4 | 5 | 2 | 2 | 3 | 2 | 4 | 4 | 65% | 6 | 3 | 4 | 1 | 5 | 5 | 72% | 8 |  | 203.1281
1456 | 1456 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | Dec 31, 2030 | 2026-10-31 | 57 | 8 | 2026-06-04 | med | med | med | high | med | 350000 | 356367 | 314154 | 56.2148 | CAPITAL | Yes | Pipeline segment |  | X | X |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 2 | 4 | 2 | 3 | 5 | 2 | 4 | 4 | 65% | 6 | 2 | 4 | 1 | 2 | 4 | 52% | 6 |  | 203.1281
1457 | 1457 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Dec 31,2028 | 2028-07-31 | 63 | 8 | 2028-01-28 | low | high | med | low | med | 550000 | 1496322 | 1504238 | 104.2124 | CAPITAL | no | Pipeline segment | X | X | X |  | X | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 2 | 3 | 2 | 2 | 3 | 5 | 5 | 65% | 6 | 5 | 1 | 1 | 3 | 4 | 56% | 6 |  | 853.1382
1458 | 1458 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Nov30,2027 | 2029-10-31 | 153 | 2 | 2028-07-31 | med | med | high | high | low | 300000 | 351489 | 352567 | 256.8876 | EXPENSE | no | Derate/low flow Pipe segment |  | X |  | X | X | Yes | Yes | no | Yes | Yes | no | no | no | no | 1 | 2 | 3 | 3 | 1 | 1 | 4 | 3 | 45% | 5 | 4 | 5 | 5 | 3 | 4 | 84% | 9 |  | 23717.2367
1459 | 1459 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Edmonton | Aug 31,2027 | 2029-10-31 | 67 | 10 | 2028-10-25 | med | low | med | low | med | 550000 | 750527 | 763520 | 21.7053 | EXPENSE | no | Pipeline segment | X |  |  |  |  | no | no | no | Yes | no | no | Yes | no | Yes | 4 | 1 | 4 | 4 | 1 | 4 | 3 | 3 | 60% | 6 | 2 | 4 | 1 | 3 | 5 | 60% | 6 |  | 746.1723
1460 | 1460 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Aug 31,2029 | 2026-10-31 | 265 | 8 | 2026-04-10 | high | low | med | med | high | 400000 | 567316 | 563023 | 42.7227 | CAPITAL | no | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | Yes | Yes | no | no | Yes | 3 | 1 | 4 | 5 | 4 | 2 | 4 | 5 | 70% | 6 | 2 | 2 | 1 | 2 | 1 | 32% | 4 |  | 1174.9707
1461 | 1461 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Sept 30,2028 | 2027-07-31 | 291 | 10 | 2026-06-13 | low | med | low | low | low | 400000 | 380028 | 388094 | 90.2519 | CAPITAL | Yes | Pipeline segment | X | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | no | 2 | 2 | 4 | 4 | 2 | 2 | 4 | 2 | 55% | 6 | 1 | 4 | 1 | 2 | 1 | 36% | 4 |  | 13677.1818
1462 | 1462 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Regina | Sept 30,2026 | 2027-12-31 | 36 | 10 | 2027-11-25 | low | high | med | low | low | 400000 | 424238 | 427119 | 61.5753 | EXPENSE | no | Pipeline segment | X |  |  |  |  | no | no | Yes | Yes | Yes | Yes | Yes | Yes | no | 2 | 2 | 3 | 5 | 1 | 1 | 3 | 4 | 52.5% | 6 | 4 | 4 | 1 | 2 | 2 | 52% | 6 |  | 16021.8416
1463 | 1463 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Mar 31,2030 | 2028-07-31 | 216 | 4 | 2027-05-29 | med | low | low | high | low | 1900000 | 2439945 | 2463759 | 28.0968 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  | X | X | no | no | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 1 | 4 | 4 | 4 | 1 | 5 | 4 | 60% | 6 | 2 | 2 | 1 | 5 | 3 | 52% | 6 |  | 7007.9205
1464 | 1464 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | April 30,2027 | 2029-10-31 | 355 | 10 | 2027-04-11 | low | low | high | high | low | 400000 | 400160 | 405476 | 7.1499 | CAPITAL | no | Pipeline segment | X |  |  | X |  | no | no | Yes | no | no | no | Yes | no | Yes | 1 | 3 | 1 | 4 | 4 | 1 | 4 | 3 | 52.5% | 6 | 3 | 3 | 1 | 3 | 1 | 44% | 5 |  | 1685.9635
1465 | 1465 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | March 31, 2026 | 2026-07-31 | 208 | 15 | 2026-06-06 | med | low | low | low | low | 500000 | 495184 | 495568 | 15.392 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | no | no | Yes | 5 | 5 | 3 | 4 | 1 | 3 | 1 | 2 | 60% | 6 | 4 | 5 | 1 | 2 | 3 | 60% | 6 |  | 643.2391
1466 | 1466 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | April 30,2028 | 2026-12-31 | 26 | 10 | 2025-12-05 | low | med | low | med | med | 350000 | 400542 | 406801 | 120.5022 | CAPITAL | Yes | Pipeline segment | X | X | X |  |  | Yes | Yes | no | Yes | no | no | Yes | Yes | Yes | 2 | 4 | 1 | 2 | 3 | 5 | 1 | 2 | 50% | 5 | 5 | 4 | 5 | 3 | 4 | 84% | 9 |  | 267.7598
1467 | 1467 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Ottawa | Sept 30,2030 | 2028-10-31 | 99 | 8 | 2028-07-24 | high | low | high | med | high | 450000 | 379319 | 375544 | 35.2892 | CAPITAL | no | pipeline segment outage | X |  | X | X | X | Yes | Yes | Yes | no | no | Yes | no | no | no | 5 | 5 | 3 | 4 | 5 | 4 | 4 | 3 | 82.5% | 9 | 1 | 4 | 1 | 3 | 4 | 52% | 6 |  | 17599.3754
1468 | 1468 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Nov30,2027 | 2026-10-31 | 36 | 8 | 2026-11-25 | med | med | med | low | low | 500000 | 544088 | 549248 | 152.364 | CAPITAL | no | Pipeline segment | X |  |  |  | X | Yes | no | Yes | no | Yes | Yes | no | Yes | Yes | 2 | 2 | 4 | 5 | 5 | 4 | 1 | 3 | 65% | 6 | 5 | 5 | 1 | 1 | 4 | 64% | 7 |  | 7024.2246
1469 | 1469 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | Sept 30, 2025 | 2027-10-31 | 264 | 8 | 2027-04-11 | low | med | med | med | low | 500000 | 990834 | 987555 | 177.3607 | CAPITAL | Yes | Pipeline segment | X |  | X | X | X | no | Yes | no | no | Yes | no | Yes | no | no | 5 | 1 | 4 | 1 | 3 | 5 | 4 | 3 | 65% | 6 | 4 | 3 | 1 | 2 | 3 | 52% | 6 |  | 1591.1704
1470 | 1470 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | May 31, 2026 | 2029-12-31 | 61 | 8 | 2029-10-31 | high | low | high | med | med | 500000 | 598707 | 598210 | 152.9866 | EXPENSE | no | Pipeline segment | X |  | X | X |  | no | Yes | no | Yes | Yes | no | no | no | no | 5 | 1 | 1 | 2 | 5 | 3 | 1 | 2 | 50% | 5 | 4 | 3 | 1 | 3 | 1 | 48% | 5 |  | 330
1471 | 1471 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | Aug 31,2027 | 2026-07-31 | 327 | 4 | 2026-05-08 | high | high | med | high | med | 1500000 | 1812742 | 1842116 | 34.0888 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  | X | no | Yes | no | no | Yes | no | no | Yes | Yes | 5 | 1 | 2 | 5 | 4 | 1 | 2 | 4 | 60% | 6 | 5 | 4 | 1 | 1 | 4 | 60% | 6 |  | 5845
1472 | 1472 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP-RECTIFIER | Edmonton | Nov 30, 2025 | 2026-10-31 | 199 | 2 | 2025-09-13 | high | low | low | low | high | 700000 | 598833 | 611085 | 218.6029 | EXPENSE | no | pipeline segment outage | X |  | X | X |  | no | no | no | Yes | no | Yes | Yes | Yes | no | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 37.5% | 4 | 1 | 1 | 1 | 1 | 1 | 20% | 2 |  | 7709.8457
1473 | 1473 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Nov30,2027 | 2027-10-31 | 46 | 4 | 2028-11-15 | high | low | high | high | low | 400000 | 587205 | 589911 | 242.1342 | CAPITAL | no | Pipeline segment |  |  |  | X |  | no | Yes | no | Yes | Yes | Yes | Yes | no | no | 3 | 3 | 1 | 4 | 2 | 2 | 4 | 2 | 52.5% | 6 | 3 | 3 | 1 | 2 | 1 | 40% | 4 |  | 4391.6369
1474 | 1474 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | Sept 30,2030 | 2026-07-31 | 160 | 4 | 2026-05-24 | med | high | low | med | low | 400000 | 408000 | 425000 | 218.7171 | EXPENSE | Yes | pipeline segment |  |  | X | X | X | no | no | no | no | no | Yes | Yes | Yes | no | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 35% | 4 | 1 | 1 | 1 | 5 | 3 | 44% | 5 |  | 4314.1949
1475 | 1475 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Aug 31,2029 | 2028-12-31 | 172 | 4 | 2028-07-12 | low | high | med | med | high | 550000 | 526296 | 558571 | 163.365 | CAPITAL | no | Pipeline segment |  | X | X | X | X | no | no | Yes | no | no | no | Yes | no | no | 1 | 4 | 1 | 4 | 5 | 2 | 1 | 5 | 57.5% | 6 | 2 | 2 | 1 | 1 | 1 | 28% | 3 |  | 4858.8867
1476 | 1476 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Quebec City | June 30, 2025 | 2026-12-31 | 106 | 8 | 2026-09-16 | high | high | med | high | high | 500000 | 481652 | 445736 | 41.1751 | EXPENSE | no | Pipeline segment |  | X | X |  |  | Yes | Yes | no | no | Yes | no | Yes | Yes | Yes | 2 | 2 | 2 | 4 | 5 | 3 | 4 | 1 | 57.5% | 6 | 3 | 1 | 1 | 5 | 1 | 44% | 5 |  | 2178.0735
1477 | 1477 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | March 31, 2026 | 2029-10-31 | 18 | 8 | 2029-12-13 | low | med | med | med | low | 520000 | 523241 | 529365 | 5.9556 | CAPITAL | no | Pipeline segment | X | X |  |  |  | Yes | no | no | Yes | no | Yes | no | no | no | 5 | 4 | 2 | 1 | 2 | 1 | 3 | 4 | 55% | 6 | 1 | 5 | 1 | 1 | 4 | 48% | 5 |  | 1090.5382
1478 | 1478 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Sept 30,2028 | 2027-07-31 | 330 | 4 | 2026-09-04 | low | high | high | high | high | 1500000 | 1804556 | 1813074 | 83.977 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  | X | Yes | Yes | no | no | Yes | no | no | no | no | 5 | 4 | 1 | 1 | 3 | 5 | 5 | 2 | 65% | 6 | 3 | 1 | 1 | 3 | 4 | 48% | 5 |  | 8501.4285
1479 | 1479 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | June 30, 2025 | 2028-07-31 | 343 | 4 | 2027-08-23 | low | high | low | med | high | 1500000 | 1853330 | 1827797 | 200.4576 | EXPENSE | no | Derate/low flow Pipe segment | [5 empty] | no | no | no | no | Yes | Yes | no | no | Yes | 5 | 3 | 2 | 3 | 1 | 5 | 4 | 3 | 65% | 6 | 3 | 3 | 1 | 3 | 1 | 44% | 5 |  | 4052.0846
1480 | 1480 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | Sept 30,2030 | 2029-10-31 | 61 | 4 | 2030-01-29 | med | high | low | high | med | 520000 | 582895 | 685540 | 199.4572 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | Yes | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 2 | 1 | 3 | 3 | 5 | 5 | 60% | 6 | 4 | 4 | 1 | 1 | 1 | 44% | 5 |  | 4995.3897
1481 | 1481 | L3 | PIPE INTEGRITY | ILI | FLOW COMPUTER | Edmonton | Sept 30, 2025 | 2026-12-31 | 298 | 2 | 2027-01-06 | high | low | med | high | high | 450000 | 442587 | 452847 | 172.7549 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | Yes | no | no | no | 4 | 3 | 3 | 3 | 5 | 2 | 1 | 4 | 62.5% | 6 | 4 | 3 | 1 | 2 | 5 | 60% | 6 |  | 6993.5456
1482 | 1482 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Montreal | March 31, 2026 | 2026-10-31 | 74 | 10 | 2026-10-18 | high | low | med | high | high | 550000 | 549928 | 591050 | 59.9299 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | no | Yes | Yes | no | no | no | Yes | no | Yes | 1 | 2 | 2 | 1 | 1 | 2 | 4 | 5 | 45% | 5 | 4 | 1 | 1 | 2 | 1 | 36% | 4 |  | 222.8052
1483 | 1483 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Ottawa | Dec 31,2026 | 2027-07-31 | 267 | 10 | 2026-07-07 | med | high | med | high | high | 500000 | 987000 | 954825 | 24.4952 | CAPITAL | no | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 1 | 4 | 2 | 1 | 2 | 2 | 4 | 3 | 47.5% | 5 | 3 | 5 | 5 | 2 | 5 | 80% | 8 |  | 840.2082
1484 | 1484 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | Sept 30, 2025 | 2026-07-31 | 36 | 4 | 2026-11-25 | high | high | med | med | med | 1500000 | 1517309 | 1527293 | 56.1178 | EXPENSE | no | Derate/low flow Pipe segment |  | X |  |  | X | Yes | Yes | Yes | no | Yes | Yes | no | Yes | no | 4 | 5 | 3 | 3 | 4 | 1 | 3 | 1 | 60% | 6 | 1 | 5 | 5 | 1 | 3 | 60% | 6 |  | 5000
1485 | 1485 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | Sept 30,2026 | 2027-07-31 | 151 | 4 | 2026-10-31 | med | med | low | high | med | 500000 | 583881 | 573876 | 11.6418 | EXPENSE | no | Pipeline segment |  | X |  | X | X | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 5 | 4 | 2 | 2 | 1 | 2 | 3 | 5 | 60% | 6 | 4 | 2 | 1 | 4 | 1 | 48% | 5 |  | 1207.7993
1486 | 1486 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Quebec City | Aug 31,2029 | 2027-10-31 | 267 | 15 | 2027-04-08 | low | med | low | low | high | 550000 | 554230 | 580197 | 6.3304 | CAPITAL | no | Pipeline segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | no | no | no | 2 | 1 | 3 | 4 | 2 | 2 | 4 | 2 | 50% | 5 | 4 | 4 | 1 | 1 | 1 | 44% | 5 |  | 191.3942
1487 | 1487 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Saskatoon | Mar 31,2030 | 2028-12-31 | 246 | 10 | 2028-04-29 | low | low | med | high | low | 800000 | 962796 | 971191 | 107.4224 | EXPENSE | no | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | no | no | no | no | Yes | Yes | 5 | 5 | 3 | 5 | 3 | 5 | 2 | 3 | 77.5% | 8 | 3 | 5 | 1 | 5 | 4 | 72% | 8 |  | 173.2929
1488 | 1488 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | Sept 30,2030 | 2028-12-31 | 274 | 10 | 2028-10-30 | med | med | low | med | low | 400000 | 422034 | 425419 | 101.2735 | EXPENSE | Yes | Pipeline segment |  |  | X | X |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 1 | 4 | 1 | 4 | 2 | 1 | 1 | 2 | 40% | 4 | 2 | 2 | 5 | 2 | 4 | 60% | 6 |  | 900.2043
1489 | 1489 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Dec 31,2026 | 2025-12-31 | 170 | 8 | 2025-10-12 | high | low | high | med | high | 420000 | 488222 | 478271 | 202.8834 | CAPITAL | Yes | Pipeline segment |  | X |  | X | X | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 1 | 2 | 5 | 3 | 1 | 3 | 5 | 57.5% | 6 | 1 | 1 | 1 | 4 | 3 | 40% | 4 |  | 749.7244
1490 | 1490 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | WINNIPEG | Sept 30,2026 | 2026-07-31 | 142 | 15 | 2026-08-11 | med | med | high | med | low | 450000 | 416535 | 407647 | 90.3714 | CAPITAL | no | Pipeline segment | X | X | X |  |  | Yes | no | Yes | Yes | no | Yes | Yes | no | no | 3 | 5 | 2 | 4 | 3 | 5 | 4 | 3 | 72.5% | 8 | 1 | 2 | 1 | 5 | 3 | 48% | 5 |  | 41798.5165
1491 | 1491 | L2 | PIPE INTEGRITY | EXCAVATION | VALIDATION | North Bay | June 30, 2025 | 2027-12-31 | 108 | 4 | 2027-09-14 | med | med | high | low | med | 250000 | 200338 | 207290 | 167.215 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  | X | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 3 | 4 | 2 | 5 | 4 | 1 | 5 | 5 | 72.5% | 8 | 5 | 5 | 1 | 3 | 5 | 76% | 8 |  | 1022.4116
1492 | 1492 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Nov 30,2029 | 2027-10-31 | 67 | 4 | 2027-10-25 | high | low | high | med | high | 1500000 | 1450980 | 1458652 | 118.0594 | EXPENSE | no | Derate/low flow Pipe segment | X |  | X |  |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 2 | 4 | 3 | 2 | 2 | 1 | 3 | 1 | 45% | 5 | 5 | 5 | 1 | 2 | 3 | 64% | 7 |  | 1022.4116
1493 | 1493 | L1 | PIPE INTEGRITY | L&R | LAUNCHER RECEIVER INSTALL | Quebec City | Aug 31,2027 | 2027-07-31 | 53 | 8 | 2027-09-08 | med | low | med | high | high | 4585000 | 4680012 | 4700046 | 91.5834 | CAPITAL | Yes | Station outage |  |  | X |  |  | no | Yes | Yes | no | Yes | no | no | no | Yes | 5 | 4 | 2 | 3 | 2 | 5 | 2 | 3 | 65% | 6 | 5 | 1 | 1 | 1 | 5 | 52% | 6 |  | 458
1494 | 1494 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Aug 31,2027 | 2027-10-31 | 17 | 4 | 2028-07-14 | high | low | low | low | med | 1500000 | 1410189 | 1490446 | 61.5579 | EXPENSE | no | Derate/low flow Pipe segment | X |  |  | X | X | Yes | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 5 | 3 | 2 | 1 | 5 | 3 | 1 | 3 | 57.5% | 6 | 4 | 3 | 1 | 5 | 5 | 72% | 8 |  | 425
1495 | 1495 | L3 | PIPE INTEGRITY | L&R | LAUNCHER RECEIVER INSTALL | Winnipeg | Dec 31, 2030 | 2027-07-31 | 259 | 4 | 2027-04-16 | med | low | low | med | low | 2500500 | 2557663 | 2756617 | 1023.831 | CAPITAL | no | Derate/low flow Pipe segment |  |  | X |  | X | no | Yes | Yes | Yes | no | Yes | no | Yes | no | 4 | 1 | 2 | 2 | 3 | 4 | 4 | 3 | 57.5% | 6 | 5 | 3 | 1 | 2 | 3 | 56% | 6 |  | 20000
1496 | 1496 | L1 | PIPE INTEGRITY | L&R | LAUNCHER RECEIVER INSTALL | Saskatoon | Sept 30, 2025 | 2027-12-31 | 160 | 4 | 2027-10-23 | med | high | low | high | high | 6620000 | 6005868 | 6132189 | 33.0673 | CAPITAL | no | Station outage |  | X |  | X |  | no | no | Yes | Yes | no | Yes | no | Yes | Yes | 3 | 5 | 2 | 3 | 3 | 2 | 4 | 5 | 67.5% | 6 | 1 | 4 | 1 | 2 | 1 | 36% | 4 |  | 1875
1497 | 1497 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | April 30,2027 | 2028-10-31 | 236 | 8 | 2027-08-08 | med | med | med | low | high | 400000 | 892844 | 905260 | 190.1713 | CAPITAL | no | Pipeline segment |  |  |  | X | X | Yes | no | no | no | no | Yes | no | no | no | 1 | 2 | 3 | 1 | 3 | 3 | 4 | 1 | 45% | 5 | 1 | 4 | 1 | 3 | 2 | 44% | 5 |  | 7718.869
1498 | 1498 | L1 | PIPE INTEGRITY | L&R | LAUNCHER RECEIVER INSTALL | Montreal | Sept 30,2028 | 2027-07-31 | 44 | 8 | 2027-06-17 | med | med | high | low | high | 3500000 | 3561440 | 3450325 | 42.5944 | CAPITAL | no | Station outage | X | X | X | X |  | Yes | no | Yes | Yes | no | no | no | Yes | Yes | 3 | 5 | 2 | 5 | 2 | 2 | 1 | 3 | 57.5% | 6 | 5 | 2 | 1 | 5 | 3 | 64% | 7 |  | 7718.869
1499 | 1499 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Dec 31,2026 | 2026-10-31 | 13 | 8 | 2026-07-18 | med | high | low | low | high | 420000 | 405834 | 402505 | 98.3964 | EXPENSE | no | pipeline segment outage |  |  |  |  | X | no | Yes | Yes | Yes | no | no | no | Yes | no | 2 | 3 | 2 | 2 | 5 | 3 | 1 | 4 | 55% | 6 | 2 | 4 | 1 | 4 | 5 | 64% | 7 |  | 6993.5456
1500 | 1500 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | Dec 31,2028 | 2026-10-31 | 346 | 8 | 2025-08-19 | low | high | low | high | high | 350000 | 307934 | 302673 | 32.9463 | CAPITAL | no | pipeline segment outage | X | X |  |  |  | Yes | no | no | Yes | no | no | Yes | Yes | Yes | 5 | 1 | 1 | 5 | 2 | 2 | 2 | 4 | 55% | 6 | 1 | 5 | 1 | 5 | 2 | 56% | 6 |  | 25393.3666
1501 | 1501 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Calgary | Sept 30, 2025 | 2027-10-31 | 248 | 7 | 2027-07-27 | med | low | high | high | high | 1900000 | 1977581 | 1989278 | 94.5144 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | no | no | Yes | Yes | Yes | Yes | Yes | no | 2 | 4 | 2 | 3 | 4 | 2 | 5 | 3 | 62.5% | 6 | 4 | 1 | 1 | 3 | 3 | 48% | 5 |  | 2369.8282
1502 | 1502 | L1 | PIPE INTEGRITY | EXCAVATION | VALIDATION | North Bay | Sept 30,2030 | 2028-07-31 | 266 | 8 | 2028-04-09 | med | high | low | low | med | 250000 | 252651 | 284871 | 56.4922 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X | X |  | no | Yes | no | Yes | no | no | Yes | no | no | 2 | 2 | 1 | 2 | 2 | 5 | 5 | 3 | 55% | 6 | 3 | 5 | 1 | 2 | 4 | 60% | 6 |  | 2369.8282
1503 | 1503 | L1 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Winnipeg | Dec 31,2026 | 2028-07-31 | 36 | 8 | 2028-09-25 | med | low | med | high | low | 250000 | 410869 | 416879 | 692.039 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X |  | no | Yes | Yes | Yes | Yes | Yes | no | no | no | 1 | 3 | 3 | 3 | 5 | 4 | 4 | 5 | 70% | 6 | 5 | 4 | 1 | 2 | 1 | 52% | 6 |  | 14928.9944
1504 | 1504 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Sept 30,2026 | 2026-10-31 | 75 | 4 | 2025-10-17 | high | high | med | med | med | 850000 | 850944 | 820000 | 24.4354 | EXPENSE | no | Derate/low flow Pipe segment |  | X | X |  | X | no | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 4 | 80% | 8 | 4 | 2 | 5 | 1 | 1 | 52% | 6 |  | 4785
1505 | 1505 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | Dec 31, 2030 | 2026-10-31 | 36 | 15 | 2026-02-23 | low | high | med | high | high | 450000 | 530563 | 545236 | 60.5912 | CAPITAL | no | Pipeline segment | X |  | X |  |  | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 1 | 2 | 3 | 4 | 3 | 5 | 3 | 4 | 62.5% | 6 | 1 | 2 | 1 | 1 | 3 | 32% | 4 |  | 477.3811
1506 | 1506 | L2 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Winnipeg | Mar 31,2030 | 2026-10-31 | 224 | 8 | 2026-05-21 | med | med | med | low | low | 250000 | 236609 | 246072 | 96.9233 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | Yes | no | Yes | Yes | Yes | no | no | Yes | no | 2 | 2 | 1 | 2 | 1 | 3 | 3 | 5 | 47.5% | 5 | 2 | 4 | 1 | 1 | 1 | 36% | 4 |  | 2679.5194
1507 | 1507 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Winnipeg | Sept 30,2026 | 2026-07-31 | 232 | 8 | 2026-08-11 | high | low | high | med | med | 400000 | 469283 | 472670 | 143.1483 | CAPITAL | Yes | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | Yes | no | Yes | Yes | no | no | 2 | 4 | 3 | 1 | 1 | 4 | 3 | 2 | 50% | 5 | 5 | 3 | 1 | 5 | 5 | 76% | 8 |  | 1072.7658
1508 | 1508 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Aug 31,2027 | 2030-07-31 | 202 | 4 | 2029-04-12 | high | med | high | med | high | 300000 | 496541 | 474310 | 86.2445 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  | X |  |  | no | Yes | no | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 4 | 4 | 3 | 1 | 1 | 2 | 50% | 5 | 4 | 4 | 1 | 2 | 5 | 64% | 7 |  | 1117.2047
1509 | 1509 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Nov 30, 2025 | 2026-07-31 | 223 | 7 | 2025-12-20 | med | low | high | med | high | 2000000 | 2451951 | 2464009 | 287.5273 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 1 | 4 | 1 | 3 | 4 | 3 | 2 | 4 | 55% | 6 | 3 | 2 | 1 | 1 | 4 | 44% | 5 |  | 45.3112
1510 | 1510 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Sept 30,2030 | 2026-10-31 | 206 | 2 | 2026-01-06 | med | med | low | med | med | 350000 | 387958 | 348402 | 338.5852 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X | X |  | Yes | no | no | Yes | no | Yes | Yes | no | Yes | 2 | 3 | 2 | 5 | 1 | 1 | 1 | 4 | 47.5% | 5 | 2 | 5 | 1 | 4 | 4 | 64% | 7 |  | 18394.3019
1511 | 1511 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Nov30,2027 | 2029-07-31 | 18 | 8 | 2029-10-13 | low | high | high | low | low | 420000 | 480344 | 486953 | 122.9237 | CAPITAL | no | Pipeline segment |  |  | X |  | X | no | Yes | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 1 | 1 | 4 | 2 | 5 | 3 | 3 | 52.5% | 6 | 2 | 5 | 1 | 2 | 3 | 52% | 6 |  | 76225.6763
1512 | 1512 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | April 30,2027 | 2025-07-31 | 360 | 4 | 2024-04-05 | low | high | med | low | high | 1750000 | 1822372 | 1853987 | 87.2637 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X | X | X | no | no | Yes | Yes | no | Yes | Yes | Yes | Yes | 1 | 3 | 1 | 1 | 3 | 5 | 1 | 2 | 42.5% | 5 | 2 | 5 | 1 | 2 | 2 | 48% | 5 |  | 16.9273
1513 | 1513 | L3 | PIPE INTEGRITY | Excavation | RECOAT | Winnipeg | April 30,2028 | 2028-07-31 | 135 | 5 | 2027-11-17 | low | low | low | low | high | 400000 | 424886 | 436808 | 9.937 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | no | Yes | no | no | Yes | Yes | Yes | Yes | no | 4 | 2 | 3 | 3 | 2 | 1 | 4 | 5 | 60% | 6 | 4 | 1 | 1 | 3 | 3 | 48% | 5 |  | 16.9273
1514 | 1514 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Edmonton | Sept 30,2030 | 2029-07-31 | 101 | 10 | 2028-12-20 | low | low | med | low | med | 400000 | 340748 | 84971 | 7.9241 | CAPITAL | no | Pipeline segment |  | X | X |  | X | no | no | no | Yes | no | no | no | Yes | no | 3 | 4 | 3 | 5 | 4 | 4 | 1 | 5 | 72.5% | 8 | 5 | 3 | 1 | 4 | 4 | 68% | 7 |  | 560.1412
1515 | 1515 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Quebec City | April 30,2027 | 2029-10-31 | 131 | 4 | 2029-08-22 | low | med | high | high | med | 1500000 | 1411959 | 1411361 | 122.5762 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | Yes | Yes | Yes | no | no | no | no | 4 | 2 | 2 | 2 | 2 | 4 | 2 | 2 | 50% | 5 | 5 | 3 | 1 | 2 | 2 | 52% | 6 |  | 16059.7772
1516 | 1516 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | North Bay | June 30, 2025 | 2027-12-31 | 204 | 2 | 2027-09-09 | high | med | high | med | med | 1000000 | 1015946 | 1061154 | 60.2487 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  |  |  | X | Yes | no | Yes | no | Yes | Yes | Yes | no | Yes | 5 | 3 | 3 | 4 | 1 | 3 | 5 | 2 | 65% | 6 | 1 | 1 | 5 | 5 | 3 | 60% | 6 |  | 2369.8282
1517 | 1517 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | Mar 31,2030 | 2030-07-31 | 133 | 2 | 2030-03-20 | low | med | low | low | med | 520000 | 520076 | 521552 | 339.8771 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X |  |  | Yes | Yes | Yes | no | no | no | Yes | Yes | Yes | 2 | 3 | 1 | 4 | 4 | 2 | 2 | 2 | 50% | 5 | 5 | 5 | 1 | 1 | 2 | 56% | 6 |  | 2491.953
1518 | 1518 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Mar 31,2030 | 2027-12-31 | 158 | 4 | 2027-02-23 | med | low | low | low | med | 1750000 | 1800359 | 1858385 | 201.382 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X |  | X | Yes | no | no | no | no | no | Yes | no | no | 4 | 3 | 1 | 3 | 4 | 1 | 4 | 3 | 57.5% | 6 | 5 | 5 | 1 | 3 | 3 | 68% | 7 |  | 2480.6254
1519 | 1519 | L1 | PIPE INTEGRITY | Excavation | RECOAT | Montreal | Dec 31,2026 | 2025-12-31 | 237 | 5 | 2025-08-06 | high | med | low | high | med | 500000 | 580071 | 863077 | 339.2298 | CAPITAL | no | pipeline segment outage |  | X | X |  |  | no | Yes | no | Yes | no | Yes | no | no | no | 2 | 4 | 2 | 1 | 5 | 3 | 5 | 4 | 65% | 6 | 2 | 5 | 1 | 1 | 4 | 52% | 6 |  | 6039.0018
1520 | 1520 | L3 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Quebec City | Sept 30,2030 | 2030-12-31 | 284 | 4 | 2029-10-20 | low | high | high | low | med | 125000 | 137635 | 149404 | 946.0832 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  |  | X | no | Yes | Yes | Yes | Yes | Yes | Yes | no | Yes | 2 | 2 | 3 | 2 | 3 | 3 | 3 | 5 | 57.5% | 6 | 1 | 4 | 1 | 2 | 2 | 40% | 4 |  | 13659.1884
1521 | 1521 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Dec 31,2028 | 2027-12-31 | 131 | 10 | 2027-08-22 | med | med | high | med | low | 500000 | 758562 | 785895 | 101.141 | CAPITAL | no | Pipeline segment |  | X |  | X |  | no | Yes | no | no | Yes | Yes | Yes | no | no | 3 | 3 | 3 | 3 | 5 | 1 | 5 | 4 | 67.5% | 6 | 4 | 2 | 1 | 2 | 5 | 56% | 6 |  | 13659.1884
1522 | 1522 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Nov30,2027 | 2030-12-31 | 103 | 8 | 2029-12-18 | low | low | high | low | med | 400000 | 1157635 | 1189920 | 105.7103 | CAPITAL | Yes | Pipeline segment | X | X | X | X | X | Yes | no | no | Yes | Yes | no | Yes | Yes | Yes | 4 | 2 | 2 | 3 | 3 | 1 | 3 | 2 | 50% | 5 | 3 | 5 | 1 | 5 | 2 | 64% | 7 |  | 17906.9371
1523 | 1523 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | April 30,2029 | 2025-10-31 | 29 | 4 | 2026-03-02 | high | low | low | low | low | 450000 | 878955 | 905888 | 80.7138 | CAPITAL | no | pipeline segment outage | X | X |  | X |  | no | Yes | no | Yes | no | Yes | no | Yes | no | 2 | 1 | 3 | 5 | 1 | 1 | 5 | 1 | 47.5% | 5 | 2 | 2 | 1 | 5 | 1 | 44% | 5 |  | 21537.8368
1524 | 1524 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | Sept 30,2026 | 2028-07-31 | 34 | 4 | 2028-02-26 | med | low | med | med | med | 1000000 | 1021505 | 1092551 | 56.5076 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | no | no | no | no | no | no | no | no | Yes | 5 | 2 | 1 | 3 | 2 | 4 | 1 | 3 | 52.5% | 6 | 2 | 5 | 1 | 3 | 4 | 60% | 6 |  | 2973.4021
1525 | 1525 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | Sept 30, 2025 | 2026-12-31 | 113 | 4 | 2026-09-09 | high | high | high | high | high | 350000 | 304631 | 304242 | 26.1799 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | Yes | no | no | no | Yes | no | Yes | Yes | 2 | 4 | 2 | 2 | 5 | 2 | 2 | 4 | 57.5% | 6 | 3 | 4 | 1 | 5 | 2 | 60% | 6 |  | 5776.4313
1526 | 1526 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Montreal | Sept 30, 2025 | 2026-07-31 | 291 | 8 | 2026-01-13 | med | med | med | low | low | 500000 | 501069 | 508000 | 20.7067 | CAPITAL | Yes | Pipeline segment | X |  |  | X | X | no | no | no | no | no | no | Yes | Yes | Yes | 3 | 3 | 3 | 3 | 4 | 1 | 5 | 5 | 67.5% | 6 | 5 | 2 | 1 | 2 | 2 | 48% | 5 |  | 2166.5828
1527 | 1527 | L3 | PIPE INTEGRITY | Excavation | RECOAT | Ottawa | Sept 30, 2025 | 2028-12-31 | 356 | 2 | 2027-08-10 | low | high | low | high | low | 400000 | 674072 | 656987 | 133.3009 | EXPENSE | no | Station outage | X | X |  |  | X | Yes | Yes | Yes | Yes | no | no | Yes | no | Yes | 3 | 2 | 4 | 3 | 3 | 5 | 1 | 4 | 62.5% | 6 | 2 | 5 | 1 | 1 | 2 | 44% | 5 |  | 1083.35
1528 | 1528 | L1 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Toronto | April 30,2027 | 2026-07-31 | 333 | 15 | 2025-05-02 | high | med | med | low | low | 450000 | 1236197 | 1274450 | 65.7764 | CAPITAL | no | Pipeline segment | X | X | X |  | X | Yes | Yes | no | no | no | no | Yes | Yes | Yes | 5 | 4 | 1 | 3 | 3 | 3 | 1 | 1 | 52.5% | 6 | 3 | 4 | 1 | 1 | 3 | 48% | 5 |  | 1846.6194
1529 | 1529 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | North Bay | Mar 31,2030 | 2027-12-31 | 86 | 1 | 2027-10-06 | med | med | high | med | low | 550000 | 531626 | 566466 | 618.2189 | EXPENSE | Yes | Pipeline segment |  | X | X |  |  | Yes | no | Yes | Yes | Yes | no | no | no | Yes | 3 | 3 | 3 | 3 | 4 | 2 | 4 | 3 | 62.5% | 6 | 1 | 1 | 1 | 4 | 5 | 48% | 5 |  | 9580.8769
1530 | 1530 | L3 | PIPE INTEGRITY | EXCAVATION | VALIDATION | North Bay | April 30,2027 | 2027-10-31 | 11 | 1 | 2027-07-20 | high | med | high | med | high | 125000 | 105456 | 105103 | 713.9495 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  |  |  | Yes | Yes | no | no | Yes | Yes | no | Yes | no | 5 | 3 | 2 | 1 | 2 | 1 | 4 | 4 | 55% | 6 | 2 | 5 | 1 | 5 | 4 | 68% | 7 |  | 5875
1531 | 1531 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | April 30,2028 | 2030-12-31 | 292 | 7 | 2030-03-14 | low | med | med | high | high | 1500000 | 1307852 | 1350870 | 152.9836 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | Yes | no | Yes | Yes | Yes | no | 3 | 1 | 1 | 3 | 1 | 1 | 5 | 2 | 42.5% | 5 | 5 | 1 | 1 | 5 | 5 | 68% | 7 |  | 25777
1532 | 1532 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Saskatoon | Nov30,2027 | 2029-12-31 | 184 | 2 | 2029-01-28 | high | med | low | med | high | 275000 | 279845 | 309640 | 500.6594 | EXPENSE | no | Derate/low flow Pipe segment | X | X |  | X | X | Yes | Yes | Yes | no | no | no | no | no | Yes | 2 | 2 | 3 | 4 | 2 | 2 | 1 | 4 | 50% | 5 | 3 | 5 | 5 | 2 | 4 | 76% | 8 |  | 5522
1533 | 1533 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP- ANODE REPL | Montreal | Mar 31,2030 | 2028-10-31 | 227 | 5 | 2027-12-17 | low | high | med | low | low | 600000 | 851724 | 857404 | 116.0893 | CAPITAL | Yes | pipeline segment outage |  | X |  | X | X | no | no | no | no | Yes | Yes | no | Yes | Yes | 2 | 5 | 1 | 3 | 2 | 5 | 4 | 1 | 57.5% | 6 | 1 | 3 | 1 | 2 | 1 | 32% | 4 |  | 4101.0339
1534 | 1534 | L2 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Saskatoon | Aug 31,2027 | 2028-12-31 | 170 | 4 | 2028-07-14 | med | low | low | med | med | 550000 | 586220 | 590135 | 33.5343 | EXPENSE | Yes | Pipeline segment | X | X | X | X |  | no | no | Yes | no | Yes | no | Yes | no | Yes | 2 | 2 | 2 | 5 | 3 | 1 | 3 | 3 | 52.5% | 6 | 1 | 5 | 1 | 4 | 1 | 48% | 5 |  | 22170.3266
1535 | 1535 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Winnipeg | June 30, 2025 | 2027-10-31 | 197 | 15 | 2026-09-15 | med | low | low | high | med | 500000 | 513676 | 518168 | 511.7996 | CAPITAL | Yes | Pipeline segment |  |  |  |  | X | Yes | no | no | Yes | Yes | Yes | Yes | no | Yes | 2 | 5 | 3 | 2 | 2 | 3 | 1 | 1 | 47.5% | 5 | 4 | 3 | 1 | 2 | 1 | 44% | 5 |  | 842.9817
1536 | 1536 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | April 30,2027 | 2031-10-31 | 234 | 10 | 2030-03-11 | low | low | med | med | med | 500000 | 491921 | 499436 | 47.5442 | EXPENSE | no | Pipeline segment | X |  |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 4 | 3 | 2 | 5 | 1 | 5 | 5 | 1 | 65% | 6 | 4 | 4 | 1 | 3 | 4 | 64% | 7 |  | 842.9817
1537 | 1537 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | April 30,2027 | 2026-10-31 | 41 | 4 | 2026-02-18 | low | high | low | low | high | 1900000 | 1900004 | 1920751 | 44.5632 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  | X |  | Yes | Yes | no | no | no | no | no | no | Yes | 4 | 5 | 4 | 2 | 2 | 2 | 2 | 4 | 62.5% | 6 | 1 | 1 | 1 | 5 | 5 | 52% | 6 |  | 13420.4072
1538 | 1538 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | North Bay | April 30,2028 | 2028-12-31 | 194 | 10 | 2027-06-20 | low | high | low | med | low | 400000 | 555683 | 550953 | 55.3744 | CAPITAL | no | Pipeline segment |  |  | X | X | X | no | no | no | no | Yes | Yes | no | Yes | no | 2 | 2 | 1 | 4 | 2 | 2 | 1 | 3 | 42.5% | 5 | 1 | 2 | 5 | 2 | 5 | 60% | 6 |  | 1727.2647
1539 | 1539 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | North Bay | Nov 30, 2025 | 2029-10-31 | 237 | 10 | 2027-08-07 | high | med | high | high | low | 550000 | 689835 | 687417 | 412.8922 | CAPITAL | no | pipeline segment outage | X |  |  |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 5 | 3 | 4 | 5 | 1 | 5 | 1 | 5 | 72.5% | 8 | 5 | 3 | 1 | 1 | 2 | 48% | 5 |  | 2588
1540 | 1540 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Sept 30,2026 | 2026-12-31 | 174 | 4 | 2026-02-07 | low | med | low | high | med | 350000 | 406595 | 482491 | 284.7276 | CAPITAL | no | Pipeline segment | X | X |  | X | X | no | no | no | Yes | Yes | Yes | Yes | no | no | 2 | 1 | 4 | 4 | 4 | 4 | 3 | 4 | 65% | 6 | 2 | 4 | 1 | 2 | 2 | 44% | 5 |  | 18109.7232
1541 | 1541 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | April 30,2028 | 2026-07-31 | 191 | 12 | 2026-01-21 | high | med | low | high | high | 350000 | 479453 | 498408 | 58.7845 | CAPITAL | no | Pipeline segment |  |  | X | X |  | no | no | no | no | Yes | no | Yes | Yes | Yes | 4 | 2 | 3 | 5 | 5 | 5 | 4 | 5 | 82.5% | 9 | 2 | 5 | 1 | 4 | 5 | 68% | 7 |  | 20815.3255
1542 | 1542 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Aug 31,2029 | Oct 31, 2027 | 211 | 10 | 2026-06-03 | low | low | low | high | high | 500000 | 852395 | 896748 | 22.5065 | EXPENSE | Yes | Pipeline segment | X | X |  |  |  | no | no | no | no | Yes | no | no | no | Yes | 1 | 1 | 2 | 2 | 4 | 3 | 4 | 3 | 50% | 5 | 3 | 2 | 1 | 5 | 4 | 60% | 6 |  | 48955
1543 | 1543 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | Nov 30,2029 | 2026-12-31 | 323 | 10 | 2026-09-11 | high | med | med | high | med | 400000 | 398965 | 399197 | 71.4985 | CAPITAL | no | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | Yes | no | no | 1 | 5 | 4 | 2 | 2 | 3 | 3 | 4 | 60% | 6 | 4 | 3 | 1 | 4 | 1 | 52% | 6 |  | 278.7236
1544 | 1544 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Nov30,2027 | Jul 31, 2027 | 32 | 10 | 2028-11-29 | high | low | med | med | high | 400000 | 805802 | 391083 | 36.3611 | EXPENSE | Yes | Pipeline segment |  |  | X |  | X | no | Yes | no | no | Yes | no | no | Yes | no | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 5 | 42.5% | 5 | 4 | 2 | 5 | 4 | 5 | 80% | 8 |  | 278.7236
1545 | 1545 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Nov30,2027 | 2028-07-31 | 165 | 1 | 2028-02-17 | low | low | low | high | low | 350000 | 374582 | 376971 | 593.4244 | EXPENSE | no | Pipeline segment | X | X | X |  | X | no | no | Yes | no | no | no | Yes | Yes | Yes | 1 | 1 | 1 | 5 | 4 | 5 | 5 | 2 | 60% | 6 | 5 | 4 | 1 | 4 | 4 | 72% | 8 |  | 203.1281
1546 | 1546 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Ottawa | April 30,2027 | 2026-10-31 | 272 | 10 | 2027-04-03 | med | med | med | low | med | 400000 | 644214 | 640670 | 101.6158 | CAPITAL | no | Pipeline segment | X |  |  |  | X | Yes | Yes | Yes | no | Yes | no | no | Yes | no | 5 | 5 | 3 | 1 | 2 | 1 | 2 | 1 | 50% | 5 | 4 | 3 | 5 | 1 | 2 | 60% | 6 |  | 203.1281
1547 | 1547 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Sept 30,2026 | 2027-10-31 | 81 | 4 | 2027-08-11 | high | low | high | low | high | 1750000 | 1875896 | 1478514 | 24.8857 | EXPENSE | Yes | Derate/low flow Pipe segment |  |  | X |  |  | no | Yes | no | Yes | no | no | no | no | Yes | 5 | 5 | 4 | 3 | 5 | 1 | 5 | 1 | 72.5% | 8 | 3 | 5 | 1 | 3 | 5 | 68% | 7 |  | 203.1281
1548 | 1548 | L2 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Regina | Sept 30,2028 | 2026-07-31 | 156 | 15 | 2026-05-28 | high | high | med | high | high | 450000 | 868046 | 874514 | 82.8772 | CAPITAL | no | Pipeline segment |  | X |  | X | X | Yes | Yes | no | no | Yes | Yes | no | no | Yes | 1 | 5 | 2 | 2 | 3 | 1 | 1 | 1 | 40% | 4 | 2 | 3 | 1 | 1 | 1 | 32% | 4 |  | 23717.2367
1549 | 1549 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Edmonton | April 30,2028 | 2026-07-31 | 75 | 4 | 2026-10-17 | med | med | med | low | low | 2450000 | 2254742 | 2248761 | 57.9714 | EXPENSE | Yes | Derate/low flow Pipe segment | X |  |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 1 | 4 | 4 | 1 | 4 | 5 | 1 | 4 | 60% | 6 | 5 | 5 | 1 | 5 | 2 | 72% | 8 |  | 1174.9707
1550 | 1550 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Nov 30, 2025 | 2027-10-31 | 24 | 8 | 2026-10-07 | high | med | low | low | low | 350000 | 379854 | 376546 | 25.9626 | CAPITAL | Yes | Pipeline segment |  |  | X |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | no | 5 | 2 | 1 | 1 | 4 | 3 | 4 | 2 | 55% | 6 | 3 | 2 | 1 | 5 | 1 | 48% | 5 |  | 13677.1818
1551 | 1551 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Calgary | April 30,2028 | 2027-07-31 | 98 | 8 | 2027-09-24 | med | med | low | med | med | 400000 | 380000 | 358470 | 183.6307 | EXPENSE | Yes | Pipeline segment |  |  | X |  |  | no | no | Yes | Yes | no | Yes | no | Yes | no | 5 | 5 | 1 | 2 | 1 | 1 | 4 | 5 | 60% | 6 | 2 | 5 | 1 | 4 | 4 | 64% | 7 |  | 16021.8416
1552 | 1552 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | WINNIPEG | Mar 31,2030 | 2028-10-31 | 141 | 10 | 2028-08-12 | low | med | high | med | low | 400000 | 388560 | 387036 | 31.5417 | EXPENSE | Yes | Pipeline segment |  | X | X |  | X | no | Yes | no | no | Yes | Yes | no | no | Yes | 1 | 4 | 3 | 2 | 3 | 4 | 5 | 1 | 57.5% | 6 | 3 | 3 | 1 | 5 | 5 | 68% | 7 |  | 7007.9205
1553 | 1553 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Regina | Aug 31,2029 | 2026-12-31 | 250 | 10 | 2025-11-23 | high | high | med | low | high | 750000 | 754518 | 786550 | 57.545 | EXPENSE | no | pipeline segment outage | X |  | X |  | X | Yes | Yes | Yes | no | no | no | no | no | no | 4 | 5 | 2 | 3 | 1 | 4 | 2 | 3 | 60% | 6 | 3 | 1 | 1 | 1 | 5 | 44% | 5 |  | 1685.963
1554 | 1554 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Winnipeg | Aug 31,2027 | 2029-07-31 | 85 | 4 | 2029-10-07 | low | med | high | med | med | 2500000 | 2758655 | 2869566 | 383.6846 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X | X | X |  | no | Yes | no | no | no | Yes | Yes | Yes | no | 4 | 5 | 4 | 3 | 2 | 1 | 1 | 1 | 52.5% | 6 | 5 | 5 | 1 | 1 | 1 | 52% | 6 |  | 778.6578
1555 | 1555 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Nov 30, 2025 | 2026-12-31 | 159 | 2 | 2026-07-25 | high | med | med | med | high | 350000 | 441828 | 446179 | 16.1628 | EXPENSE | no | Derate/low flow Pipe segment |  | X | X | X | X | no | Yes | Yes | Yes | no | Yes | Yes | Yes | no | 5 | 1 | 4 | 3 | 3 | 4 | 2 | 3 | 62.5% | 6 | 2 | 5 | 1 | 4 | 2 | 56% | 6 |  | 121.8769
1556 | 1556 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Dec 31, 2030 | 2027-07-31 | 197 | 4 | 2027-06-17 | med | high | high | med | low | 1800000 | 1909884 | 1937687 | 97.7988 | EXPENSE | Yes | Derate/low flow Pipe segment | [5 empty] | no | no | Yes | no | no | no | no | no | Yes | 5 | 4 | 2 | 5 | 1 | 3 | 3 | 2 | 62.5% | 6 | 1 | 3 | 1 | 2 | 2 | 36% | 4 |  | 643.2391
1557 | 1557 | L1 | PIPE INTEGRITY | CLASS | CLASS UPGRADE | Quebec City | Mar 31,2030 | 2027-12-31 | 245 | 20 | 2028-04-30 | med | low | low | med | med | 8550000 | 8506803 | 8740397 | 96.8203 | CAPITAL | no | pipeline segment outage | X |  | X | X | X | Yes | no | no | no | Yes | Yes | Yes | Yes | no | 3 | 3 | 1 | 2 | 3 | 2 | 5 | 3 | 55% | 6 | 4 | 5 | 1 | 5 | 4 | 76% | 8 |  | 267.7598
1558 | 1558 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Toronto | Sept 30,2030 | 2028-10-31 | 335 | 4 | 2027-12-01 | med | med | low | high | low | 1500000 | 1871375 | 1900437 | 20.7353 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  | X | X | Yes | no | Yes | Yes | no | Yes | Yes | no | Yes | 5 | 2 | 3 | 3 | 5 | 2 | 3 | 5 | 70% | 6 | 5 | 5 | 1 | 2 | 2 | 60% | 6 |  | 267.7598
1559 | 1559 | L1 | PIPE INTEGRITY | CLASS | CLASS UPGRADE | North Bay | Aug 31,2027 | 2027-12-31 | 117 | 25 | 2027-04-05 | med | high | med | high | med | 14050000 | 15158244 | 15509480 | 80.1164 | CAPITAL | Yes | pipeline segment outage | X |  |  | X | X | no | Yes | no | Yes | no | Yes | Yes | Yes | no | 1 | 5 | 1 | 3 | 1 | 2 | 4 | 3 | 50% | 5 | 2 | 5 | 1 | 1 | 4 | 52% | 6 |  | 17599.38
1560 | 1560 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Montreal | Sept 30,2028 | 2027-12-31 | 208 | 10 | 2027-09-05 | med | low | low | high | high | 500000 | 564753 | 562254 | 91.2063 | CAPITAL | no | Pipeline segment |  |  | X |  |  | no | Yes | Yes | no | Yes | no | Yes | no | no | 3 | 5 | 4 | 5 | 4 | 1 | 2 | 5 | 72.5% | 8 | 4 | 2 | 1 | 1 | 1 | 36% | 4 |  | 7024.225
1561 | 1561 | L1 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Edmonton | April 30,2029 | 2026-07-31 | 60 | 10 | 2026-06-01 | high | high | low | med | med | 1300000 | 1227077 | 1411856 | 80.7922 | EXPENSE | Yes | pipeline segment outage |  |  | X |  | X | no | Yes | Yes | no | Yes | Yes | Yes | no | Yes | 4 | 4 | 4 | 5 | 1 | 1 | 3 | 5 | 67.5% | 6 | 2 | 1 | 1 | 4 | 3 | 44% | 5 |  | 1591.17
1562 | 1562 | L3 | PIPE INTEGRITY | CATHODIC PROTECT | CP-BRUSHING | Montreal | May 31, 2026 | Oct 31, 2027 | 161 | 8 | 2027-05-23 | med | med | high | low | med | 1000000 | 1022203 | 1280954 | 44.865 | EXPENSE | no | pipeline segment outage |  | X | X | X |  | Yes | Yes | no | no | Yes | no | no | no | no | 4 | 1 | 4 | 4 | 3 | 2 | 5 | 3 | 65% | 6 | 2 | 1 | 5 | 1 | 4 | 52% | 6 |  | 6832.492
1563 | 1563 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Mar 31,2030 | 2028-07-31 | 118 | 5 | 2028-07-05 | med | high | high | high | high | 420000 | 434790 | 444911 | 114.2737 | EXPENSE | no | Pipeline segment | X |  |  |  |  | no | Yes | Yes | Yes | no | no | Yes | no | no | 2 | 5 | 1 | 3 | 2 | 2 | 3 | 2 | 50% | 5 | 3 | 4 | 5 | 1 | 5 | 72% | 8 |  | 5845
1564 | 1564 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Sept 30,2030 | 2026-10-31 | 201 | 2 | 2026-01-11 | med | med | med | high | med | 650000 | 835557 | 838033 | 224.9398 | EXPENSE | no | Derate/low flow Pipe segment |  | X | X |  |  | Yes | Yes | no | Yes | Yes | Yes | Yes | Yes | no | 5 | 5 | 1 | 2 | 4 | 2 | 2 | 1 | 55% | 6 | 1 | 5 | 1 | 5 | 1 | 52% | 6 |  | 5732.891
1565 | 1565 | L2 | PIPE INTEGRITY | CLASS | CLASS UPGRADE | Winnipeg | April 30,2027 | 2029-07-31 | 21 | 12 | 2029-03-10 | low | med | high | med | high | 3420000 | 3477100 | 3401079 | 369.6154 | CAPITAL | Yes | pipeline segment outage | X | X |  |  | X | no | Yes | no | Yes | no | Yes | Yes | no | no | 5 | 5 | 1 | 4 | 3 | 3 | 3 | 1 | 62.5% | 6 | 1 | 5 | 1 | 3 | 4 | 56% | 6 |  | 5097.261
1566 | 1566 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30,2030 | 2029-10-31 | 18 | 5 | 2029-12-13 | med | high | high | low | high | 400000 | 408461 | 404334 | 125.3264 | EXPENSE | no | Pipeline segment | X |  | X |  | X | no | Yes | no | Yes | no | Yes | no | Yes | no | 3 | 1 | 2 | 1 | 5 | 3 | 2 | 5 | 55% | 6 | 1 | 1 | 1 | 4 | 2 | 36% | 4 |  | 4391.637
1567 | 1567 | L3 | PIPE INTEGRITY | EXCAVATION | VALIDATION | Montreal | Sept 30, 2025 | 2030-10-31 | 226 | 5 | 2030-05-19 | med | high | high | high | high | 250000 | 282472 | 312000 | 68.1605 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X |  | X | no | no | no | Yes | no | Yes | Yes | no | no | 2 | 1 | 3 | 3 | 1 | 4 | 5 | 5 | 60% | 6 | 5 | 2 | 5 | 2 | 1 | 60% | 6 |  | 4314.195
1568 | 1568 | L3 | PIPE INTEGRITY | CLASS | CLASS UPGRADE | Ottawa | Nov30,2027 | 2026-12-31 | 226 | 15 | 2025-08-17 | low | low | high | med | low | 5400000 | 5427475 | 5354713 | 89.0006 | CAPITAL | no | pipeline segment outage | X |  | X | X |  | Yes | Yes | Yes | no | Yes | no | no | no | no | 2 | 1 | 1 | 4 | 3 | 1 | 3 | 3 | 45% | 5 | 2 | 5 | 5 | 2 | 1 | 60% | 6 |  | 4858.887
1569 | 1569 | L1 | PIPE INTEGRITY | CATHODIC PROTECT | CP-RECTIFIER | Quebec City | May 31, 2026 | 2027-10-31 | 244 | 4 | 2027-03-01 | med | med | med | high | low | 700000 | 657099 | 685103 | 484.7808 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  | X |  | no | no | Yes | no | Yes | no | Yes | Yes | no | 1 | 2 | 2 | 4 | 1 | 4 | 2 | 3 | 47.5% | 5 | 3 | 2 | 5 | 4 | 4 | 72% | 8 |  | 2178.073
1570 | 1570 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | May 31, 2026 | 2028-10-31 | 238 | 4 | 2027-12-06 | high | high | med | high | low | 1750000 | 1770877 | 1780700 | 91.2089 | EXPENSE | no | Derate/low flow Pipe segment |  | X |  | X |  | Yes | Yes | no | no | Yes | Yes | Yes | Yes | no | 3 | 2 | 1 | 5 | 1 | 3 | 1 | 4 | 50% | 5 | 5 | 3 | 1 | 3 | 4 | 64% | 7 |  | 1090.538
1571 | 1571 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Quebec City | Dec 31, 2030 | 2026-07-31 | 320 | 4 | 2025-05-15 | med | high | med | high | high | 1500000 | 1500982 | 1500604 | 7.9794 | EXPENSE | no | Derate/low flow Pipe segment |  |  |  | X | X | Yes | Yes | no | Yes | Yes | no | no | Yes | no | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20% | 2 | 2 | 1 | 1 | 5 | 2 | 44% | 5 |  | 8501.429
1572 | 1572 | L3 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Dec 31,2026 | 2029-10-31 | 288 | 8 | 2028-10-16 | med | low | med | low | med | 400000 | 366358 | 369590 | 32.0854 | CAPITAL | no | Pipeline segment |  |  | X | X |  | no | Yes | no | no | Yes | no | Yes | no | no | 2 | 3 | 4 | 1 | 1 | 1 | 2 | 1 | 37.5% | 4 | 1 | 1 | 1 | 1 | 3 | 28% | 3 |  | 4052.085
1573 | 1573 | L3 | PIPE INTEGRITY | EXCAVATION | CUTOUT | Edmonton | April 30,2028 | 2028-07-31 | 253 | 8 | 2027-11-21 | low | med | high | high | high | 550000 | 553200 | 542753 | 123.3918 | CAPITAL | no | Pipeline segment |  | X |  |  | X | Yes | no | no | no | no | Yes | Yes | no | Yes | 1 | 1 | 2 | 4 | 4 | 3 | 2 | 1 | 45% | 5 | 1 | 1 | 1 | 1 | 1 | 20% | 2 |  | 6062.603
1574 | 1574 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Dec 31,2028 | 2025-12-31 | 355 | 4 | 2025-11-10 | high | high | low | low | high | 1500000 | 1708182 | 1716547 | 45.4478 | EXPENSE | no | Derate/low flow Pipe segment | X | X | X |  |  | Yes | no | no | no | no | no | Yes | Yes | no | 3 | 3 | 3 | 2 | 5 | 4 | 3 | 2 | 62.5% | 6 | 1 | 5 | 1 | 4 | 4 | 60% | 6 |  | 2610.39
1575 | 1575 | L2 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | May 31, 2026 | 2026-10-31 | 71 | 2 | 2026-10-21 | high | high | high | low | high | 300000 | 378545 | 398478 | 311.1133 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X | X | X | X | no | no | no | Yes | Yes | no | no | Yes | no | 3 | 5 | 3 | 3 | 3 | 4 | 2 | 5 | 70% | 6 | 3 | 1 | 1 | 5 | 4 | 56% | 6 |  | 241.5599
1576 | 1576 | L2 | PIPE INTEGRITY | CATHODIC PROTECT | CP-RECTIFIER | Saskatoon | Dec 31,2026 | 2027-12-31 | 288 | 8 | 2027-01-16 | high | low | high | low | high | 700000 | 855692 | 885145 | 139.156 | CAPITAL | Yes | Derate/low flow Pipe segment |  | X | X |  | X | Yes | Yes | no | no | no | Yes | no | no | Yes | 5 | 1 | 2 | 1 | 1 | 2 | 1 | 4 | 42.5% | 5 | 2 | 1 | 1 | 3 | 1 | 32% | 4 |  | 6993.546
1577 | 1577 | L1 | PIPE INTEGRITY | EXCAVATION | SLEEVE | Edmonton | Sept 30, 2025 | 2026-12-31 | 46 | 4 | 2026-11-15 | med | low | high | low | med | 550000 | 600984 | 601355 | 83.4126 | EXPENSE | Yes | Pipeline segment |  | X | X | X |  | no | no | no | Yes | Yes | Yes | Yes | no | Yes | 3 | 5 | 2 | 3 | 5 | 5 | 4 | 3 | 75% | 8 | 4 | 1 | 1 | 4 | 4 | 56% | 6 |  | 222.8052
1578 | 1578 | L1 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Regina | Sept 30, 2025 | 2027-10-31 | 206 | 10 | 2027-06-08 | med | low | low | low | med | 1800000 | 1807733 | 1857547 | 76.4961 | EXPENSE | no | pipeline segment outage |  | X | X |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | Yes | 5 | 1 | 1 | 5 | 4 | 4 | 4 | 1 | 62.5% | 6 | 4 | 3 | 1 | 4 | 5 | 68% | 7 |  | 840.2082
1579 | 1579 | L2 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Saskatoon | Sept 30, 2025 | 2026-10-31 | 12 | 4 | 2026-12-19 | high | high | med | med | high | 425000 | 662668 | 637944 | 32.9243 | EXPENSE | Yes | pipeline segment outage | X | X | X |  | X | no | Yes | Yes | no | Yes | no | no | no | no | 4 | 2 | 4 | 3 | 2 | 2 | 4 | 2 | 57.5% | 6 | 5 | 1 | 1 | 4 | 1 | 48% | 5 |  | 5000
1580 | 1580 | L1 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Saskatoon | Nov 30,2029 | 2030-10-31 | 64 | 10 | 2030-05-28 | low | low | med | high | med | 1800000 | 1875000 | 1830883 | 49.4725 | EXPENSE | no | pipeline segment outage |  |  |  | X |  | no | no | no | Yes | Yes | Yes | Yes | no | no | 1 | 2 | 4 | 5 | 5 | 2 | 5 | 2 | 65% | 6 | 5 | 2 | 1 | 3 | 3 | 56% | 6 |  | 646
1581 | 1581 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Quebec City | Aug 31,2027 | 2027-10-31 | 52 | 2 | 2027-09-09 | med | med | high | med | high | 450000 | 486253 | 471492 | 34.7089 | EXPENSE | no | Derate/low flow Pipe segment |  |  | X | X |  | no | Yes | no | no | Yes | Yes | Yes | no | Yes | 5 | 1 | 4 | 5 | 4 | 4 | 5 | 4 | 80% | 8 | 4 | 1 | 1 | 2 | 2 | 40% | 4 |  | 289
1582 | 1582 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Montreal | Sept 30,2030 | 2028-10-31 | 41 | 4 | 2028-06-20 | med | med | high | med | high | 1000000 | 1649706 | 1663088 | 96.0767 | EXPENSE | no | Derate/low flow Pipe segment | X |  | X | X | X | no | Yes | no | no | Yes | Yes | no | no | no | 5 | 5 | 3 | 2 | 5 | 2 | 2 | 3 | 67.5% | 6 | 3 | 5 | 1 | 4 | 1 | 56% | 6 |  | 347
1583 | 1583 | L1 | PIPE INTEGRITY | EXCAVATION | RECOAT | Saskatoon | Sept 30, 2025 | 2027-07-31 | 213 | 4 | 2026-12-30 | med | low | med | med | low | 400000 | 450000 | 495000 | 24.5147 | EXPENSE | no | Pipeline segment |  | X |  | X |  | no | no | no | no | no | no | Yes | Yes | no | 3 | 1 | 1 | 3 | 5 | 5 | 3 | 1 | 55% | 6 | 5 | 2 | 1 | 2 | 3 | 52% | 6 |  | 1207.799
1584 | 1584 | L1 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Edmonton | Aug 31,2027 | 2026-10-31 | 184 | 10 | 2026-01-28 | low | high | med | high | low | 1300000 | 1281295 | 1270817 | 714.4143 | EXPENSE | no | pipeline segment outage | X |  | X |  |  | no | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 3 | 4 | 1 | 4 | 5 | 2 | 4 | 1 | 60% | 6 | 2 | 1 | 1 | 1 | 5 | 40% | 4 |  | 898
1585 | 1585 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | May 31, 2026 | 2028-10-31 | 296 | 2 | 2027-06-09 | high | low | low | low | med | 350000 | 378827 | 442990 | 523.2809 | EXPENSE | Yes | Derate/low flow Pipe segment | X | X |  |  | X | Yes | Yes | no | Yes | no | no | no | Yes | no | 5 | 4 | 2 | 2 | 2 | 2 | 5 | 1 | 57.5% | 6 | 2 | 2 | 5 | 3 | 1 | 52% | 6 |  | 172.2548
1586 | 1586 | L1 | PIPE INTEGRITY | ILI | INSPECTION RUN | Ottawa | Aug 31,2027 | 2027-07-31 | 214 | 2 | 2027-12-30 | med | low | high | high | high | 1000000 | 1200000 | 1281639 | 8.2654 | EXPENSE | Yes | Derate/low flow Pipe segment |  | X |  |  | X | no | no | no | Yes | no | Yes | Yes | no | Yes | 4 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 42.5% | 5 | 4 | 2 | 5 | 4 | 1 | 64% | 7 |  | 382.7885
1587 | 1587 | L2 | PIPE INTEGRITY | INSPECTION | HYDROTEST | Winnipeg | Sept 30, 2025 | 2026-07-31 | 250 | 10 | 2025-11-23 | high | high | med | med | low | 1300000 | 1424785 | 1450260 | 2123.4281 | EXPENSE | Yes | pipeline segment outage | X |  |  |  | X | no | Yes | Yes | Yes | Yes | no | Yes | no | no | 1 | 4 | 2 | 2 | 4 | 4 | 4 | 1 | 55% | 6 | 2 | 3 | 5 | 5 | 4 | 76% | 8 |  | 173.2929
1588 | 1588 | L3 | PIPE INTEGRITY | ILI | INSPECTION RUN | Regina | Dec 31,2028 | 2026-10-31 | 114 | 4 | 2025-12-07 | med | high | med | med | low | 1800000 | 1817708 | 1819840 | 73.0943 | EXPENSE | no | Derate/low flow Pipe segment | X |  | X | X |  | Yes | no | Yes | no | no | Yes | Yes | Yes | Yes | 2 | 2 | 4 | 4 | 4 | 4 | 1 | 1 | 55% | 6 | 2 | 5 | 1 | 4 | 3 | 60% | 6 |  | 900.2043
1589 | 1589 | L3 | PIPE INTEGRITY | EXCAVATION | SLEEVE | North Bay | Aug 31,2029 | 2029-10-31 | 186 | 10 | 2029-01-26 | low | low | low | low | high | 550000 | 781048 | 788414 | 41.8408 | EXPENSE | no | Pipeline segment | X |  | X | X | X | no | Yes | Yes | Yes | Yes | no | no | no | no | 1 | 5 | 1 | 3 | 1 | 1 | 4 | 3 | 47.5% | 5 | 3 | 1 | 1 | 4 | 3 | 48% | 5 |  | 749.7244
1590 | 1590 | L2 | PIPE INTEGRITY | EXCAVATION | RECOAT | Toronto | Nov 30,2029 | 2027-07-31 | 137 | 4 | 2027-08-16 | high | low | low | high | low | 400000 | 301807 | 325115 | 243.4001 | EXPENSE | no | Pipeline segment |  | X |  |  |  | Yes | no | no | no | Yes | no | Yes | Yes | Yes | 1 | 5 | 4 | 1 | 3 | 1 | 4 | 5 | 60% | 6 | 1 | 1 | 1 | 1 | 3 | 28% | 3 |  | 1022.412

## FLOW FORECASTS
FLOW FORECASTS |  | 10^6 M3
2010-04-01 | Flows | 2500.2046 | 265.5114 | 109.2378 | 2874.9538 | 81.4412 | 631.1562 | 17.8793 | 482.6933 | 996.7068 | 209.7783 | 1689.1783 | 47.8508
2010-05-01 | Flows | 2419.9997 | 259 | 88.796 | 2767.7957 | 78.4057 | 427.4795 | 12.1096 | 302.0879 | 970 | 134 | 1406.0879 | 39.8314
2010-06-01 | Flows | 2668.9996 | 265 | 124.997 | 3058.9966 | 86.6548 | 611.0108 | 17.3086 | 502.3875 | 719.1023 | 170 | 1391.4898 | 39.4179
2010-07-01 | Flows | 2324.9995 | 260 | 125 | 2709.9995 | 76.7684 | 422.4986 | 11.9685 | 321.0468 | 969.967 | 218 | 1509.0138 | 42.7471
2010-08-01 | Flows | 2574 | 260 | 125 | 2959 | 83.8221 | 599.5995 | 16.9854 | 491.3766 | 801.8551 | 238 | 1531.2316 | 43.3765
2010-09-01 | Flows | 2675 | 260 | 125 | 3060 | 86.6832 | 716.6553 | 20.3013 | 589.1632 | 752.6469 | 189 | 1530.81 | 43.3645
2010-10-01 | Flows | 2350 | 260 | 125 | 2735 | 77.4766 | 617.0904 | 17.4808 | 438.7914 | 1058.5035 | 213 | 1710.2949 | 48.449
2010-11-01 | Flows | 2564.9995 | 265 | 125 | 2954.9995 | 83.7088 | 1118.1068 | 31.6736 | 887.1348 | 1308.6749 | 305 | 2500.8097 | 70.8425
2010-12-01 | Flows | 3062.0005 | 265 | 125 | 3452.0005 | 97.7877 | 1625.3229 | 46.0419 | 1337.3134 | 1526.4562 | 449.52 | 3313.2896 | 93.8583
2011-01-01 | Flows | 2679.9178 | 259.974 | 45 | 2984.8918 | 84.5555 | 1780.067 | 50.4255 | 1436.8689 | 1700 | 277.7078 | 3414.5767 | 96.7276
2011-02-01 | Flows | 2618.6348 | 259.974 | 189.6459 | 3068.2547 | 86.917 | 1631.8821 | 46.2277 | 1313.6547 | 1700 | 539.3568 | 3553.0115 | 100.6491
2011-03-01 | Flows | 2687.4945 | 259.974 | 83.6146 | 3031.0831 | 85.864 | 1005.8591 | 28.4938 | 751.9161 | 1637.4884 | 240.9396 | 2630.3441 | 74.512

## Background (hidden)
ProjectReadinessScope | ProjectEngDesign | ProjectFunding | ProjectPermits | ProjectStkholdrEngagmnt | ProjectProcurementScm | ProjectResourceMgmt | ProjectExeqtnSched | ProjectReadinessRank | PriorityScopeClarity | ProorityImpact Assessmt | PrioritySafetyReqmt | PriorityCommCapacityReliabiilty | PriorityOutageImpacts | PriorityRank (RISK)
5 | 1 | 1 | 3 | 5 | 3 | 1 | 2 | 52.5% | 4 | 3 | TRUE | 2 | 3 | 9
4 | 1 | 1 | 3 | 2 | 3 | 5 | 1 | 50% | 2 | 5 |  | 1 | 3 | 6
2 | 1 | 5 | 5 | 2 | 4 | 5 | 1 | 62.5% | 4 | 3 |  | 5 | 3 | 6
5 | 5 | 1 | 1 | 5 | 1 | 1 | 5 | 60% | 3 | 1 |  | 5 | 1 | 3
5 | 5 | 3 | 1 | 5 | 4 | 5 | 1 | 72.5% | 1 | 4 |  | 1 | 5 | 1
4 | 2 | 2 | 5 | 3 | 5 | 4 | 3 | 70% | 1 | 2 |  | 5 | 4 | 5
1 | 1 | 3 | 1 | 5 | 5 | 1 | 1 | 45% | 4 | 1 |  | 2 | 5 | 4
4 | 4 | 2 | 3 | 5 | 2 | 3 | 3 | 65% | 2 | 3 |  | 5 | 1 | 3
2 | 4 | 3 | 1 | 5 | 3 | 1 | 4 | 57.5% | 3 | 2 |  | 4 | 4 | 3
3 | 3 | 2 | 5 | 2 | 2 | 2 | 4 | 57.5% | 3 | 3 |  | 1 | 3 | 4
3 | 2 | 5 | 3 | 2 | 2 | 5 | 3 | 62.5% | 1 | 5 |  | 3 | 5 | 6
2 | 3 | 5 | 2 | 4 | 4 | 3 | 1 | 60% | 1 | 3 |  | 5 | 5 | 3
5 | 3 | 2 | 3 | 1 | 5 | 4 | 5 | 70% | 1 | 2 |  | 4 | 5 | 2
5 | 4 | 1 | 1 | 2 | 2 | 2 | 5 | 55% | 5 | 3 |  | 5 | 3 | 9
4 | 3 | 1 | 5 | 2 | 4 | 4 | 4 | 67.5% | 4 | 4 |  | 4 | 3 | 5
2 | 2 | 2 | 2 | 3 | 4 | 4 | 5 | 60% | 2 | 2 |  | 1 | 3 | 2
5 | 1 | 1 | 3 | 5 | 1 | 3 | 1 | 50% | 1 | 2 |  | 4 | 1 | 2
4 | 3 | 2 | 4 | 4 | 2 | 3 | 2 | 60% | 3 | 5 |  | 2 | 3 | 1
3 | 4 | 5 | 5 | 5 | 3 | 4 | 3 | 80% | 5 | 2 |  | 1 | 1 | 8
2 | 4 | 5 | 1 | 4 | 5 | 1 | 4 | 65% | 3 | 3 |  | 3 | 2 | 4
5 | 4 | 1 | 1 | 3 | 3 | 3 | 2 | 55% | 1 | 1 |  | 5 | 4 | 4
2 | 1 | 3 | 5 | 5 | 5 | 5 | 5 | 77.5% | 1 | 3 |  | 2 | 2 | 6
5 | 5 | 5 | 1 | 5 | 1 | 3 | 2 | 67.5% | 4 | 4 |  | 4 | 1 | 7
1 | 1 | 4 | 5 | 3 | 2 | 3 | 3 | 55% | 4 | 5 |  | 1 | 2 | 9
3 | 2 | 2 | 4 | 1 | 3 | 3 | 3 | 52.5% | 5 | 2 |  | 3 | 2 | 2
5 | 4 | 3 | 5 | 3 | 4 | 3 | 4 | 77.5% | 3 | 2 |  | 5 | 4 | 8
1 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 75% | 2 | 3 |  | 5 | 4 | 1
5 | 5 | 3 | 1 | 2 | 2 | 3 | 2 | 57.5% | 1 | 4 |  | 2 | 2 | 1
5 | 1 | 1 | 1 | 4 | 5 | 5 | 4 | 65% | 2 | 3 |  | 1 | 4 | 7
2 | 2 | 1 | 1 | 4 | 5 | 1 | 5 | 52.5% | 4 | 2 |  | 1 | 1 | 7
3 | 5 | 1 | 1 | 3 | 2 | 1 | 4 | 50% | 5 | 2 |  | 5 | 4 | 8
2 | 1 | 3 | 5 | 5 | 3 | 1 | 1 | 52.5% | 3 | 3 |  | 2 | 2 | 2
2 | 5 | 1 | 1 | 5 | 4 | 5 | 4 | 67.5% | 3 | 3 |  | 1 | 5 | 1
5 | 3 | 1 | 4 | 5 | 5 | 5 | 1 | 72.5% | 5 | 3 |  | 4 | 1 | 9
1 | 4 | 2 | 2 | 4 | 3 | 4 | 2 | 55% | 2 | 1 |  | 2 | 4 | 6
1 | 5 | 4 | 4 | 3 | 5 | 2 | 3 | 67.5% | 3 | 4 |  | 1 | 1 | 8
1 | 3 | 4 | 4 | 5 | 4 | 1 | 1 | 57.5% | 4 | 2 |  | 5 | 4 | 1
1 | 1 | 3 | 5 | 5 | 4 | 5 | 3 | 67.5% | 5 | 2 |  | 5 | 1 | 7
3 | 1 | 4 | 2 | 4 | 3 | 3 | 1 | 52.5% | 5 | 1 |  | 5 | 5 | 4
2 | 3 | 1 | 3 | 1 | 3 | 4 | 2 | 47.5% | 4 | 3 |  | 5 | 2 | 1
1 | 1 | 3 | 4 | 1 | 4 | 1 | 3 | 45% | 1 | 4 |  | 3 | 3 | 5
4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 42.5% | 5 | 4 |  | 4 | 1 | 8
3 | 4 | 4 | 2 | 4 | 1 | 4 | 5 | 67.5% | 1 | 2 |  | 4 | 2 | 4
3 | 4 | 4 | 5 | 4 | 5 | 4 | 1 | 75% | 5 | 1 |  | 5 | 2 | 5
4 | 5 | 2 | 4 | 4 | 1 | 2 | 4 | 65% | 2 | 4 |  | 1 | 1 | 2
2 | 4 | 1 | 2 | 1 | 5 | 5 | 4 | 60% | 5 | 1 |  | 5 | 3 | 5
1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 30% | 3 | 2 |  | 3 | 2 | 5
2 | 2 | 4 | 5 | 3 | 5 | 3 | 2 | 65% | 1 | 5 |  | 5 | 5 | 8
4 | 3 | 1 | 5 | 4 | 2 | 4 | 3 | 65% | 4 | 5 |  | 2 | 5 | 4
1 | 4 | 2 | 4 | 2 | 4 | 3 | 4 | 60% | 3 | 4 |  | 2 | 5 | 6
3 | 4 | 1 | 4 | 3 | 2 | 1 | 1 | 47.5% | 4 | 5 |  | 4 | 1 | 8
5 | 4 | 5 | 1 | 5 | 4 | 3 | 3 | 75% | 3 | 1 |  | 5 | 1 | 2
3 | 1 | 4 | 5 | 3 | 3 | 3 | 3 | 62.5% | 3 | 4 |  | 4 | 4 | 7
3 | 1 | 4 | 4 | 1 | 2 | 5 | 3 | 57.5% | 2 | 2 |  | 5 | 1 | 6
4 | 5 | 2 | 1 | 1 | 4 | 4 | 3 | 60% | 1 | 5 |  | 3 | 5 | 7
2 | 4 | 4 | 1 | 5 | 4 | 4 | 2 | 65% | 5 | 1 |  | 2 | 3 | 7
1 | 4 | 4 | 4 | 3 | 5 | 2 | 4 | 67.5% | 4 | 1 |  | 4 | 2 | 5
5 | 2 | 5 | 4 | 4 | 3 | 4 | 5 | 80% | 2 | 3 |  | 2 | 5 | 6
4 | 3 | 3 | 5 | 2 | 4 | 1 | 4 | 65% | 4 | 5 |  | 2 | 2 | 2
3 | 3 | 3 | 2 | 2 | 1 | 2 | 3 | 47.5% | 3 | 4 |  | 2 | 2 | 5
4 | 1 | 1 | 5 | 3 | 5 | 3 | 1 | 57.5% | 3 | 3 |  | 3 | 2 | 6
4 | 4 | 5 | 4 | 5 | 2 | 2 | 4 | 75% | 2 | 2 |  | 2 | 2 | 3
1 | 3 | 4 | 3 | 5 | 2 | 2 | 4 | 60% | 4 | 5 |  | 3 | 1 | 8
5 | 2 | 4 | 3 | 1 | 2 | 1 | 2 | 50% | 5 | 2 |  | 2 | 2 | 7
5 | 5 | 1 | 3 | 2 | 4 | 4 | 4 | 70% | 3 | 4 |  | 5 | 5 | 9
1 | 3 | 5 | 4 | 2 | 3 | 5 | 2 | 62.5% | 2 | 5 |  | 4 | 4 | 4
5 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 45% | 2 | 4 |  | 3 | 5 | 6
1 | 5 | 1 | 2 | 3 | 5 | 3 | 4 | 60% | 2 | 1 |  | 2 | 2 | 6
1 | 5 | 3 | 4 | 2 | 1 | 5 | 1 | 55% | 4 | 3 |  | 2 | 5 | 4
5 | 3 | 3 | 1 | 2 | 5 | 2 | 1 | 55% | 2 | 5 |  | 5 | 1 | 9
5 | 3 | 2 | 4 | 2 | 2 | 2 | 4 | 60% | 3 | 2 |  | 3 | 1 | 5
5 | 3 | 5 | 1 | 1 | 5 | 5 | 2 | 67.5% | 3 | 5 |  | 1 | 4 | 6
4 | 2 | 1 | 3 | 1 | 4 | 2 | 1 | 45% | 4 | 4 |  | 1 | 1 | 5
3 | 5 | 5 | 5 | 4 | 3 | 3 | 3 | 77.5% | 3 | 2 |  | 4 | 5 | 5
5 | 4 | 3 | 1 | 4 | 2 | 2 | 5 | 65% | 5 | 4 |  | 1 | 3 | 8
2 | 5 | 5 | 3 | 2 | 3 | 3 | 5 | 70% | 1 | 2 |  | 4 | 1 | 8
5 | 3 | 3 | 3 | 2 | 3 | 3 | 5 | 67.5% | 5 | 5 |  | 1 | 4 | 1
3 | 1 | 4 | 1 | 4 | 2 | 2 | 5 | 55% | 1 | 3 |  | 2 | 5 | 6
4 | 4 | 2 | 2 | 3 | 2 | 3 | 4 | 60% | 3 | 4 |  | 2 | 5 | 2
4 | 1 | 2 | 3 | 2 | 1 | 5 | 4 | 55% | 5 | 5 |  | 3 | 1 | 8
5 | 2 | 1 | 1 | 1 | 5 | 5 | 4 | 60% | 1 | 4 |  | 4 | 5 | 8
2 | 4 | 3 | 3 | 2 | 4 | 4 | 5 | 67.5% | 4 | 3 |  | 2 | 4 | 4
3 | 4 | 5 | 1 | 3 | 3 | 5 | 1 | 62.5% | 1 | 1 |  | 3 | 1 | 4
4 | 3 | 4 | 1 | 4 | 1 | 3 | 2 | 55% | 5 | 4 |  | 3 | 2 | 1
4 | 5 | 2 | 2 | 4 | 2 | 1 | 1 | 52.5% | 4 | 3 |  | 2 | 1 | 5
5 | 3 | 4 | 5 | 4 | 5 | 3 | 3 | 80% | 4 | 3 |  | 1 | 3 | 5
1 | 1 | 5 | 1 | 5 | 3 | 3 | 2 | 52.5% | 5 | 3 |  | 3 | 1 | 3
3 | 4 | 2 | 5 | 4 | 5 | 1 | 5 | 72.5% | 5 | 2 |  | 1 | 3 | 2
1 | 2 | 1 | 2 | 2 | 5 | 5 | 1 | 47.5% | 4 | 2 |  | 5 | 3 | 2
5 | 5 | 5 | 4 | 3 | 5 | 4 | 4 | 87.5% | 2 | 4 |  | 2 | 2 | 9
1 | 4 | 5 | 3 | 5 | 4 | 5 | 4 | 77.5% | 1 | 1 |  | 3 | 4 | 7
3 | 4 | 2 | 2 | 3 | 5 | 1 | 2 | 55% | 4 | 4 |  | 5 | 3 | 5
3 | 3 | 1 | 4 | 2 | 4 | 2 | 4 | 57.5% | 2 | 5 |  | 4 | 4 | 9
3 | 4 | 2 | 4 | 5 | 2 | 4 | 3 | 67.5% | 1 | 4 |  | 4 | 3 | 1
5 | 2 | 4 | 4 | 5 | 1 | 3 | 3 | 67.5% | 3 | 3 |  | 3 | 5 | 8
1 | 2 | 5 | 3 | 3 | 2 | 5 | 4 | 62.5% | 2 | 4 |  | 4 | 2 | 6
4 | 3 | 1 | 5 | 1 | 5 | 2 | 3 | 60% | 3 | 2 |  | 2 | 5 | 8
5 | 3 | 1 | 5 | 1 | 4 | 3 | 4 | 65% | 1 | 2 |  | 1 | 2 | 3
2 | 3 | 5 | 5 | 3 | 3 | 4 | 2 | 67.5% | 5 | 5 |  | 5 | 5 | 1
2 | 1 | 2 | 2 | 4 | 1 | 3 | 3 | 45% | 2 | 5 |  | 3 | 3 | 2
3 | 3 | 2 | 2 | 1 | 2 | 3 | 1 | 42.5% | 4 | 3 |  | 4 | 2 | 8
2 | 1 | 2 | 4 | 5 | 2 | 1 | 4 | 52.5% | 3 | 2 |  | 1 | 2 | 8
3 | 1 | 5 | 1 | 2 | 4 | 5 | 4 | 62.5% | 1 | 1 |  | 3 | 4 | 2
1 | 3 | 2 | 3 | 2 | 3 | 1 | 3 | 45% | 3 | 5 |  | 5 | 4 | 7
3 | 2 | 2 | 2 | 1 | 4 | 4 | 1 | 47.5% | 3 | 5 |  | 5 | 3 | 5
5 | 4 | 1 | 2 | 3 | 4 | 4 | 1 | 60% | 1 | 5 |  | 2 | 3 | 9
3 | 4 | 3 | 2 | 3 | 2 | 5 | 2 | 60% | 4 | 5 |  | 1 | 3 | 6
4 | 5 | 3 | 5 | 1 | 4 | 1 | 4 | 67.5% | 5 | 4 |  | 2 | 1 | 8
5 | 3 | 2 | 1 | 1 | 2 | 2 | 5 | 52.5% | 2 | 3 |  | 5 | 5 | 8
3 | 4 | 3 | 3 | 3 | 5 | 2 | 2 | 62.5% | 2 | 1 |  | 2 | 5 | 1
5 | 4 | 2 | 2 | 4 | 5 | 1 | 2 | 62.5% | 3 | 5 |  | 4 | 2 | 5
3 | 4 | 3 | 5 | 1 | 3 | 4 | 1 | 60% | 2 | 3 |  | 2 | 3 | 1
1 | 2 | 4 | 3 | 1 | 3 | 3 | 1 | 45% | 4 | 3 |  | 5 | 4 | 2
1 | 4 | 3 | 5 | 5 | 4 | 3 | 4 | 72.5% | 5 | 2 |  | 1 | 5 | 8
4 | 3 | 5 | 5 | 1 | 4 | 5 | 2 | 72.5% | 1 | 2 |  | 4 | 3 | 7
1 | 3 | 2 | 5 | 4 | 4 | 5 | 5 | 72.5% | 2 | 2 |  | 3 | 5 | 1
3 | 5 | 1 | 3 | 5 | 1 | 1 | 4 | 57.5% | 2 | 5 |  | 3 | 3 | 2
1 | 4 | 1 | 3 | 3 | 4 | 3 | 3 | 55% | 4 | 1 |  | 1 | 5 | 8
5 | 4 | 4 | 3 | 3 | 3 | 4 | 3 | 72.5% | 3 | 1 |  | 1 | 3 | 7
5 | 3 | 4 | 2 | 2 | 5 | 5 | 1 | 67.5% | 2 | 3 |  | 4 | 2 | 3
5 | 5 | 3 | 2 | 4 | 2 | 4 | 2 | 67.5% | 2 | 2 |  | 3 | 4 | 4
2 | 4 | 4 | 5 | 5 | 1 | 1 | 1 | 57.5% | 2 | 3 |  | 2 | 1 | 5
2 | 2 | 4 | 4 | 3 | 4 | 3 | 2 | 60% | 5 | 4 |  | 1 | 5 | 8
2 | 2 | 1 | 5 | 4 | 1 | 3 | 2 | 50% | 5 | 1 |  | 4 | 4 | 9
1 | 4 | 5 | 5 | 5 | 3 | 4 | 5 | 80% | 4 | 4 |  | 3 | 1 | 3
5 | 1 | 2 | 4 | 2 | 4 | 2 | 3 | 57.5% | 3 | 5 |  | 1 | 2 | 8
5 | 2 | 3 | 3 | 5 | 2 | 3 | 1 | 60% | 3 | 3 |  | 5 | 1 | 2
5 | 2 | 2 | 3 | 4 | 2 | 1 | 5 | 60% | 2 | 1 |  | 3 | 5 | 7
3 | 4 | 5 | 5 | 2 | 5 | 2 | 4 | 75% | 1 | 2 |  | 3 | 1 | 2
3 | 3 | 5 | 1 | 3 | 2 | 5 | 1 | 57.5% | 4 | 2 |  | 5 | 4 | 6
4 | 1 | 3 | 2 | 4 | 3 | 2 | 3 | 55% | 1 | 5 |  | 4 | 5 | 1
5 | 3 | 2 | 3 | 5 | 4 | 3 | 2 | 67.5% | 2 | 3 |  | 4 | 3 | 6
1 | 3 | 1 | 3 | 5 | 2 | 5 | 4 | 60% | 5 | 2 |  | 3 | 5 | 7
2 | 4 | 1 | 3 | 3 | 2 | 4 | 4 | 57.5% | 4 | 2 |  | 4 | 3 | 3
2 | 3 | 2 | 3 | 4 | 2 | 1 | 4 | 52.5% | 5 | 3 |  | 2 | 1 | 8
4 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 40% | 3 | 4 |  | 3 | 3 | 3
5 | 1 | 4 | 3 | 5 | 5 | 3 | 5 | 77.5% | 1 | 4 |  | 3 | 5 | 4
4 | 5 | 2 | 5 | 4 | 2 | 2 | 5 | 72.5% | 3 | 3 |  | 1 | 2 | 2
5 | 4 | 4 | 1 | 3 | 2 | 4 | 1 | 60% | 1 | 5 |  | 4 | 3 | 8
1 | 1 | 3 | 5 | 3 | 4 | 2 | 2 | 52.5% | 4 | 2 |  | 1 | 2 | 7
3 | 2 | 5 | 4 | 2 | 3 | 1 | 3 | 57.5% | 2 | 5 |  | 1 | 1 | 4
3 | 4 | 4 | 2 | 5 | 3 | 2 | 1 | 60% | 4 | 5 |  | 4 | 5 | 7
1 | 5 | 1 | 2 | 4 | 1 | 4 | 3 | 52.5% | 3 | 1 |  | 4 | 5 | 6
3 | 2 | 5 | 1 | 5 | 1 | 5 | 1 | 57.5% | 4 | 5 |  | 3 | 1 | 7
4 | 2 | 4 | 5 | 1 | 5 | 5 | 3 | 72.5% | 3 | 1 |  | 4 | 1 | 2
3 | 4 | 4 | 5 | 5 | 2 | 1 | 3 | 67.5% | 2 | 5 |  | 5 | 1 | 8
4 | 3 | 5 | 1 | 4 | 1 | 4 | 5 | 67.5% | 2 | 3 |  | 2 | 4 | 7
5 | 2 | 1 | 1 | 1 | 2 | 3 | 4 | 47.5% | 4 | 1 |  | 3 | 4 | 2
4 | 5 | 2 | 5 | 1 | 4 | 1 | 4 | 65% | 5 | 3 |  | 1 | 2 | 7
4 | 3 | 2 | 3 | 4 | 4 | 4 | 5 | 72.5% | 3 | 3 |  | 4 | 1 | 3
2 | 2 | 5 | 2 | 4 | 3 | 2 | 4 | 60% | 2 | 5 |  | 1 | 1 | 6
3 | 4 | 4 | 5 | 4 | 3 | 4 | 3 | 75% | 3 | 2 |  | 5 | 2 | 1
5 | 1 | 4 | 3 | 3 | 5 | 2 | 5 | 70% | 4 | 1 |  | 5 | 5 | 5
1 | 5 | 3 | 5 | 1 | 4 | 4 | 5 | 70% | 3 | 5 |  | 5 | 2 | 3
1 | 1 | 4 | 1 | 2 | 2 | 5 | 1 | 42.5% | 5 | 1 |  | 4 | 4 | 7
5 | 4 | 5 | 1 | 3 | 1 | 4 | 3 | 65% | 3 | 1 |  | 4 | 5 | 1
4 | 3 | 4 | 4 | 3 | 2 | 3 | 5 | 70% | 4 | 4 |  | 3 | 5 | 7
5 | 4 | 2 | 1 | 3 | 3 | 1 | 2 | 52.5% | 3 | 3 |  | 3 | 3 | 9
4 | 5 | 2 | 2 | 3 | 3 | 5 | 4 | 70% | 1 | 2 |  | 3 | 5 | 7
5 | 2 | 2 | 3 | 3 | 1 | 1 | 4 | 52.5% | 1 | 3 |  | 1 | 3 | 7
5 | 2 | 2 | 2 | 3 | 5 | 1 | 1 | 52.5% | 5 | 1 |  | 2 | 5 | 9
5 | 3 | 5 | 5 | 3 | 2 | 2 | 4 | 72.5% | 1 | 3 |  | 3 | 4 | 9
5 | 1 | 2 | 4 | 3 | 2 | 1 | 4 | 55% | 5 | 2 |  | 3 | 1 | 9
2 | 5 | 1 | 5 | 3 | 3 | 2 | 5 | 65% | 1 | 3 |  | 1 | 2 | 9
1 | 3 | 2 | 4 | 5 | 3 | 1 | 4 | 57.5% | 4 | 5 |  | 5 | 5 | 9
4 | 5 | 4 | 5 | 3 | 5 | 3 | 5 | 85% | 5 | 5 |  | 4 | 3 | 4
3 | 3 | 5 | 3 | 1 | 1 | 2 | 3 | 52.5% | 3 | 4 |  | 4 | 4 | 9
3 | 5 | 3 | 3 | 2 | 3 | 5 | 1 | 62.5% | 2 | 3 |  | 5 | 3 | 7
3 | 3 | 5 | 2 | 3 | 2 | 5 | 5 | 70% | 5 | 4 |  | 3 | 5 | 9
4 | 1 | 5 | 1 | 1 | 3 | 5 | 2 | 55% | 2 | 5 |  | 3 | 1 | 9
3 | 3 | 2 | 3 | 1 | 3 | 4 | 1 | 50% | 5 | 4 |  | 5 | 4 | 6
4 | 3 | 2 | 5 | 2 | 2 | 2 | 5 | 62.5% | 1 | 2 |  | 3 | 4 | 9
2 | 5 | 4 | 1 | 5 | 2 | 2 | 5 | 65% | 4 | 3 |  | 1 | 5 | 9
1 | 1 | 5 | 3 | 5 | 1 | 2 | 4 | 55% | 1 | 4 |  | 4 | 3 | 3
3 | 2 | 4 | 3 | 2 | 2 | 3 | 4 | 57.5% | 2 | 1 |  | 2 | 5 | 3
3 | 2 | 1 | 1 | 5 | 3 | 1 | 3 | 47.5% | 2 | 4 |  | 3 | 4 | 7
3 | 4 | 5 | 5 | 3 | 4 | 4 | 4 | 80% | 5 | 4 |  | 2 | 5 | 7
5 | 1 | 2 | 2 | 4 | 5 | 2 | 5 | 65% | 1 | 5 |  | 2 | 1 | 9
2 | 4 | 3 | 4 | 3 | 5 | 5 | 2 | 70% | 4 | 1 |  | 1 | 5 | 7
2 | 2 | 1 | 3 | 3 | 1 | 4 | 3 | 47.5% | 1 | 5 |  | 5 | 1 | 7
3 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 42.5% | 4 | 3 |  | 4 | 4 | 5
3 | 2 | 5 | 5 | 5 | 5 | 4 | 5 | 85% | 4 | 2 |  | 4 | 1 | 6
4 | 1 | 1 | 4 | 1 | 3 | 1 | 5 | 50% | 3 | 5 |  | 2 | 5 | 8
3 | 5 | 2 | 2 | 5 | 5 | 2 | 2 | 65% | 5 | 2 |  | 3 | 5 | 5
3 | 4 | 4 | 1 | 2 | 2 | 3 | 2 | 52.5% | 1 | 3 |  | 4 | 5 | 8
3 | 5 | 2 | 2 | 4 | 3 | 5 | 5 | 72.5% | 3 | 2 |  | 4 | 2 | 5
3 | 4 | 1 | 5 | 4 | 2 | 4 | 1 | 60% | 2 | 4 |  | 5 | 4 | 2
4 | 3 | 4 | 1 | 4 | 5 | 3 | 1 | 62.5% | 5 | 5 |  | 3 | 1 | 6
2 | 3 | 4 | 5 | 4 | 5 | 4 | 3 | 75% | 3 | 1 |  | 2 | 5 | 4
1 | 2 | 1 | 5 | 1 | 1 | 4 | 3 | 45% | 1 | 5 |  | 2 | 2 | 7
5 | 2 | 5 | 5 | 4 | 1 | 2 | 2 | 65% | 4 | 3 |  | 3 | 2 | 4
3 | 2 | 2 | 4 | 2 | 2 | 5 | 2 | 55% | 1 | 2 |  | 1 | 4 | 2
1 | 5 | 5 | 3 | 2 | 5 | 2 | 1 | 60% | 3 | 4 |  | 3 | 4 | 7
2 | 1 | 2 | 3 | 1 | 4 | 4 | 3 | 50% | 1 | 2 |  | 4 | 2 | 1
2 | 4 | 1 | 3 | 1 | 5 | 2 | 1 | 47.5% | 4 | 3 |  | 3 | 4 | 6
3 | 3 | 2 | 3 | 4 | 5 | 1 | 4 | 62.5% | 3 | 2 |  | 5 | 4 | 7
2 | 4 | 2 | 5 | 5 | 1 | 5 | 5 | 72.5% | 2 | 2 |  | 5 | 4 | 6
4 | 2 | 2 | 3 | 3 | 2 | 5 | 5 | 65% | 5 | 5 |  | 3 | 5 | 9
4 | 5 | 3 | 2 | 2 | 3 | 2 | 5 | 65% | 2 | 3 |  | 1 | 3 | 4
1 | 2 | 5 | 4 | 3 | 3 | 4 | 1 | 57.5% | 5 | 5 |  | 4 | 5 | 3
2 | 5 | 3 | 5 | 4 | 1 | 4 | 1 | 62.5% | 1 | 2 |  | 1 | 1 | 3
3 | 5 | 3 | 3 | 5 | 3 | 5 | 5 | 80% | 4 | 2 |  | 5 | 5 | 7
2 | 1 | 2 | 1 | 2 | 1 | 3 | 5 | 42.5% | 1 | 3 |  | 3 | 2 | 9
1 | 3 | 1 | 4 | 5 | 5 | 4 | 3 | 65% | 3 | 4 |  | 2 | 5 | 8
1 | 3 | 3 | 4 | 1 | 1 | 3 | 1 | 42.5% | 2 | 1 |  | 4 | 1 | 5
2 | 1 | 4 | 4 | 3 | 3 | 5 | 1 | 57.5% | 4 | 1 |  | 4 | 4 | 7
1 | 1 | 5 | 3 | 2 | 5 | 5 | 1 | 57.5% | 4 | 5 |  | 4 | 3 | 9
3 | 2 | 1 | 3 | 5 | 5 | 3 | 4 | 65% | 1 | 3 |  | 3 | 5 | 5
5 | 2 | 1 | 3 | 5 | 4 | 1 | 3 | 60% | 3 | 4 |  | 3 | 3 | 6
2 | 2 | 2 | 2 | 2 | 2 | 4 | 2 | 45% | 3 | 5 |  | 5 | 3 | 5
2 | 2 | 5 | 5 | 4 | 2 | 2 | 2 | 60% | 4 | 4 |  | 3 | 1 | 8
2 | 5 | 3 | 2 | 3 | 1 | 2 | 3 | 52.5% | 1 | 3 |  | 5 | 4 | 8
1 | 1 | 2 | 2 | 3 | 2 | 3 | 4 | 45% | 2 | 4 |  | 3 | 4 | 2
5 | 2 | 3 | 2 | 3 | 5 | 2 | 4 | 65% | 1 | 1 |  | 1 | 1 | 3
4 | 3 | 5 | 1 | 3 | 1 | 5 | 2 | 60% | 2 | 5 |  | 3 | 1 | 4
4 | 2 | 4 | 4 | 4 | 1 | 5 | 3 | 67.5% | 1 | 4 |  | 4 | 1 | 5
4 | 5 | 1 | 3 | 3 | 3 | 2 | 5 | 65% | 3 | 2 |  | 2 | 3 | 4
3 | 1 | 4 | 1 | 3 | 3 | 5 | 1 | 52.5% | 2 | 3 |  | 5 | 5 | 4
1 | 3 | 3 | 5 | 4 | 4 | 3 | 4 | 67.5% | 2 | 2 |  | 4 | 2 | 9
5 | 1 | 3 | 4 | 5 | 2 | 1 | 4 | 62.5% | 2 | 5 |  | 3 | 2 | 7
1 | 3 | 2 | 2 | 1 | 5 | 4 | 2 | 50% | 1 | 2 |  | 1 | 5 | 4
5 | 3 | 2 | 2 | 1 | 4 | 1 | 5 | 57.5% | 4 | 1 |  | 2 | 3 | 6
2 | 3 | 5 | 1 | 2 | 1 | 4 | 4 | 55% | 2 | 5 |  | 5 | 3 | 1
1 | 4 | 5 | 5 | 3 | 3 | 4 | 3 | 70% | 1 | 3 |  | 4 | 4 | 9
4 | 2 | 3 | 1 | 4 | 4 | 5 | 1 | 60% | 4 | 1 |  | 2 | 4 | 8
1 | 2 | 5 | 3 | 3 | 3 | 5 | 2 | 60% | 2 | 5 |  | 3 | 5 | 9
4 | 2 | 5 | 1 | 5 | 1 | 1 | 5 | 60% | 2 | 1 |  | 1 | 3 | 8
1 | 5 | 2 | 5 | 3 | 5 | 1 | 5 | 67.5% | 5 | 5 |  | 5 | 5 | 3
5 | 3 | 2 | 2 | 5 | 4 | 2 | 2 | 62.5% | 5 | 5 |  | 1 | 4 | 2
4 | 2 | 5 | 5 | 4 | 4 | 5 | 1 | 75% | 1 | 2 |  | 4 | 1 | 9
1 | 3 | 3 | 5 | 4 | 4 | 2 | 1 | 57.5% | 3 | 4 |  | 4 | 2 | 6
5 | 2 | 5 | 4 | 5 | 2 | 5 | 4 | 80% | 5 | 5 |  | 1 | 2 | 7
2 | 5 | 4 | 5 | 1 | 3 | 1 | 1 | 55% | 3 | 1 |  | 3 | 5 | 7
3 | 3 | 5 | 1 | 5 | 2 | 3 | 5 | 67.5% | 4 | 2 |  | 4 | 2 | 5
2 | 1 | 3 | 1 | 1 | 2 | 4 | 3 | 42.5% | 3 | 5 |  | 3 | 1 | 8
4 | 4 | 5 | 4 | 2 | 5 | 2 | 4 | 75% | 5 | 4 |  | 5 | 4 | 2
3 | 2 | 1 | 4 | 4 | 4 | 1 | 4 | 57.5% | 3 | 4 |  | 3 | 1 | 7
2 | 2 | 1 | 1 | 4 | 2 | 2 | 3 | 42.5% | 5 | 5 |  | 4 | 5 | 1
4 | 4 | 2 | 5 | 5 | 5 | 3 | 3 | 77.5% | 4 | 2 |  | 4 | 5 | 5
5 | 5 | 1 | 5 | 2 | 5 | 5 | 3 | 77.5% | 4 | 5 |  | 1 | 4 | 3
5 | 1 | 1 | 4 | 2 | 5 | 2 | 2 | 55% | 3 | 3 |  | 3 | 3 | 4
1 | 4 | 3 | 3 | 4 | 3 | 5 | 2 | 62.5% | 5 | 5 |  | 5 | 5 | 6
2 | 3 | 3 | 3 | 3 | 5 | 2 | 3 | 60% | 1 | 4 |  | 1 | 4 | 1
2 | 3 | 1 | 2 | 3 | 5 | 3 | 4 | 57.5% | 5 | 5 |  | 1 | 3 | 6
4 | 1 | 1 | 5 | 2 | 3 | 5 | 5 | 65% | 3 | 3 |  | 2 | 4 | 4
1 | 1 | 2 | 1 | 4 | 4 | 2 | 2 | 42.5% | 1 | 1 |  | 5 | 1 | 8
4 | 3 | 2 | 2 | 4 | 1 | 3 | 5 | 60% | 2 | 3 |  | 2 | 3 | 1
5 | 5 | 1 | 2 | 3 | 4 | 3 | 5 | 70% | 1 | 3 |  | 5 | 4 | 2
5 | 2 | 5 | 1 | 4 | 5 | 3 | 2 | 67.5% | 3 | 4 |  | 4 | 3 | 7
5 | 5 | 3 | 3 | 5 | 5 | 5 | 3 | 85% | 2 | 1 |  | 2 | 2 | 6
3 | 5 | 5 | 2 | 1 | 4 | 5 | 3 | 70% | 1 | 4 |  | 4 | 4 | 1
2 | 1 | 5 | 1 | 3 | 4 | 4 | 4 | 60% | 2 | 4 |  | 2 | 3 | 4
4 | 5 | 1 | 3 | 1 | 1 | 4 | 5 | 60% | 2 | 2 |  | 4 | 2 | 7
3 | 5 | 4 | 3 | 2 | 4 | 1 | 4 | 65% | 1 | 1 |  | 1 | 3 | 9
2 | 5 | 2 | 1 | 2 | 3 | 5 | 2 | 55% | 1 | 1 |  | 1 | 5 | 9
4 | 3 | 5 | 3 | 2 | 5 | 2 | 1 | 62.5% | 5 | 1 |  | 1 | 4 | 8
3 | 5 | 4 | 1 | 1 | 2 | 5 | 4 | 62.5% | 5 | 1 |  | 5 | 1 | 2
1 | 2 | 3 | 4 | 5 | 5 | 3 | 4 | 67.5% | 3 | 2 |  | 1 | 4 | 6
1 | 3 | 4 | 5 | 3 | 2 | 1 | 1 | 50% | 2 | 3 |  | 3 | 4 | 4
5 | 2 | 4 | 3 | 4 | 5 | 2 | 1 | 65% | 4 | 1 |  | 3 | 1 | 9
1 | 3 | 3 | 5 | 1 | 3 | 3 | 1 | 50% | 1 | 3 |  | 4 | 5 | 2
5 | 2 | 3 | 1 | 1 | 1 | 2 | 4 | 47.5% | 3 | 5 |  | 5 | 1 | 2
1 | 4 | 2 | 1 | 3 | 1 | 5 | 1 | 45% | 1 | 2 |  | 5 | 3 | 8
5 | 4 | 5 | 3 | 2 | 1 | 4 | 4 | 70% | 2 | 1 |  | 5 | 4 | 9
1 | 2 | 3 | 1 | 5 | 2 | 1 | 1 | 40% | 2 | 5 |  | 5 | 3 | 3
1 | 4 | 2 | 4 | 5 | 2 | 1 | 5 | 60% | 3 | 5 |  | 5 | 2 | 1
4 | 3 | 4 | 3 | 2 | 3 | 4 | 3 | 65% | 3 | 4 |  | 5 | 4 | 8
2 | 2 | 2 | 5 | 5 | 4 | 1 | 3 | 60% | 2 | 1 |  | 1 | 5 | 9
1 | 1 | 3 | 1 | 2 | 4 | 3 | 2 | 42.5% | 4 | 5 |  | 1 | 1 | 6
2 | 5 | 4 | 4 | 5 | 2 | 3 | 4 | 72.5% | 4 | 4 |  | 1 | 4 | 7
3 | 5 | 1 | 3 | 3 | 2 | 5 | 1 | 57.5% | 4 | 1 |  | 1 | 3 | 9
3 | 3 | 5 | 4 | 3 | 3 | 5 | 2 | 70% | 2 | 5 |  | 2 | 1 | 8
1 | 4 | 2 | 3 | 4 | 1 | 1 | 5 | 52.5% | 2 | 2 |  | 5 | 1 | 7
5 | 4 | 3 | 4 | 2 | 3 | 1 | 2 | 60% | 4 | 5 |  | 3 | 2 | 7
5 | 4 | 3 | 3 | 1 | 2 | 5 | 3 | 65% | 3 | 4 |  | 5 | 2 | 5
5 | 3 | 2 | 1 | 3 | 4 | 3 | 3 | 60% | 2 | 3 |  | 2 | 2 | 5
4 | 4 | 4 | 5 | 1 | 3 | 2 | 4 | 67.5% | 1 | 4 |  | 2 | 5 | 7
1 | 2 | 3 | 1 | 4 | 5 | 3 | 2 | 52.5% | 3 | 1 |  | 5 | 1 | 2
1 | 4 | 5 | 4 | 4 | 3 | 1 | 5 | 67.5% | 2 | 1 |  | 3 | 3 | 2
4 | 3 | 1 | 4 | 4 | 4 | 4 | 3 | 67.5% | 1 | 3 |  | 4 | 3 | 6
4 | 5 | 3 | 1 | 1 | 4 | 4 | 3 | 62.5% | 3 | 2 |  | 1 | 4 | 3
5 | 3 | 5 | 3 | 3 | 3 | 2 | 2 | 65% | 1 | 1 |  | 1 | 4 | 3
3 | 3 | 3 | 4 | 5 | 1 | 4 | 5 | 70% | 4 | 5 |  | 1 | 4 | 8
1 | 5 | 5 | 5 | 4 | 1 | 2 | 3 | 65% | 1 | 2 |  | 1 | 5 | 5
2 | 1 | 4 | 4 | 3 | 2 | 1 | 2 | 47.5% | 2 | 4 |  | 3 | 2 | 9
3 | 1 | 4 | 5 | 4 | 1 | 4 | 3 | 62.5% | 1 | 4 |  | 5 | 2 | 3
5 | 4 | 1 | 5 | 3 | 3 | 1 | 1 | 57.5% | 5 | 3 |  | 2 | 5 | 4
5 | 2 | 3 | 4 | 2 | 1 | 4 | 3 | 60% | 2 | 2 |  | 2 | 4 | 4
4 | 1 | 3 | 1 | 5 | 1 | 3 | 1 | 47.5% | 4 | 1 |  | 2 | 2 | 7
5 | 1 | 1 | 2 | 2 | 4 | 1 | 3 | 47.5% | 1 | 5 |  | 4 | 2 | 3
4 | 1 | 4 | 1 | 2 | 4 | 3 | 5 | 60% | 3 | 2 |  | 5 | 1 | 7
4 | 4 | 2 | 3 | 5 | 4 | 2 | 4 | 70% | 1 | 1 |  | 1 | 3 | 9
1 | 2 | 3 | 1 | 3 | 2 | 1 | 5 | 45% | 2 | 1 |  | 3 | 5 | 3
3 | 4 | 4 | 1 | 2 | 3 | 1 | 4 | 55% | 5 | 3 |  | 5 | 3 | 6
2 | 3 | 1 | 4 | 2 | 2 | 2 | 1 | 42.5% | 5 | 4 |  | 4 | 5 | 1
2 | 2 | 3 | 5 | 3 | 4 | 2 | 4 | 62.5% | 3 | 1 |  | 2 | 5 | 5
1 | 4 | 4 | 5 | 4 | 2 | 4 | 2 | 65% | 5 | 5 |  | 5 | 1 | 2
3 | 5 | 4 | 3 | 5 | 4 | 3 | 2 | 72.5% | 3 | 5 |  | 1 | 2 | 9
1 | 4 | 1 | 3 | 2 | 3 | 5 | 2 | 52.5% | 4 | 3 |  | 5 | 3 | 5
3 | 5 | 1 | 1 | 4 | 3 | 1 | 2 | 50% | 1 | 1 |  | 5 | 3 | 1
1 | 4 | 3 | 2 | 1 | 4 | 4 | 2 | 52.5% | 4 | 4 |  | 2 | 3 | 4
2 | 1 | 4 | 1 | 2 | 1 | 3 | 5 | 47.5% | 1 | 4 |  | 5 | 4 | 8
4 | 3 | 4 | 3 | 3 | 1 | 2 | 1 | 52.5% | 3 | 2 |  | 1 | 1 | 2
3 | 3 | 1 | 4 | 2 | 2 | 1 | 1 | 42.5% | 4 | 5 |  | 2 | 4 | 4
5 | 5 | 2 | 4 | 3 | 5 | 4 | 5 | 82.5% | 5 | 4 |  | 4 | 5 | 6
3 | 4 | 3 | 2 | 1 | 5 | 2 | 4 | 60% | 5 | 1 |  | 5 | 1 | 4
5 | 5 | 2 | 3 | 3 | 2 | 3 | 1 | 60% | 1 | 4 |  | 1 | 2 | 8
2 | 2 | 1 | 3 | 4 | 4 | 4 | 2 | 55% | 3 | 1 |  | 1 | 1 | 3
1 | 4 | 1 | 5 | 1 | 3 | 3 | 4 | 55% | 4 | 1 |  | 3 | 3 | 4
4 | 5 | 1 | 3 | 5 | 3 | 1 | 3 | 62.5% | 2 | 4 |  | 5 | 5 | 5
3 | 4 | 3 | 4 | 2 | 5 | 5 | 3 | 72.5% | 3 | 4 |  | 1 | 4 | 7
4 | 5 | 4 | 5 | 2 | 5 | 2 | 1 | 70% | 4 | 5 |  | 1 | 1 | 2
3 | 5 | 4 | 1 | 3 | 4 | 4 | 4 | 70% | 3 | 4 |  | 3 | 2 | 4
3 | 4 | 1 | 4 | 1 | 2 | 3 | 3 | 52.5% | 3 | 1 |  | 3 | 4 | 8
5 | 4 | 2 | 4 | 5 | 1 | 5 | 4 | 75% | 2 | 1 |  | 3 | 2 | 3
4 | 4 | 5 | 3 | 4 | 5 | 5 | 5 | 87.5% | 1 | 2 |  | 2 | 3 | 7
2 | 4 | 2 | 4 | 1 | 2 | 5 | 4 | 60% | 4 | 2 |  | 5 | 1 | 9
3 | 1 | 1 | 4 | 5 | 5 | 4 | 2 | 62.5% | 1 | 3 |  | 1 | 1 | 5
3 | 4 | 3 | 1 | 5 | 5 | 2 | 3 | 65% | 5 | 3 |  | 5 | 3 | 6
2 | 4 | 2 | 3 | 4 | 4 | 1 | 4 | 60% | 1 | 4 |  | 4 | 1 | 6
3 | 4 | 4 | 2 | 3 | 5 | 4 | 3 | 70% | 5 | 1 |  | 3 | 2 | 4
1 | 5 | 5 | 1 | 2 | 4 | 3 | 5 | 65% | 4 | 3 |  | 4 | 1 | 4
2 | 1 | 3 | 4 | 1 | 4 | 3 | 5 | 57.5% | 1 | 3 |  | 4 | 5 | 3
1 | 5 | 1 | 4 | 5 | 5 | 5 | 5 | 77.5% | 5 | 1 |  | 1 | 5 | 3
3 | 1 | 3 | 5 | 2 | 3 | 3 | 3 | 57.5% | 2 | 1 |  | 5 | 5 | 3
1 | 3 | 1 | 2 | 3 | 4 | 3 | 5 | 55% | 2 | 1 |  | 2 | 4 | 6
1 | 4 | 5 | 3 | 2 | 2 | 4 | 2 | 57.5% | 4 | 5 |  | 1 | 1 | 6
4 | 4 | 4 | 2 | 1 | 1 | 5 | 1 | 55% | 1 | 2 |  | 4 | 4 | 2
2 | 3 | 1 | 1 | 5 | 2 | 4 | 5 | 57.5% | 4 | 5 |  | 4 | 2 | 1
1 | 1 | 3 | 3 | 5 | 1 | 3 | 1 | 45% | 2 | 1 |  | 3 | 3 | 6
5 | 5 | 1 | 1 | 4 | 2 | 2 | 2 | 55% | 5 | 1 |  | 3 | 2 | 9
2 | 1 | 1 | 4 | 4 | 5 | 1 | 2 | 50% | 4 | 2 |  | 1 | 2 | 9
4 | 4 | 1 | 2 | 4 | 3 | 1 | 5 | 60% | 2 | 2 |  | 3 | 2 | 6
5 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 47.5% | 1 | 3 |  | 5 | 3 | 2
1 | 1 | 4 | 2 | 4 | 1 | 3 | 2 | 45% | 1 | 3 |  | 2 | 2 | 9
2 | 5 | 1 | 2 | 1 | 2 | 3 | 5 | 52.5% | 3 | 5 |  | 5 | 5 | 5
3 | 3 | 5 | 2 | 3 | 2 | 4 | 3 | 62.5% | 3 | 1 |  | 4 | 4 | 1
5 | 2 | 3 | 5 | 3 | 5 | 5 | 5 | 82.5% | 3 | 4 |  | 4 | 4 | 1
1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 60% | 5 | 5 |  | 2 | 1 | 8
3 | 5 | 4 | 5 | 4 | 1 | 1 | 2 | 62.5% | 5 | 5 |  | 4 | 3 | 9
3 | 2 | 3 | 2 | 4 | 1 | 1 | 5 | 52.5% | 3 | 4 |  | 4 | 5 | 3
4 | 2 | 3 | 4 | 1 | 3 | 5 | 3 | 62.5% | 2 | 1 |  | 1 | 5 | 7
5 | 4 | 1 | 5 | 2 | 2 | 2 | 3 | 60% | 1 | 1 |  | 5 | 5 | 3
4 | 2 | 3 | 2 | 4 | 2 | 3 | 2 | 55% | 4 | 5 |  | 2 | 1 | 6
5 | 2 | 4 | 5 | 4 | 2 | 1 | 4 | 67.5% | 3 | 3 |  | 4 | 1 | 6
5 | 2 | 4 | 4 | 2 | 2 | 4 | 2 | 62.5% | 4 | 1 |  | 4 | 1 | 4
4 | 1 | 2 | 5 | 4 | 3 | 3 | 1 | 57.5% | 4 | 1 |  | 3 | 4 | 7
5 | 1 | 3 | 4 | 3 | 1 | 2 | 5 | 60% | 4 | 5 |  | 4 | 2 | 4
5 | 4 | 2 | 3 | 2 | 2 | 4 | 1 | 57.5% | 1 | 1 |  | 2 | 5 | 9
2 | 1 | 4 | 5 | 4 | 2 | 4 | 1 | 57.5% | 2 | 3 |  | 3 | 2 | 3
3 | 2 | 1 | 1 | 2 | 3 | 4 | 5 | 52.5% | 1 | 4 |  | 5 | 2 | 4
5 | 4 | 1 | 4 | 2 | 3 | 3 | 4 | 65% | 5 | 4 |  | 1 | 5 | 2
5 | 3 | 4 | 1 | 5 | 1 | 3 | 3 | 62.5% | 2 | 3 |  | 2 | 3 | 1
1 | 5 | 5 | 3 | 3 | 5 | 4 | 2 | 70% | 2 | 5 |  | 3 | 1 | 2
3 | 3 | 2 | 1 | 3 | 4 | 1 | 3 | 50% | 1 | 2 |  | 3 | 5 | 3
5 | 5 | 2 | 3 | 5 | 4 | 2 | 2 | 70% | 4 | 4 |  | 5 | 1 | 1
2 | 4 | 5 | 4 | 4 | 2 | 2 | 4 | 67.5% | 4 | 1 |  | 2 | 2 | 1
5 | 2 | 2 | 4 | 4 | 2 | 2 | 5 | 65% | 4 | 4 |  | 4 | 4 | 7
1 | 2 | 3 | 2 | 3 | 3 | 1 | 4 | 47.5% | 1 | 5 |  | 1 | 2 | 1
1 | 2 | 4 | 1 | 5 | 4 | 1 | 5 | 57.5% | 4 | 3 |  | 1 | 5 | 9
3 | 2 | 1 | 2 | 4 | 5 | 5 | 3 | 62.5% | 2 | 3 |  | 4 | 4 | 5
3 | 5 | 1 | 1 | 4 | 5 | 1 | 5 | 62.5% | 1 | 2 |  | 3 | 2 | 3
1 | 2 | 3 | 3 | 4 | 3 | 4 | 5 | 62.5% | 2 | 5 |  | 1 | 3 | 6
1 | 5 | 5 | 4 | 2 | 5 | 2 | 4 | 70% | 3 | 2 |  | 4 | 5 | 3
1 | 5 | 4 | 4 | 1 | 2 | 5 | 5 | 67.5% | 1 | 1 |  | 5 | 2 | 2
2 | 4 | 3 | 4 | 2 | 1 | 1 | 2 | 47.5% | 5 | 1 |  | 3 | 3 | 2
4 | 1 | 5 | 4 | 5 | 1 | 4 | 5 | 72.5% | 5 | 2 |  | 5 | 1 | 3
3 | 1 | 1 | 4 | 5 | 3 | 5 | 3 | 62.5% | 2 | 3 |  | 5 | 1 | 3
5 | 2 | 3 | 1 | 4 | 1 | 2 | 5 | 57.5% | 1 | 5 |  | 3 | 2 | 3
5 | 3 | 3 | 2 | 4 | 1 | 3 | 3 | 60% | 3 | 4 |  | 5 | 1 | 2
3 | 2 | 4 | 4 | 5 | 5 | 2 | 4 | 72.5% | 2 | 1 |  | 4 | 2 | 6
5 | 2 | 4 | 2 | 4 | 1 | 5 | 4 | 67.5% | 4 | 2 |  | 3 | 1 | 5
5 | 2 | 4 | 5 | 4 | 5 | 4 | 3 | 80% | 3 | 4 |  | 3 | 4 | 2
4 | 5 | 5 | 4 | 2 | 2 | 1 | 4 | 67.5% | 2 | 3 |  | 4 | 3 | 9
3 | 2 | 2 | 1 | 5 | 2 | 2 | 5 | 55% | 3 | 1 |  | 5 | 4 | 6
3 | 4 | 3 | 2 | 2 | 3 | 1 | 3 | 52.5% | 1 | 2 |  | 3 | 1 | 1
1 | 4 | 2 | 5 | 3 | 5 | 4 | 4 | 70% | 3 | 5 |  | 4 | 5 | 3
1 | 2 | 2 | 4 | 5 | 2 | 3 | 4 | 57.5% | 4 | 1 |  | 1 | 5 | 6
2 | 4 | 3 | 2 | 5 | 1 | 2 | 1 | 50% | 5 | 4 |  | 1 | 1 | 9
1 | 1 | 4 | 1 | 5 | 5 | 1 | 4 | 55% | 3 | 2 |  | 2 | 3 | 8
1 | 5 | 4 | 5 | 1 | 5 | 3 | 4 | 70% | 4 | 2 |  | 1 | 1 | 6
3 | 3 | 3 | 3 | 4 | 4 | 2 | 1 | 57.5% | 5 | 1 |  | 2 | 5 | 2
1 | 2 | 3 | 4 | 4 | 1 | 5 | 3 | 57.5% | 5 | 4 |  | 3 | 5 | 3
4 | 1 | 4 | 4 | 2 | 2 | 3 | 1 | 52.5% | 1 | 2 |  | 4 | 5 | 5
2 | 2 | 4 | 1 | 4 | 2 | 1 | 2 | 45% | 3 | 1 |  | 1 | 3 | 3
1 | 3 | 5 | 4 | 4 | 3 | 3 | 1 | 60% | 3 | 2 |  | 3 | 5 | 8
1 | 3 | 3 | 5 | 3 | 2 | 4 | 5 | 65% | 3 | 1 |  | 5 | 3 | 3
4 | 4 | 4 | 3 | 5 | 5 | 2 | 1 | 70% | 3 | 2 |  | 3 | 2 | 5
3 | 3 | 5 | 2 | 4 | 3 | 2 | 5 | 67.5% | 4 | 3 |  | 2 | 4 | 5
2 | 2 | 5 | 1 | 4 | 4 | 5 | 1 | 60% | 2 | 1 |  | 5 | 5 | 5
1 | 2 | 2 | 1 | 2 | 2 | 2 | 5 | 42.5% | 3 | 1 |  | 5 | 1 | 3
5 | 4 | 5 | 3 | 5 | 4 | 3 | 1 | 75% | 2 | 1 |  | 2 | 1 | 8
4 | 2 | 1 | 1 | 5 | 5 | 1 | 2 | 52.5% | 5 | 3 |  | 3 | 1 | 5
2 | 4 | 1 | 2 | 3 | 4 | 2 | 3 | 52.5% | 2 | 4 |  | 2 | 2 | 7
4 | 4 | 4 | 3 | 2 | 5 | 4 | 3 | 72.5% | 4 | 2 |  | 2 | 4 | 9
1 | 5 | 5 | 3 | 1 | 3 | 4 | 4 | 65% | 2 | 5 |  | 2 | 5 | 2
5 | 4 | 2 | 3 | 5 | 5 | 1 | 4 | 72.5% | 4 | 2 |  | 3 | 5 | 1
4 | 5 | 1 | 4 | 1 | 1 | 4 | 1 | 52.5% | 5 | 1 |  | 3 | 1 | 4
4 | 5 | 4 | 1 | 5 | 4 | 2 | 1 | 65% | 3 | 5 |  | 5 | 2 | 8
5 | 2 | 4 | 4 | 1 | 5 | 1 | 5 | 67.5% | 4 | 4 |  | 1 | 3 | 6
5 | 1 | 4 | 1 | 1 | 1 | 1 | 2 | 40% | 1 | 1 |  | 3 | 2 | 5
2 | 5 | 3 | 1 | 3 | 5 | 1 | 3 | 57.5% | 5 | 3 |  | 2 | 4 | 4
2 | 3 | 2 | 2 | 4 | 2 | 1 | 4 | 50% | 3 | 1 |  | 4 | 4 | 1
5 | 3 | 5 | 1 | 2 | 3 | 3 | 3 | 62.5% | 4 | 1 |  | 4 | 2 | 2
5 | 5 | 4 | 1 | 5 | 3 | 3 | 5 | 77.5% | 1 | 5 |  | 3 | 3 | 7
5 | 2 | 1 | 4 | 4 | 3 | 2 | 3 | 60% | 1 | 4 |  | 5 | 4 | 1
1 | 2 | 3 | 5 | 2 | 3 | 1 | 3 | 50% | 1 | 1 |  | 2 | 1 | 1
5 | 1 | 1 | 4 | 2 | 4 | 3 | 2 | 55% | 1 | 5 |  | 3 | 5 | 2
2 | 5 | 4 | 4 | 4 | 1 | 4 | 4 | 70% | 2 | 5 |  | 4 | 2 | 4
3 | 4 | 5 | 2 | 4 | 3 | 3 | 5 | 72.5% | 1 | 4 |  | 2 | 2 | 9
5 | 3 | 3 | 2 | 4 | 1 | 3 | 1 | 55% | 1 | 5 |  | 5 | 1 | 6
5 | 1 | 3 | 5 | 4 | 3 | 2 | 3 | 65% | 3 | 5 |  | 1 | 3 | 5
2 | 5 | 2 | 4 | 5 | 1 | 5 | 4 | 70% | 2 | 3 |  | 1 | 2 | 5
3 | 2 | 4 | 3 | 2 | 1 | 3 | 3 | 52.5% | 4 | 5 |  | 5 | 5 | 3
3 | 3 | 1 | 5 | 1 | 3 | 3 | 3 | 55% | 2 | 1 |  | 5 | 4 | 5
3 | 3 | 5 | 3 | 1 | 1 | 2 | 2 | 50% | 3 | 2 |  | 5 | 2 | 3
5 | 5 | 3 | 4 | 1 | 1 | 3 | 4 | 65% | 5 | 3 |  | 4 | 1 | 6
2 | 4 | 3 | 2 | 4 | 2 | 5 | 1 | 57.5% | 3 | 4 |  | 3 | 1 | 3
4 | 3 | 1 | 4 | 4 | 1 | 5 | 3 | 62.5% | 4 | 3 |  | 4 | 4 | 1
3 | 5 | 4 | 1 | 2 | 5 | 2 | 1 | 57.5% | 3 | 3 |  | 1 | 4 | 3
1 | 1 | 5 | 5 | 5 | 3 | 1 | 5 | 65% | 2 | 3 |  | 1 | 1 | 7
3 | 2 | 1 | 1 | 3 | 2 | 5 | 5 | 55% | 4 | 5 |  | 2 | 5 | 4
2 | 1 | 5 | 3 | 4 | 5 | 1 | 2 | 57.5% | 3 | 4 |  | 2 | 1 | 3
1 | 3 | 4 | 1 | 3 | 1 | 1 | 2 | 40% | 2 | 3 |  | 5 | 1 | 2
3 | 5 | 2 | 4 | 3 | 2 | 4 | 4 | 67.5% | 4 | 3 |  | 2 | 1 | 8
5 | 2 | 4 | 2 | 1 | 4 | 1 | 4 | 57.5% | 2 | 3 |  | 4 | 4 | 1
3 | 3 | 5 | 3 | 5 | 2 | 4 | 5 | 75% | 1 | 4 |  | 4 | 1 | 8
1 | 5 | 4 | 4 | 2 | 4 | 5 | 5 | 75% | 2 | 1 |  | 3 | 1 | 4
4 | 3 | 2 | 1 | 2 | 4 | 3 | 1 | 50% | 4 | 4 |  | 1 | 4 | 6
1 | 2 | 3 | 4 | 3 | 3 | 3 | 5 | 60% | 2 | 5 |  | 5 | 5 | 1
4 | 5 | 1 | 2 | 1 | 5 | 3 | 3 | 60% | 4 | 2 |  | 5 | 1 | 9
5 | 1 | 3 | 3 | 1 | 1 | 4 | 2 | 50% | 3 | 5 |  | 2 | 1 | 5
4 | 1 | 2 | 2 | 5 | 2 | 4 | 3 | 57.5% | 5 | 2 |  | 2 | 5 | 3
5 | 5 | 1 | 3 | 2 | 5 | 4 | 5 | 75% | 1 | 2 |  | 2 | 1 | 8
3 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 72.5% | 5 | 2 |  | 2 | 4 | 9
3 | 5 | 5 | 4 | 2 | 3 | 3 | 5 | 75% | 1 | 4 |  | 2 | 2 | 4
2 | 3 | 3 | 4 | 5 | 1 | 5 | 3 | 65% | 3 | 2 |  | 4 | 4 | 3
1 | 1 | 1 | 3 | 4 | 3 | 1 | 5 | 47.5% | 5 | 3 |  | 3 | 5 | 5
5 | 3 | 2 | 4 | 2 | 5 | 1 | 5 | 67.5% | 5 | 4 |  | 2 | 4 | 2
2 | 3 | 1 | 5 | 5 | 1 | 4 | 4 | 62.5% | 5 | 3 |  | 2 | 4 | 9
5 | 3 | 1 | 1 | 1 | 3 | 5 | 4 | 57.5% | 1 | 5 |  | 2 | 2 | 4
1 | 3 | 4 | 3 | 1 | 2 | 4 | 4 | 55% | 5 | 1 |  | 3 | 2 | 1
4 | 3 | 5 | 1 | 4 | 3 | 4 | 3 | 67.5% | 4 | 4 |  | 4 | 5 | 4
2 | 5 | 2 | 3 | 3 | 2 | 3 | 2 | 55% | 5 | 2 |  | 1 | 4 | 8
5 | 1 | 1 | 1 | 4 | 1 | 5 | 4 | 55% | 2 | 1 |  | 1 | 3 | 9
4 | 1 | 3 | 2 | 4 | 3 | 4 | 1 | 55% | 4 | 2 |  | 2 | 3 | 4
4 | 2 | 3 | 2 | 2 | 3 | 3 | 2 | 52.5% | 2 | 5 |  | 4 | 3 | 9
4 | 5 | 4 | 2 | 3 | 1 | 3 | 5 | 67.5% | 5 | 4 |  | 2 | 3 | 5
2 | 4 | 1 | 2 | 3 | 4 | 5 | 4 | 62.5% | 4 | 2 |  | 1 | 2 | 4
3 | 1 | 5 | 3 | 3 | 2 | 1 | 4 | 55% | 3 | 1 |  | 2 | 2 | 8
5 | 2 | 5 | 3 | 3 | 1 | 3 | 4 | 65% | 3 | 4 |  | 4 | 3 | 3
3 | 2 | 3 | 1 | 4 | 4 | 3 | 2 | 55% | 1 | 3 |  | 4 | 1 | 1
5 | 1 | 1 | 1 | 4 | 1 | 3 | 2 | 45% | 2 | 3 |  | 2 | 3 | 3
4 | 5 | 1 | 5 | 3 | 1 | 4 | 3 | 65% | 1 | 3 |  | 1 | 4 | 6
3 | 4 | 4 | 5 | 3 | 4 | 3 | 3 | 72.5% | 3 | 3 |  | 2 | 2 | 4
5 | 1 | 3 | 2 | 4 | 2 | 2 | 3 | 55% | 3 | 5 |  | 3 | 3 | 5
3 | 2 | 1 | 2 | 1 | 5 | 2 | 5 | 52.5% | 2 | 1 |  | 1 | 4 | 9
2 | 5 | 5 | 3 | 1 | 1 | 5 | 1 | 57.5% | 4 | 2 |  | 2 | 1 | 9
5 | 3 | 1 | 4 | 3 | 1 | 5 | 5 | 67.5% | 5 | 2 |  | 1 | 5 | 4
5 | 3 | 4 | 4 | 3 | 1 | 4 | 2 | 65% | 3 | 1 |  | 3 | 3 | 2
4 | 2 | 3 | 2 | 3 | 3 | 1 | 1 | 47.5% | 4 | 4 |  | 4 | 4 | 3
4 | 3 | 1 | 1 | 3 | 5 | 2 | 4 | 57.5% | 1 | 5 |  | 1 | 4 | 4
3 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 47.5% | 4 | 5 |  | 4 | 2 | 6
1 | 5 | 2 | 1 | 2 | 2 | 1 | 4 | 45% | 3 | 5 |  | 2 | 3 | 4
1 | 5 | 5 | 4 | 1 | 4 | 3 | 1 | 60% | 1 | 5 |  | 2 | 1 | 8
2 | 3 | 1 | 4 | 3 | 2 | 3 | 1 | 47.5% | 3 | 4 |  | 4 | 1 | 8
4 | 1 | 3 | 4 | 2 | 5 | 3 | 2 | 60% | 1 | 1 |  | 4 | 2 | 6
4 | 1 | 2 | 5 | 4 | 3 | 4 | 2 | 62.5% | 3 | 3 |  | 3 | 4 | 7
3 | 1 | 3 | 3 | 4 | 1 | 3 | 1 | 47.5% | 1 | 5 |  | 5 | 3 | 3
2 | 4 | 2 | 1 | 1 | 4 | 5 | 5 | 60% | 5 | 4 |  | 1 | 2 | 3
1 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 35% | 4 | 1 |  | 5 | 2 | 5
4 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 32.5% | 2 | 4 |  | 3 | 5 | 7
5 | 4 | 2 | 5 | 3 | 3 | 3 | 5 | 75% | 1 | 3 |  | 5 | 2 | 7
2 | 1 | 1 | 4 | 5 | 1 | 1 | 2 | 42.5% | 5 | 1 |  | 1 | 5 | 8
2 | 5 | 5 | 1 | 4 | 5 | 4 | 5 | 77.5% | 3 | 5 |  | 5 | 2 | 9
1 | 4 | 1 | 3 | 3 | 5 | 1 | 5 | 57.5% | 4 | 5 |  | 1 | 3 | 8
1 | 3 | 1 | 2 | 4 | 5 | 4 | 1 | 52.5% | 2 | 4 |  | 5 | 1 | 4
3 | 4 | 4 | 1 | 2 | 1 | 3 | 4 | 55% | 1 | 4 |  | 5 | 1 | 6
3 | 2 | 2 | 2 | 4 | 2 | 4 | 3 | 55% | 4 | 5 |  | 5 | 2 | 6
5 | 2 | 4 | 3 | 3 | 5 | 5 | 5 | 80% | 4 | 5 |  | 1 | 4 | 3
1 | 4 | 1 | 3 | 4 | 2 | 3 | 5 | 57.5% | 2 | 2 |  | 2 | 2 | 4
1 | 1 | 3 | 2 | 3 | 4 | 5 | 3 | 55% | 1 | 3 |  | 5 | 3 | 2
2 | 2 | 1 | 2 | 5 | 3 | 3 | 5 | 57.5% | 5 | 4 |  | 3 | 3 | 2
1 | 5 | 2 | 3 | 2 | 5 | 4 | 5 | 67.5% | 1 | 4 |  | 1 | 2 | 6
5 | 1 | 1 | 3 | 2 | 4 | 5 | 3 | 60% | 5 | 1 |  | 3 | 3 | 9
2 | 1 | 4 | 2 | 1 | 1 | 1 | 4 | 40% | 5 | 1 |  | 5 | 5 | 8
2 | 3 | 4 | 2 | 3 | 4 | 3 | 2 | 57.5% | 4 | 2 |  | 4 | 2 | 5
2 | 2 | 2 | 3 | 2 | 1 | 3 | 4 | 47.5% | 4 | 5 |  | 5 | 3 | 8
3 | 4 | 4 | 2 | 2 | 4 | 2 | 1 | 55% | 2 | 4 |  | 5 | 4 | 5
1 | 4 | 2 | 1 | 5 | 4 | 2 | 3 | 55% | 4 | 4 |  | 4 | 4 | 5
2 | 5 | 5 | 5 | 5 | 2 | 3 | 5 | 80% | 1 | 2 |  | 1 | 3 | 7
3 | 4 | 2 | 1 | 1 | 5 | 3 | 2 | 52.5% | 4 | 4 |  | 5 | 2 | 7
2 | 3 | 1 | 5 | 3 | 4 | 3 | 1 | 55% | 2 | 5 |  | 3 | 5 | 4
1 | 4 | 4 | 4 | 5 | 3 | 5 | 5 | 77.5% | 5 | 1 |  | 4 | 3 | 7
2 | 1 | 4 | 1 | 5 | 3 | 3 | 1 | 50% | 3 | 2 |  | 4 | 3 | 2
5 | 5 | 3 | 5 | 2 | 2 | 3 | 5 | 75% | 5 | 1 |  | 2 | 2 | 7
5 | 1 | 5 | 5 | 2 | 2 | 5 | 3 | 70% | 2 | 2 |  | 2 | 5 | 9
1 | 3 | 1 | 4 | 3 | 4 | 1 | 4 | 52.5% | 4 | 2 |  | 2 | 4 | 5
5 | 4 | 5 | 2 | 5 | 3 | 2 | 2 | 70% | 1 | 1 |  | 5 | 5 | 9
2 | 4 | 2 | 5 | 4 | 4 | 2 | 1 | 60% | 1 | 2 |  | 3 | 5 | 6
4 | 5 | 2 | 4 | 1 | 1 | 2 | 5 | 60% | 1 | 2 |  | 3 | 4 | 6
4 | 4 | 5 | 2 | 1 | 2 | 1 | 4 | 57.5% | 2 | 2 |  | 1 | 1 | 3
3 | 2 | 1 | 1 | 2 | 3 | 2 | 5 | 47.5% | 5 | 4 |  | 5 | 2 | 1
5 | 2 | 1 | 4 | 3 | 4 | 1 | 4 | 60% | 4 | 4 |  | 2 | 5 | 5
1 | 3 | 5 | 2 | 3 | 4 | 5 | 5 | 70% | 1 | 2 |  | 2 | 3 | 4
2 | 5 | 3 | 2 | 5 | 3 | 5 | 4 | 72.5% | 2 | 4 |  | 2 | 2 | 3
2 | 5 | 5 | 1 | 2 | 2 | 5 | 1 | 57.5% | 1 | 3 |  | 4 | 3 | 3
1 | 3 | 3 | 1 | 1 | 5 | 1 | 1 | 40% | 2 | 1 |  | 5 | 1 | 4
5 | 5 | 1 | 2 | 3 | 1 | 3 | 2 | 55% | 4 | 4 |  | 2 | 4 | 6
1 | 1 | 3 | 2 | 4 | 4 | 2 | 2 | 47.5% | 5 | 3 |  | 4 | 4 | 3
3 | 3 | 2 | 2 | 2 | 5 | 1 | 2 | 50% | 4 | 1 |  | 5 | 2 | 2
5 | 3 | 3 | 5 | 5 | 1 | 2 | 3 | 67.5% | 5 | 5 |  | 5 | 5 | 9
1 | 5 | 4 | 3 | 2 | 2 | 3 | 5 | 62.5% | 3 | 2 |  | 1 | 5 | 5
1 | 4 | 3 | 4 | 5 | 2 | 2 | 3 | 60% | 2 | 2 |  | 2 | 1 | 2
1 | 4 | 2 | 5 | 4 | 5 | 3 | 1 | 62.5% | 3 | 5 |  | 3 | 4 | 2
1 | 1 | 4 | 2 | 4 | 2 | 4 | 3 | 52.5% | 4 | 2 |  | 2 | 4 | 1
2 | 2 | 3 | 4 | 3 | 3 | 5 | 2 | 60% | 4 | 1 |  | 5 | 4 | 8
2 | 2 | 1 | 5 | 1 | 2 | 3 | 1 | 42.5% | 2 | 5 |  | 1 | 3 | 4
3 | 5 | 2 | 5 | 1 | 2 | 3 | 4 | 62.5% | 3 | 2 |  | 4 | 1 | 4
3 | 4 | 2 | 2 | 3 | 1 | 3 | 3 | 52.5% | 3 | 5 |  | 2 | 2 | 6
2 | 5 | 5 | 3 | 5 | 3 | 5 | 2 | 75% | 4 | 3 |  | 1 | 4 | 7
4 | 3 | 2 | 4 | 5 | 2 | 3 | 3 | 65% | 1 | 5 |  | 4 | 2 | 9
1 | 4 | 3 | 2 | 4 | 1 | 5 | 3 | 57.5% | 4 | 3 |  | 5 | 2 | 2
5 | 3 | 1 | 3 | 2 | 5 | 3 | 3 | 62.5% | 2 | 2 |  | 5 | 4 | 8
3 | 4 | 2 | 5 | 4 | 3 | 4 | 2 | 67.5% | 3 | 1 |  | 3 | 1 | 1
3 | 4 | 5 | 5 | 5 | 3 | 4 | 5 | 85% | 3 | 3 |  | 4 | 4 | 1
3 | 5 | 2 | 1 | 4 | 4 | 4 | 2 | 62.5% | 4 | 4 |  | 2 | 4 | 7
2 | 2 | 5 | 3 | 4 | 2 | 5 | 2 | 62.5% | 3 | 3 |  | 1 | 1 | 7
1 | 5 | 2 | 1 | 4 | 3 | 4 | 4 | 60% | 1 | 1 |  | 2 | 1 | 8
1 | 1 | 1 | 1 | 4 | 1 | 3 | 1 | 32.5% | 4 | 1 |  | 5 | 1 | 2
5 | 1 | 4 | 5 | 4 | 3 | 2 | 5 | 72.5% | 3 | 4 |  | 5 | 1 | 1
3 | 3 | 5 | 1 | 2 | 2 | 3 | 2 | 52.5% | 2 | 5 |  | 5 | 2 | 9
4 | 4 | 2 | 3 | 5 | 1 | 3 | 1 | 57.5% | 2 | 5 |  | 4 | 3 | 6
5 | 2 | 2 | 5 | 5 | 3 | 4 | 4 | 75% | 1 | 2 |  | 3 | 3 | 8
3 | 2 | 1 | 4 | 1 | 3 | 3 | 4 | 52.5% | 5 | 4 |  | 3 | 5 | 1
2 | 3 | 5 | 2 | 5 | 5 | 4 | 5 | 77.5% | 5 | 3 |  | 3 | 2 | 7
2 | 4 | 3 | 4 | 4 | 1 | 1 | 3 | 55% | 4 | 1 |  | 4 | 4 | 4
3 | 1 | 4 | 5 | 4 | 2 | 2 | 4 | 62.5% | 5 | 4 |  | 4 | 3 | 1
3 | 1 | 5 | 5 | 4 | 5 | 5 | 4 | 80% | 4 | 1 |  | 5 | 3 | 5
2 | 4 | 5 | 5 | 2 | 3 | 1 | 3 | 62.5% | 5 | 3 |  | 4 | 3 | 8
3 | 5 | 3 | 1 | 1 | 4 | 4 | 4 | 62.5% | 5 | 2 |  | 2 | 3 | 4
3 | 4 | 2 | 2 | 2 | 2 | 4 | 4 | 57.5% | 5 | 5 |  | 4 | 5 | 5
4 | 3 | 4 | 4 | 2 | 4 | 5 | 4 | 75% | 1 | 4 |  | 2 | 2 | 2
1 | 3 | 4 | 3 | 3 | 1 | 2 | 3 | 50% | 5 | 5 |  | 2 | 4 | 5
5 | 4 | 5 | 2 | 4 | 3 | 2 | 2 | 67.5% | 3 | 1 |  | 5 | 1 | 5
4 | 2 | 4 | 4 | 3 | 4 | 4 | 2 | 67.5% | 2 | 3 |  | 4 | 5 | 8
3 | 3 | 2 | 5 | 5 | 2 | 3 | 5 | 70% | 2 | 5 |  | 2 | 3 | 4
2 | 4 | 2 | 3 | 1 | 3 | 4 | 3 | 55% | 1 | 2 |  | 3 | 5 | 6
3 | 2 | 4 | 5 | 5 | 1 | 4 | 3 | 67.5% | 1 | 2 |  | 2 | 2 | 8
2 | 5 | 1 | 4 | 1 | 5 | 1 | 5 | 60% | 3 | 4 |  | 4 | 1 | 2
3 | 3 | 1 | 2 | 5 | 5 | 3 | 2 | 60% | 5 | 5 |  | 4 | 3 | 7
2 | 1 | 2 | 5 | 5 | 1 | 1 | 3 | 50% | 4 | 4 |  | 4 | 2 | 6
3 | 3 | 1 | 3 | 5 | 5 | 5 | 3 | 70% | 1 | 1 |  | 5 | 3 | 7
1 | 2 | 2 | 3 | 2 | 3 | 2 | 4 | 47.5% | 5 | 3 |  | 1 | 5 | 7
1 | 3 | 5 | 5 | 4 | 5 | 5 | 3 | 77.5% | 3 | 1 |  | 1 | 4 | 5
4 | 3 | 1 | 4 | 1 | 4 | 2 | 4 | 57.5% | 3 | 2 |  | 3 | 3 | 6
2 | 1 | 1 | 4 | 1 | 4 | 3 | 5 | 52.5% | 5 | 4 |  | 3 | 4 | 2
4 | 5 | 1 | 4 | 2 | 4 | 5 | 1 | 65% | 3 | 5 |  | 4 | 1 | 5
3 | 3 | 1 | 3 | 4 | 3 | 5 | 1 | 57.5% | 2 | 5 |  | 1 | 1 | 6
2 | 1 | 1 | 5 | 3 | 4 | 1 | 1 | 45% | 5 | 3 |  | 1 | 2 | 3
5 | 1 | 3 | 2 | 3 | 3 | 1 | 4 | 55% | 3 | 4 |  | 5 | 5 | 8
1 | 5 | 4 | 4 | 1 | 1 | 3 | 1 | 50% | 4 | 4 |  | 3 | 2 | 7
4 | 3 | 4 | 3 | 2 | 5 | 2 | 5 | 70% | 2 | 3 |  | 1 | 5 | 9
4 | 1 | 2 | 4 | 4 | 5 | 3 | 2 | 62.5% | 1 | 2 |  | 5 | 3 | 4
4 | 2 | 3 | 4 | 4 | 3 | 1 | 3 | 60% | 5 | 3 |  | 3 | 1 | 6
4 | 5 | 1 | 4 | 2 | 4 | 2 | 4 | 65% | 1 | 3 |  | 3 | 1 | 6
5 | 4 | 3 | 4 | 1 | 3 | 2 | 3 | 62.5% | 4 | 5 |  | 3 | 2 | 4
1 | 1 | 3 | 2 | 2 | 4 | 2 | 2 | 42.5% | 1 | 4 |  | 3 | 5 | 9
4 | 3 | 3 | 4 | 5 | 1 | 1 | 3 | 60% | 5 | 5 |  | 5 | 4 | 5
5 | 2 | 4 | 3 | 1 | 1 | 1 | 4 | 52.5% | 3 | 2 |  | 3 | 2 | 6
4 | 3 | 3 | 2 | 4 | 2 | 1 | 4 | 57.5% | 3 | 2 |  | 2 | 5 | 5
4 | 2 | 4 | 4 | 1 | 2 | 4 | 4 | 62.5% | 4 | 3 |  | 2 | 5 | 5
5 | 5 | 5 | 4 | 5 | 2 | 2 | 2 | 75% | 4 | 4 |  | 3 | 4 | 8
3 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 37.5% | 5 | 1 |  | 4 | 5 | 8
5 | 3 | 1 | 3 | 3 | 2 | 1 | 2 | 50% | 2 | 4 |  | 1 | 4 | 1
1 | 3 | 1 | 1 | 1 | 5 | 1 | 1 | 35% | 5 | 5 |  | 1 | 3 | 6
2 | 1 | 4 | 2 | 3 | 5 | 2 | 1 | 50% | 4 | 3 |  | 3 | 5 | 2
5 | 5 | 5 | 4 | 5 | 4 | 3 | 3 | 85% | 4 | 3 |  | 2 | 3 | 8
1 | 4 | 2 | 3 | 1 | 3 | 4 | 3 | 52.5% | 2 | 3 |  | 3 | 5 | 8
4 | 4 | 3 | 5 | 5 | 3 | 4 | 2 | 75% | 3 | 2 |  | 5 | 1 | 4
3 | 3 | 1 | 5 | 4 | 3 | 4 | 5 | 70% | 2 | 3 |  | 2 | 1 | 4
1 | 2 | 2 | 4 | 3 | 4 | 4 | 2 | 55% | 4 | 3 |  | 4 | 1 | 1
4 | 3 | 5 | 5 | 1 | 5 | 5 | 4 | 80% | 2 | 1 |  | 1 | 3 | 5
4 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 42.5% | 4 | 1 |  | 3 | 2 | 5
5 | 4 | 2 | 1 | 4 | 5 | 2 | 1 | 60% | 1 | 3 |  | 2 | 5 | 3
4 | 5 | 4 | 4 | 1 | 3 | 2 | 1 | 60% | 1 | 5 |  | 4 | 4 | 2
3 | 5 | 1 | 4 | 5 | 4 | 3 | 3 | 70% | 5 | 2 |  | 3 | 3 | 2
3 | 3 | 2 | 4 | 3 | 5 | 4 | 5 | 72.5% | 4 | 5 |  | 5 | 4 | 1
2 | 5 | 2 | 3 | 2 | 2 | 1 | 3 | 50% | 1 | 2 |  | 2 | 5 | 7
4 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 57.5% | 1 | 2 |  | 3 | 3 | 5
1 | 2 | 1 | 1 | 3 | 4 | 1 | 3 | 40% | 4 | 3 |  | 5 | 2 | 9
2 | 2 | 5 | 5 | 1 | 5 | 1 | 5 | 65% | 1 | 5 |  | 5 | 3 | 1
1 | 2 | 2 | 3 | 2 | 4 | 3 | 1 | 45% | 1 | 4 |  | 3 | 1 | 8
1 | 4 | 2 | 1 | 5 | 5 | 2 | 2 | 55% | 3 | 4 |  | 3 | 1 | 6
2 | 4 | 2 | 4 | 5 | 2 | 5 | 1 | 62.5% | 4 | 4 |  | 3 | 3 | 8
5 | 2 | 3 | 2 | 4 | 1 | 2 | 5 | 60% | 4 | 5 |  | 4 | 3 | 3
3 | 4 | 3 | 3 | 1 | 5 | 2 | 5 | 65% | 5 | 4 |  | 5 | 1 | 1
2 | 1 | 2 | 5 | 2 | 2 | 4 | 2 | 50% | 3 | 5 |  | 4 | 1 | 2
1 | 2 | 1 | 5 | 1 | 4 | 1 | 3 | 45% | 3 | 3 |  | 1 | 1 | 8
3 | 1 | 4 | 1 | 5 | 5 | 3 | 5 | 67.5% | 3 | 4 |  | 4 | 3 | 8
2 | 5 | 3 | 2 | 4 | 4 | 5 | 3 | 70% | 2 | 3 |  | 2 | 4 | 2
1 | 4 | 1 | 2 | 4 | 3 | 5 | 1 | 52.5% | 3 | 1 |  | 3 | 2 | 7
4 | 4 | 3 | 1 | 4 | 3 | 1 | 4 | 60% | 2 | 2 |  | 3 | 4 | 5
1 | 1 | 2 | 5 | 1 | 3 | 3 | 4 | 50% | 4 | 3 |  | 4 | 5 | 1
4 | 4 | 2 | 3 | 4 | 4 | 1 | 1 | 57.5% | 5 | 4 |  | 5 | 5 | 6
3 | 4 | 3 | 3 | 4 | 2 | 5 | 2 | 65% | 2 | 3 |  | 4 | 4 | 8
5 | 4 | 1 | 1 | 4 | 4 | 4 | 1 | 60% | 4 | 2 |  | 1 | 5 | 8
4 | 5 | 2 | 1 | 4 | 2 | 5 | 5 | 70% | 2 | 2 |  | 1 | 3 | 1
4 | 1 | 2 | 3 | 4 | 5 | 4 | 3 | 65% | 1 | 2 |  | 3 | 4 | 5
5 | 2 | 5 | 3 | 3 | 3 | 3 | 5 | 72.5% | 2 | 2 |  | 5 | 5 | 1
1 | 2 | 1 | 4 | 5 | 1 | 5 | 3 | 55% | 4 | 4 |  | 4 | 1 | 2
4 | 5 | 2 | 1 | 5 | 1 | 4 | 4 | 65% | 2 | 5 |  | 3 | 4 | 8
5 | 1 | 4 | 4 | 5 | 2 | 3 | 5 | 72.5% | 4 | 3 |  | 4 | 5 | 7
2 | 2 | 4 | 2 | 1 | 5 | 5 | 5 | 65% | 3 | 3 |  | 1 | 1 | 1
2 | 2 | 2 | 2 | 1 | 4 | 5 | 1 | 47.5% | 4 | 2 |  | 2 | 5 | 2
4 | 2 | 3 | 5 | 2 | 1 | 2 | 2 | 52.5% | 1 | 5 |  | 4 | 1 | 8
2 | 5 | 4 | 3 | 4 | 3 | 5 | 5 | 77.5% | 4 | 4 |  | 5 | 1 | 7
4 | 2 | 5 | 1 | 2 | 5 | 5 | 3 | 67.5% | 2 | 3 |  | 2 | 1 | 3
3 | 2 | 3 | 2 | 5 | 4 | 5 | 1 | 62.5% | 2 | 4 |  | 4 | 4 | 4
2 | 4 | 5 | 5 | 4 | 4 | 2 | 4 | 75% | 2 | 1 |  | 2 | 5 | 5
1 | 5 | 4 | 1 | 1 | 2 | 5 | 1 | 50% | 1 | 1 |  | 4 | 4 | 8
2 | 3 | 1 | 1 | 3 | 1 | 4 | 4 | 47.5% | 3 | 2 |  | 5 | 3 | 9
5 | 3 | 3 | 4 | 1 | 5 | 2 | 5 | 70% | 2 | 1 |  | 3 | 3 | 3
1 | 2 | 4 | 1 | 1 | 3 | 4 | 5 | 52.5% | 2 | 2 |  | 1 | 2 | 8
3 | 5 | 4 | 1 | 2 | 3 | 1 | 4 | 57.5% | 2 | 2 |  | 3 | 3 | 2
2 | 3 | 3 | 1 | 2 | 2 | 4 | 5 | 55% | 2 | 2 |  | 2 | 1 | 7
3 | 1 | 5 | 5 | 3 | 1 | 1 | 4 | 57.5% | 1 | 1 |  | 4 | 1 | 2
4 | 1 | 4 | 2 | 4 | 1 | 3 | 2 | 52.5% | 4 | 1 |  | 3 | 1 | 6
5 | 5 | 3 | 4 | 4 | 1 | 2 | 2 | 65% | 2 | 4 |  | 3 | 3 | 1
2 | 3 | 3 | 1 | 4 | 5 | 4 | 1 | 57.5% | 3 | 2 |  | 5 | 3 | 6
4 | 3 | 2 | 2 | 1 | 2 | 1 | 5 | 50% | 5 | 5 |  | 3 | 1 | 7
2 | 5 | 5 | 2 | 2 | 4 | 4 | 2 | 65% | 4 | 2 |  | 4 | 5 | 3
5 | 1 | 1 | 1 | 1 | 5 | 5 | 4 | 57.5% | 4 | 4 |  | 3 | 1 | 8
3 | 3 | 5 | 1 | 2 | 5 | 5 | 1 | 62.5% | 1 | 5 |  | 2 | 1 | 3
1 | 2 | 1 | 3 | 5 | 1 | 1 | 1 | 37.5% | 5 | 5 |  | 5 | 5 | 4
2 | 4 | 1 | 5 | 2 | 2 | 5 | 4 | 62.5% | 2 | 5 |  | 3 | 2 | 2
5 | 5 | 1 | 1 | 4 | 4 | 1 | 2 | 57.5% | 2 | 1 |  | 5 | 5 | 8
3 | 2 | 5 | 4 | 4 | 3 | 4 | 4 | 72.5% | 4 | 2 |  | 4 | 1 | 7
3 | 2 | 1 | 3 | 2 | 5 | 5 | 4 | 62.5% | 5 | 1 |  | 2 | 4 | 4
4 | 3 | 1 | 5 | 1 | 1 | 2 | 1 | 45% | 1 | 4 |  | 2 | 4 | 7
3 | 5 | 1 | 1 | 1 | 1 | 4 | 4 | 50% | 1 | 1 |  | 3 | 2 | 6
2 | 4 | 1 | 1 | 3 | 1 | 3 | 1 | 40% | 5 | 1 |  | 1 | 4 | 7
3 | 3 | 3 | 5 | 2 | 3 | 3 | 3 | 62.5% | 5 | 4 |  | 4 | 4 | 2
1 | 3 | 5 | 4 | 3 | 4 | 4 | 1 | 62.5% | 1 | 2 |  | 1 | 4 | 8
4 | 4 | 1 | 3 | 1 | 1 | 4 | 1 | 47.5% | 1 | 5 |  | 3 | 2 | 7
2 | 1 | 5 | 4 | 1 | 2 | 2 | 3 | 50% | 3 | 3 |  | 1 | 2 | 2
4 | 2 | 3 | 1 | 4 | 5 | 2 | 4 | 62.5% | 4 | 3 |  | 3 | 5 | 7
4 | 2 | 3 | 2 | 3 | 2 | 2 | 4 | 55% | 2 | 3 |  | 4 | 1 | 3
1 | 1 | 4 | 1 | 1 | 4 | 4 | 3 | 47.5% | 4 | 2 |  | 5 | 1 | 6
4 | 3 | 1 | 4 | 2 | 2 | 1 | 3 | 50% | 3 | 2 |  | 3 | 1 | 1
4 | 3 | 4 | 1 | 1 | 2 | 3 | 5 | 57.5% | 3 | 5 |  | 4 | 1 | 5
3 | 4 | 3 | 2 | 5 | 4 | 1 | 4 | 65% | 5 | 1 |  | 5 | 5 | 3
2 | 5 | 2 | 1 | 5 | 3 | 3 | 4 | 62.5% | 1 | 1 |  | 2 | 4 | 7
5 | 3 | 5 | 4 | 1 | 2 | 3 | 3 | 65% | 4 | 3 |  | 1 | 4 | 1
1 | 5 | 2 | 2 | 1 | 4 | 2 | 1 | 45% | 4 | 5 |  | 3 | 3 | 7
1 | 4 | 1 | 3 | 3 | 2 | 1 | 5 | 50% | 3 | 2 |  | 5 | 3 | 9
5 | 4 | 1 | 4 | 3 | 2 | 4 | 1 | 60% | 3 | 3 |  | 3 | 4 | 7
3 | 3 | 1 | 4 | 1 | 5 | 2 | 4 | 57.5% | 4 | 2 |  | 3 | 4 | 7
2 | 4 | 5 | 5 | 4 | 2 | 2 | 3 | 67.5% | 4 | 3 |  | 5 | 1 | 9
4 | 2 | 1 | 4 | 5 | 1 | 5 | 3 | 62.5% | 1 | 3 |  | 4 | 5 | 9
1 | 4 | 5 | 3 | 3 | 3 | 1 | 5 | 62.5% | 1 | 4 |  | 5 | 4 | 9
4 | 4 | 4 | 1 | 3 | 3 | 1 | 1 | 52.5% | 3 | 2 |  | 2 | 4 | 9
1 | 3 | 4 | 4 | 5 | 3 | 3 | 4 | 67.5% | 5 | 3 |  | 5 | 2 | 9
2 | 2 | 3 | 1 | 4 | 3 | 3 | 5 | 57.5% | 2 | 2 |  | 4 | 4 | 4
2 | 4 | 4 | 4 | 3 | 2 | 5 | 2 | 65% | 4 | 3 |  | 2 | 4 | 9
3 | 2 | 5 | 5 | 3 | 2 | 1 | 2 | 57.5% | 2 | 5 |  | 4 | 5 | 4
4 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 40% | 5 | 1 |  | 2 | 4 | 9
5 | 3 | 3 | 2 | 4 | 4 | 5 | 4 | 75% | 4 | 5 |  | 5 | 4 | 9
2 | 3 | 5 | 5 | 3 | 5 | 5 | 5 | 82.5% | 3 | 1 |  | 4 | 3 | 6
3 | 4 | 1 | 3 | 1 | 5 | 1 | 4 | 55% | 2 | 5 |  | 4 | 5 | 9
1 | 1 | 5 | 5 | 1 | 5 | 5 | 4 | 67.5% | 5 | 5 |  | 4 | 2 | 9
5 | 3 | 1 | 2 | 3 | 3 | 2 | 5 | 60% | 3 | 5 |  | 1 | 5 | 3
5 | 5 | 1 | 1 | 4 | 3 | 1 | 1 | 52.5% | 2 | 2 |  | 2 | 1 | 3
3 | 5 | 5 | 5 | 3 | 3 | 5 | 2 | 77.5% | 3 | 2 |  | 2 | 3 | 7
1 | 3 | 1 | 5 | 4 | 1 | 1 | 3 | 47.5% | 2 | 3 |  | 2 | 5 | 7
1 | 1 | 4 | 5 | 5 | 2 | 2 | 4 | 60% | 2 | 3 |  | 3 | 1 | 9
3 | 3 | 2 | 5 | 5 | 5 | 3 | 3 | 72.5% | 4 | 3 |  | 2 | 3 | 7
2 | 5 | 5 | 3 | 1 | 4 | 5 | 1 | 65% | 4 | 2 |  | 1 | 2 | 4
5 | 4 | 2 | 5 | 2 | 1 | 5 | 2 | 65% | 4 | 1 |  | 3 | 3 | 5
4 | 3 | 2 | 1 | 4 | 4 | 2 | 4 | 60% | 3 | 4 |  | 4 | 3 | 6
5 | 4 | 3 | 1 | 5 | 1 | 1 | 3 | 57.5% | 5 | 4 |  | 3 | 3 | 8
3 | 1 | 3 | 4 | 3 | 3 | 2 | 3 | 55% | 3 | 3 |  | 1 | 3 | 5
2 | 2 | 1 | 2 | 4 | 3 | 5 | 2 | 52.5% | 5 | 2 |  | 5 | 2 | 8
2 | 5 | 1 | 4 | 3 | 1 | 1 | 1 | 45% | 5 | 5 |  | 4 | 2 | 5
5 | 5 | 1 | 1 | 1 | 3 | 3 | 5 | 60% | 3 | 2 |  | 1 | 2 | 2
1 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 82.5% | 5 | 2 |  | 4 | 4 | 6
3 | 5 | 1 | 2 | 4 | 3 | 2 | 2 | 55% | 4 | 2 |  | 5 | 3 | 4
2 | 2 | 3 | 5 | 3 | 5 | 1 | 1 | 55% | 5 | 1 |  | 1 | 2 | 7
4 | 4 | 2 | 5 | 4 | 5 | 1 | 2 | 67.5% | 5 | 1 |  | 2 | 3 | 4
5 | 1 | 5 | 3 | 4 | 2 | 1 | 4 | 62.5% | 4 | 5 |  | 1 | 2 | 5
3 | 3 | 1 | 3 | 2 | 1 | 5 | 2 | 50% | 4 | 4 |  | 3 | 1 | 7
4 | 4 | 2 | 1 | 4 | 3 | 4 | 5 | 67.5% | 5 | 1 |  | 3 | 3 | 1
4 | 3 | 2 | 5 | 5 | 1 | 3 | 5 | 70% | 4 | 3 |  | 1 | 3 | 6
2 | 1 | 2 | 2 | 2 | 2 | 1 | 3 | 37.5% | 1 | 5 |  | 1 | 4 | 7
5 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 47.5% | 5 | 1 |  | 2 | 4 | 6
4 | 1 | 2 | 4 | 3 | 2 | 2 | 5 | 57.5% | 3 | 4 |  | 4 | 4 | 9
1 | 2 | 3 | 3 | 5 | 2 | 5 | 4 | 62.5% | 4 | 4 |  | 4 | 2 | 4
3 | 1 | 2 | 2 | 4 | 5 | 3 | 2 | 55% | 3 | 5 |  | 4 | 4 | 3
4 | 5 | 2 | 2 | 2 | 1 | 4 | 3 | 57.5% | 3 | 4 |  | 1 | 1 | 3
2 | 1 | 2 | 4 | 4 | 2 | 1 | 4 | 50% | 3 | 2 |  | 5 | 1 | 7
4 | 4 | 5 | 4 | 1 | 4 | 2 | 1 | 62.5% | 4 | 4 |  | 5 | 5 | 9
1 | 1 | 4 | 2 | 2 | 5 | 2 | 3 | 50% | 4 | 5 |  | 1 | 1 | 8
5 | 4 | 3 | 5 | 2 | 4 | 3 | 3 | 72.5% | 2 | 3 |  | 5 | 2 | 5
3 | 1 | 4 | 3 | 1 | 4 | 3 | 4 | 57.5% | 4 | 1 |  | 2 | 5 | 7
4 | 1 | 3 | 4 | 3 | 1 | 2 | 3 | 52.5% | 5 | 3 |  | 5 | 1 | 9
2 | 4 | 1 | 5 | 5 | 1 | 5 | 1 | 60% | 3 | 3 |  | 3 | 1 | 5
4 | 4 | 5 | 2 | 1 | 2 | 2 | 1 | 52.5% | 4 | 2 |  | 4 | 4 | 6
3 | 2 | 5 | 5 | 1 | 4 | 1 | 1 | 55% | 5 | 2 |  | 5 | 2 | 5
5 | 5 | 3 | 4 | 3 | 5 | 1 | 3 | 72.5% | 2 | 3 |  | 1 | 3 | 8
2 | 4 | 2 | 2 | 4 | 4 | 5 | 4 | 67.5% | 1 | 4 |  | 1 | 1 | 8
5 | 4 | 1 | 3 | 4 | 4 | 3 | 1 | 62.5% | 5 | 1 |  | 2 | 2 | 5
3 | 1 | 1 | 3 | 1 | 5 | 1 | 1 | 40% | 4 | 2 |  | 3 | 4 | 3
2 | 5 | 1 | 1 | 2 | 3 | 5 | 1 | 50% | 4 | 4 |  | 4 | 1 | 4
2 | 2 | 3 | 5 | 2 | 5 | 4 | 5 | 70% | 2 | 4 |  | 1 | 1 | 5
2 | 3 | 2 | 5 | 3 | 2 | 2 | 5 | 60% | 1 | 5 |  | 3 | 3 | 4
1 | 2 | 2 | 3 | 1 | 5 | 3 | 4 | 52.5% | 3 | 1 |  | 2 | 2 | 4
3 | 1 | 2 | 1 | 4 | 5 | 5 | 4 | 62.5% | 1 | 1 |  | 2 | 2 | 9
2 | 3 | 5 | 5 | 1 | 5 | 1 | 4 | 65% | 1 | 4 |  | 4 | 4 | 7
4 | 2 | 5 | 1 | 3 | 5 | 5 | 2 | 67.5% | 4 | 1 |  | 3 | 5 | 4
5 | 5 | 3 | 5 | 3 | 1 | 1 | 4 | 67.5% | 4 | 2 |  | 1 | 5 | 6
2 | 3 | 1 | 4 | 5 | 4 | 3 | 5 | 67.5% | 4 | 4 |  | 1 | 1 | 1
3 | 2 | 5 | 1 | 2 | 4 | 3 | 3 | 57.5% | 2 | 3 |  | 2 | 2 | 9
2 | 2 | 3 | 1 | 2 | 2 | 3 | 4 | 47.5% | 5 | 3 |  | 2 | 3 | 8
4 | 5 | 2 | 1 | 4 | 1 | 4 | 2 | 57.5% | 2 | 3 |  | 4 | 4 | 9
2 | 4 | 1 | 1 | 4 | 1 | 3 | 4 | 50% | 1 | 2 |  | 5 | 4 | 8
5 | 5 | 5 | 3 | 1 | 1 | 4 | 2 | 65% | 1 | 4 |  | 5 | 5 | 3
2 | 1 | 3 | 4 | 1 | 4 | 1 | 4 | 50% | 4 | 5 |  | 5 | 5 | 2
2 | 5 | 5 | 4 | 2 | 4 | 3 | 1 | 65% | 3 | 3 |  | 1 | 2 | 1
2 | 3 | 2 | 2 | 5 | 4 | 3 | 1 | 55% | 3 | 4 |  | 3 | 5 | 6
4 | 5 | 5 | 5 | 5 | 3 | 3 | 1 | 77.5% | 5 | 5 |  | 4 | 3 | 7
2 | 2 | 4 | 5 | 1 | 5 | 3 | 5 | 67.5% | 2 | 4 |  | 2 | 5 | 7
3 | 5 | 1 | 3 | 4 | 4 | 2 | 4 | 65% | 5 | 4 |  | 2 | 2 | 5
3 | 4 | 5 | 5 | 5 | 2 | 3 | 1 | 70% | 4 | 4 |  | 2 | 3 | 8
3 | 1 | 5 | 2 | 3 | 4 | 5 | 5 | 70% | 4 | 5 |  | 3 | 2 | 2
5 | 4 | 1 | 3 | 3 | 1 | 4 | 5 | 65% | 2 | 1 |  | 5 | 2 | 7
3 | 4 | 5 | 3 | 2 | 3 | 5 | 5 | 75% | 1 | 1 |  | 3 | 1 | 1
3 | 3 | 5 | 5 | 4 | 3 | 2 | 3 | 70% | 4 | 1 |  | 1 | 5 | 5
5 | 3 | 3 | 1 | 2 | 2 | 3 | 2 | 52.5% | 2 | 4 |  | 4 | 2 | 3
5 | 4 | 4 | 1 | 2 | 2 | 3 | 4 | 62.5% | 3 | 4 |  | 1 | 1 | 4
5 | 5 | 1 | 2 | 1 | 2 | 3 | 5 | 60% | 5 | 3 |  | 2 | 5 | 6
5 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 55% | 2 | 1 |  | 4 | 3 | 1
3 | 5 | 4 | 2 | 5 | 1 | 5 | 4 | 72.5% | 2 | 2 |  | 2 | 3 | 6
5 | 4 | 5 | 5 | 1 | 5 | 4 | 3 | 80% | 4 | 3 |  | 4 | 5 | 4
4 | 4 | 4 | 5 | 5 | 5 | 2 | 4 | 82.5% | 2 | 5 |  | 2 | 4 | 8
1 | 4 | 3 | 1 | 4 | 5 | 4 | 2 | 60% | 1 | 1 |  | 1 | 4 | 1
4 | 2 | 3 | 4 | 2 | 1 | 2 | 3 | 52.5% | 5 | 5 |  | 3 | 2 | 2
5 | 5 | 1 | 2 | 5 | 1 | 3 | 2 | 60% | 3 | 2 |  | 3 | 1 | 7
5 | 1 | 1 | 4 | 2 | 2 | 2 | 4 | 52.5% | 5 | 3 |  | 2 | 3 | 6
4 | 4 | 3 | 5 | 2 | 4 | 4 | 3 | 72.5% | 1 | 1 |  | 1 | 4 | 1
5 | 2 | 1 | 5 | 2 | 3 | 3 | 4 | 62.5% | 5 | 4 |  | 2 | 5 | 4
5 | 1 | 4 | 4 | 5 | 2 | 5 | 5 | 77.5% | 4 | 4 |  | 4 | 5 | 7
2 | 3 | 5 | 5 | 5 | 2 | 5 | 3 | 75% | 3 | 3 |  | 1 | 3 | 9
2 | 1 | 3 | 3 | 5 | 2 | 5 | 2 | 57.5% | 2 | 3 |  | 4 | 4 | 9
4 | 5 | 5 | 3 | 2 | 1 | 1 | 1 | 55% | 4 | 5 |  | 3 | 3 | 8
1 | 4 | 5 | 5 | 2 | 4 | 1 | 4 | 65% | 2 | 3 |  | 5 | 2 | 2
2 | 1 | 5 | 5 | 2 | 1 | 2 | 4 | 55% | 1 | 3 |  | 4 | 4 | 6
3 | 2 | 5 | 4 | 5 | 3 | 2 | 1 | 62.5% | 4 | 3 |  | 1 | 3 | 4
3 | 3 | 2 | 5 | 5 | 3 | 4 | 4 | 72.5% | 3 | 5 |  | 2 | 1 | 1
1 | 4 | 1 | 5 | 3 | 1 | 3 | 2 | 50% | 4 | 4 |  | 3 | 4 | 2
2 | 3 | 5 | 4 | 3 | 3 | 4 | 3 | 67.5% | 5 | 2 |  | 4 | 1 | 2
4 | 5 | 1 | 4 | 1 | 4 | 5 | 1 | 62.5% | 2 | 4 |  | 4 | 3 | 8
4 | 5 | 3 | 4 | 3 | 3 | 3 | 4 | 72.5% | 5 | 2 |  | 3 | 5 | 9
3 | 1 | 5 | 3 | 4 | 5 | 2 | 4 | 67.5% | 5 | 5 |  | 1 | 3 | 3
1 | 1 | 1 | 4 | 2 | 1 | 3 | 4 | 42.5% | 2 | 1 |  | 1 | 1 | 1
3 | 3 | 2 | 2 | 5 | 3 | 4 | 5 | 67.5% | 2 | 5 |  | 3 | 3 | 8
5 | 3 | 2 | 1 | 4 | 1 | 1 | 3 | 50% | 1 | 5 |  | 2 | 2 | 9
1 | 4 | 4 | 1 | 5 | 3 | 2 | 4 | 60% | 2 | 5 |  | 1 | 5 | 6
5 | 5 | 3 | 5 | 5 | 4 | 3 | 2 | 80% | 2 | 3 |  | 3 | 1 | 7
1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 27.5% | 3 | 5 |  | 3 | 4 | 9
3 | 4 | 3 | 2 | 3 | 3 | 1 | 4 | 57.5% | 1 | 2 |  | 1 | 3 | 8
3 | 3 | 2 | 4 | 2 | 3 | 2 | 5 | 60% | 5 | 4 |  | 3 | 4 | 7
1 | 3 | 3 | 4 | 4 | 4 | 3 | 2 | 60% | 1 | 3 |  | 3 | 3 | 7
5 | 1 | 5 | 5 | 1 | 4 | 1 | 1 | 57.5% | 5 | 3 |  | 4 | 3 | 5
3 | 4 | 5 | 2 | 5 | 5 | 1 | 5 | 75% | 1 | 5 |  | 1 | 4 | 5
5 | 5 | 2 | 5 | 4 | 5 | 5 | 2 | 82.5% | 4 | 3 |  | 5 | 1 | 7
1 | 1 | 5 | 5 | 4 | 5 | 5 | 2 | 70% | 4 | 2 |  | 4 | 1 | 2
1 | 4 | 3 | 1 | 5 | 2 | 5 | 3 | 60% | 2 | 3 |  | 3 | 4 | 2
4 | 1 | 3 | 5 | 2 | 1 | 3 | 4 | 57.5% | 5 | 3 |  | 2 | 1 | 6
1 | 2 | 2 | 4 | 2 | 1 | 2 | 3 | 42.5% | 1 | 1 |  | 4 | 1 | 3
2 | 2 | 5 | 1 | 1 | 3 | 2 | 4 | 50% | 2 | 2 |  | 3 | 1 | 3
3 | 4 | 4 | 1 | 1 | 2 | 5 | 3 | 57.5% | 2 | 4 |  | 4 | 5 | 8
3 | 4 | 4 | 1 | 3 | 2 | 4 | 5 | 65% | 4 | 2 |  | 4 | 4 | 5
2 | 2 | 4 | 4 | 1 | 2 | 2 | 5 | 55% | 1 | 3 |  | 3 | 4 | 9
3 | 3 | 1 | 4 | 5 | 5 | 4 | 4 | 72.5% | 5 | 2 |  | 5 | 1 | 3
4 | 4 | 5 | 4 | 3 | 3 | 4 | 2 | 72.5% | 2 | 3 |  | 1 | 5 | 4
4 | 3 | 3 | 3 | 5 | 4 | 5 | 5 | 80% | 3 | 2 |  | 2 | 5 | 4
1 | 5 | 5 | 3 | 5 | 3 | 5 | 1 | 70% | 3 | 1 |  | 4 | 3 | 7
3 | 3 | 3 | 2 | 3 | 4 | 4 | 1 | 57.5% | 5 | 2 |  | 1 | 5 | 3
2 | 3 | 1 | 3 | 2 | 5 | 2 | 1 | 47.5% | 1 | 1 |  | 4 | 5 | 7
1 | 5 | 1 | 1 | 5 | 4 | 5 | 5 | 67.5% | 1 | 1 |  | 2 | 4 | 9
1 | 2 | 1 | 5 | 1 | 2 | 4 | 2 | 45% | 2 | 2 |  | 2 | 1 | 3
5 | 2 | 3 | 5 | 4 | 1 | 3 | 3 | 65% | 3 | 3 |  | 1 | 5 | 6
5 | 1 | 4 | 3 | 3 | 1 | 3 | 1 | 52.5% | 4 | 5 |  | 5 | 3 | 1
1 | 1 | 2 | 5 | 4 | 4 | 1 | 1 | 47.5% | 3 | 1 |  | 4 | 3 | 5
4 | 5 | 2 | 4 | 3 | 3 | 4 | 5 | 75% | 2 | 3 |  | 2 | 3 | 2
1 | 4 | 4 | 2 | 2 | 4 | 5 | 5 | 67.5% | 4 | 1 |  | 1 | 4 | 9
1 | 4 | 4 | 4 | 2 | 3 | 5 | 1 | 60% | 3 | 4 |  | 1 | 5 | 5
5 | 1 | 3 | 2 | 5 | 3 | 4 | 4 | 67.5% | 4 | 3 |  | 4 | 5 | 1
2 | 2 | 2 | 2 | 3 | 4 | 5 | 4 | 60% | 4 | 1 |  | 2 | 3 | 4
5 | 5 | 3 | 1 | 2 | 5 | 5 | 1 | 67.5% | 2 | 1 |  | 5 | 5 | 8
3 | 3 | 2 | 3 | 2 | 4 | 1 | 1 | 47.5% | 5 | 1 |  | 1 | 4 | 2
4 | 3 | 2 | 1 | 5 | 2 | 2 | 1 | 50% | 3 | 1 |  | 2 | 4 | 4
4 | 4 | 2 | 3 | 2 | 5 | 3 | 2 | 62.5% | 5 | 1 |  | 3 | 1 | 6
5 | 3 | 4 | 3 | 4 | 1 | 5 | 5 | 75% | 3 | 1 |  | 4 | 1 | 5
2 | 3 | 3 | 5 | 3 | 4 | 5 | 5 | 75% | 5 | 4 |  | 1 | 2 | 8
1 | 3 | 1 | 2 | 4 | 4 | 2 | 1 | 45% | 5 | 5 |  | 1 | 3 | 3
3 | 2 | 5 | 4 | 5 | 2 | 3 | 3 | 67.5% | 5 | 4 |  | 1 | 3 | 5
4 | 3 | 5 | 4 | 2 | 1 | 3 | 5 | 67.5% | 2 | 5 |  | 5 | 5 | 5
5 | 4 | 1 | 5 | 4 | 5 | 3 | 5 | 80% | 1 | 1 |  | 1 | 2 | 7
5 | 2 | 3 | 1 | 2 | 1 | 4 | 3 | 52.5% | 5 | 2 |  | 4 | 3 | 2
1 | 3 | 2 | 4 | 3 | 4 | 1 | 1 | 47.5% | 2 | 3 |  | 1 | 5 | 4
1 | 3 | 2 | 2 | 5 | 1 | 5 | 2 | 52.5% | 3 | 4 |  | 3 | 4 | 8
4 | 4 | 5 | 4 | 3 | 4 | 4 | 2 | 75% | 2 | 4 |  | 2 | 2 | 3
5 | 3 | 4 | 1 | 4 | 5 | 3 | 3 | 70% | 4 | 3 |  | 1 | 5 | 7
1 | 2 | 4 | 3 | 2 | 4 | 3 | 4 | 57.5% | 4 | 5 |  | 3 | 1 | 9
2 | 5 | 4 | 3 | 2 | 1 | 2 | 2 | 52.5% | 3 | 2 |  | 2 | 4 | 5
5 | 4 | 3 | 4 | 5 | 1 | 2 | 4 | 70% | 3 | 3 |  | 2 | 4 | 6
3 | 5 | 2 | 4 | 1 | 1 | 4 | 1 | 52.5% | 2 | 2 |  | 2 | 2 | 6
1 | 4 | 3 | 5 | 5 | 2 | 3 | 5 | 70% | 1 | 2 |  | 5 | 2 | 4
1 | 2 | 2 | 5 | 1 | 2 | 2 | 1 | 40% | 5 | 4 |  | 1 | 5 | 4
5 | 2 | 2 | 5 | 1 | 2 | 1 | 2 | 50% | 5 | 1 |  | 3 | 3 | 3
3 | 4 | 2 | 5 | 3 | 1 | 4 | 3 | 62.5% | 3 | 5 |  | 5 | 3 | 3
2 | 4 | 5 | 3 | 3 | 4 | 2 | 5 | 70% | 2 | 2 |  | 4 | 3 | 3
5 | 1 | 5 | 5 | 5 | 1 | 2 | 5 | 72.5% | 3 | 1 |  | 4 | 1 | 6
5 | 2 | 4 | 1 | 1 | 4 | 4 | 4 | 62.5% | 5 | 2 |  | 2 | 4 | 6
2 | 5 | 4 | 5 | 4 | 1 | 1 | 4 | 65% | 2 | 3 |  | 3 | 1 | 2
3 | 2 | 4 | 4 | 4 | 2 | 5 | 5 | 72.5% | 5 | 3 |  | 3 | 2 | 1
2 | 3 | 5 | 2 | 2 | 4 | 2 | 2 | 55% | 1 | 1 |  | 3 | 3 | 6
3 | 5 | 4 | 1 | 1 | 5 | 2 | 2 | 57.5% | 3 | 4 |  | 1 | 4 | 9
1 | 3 | 5 | 2 | 4 | 3 | 3 | 1 | 55% | 3 | 2 |  | 5 | 5 | 9
4 | 3 | 3 | 2 | 2 | 4 | 1 | 5 | 60% | 1 | 4 |  | 2 | 4 | 6
5 | 2 | 1 | 5 | 2 | 3 | 2 | 4 | 60% | 5 | 2 |  | 4 | 2 | 2
3 | 5 | 2 | 2 | 3 | 4 | 5 | 4 | 70% | 4 | 3 |  | 4 | 3 | 9
2 | 4 | 2 | 2 | 5 | 3 | 5 | 3 | 65% | 4 | 3 |  | 5 | 1 | 5
3 | 5 | 2 | 1 | 3 | 5 | 3 | 2 | 60% | 3 | 3 |  | 3 | 2 | 1
4 | 1 | 4 | 5 | 5 | 3 | 4 | 2 | 70% | 3 | 2 |  | 2 | 2 | 1
1 | 5 | 3 | 4 | 4 | 5 | 1 | 2 | 62.5% | 3 | 1 |  | 1 | 2 | 8
5 | 1 | 5 | 5 | 4 | 2 | 4 | 1 | 67.5% | 2 | 3 |  | 4 | 2 | 9
1 | 5 | 5 | 5 | 1 | 5 | 2 | 5 | 72.5% | 5 | 5 |  | 3 | 2 | 3
1 | 3 | 2 | 1 | 5 | 5 | 2 | 1 | 50% | 3 | 3 |  | 4 | 1 | 7
3 | 1 | 1 | 5 | 4 | 3 | 5 | 1 | 57.5% | 2 | 5 |  | 1 | 4 | 3
1 | 3 | 5 | 2 | 2 | 1 | 2 | 1 | 42.5% | 2 | 2 |  | 1 | 4 | 6
3 | 2 | 3 | 4 | 4 | 5 | 4 | 4 | 72.5% | 4 | 1 |  | 5 | 1 | 6
5 | 3 | 5 | 2 | 4 | 5 | 5 | 4 | 82.5% | 2 | 3 |  | 4 | 5 | 4
5 | 1 | 5 | 3 | 3 | 2 | 1 | 4 | 60% | 1 | 5 |  | 3 | 4 | 7
2 | 5 | 4 | 2 | 1 | 3 | 5 | 5 | 67.5% | 5 | 1 |  | 3 | 5 | 4
2 | 4 | 4 | 4 | 4 | 2 | 3 | 2 | 62.5% | 2 | 5 |  | 3 | 1 | 9
3 | 1 | 4 | 3 | 1 | 5 | 4 | 4 | 62.5% | 4 | 2 |  | 3 | 2 | 3
3 | 4 | 5 | 1 | 2 | 1 | 5 | 5 | 65% | 2 | 5 |  | 5 | 1 | 4
2 | 2 | 2 | 3 | 1 | 4 | 5 | 4 | 57.5% | 3 | 4 |  | 1 | 4 | 2
4 | 1 | 4 | 1 | 1 | 3 | 1 | 2 | 42.5% | 4 | 3 |  | 3 | 1 | 1
3 | 1 | 4 | 3 | 3 | 3 | 4 | 3 | 60% | 1 | 1 |  | 4 | 3 | 6
1 | 2 | 5 | 4 | 2 | 1 | 2 | 1 | 45% | 1 | 5 |  | 4 | 4 | 3
3 | 5 | 4 | 2 | 1 | 2 | 4 | 1 | 55% | 4 | 3 |  | 4 | 4 | 1
4 | 5 | 2 | 3 | 5 | 3 | 5 | 1 | 70% | 5 | 4 |  | 2 | 2 | 1
2 | 4 | 1 | 3 | 3 | 3 | 3 | 2 | 52.5% | 3 | 5 |  | 4 | 1 | 7
1 | 3 | 4 | 5 | 5 | 1 | 4 | 1 | 60% | 2 | 4 |  | 3 | 5 | 1
4 | 5 | 2 | 5 | 1 | 3 | 5 | 3 | 70% | 4 | 5 |  | 2 | 1 | 9
4 | 4 | 1 | 5 | 5 | 4 | 3 | 5 | 77.5% | 5 | 4 |  | 4 | 5 | 5
5 | 2 | 2 | 4 | 4 | 5 | 4 | 5 | 77.5% | 5 | 2 |  | 5 | 1 | 3
4 | 1 | 2 | 3 | 2 | 1 | 3 | 4 | 50% | 3 | 5 |  | 4 | 2 | 6
3 | 1 | 5 | 1 | 5 | 2 | 1 | 3 | 52.5% | 5 | 3 |  | 5 | 5 | 3
2 | 1 | 4 | 3 | 4 | 3 | 4 | 4 | 62.5% | 4 | 5 |  | 3 | 3 | 2
1 | 4 | 1 | 2 | 1 | 3 | 1 | 2 | 37.5% | 4 | 1 |  | 4 | 2 | 6
3 | 4 | 4 | 3 | 2 | 4 | 5 | 2 | 67.5% | 5 | 5 |  | 4 | 4 | 3
5 | 3 | 5 | 2 | 1 | 1 | 2 | 4 | 57.5% | 3 | 5 |  | 4 | 4 | 5
4 | 1 | 4 | 5 | 3 | 5 | 2 | 1 | 62.5% | 5 | 5 |  | 1 | 1 | 3
5 | 5 | 3 | 2 | 4 | 2 | 2 | 4 | 67.5% | 5 | 1 |  | 1 | 2 | 2
5 | 2 | 2 | 4 | 2 | 2 | 3 | 3 | 57.5% | 4 | 1 |  | 1 | 4 | 6
1 | 2 | 4 | 2 | 2 | 5 | 4 | 4 | 60% | 5 | 5 |  | 2 | 2 | 5
4 | 4 | 1 | 2 | 1 | 3 | 4 | 2 | 52.5% | 3 | 1 |  | 3 | 5 | 2
4 | 1 | 1 | 5 | 1 | 3 | 2 | 2 | 47.5% | 3 | 3 |  | 2 | 2 | 9
3 | 4 | 5 | 5 | 3 | 1 | 1 | 3 | 62.5% | 1 | 5 |  | 1 | 2 | 6
4 | 2 | 2 | 4 | 2 | 2 | 5 | 1 | 55% | 2 | 3 |  | 3 | 4 | 1
5 | 2 | 5 | 2 | 4 | 4 | 5 | 2 | 72.5% | 5 | 2 |  | 3 | 1 | 5
3 | 1 | 4 | 4 | 3 | 1 | 1 | 1 | 45% | 4 | 3 |  | 3 | 4 | 6
3 | 3 | 2 | 2 | 1 | 2 | 3 | 2 | 45% | 2 | 2 |  | 2 | 3 | 9
4 | 3 | 1 | 5 | 1 | 4 | 3 | 1 | 55% | 5 | 1 |  | 3 | 1 | 8
3 | 3 | 3 | 5 | 4 | 2 | 2 | 4 | 65% | 5 | 1 |  | 3 | 5 | 6
2 | 2 | 4 | 1 | 2 | 1 | 1 | 2 | 37.5% | 3 | 5 |  | 1 | 1 | 2
5 | 4 | 3 | 5 | 5 | 5 | 5 | 4 | 90% | 4 | 1 |  | 5 | 5 | 9
2 | 3 | 3 | 3 | 4 | 1 | 1 | 4 | 52.5% | 5 | 2 |  | 2 | 1 | 5
5 | 2 | 1 | 2 | 4 | 1 | 1 | 3 | 47.5% | 4 | 4 |  | 1 | 2 | 3
3 | 4 | 2 | 5 | 3 | 4 | 4 | 1 | 65% | 4 | 3 |  | 1 | 5 | 8
5 | 1 | 4 | 4 | 1 | 1 | 3 | 1 | 50% | 2 | 4 |  | 3 | 4 | 9
4 | 3 | 4 | 5 | 4 | 3 | 4 | 3 | 75% | 4 | 3 |  | 4 | 2 | 5
4 | 1 | 5 | 4 | 5 | 2 | 1 | 5 | 67.5% | 4 | 3 |  | 4 | 1 | 5
1 | 4 | 2 | 1 | 2 | 4 | 5 | 4 | 57.5% | 2 | 3 |  | 2 | 2 | 5
3 | 1 | 2 | 3 | 2 | 1 | 5 | 3 | 50% | 2 | 4 |  | 3 | 5 | 3
2 | 3 | 2 | 2 | 1 | 4 | 3 | 3 | 50% | 1 | 2 |  | 2 | 4 | 8
1 | 4 | 5 | 5 | 5 | 3 | 5 | 2 | 75% | 3 | 3 |  | 5 | 1 | 5
1 | 5 | 3 | 4 | 3 | 5 | 5 | 4 | 75% | 2 | 5 |  | 5 | 4 | 7
2 | 1 | 3 | 5 | 4 | 3 | 1 | 5 | 60% | 1 | 2 |  | 3 | 1 | 2
2 | 5 | 4 | 3 | 1 | 4 | 1 | 3 | 57.5% | 5 | 5 |  | 3 | 3 | 2
5 | 5 | 1 | 4 | 3 | 3 | 2 | 4 | 67.5% | 1 | 5 |  | 5 | 4 | 1
2 | 5 | 1 | 2 | 4 | 4 | 4 | 5 | 67.5% | 1 | 4 |  | 3 | 2 | 4
3 | 5 | 1 | 1 | 3 | 1 | 2 | 4 | 50% | 5 | 3 |  | 1 | 1 | 8
5 | 1 | 4 | 2 | 1 | 2 | 3 | 5 | 57.5% | 4 | 3 |  | 3 | 1 | 6
1 | 3 | 5 | 2 | 4 | 1 | 5 | 5 | 65% | 5 | 4 |  | 3 | 2 | 5
4 | 1 | 3 | 1 | 3 | 4 | 2 | 4 | 55% | 5 | 4 |  | 4 | 5 | 4
1 | 1 | 1 | 1 | 2 | 3 | 5 | 1 | 37.5% | 2 | 3 |  | 3 | 5 | 1
3 | 5 | 3 | 1 | 5 | 4 | 3 | 2 | 65% | 4 | 5 |  | 2 | 2 | 2
2 | 2 | 1 | 4 | 4 | 4 | 1 | 5 | 57.5% | 5 | 1 |  | 3 | 1 | 7
2 | 2 | 2 | 3 | 3 | 3 | 1 | 4 | 50% | 1 | 1 |  | 1 | 2 | 1
5 | 1 | 1 | 3 | 5 | 5 | 2 | 1 | 57.5% | 4 | 4 |  | 5 | 1 | 1
1 | 3 | 2 | 2 | 2 | 3 | 5 | 4 | 55% | 1 | 1 |  | 2 | 3 | 2
4 | 4 | 1 | 4 | 1 | 3 | 3 | 1 | 52.5% | 2 | 3 |  | 1 | 4 | 4
5 | 2 | 3 | 2 | 2 | 3 | 1 | 2 | 50% | 3 | 3 |  | 1 | 4 | 2
1 | 4 | 5 | 3 | 4 | 2 | 5 | 4 | 70% | 2 | 4 |  | 2 | 2 | 6
2 | 4 | 2 | 1 | 1 | 4 | 3 | 2 | 47.5% | 2 | 4 |  | 5 | 1 | 5
4 | 4 | 4 | 5 | 2 | 5 | 3 | 4 | 77.5% | 2 | 2 |  | 4 | 3 | 5
1 | 3 | 4 | 3 | 4 | 4 | 5 | 5 | 72.5% | 2 | 2 |  | 3 | 3 | 3
5 | 2 | 3 | 5 | 5 | 5 | 2 | 3 | 75% | 5 | 4 |  | 4 | 1 | 4
4 | 4 | 1 | 2 | 2 | 2 | 4 | 5 | 60% | 4 | 2 |  | 4 | 5 | 3
1 | 3 | 2 | 4 | 3 | 4 | 3 | 4 | 60% | 5 | 1 |  | 1 | 3 | 6
1 | 4 | 2 | 1 | 1 | 4 | 5 | 4 | 55% | 3 | 3 |  | 2 | 5 | 3
4 | 3 | 5 | 4 | 2 | 2 | 4 | 2 | 65% | 4 | 4 |  | 2 | 5 | 1
5 | 5 | 5 | 1 | 1 | 5 | 4 | 2 | 70% | 5 | 4 |  | 2 | 3 | 3
4 | 4 | 3 | 4 | 2 | 5 | 1 | 3 | 65% | 1 | 1 |  | 4 | 2 | 7
5 | 4 | 2 | 1 | 5 | 3 | 5 | 4 | 72.5% | 5 | 5 |  | 1 | 1 | 4
5 | 2 | 2 | 5 | 4 | 4 | 2 | 4 | 70% | 4 | 3 |  | 1 | 2 | 3
5 | 5 | 3 | 4 | 2 | 2 | 3 | 4 | 70% | 3 | 2 |  | 1 | 5 | 2
5 | 3 | 5 | 3 | 5 | 2 | 1 | 5 | 72.5% | 4 | 3 |  | 3 | 1 | 8
1 | 5 | 4 | 3 | 2 | 2 | 3 | 5 | 62.5% | 3 | 2 |  | 2 | 5 | 1
4 | 4 | 1 | 3 | 5 | 1 | 4 | 4 | 65% | 1 | 1 |  | 5 | 5 | 8
5 | 5 | 1 | 4 | 2 | 3 | 3 | 2 | 62.5% | 1 | 2 |  | 5 | 2 | 4
4 | 1 | 4 | 4 | 5 | 5 | 5 | 1 | 72.5% | 3 | 2 |  | 3 | 2 | 6
3 | 4 | 2 | 4 | 5 | 4 | 3 | 1 | 65% | 1 | 5 |  | 4 | 1 | 1
3 | 1 | 2 | 3 | 1 | 1 | 5 | 3 | 47.5% | 1 | 2 |  | 1 | 3 | 9
5 | 1 | 4 | 4 | 5 | 1 | 5 | 2 | 67.5% | 1 | 4 |  | 1 | 5 | 5
4 | 4 | 1 | 2 | 1 | 1 | 4 | 5 | 55% | 4 | 2 |  | 5 | 4 | 3
4 | 4 | 5 | 4 | 2 | 2 | 4 | 5 | 75% | 1 | 5 |  | 5 | 5 | 8
1 | 1 | 1 | 3 | 4 | 4 | 1 | 1 | 40% | 2 | 3 |  | 5 | 4 | 9
1 | 2 | 4 | 2 | 4 | 5 | 1 | 3 | 55% | 1 | 5 |  | 1 | 1 | 4
3 | 5 | 1 | 5 | 1 | 4 | 1 | 5 | 62.5% | 1 | 2 |  | 3 | 3 | 3
1 | 5 | 5 | 2 | 2 | 1 | 2 | 3 | 52.5% | 3 | 4 |  | 4 | 2 | 5
1 | 4 | 2 | 1 | 3 | 2 | 3 | 4 | 50% | 3 | 3 |  | 1 | 3 | 2
4 | 2 | 5 | 3 | 5 | 1 | 2 | 3 | 62.5% | 5 | 3 |  | 2 | 5 | 9
4 | 3 | 3 | 5 | 4 | 5 | 4 | 3 | 77.5% | 3 | 3 |  | 2 | 3 | 4
3 | 4 | 2 | 3 | 1 | 1 | 2 | 3 | 47.5% | 5 | 5 |  | 2 | 2 | 1
3 | 4 | 5 | 2 | 1 | 4 | 1 | 2 | 55% | 5 | 2 |  | 2 | 3 | 4
5 | 1 | 3 | 5 | 1 | 4 | 5 | 3 | 67.5% | 2 | 3 |  | 2 | 4 | 8
2 | 3 | 2 | 4 | 2 | 5 | 4 | 5 | 67.5% | 2 | 3 |  | 3 | 2 | 9
2 | 4 | 5 | 5 | 1 | 4 | 1 | 4 | 65% | 1 | 2 |  | 5 | 1 | 4
1 | 2 | 4 | 5 | 2 | 3 | 5 | 2 | 60% | 4 | 5 |  | 4 | 4 | 9
4 | 5 | 4 | 2 | 5 | 5 | 3 | 4 | 80% | 2 | 1 |  | 1 | 3 | 5
4 | 3 | 4 | 5 | 5 | 1 | 3 | 3 | 70% | 3 | 5 |  | 2 | 2 | 4
4 | 5 | 5 | 2 | 2 | 2 | 1 | 1 | 55% | 2 | 2 |  | 5 | 2 | 8
2 | 2 | 2 | 4 | 4 | 1 | 5 | 2 | 55% | 1 | 4 |  | 4 | 5 | 3
2 | 5 | 1 | 2 | 2 | 1 | 1 | 1 | 37.5% | 3 | 4 |  | 1 | 5 | 1
1 | 3 | 4 | 1 | 4 | 4 | 2 | 3 | 55% | 5 | 1 |  | 4 | 2 | 3
2 | 4 | 5 | 2 | 2 | 2 | 4 | 2 | 57.5% | 4 | 4 |  | 4 | 4 | 6
5 | 1 | 3 | 1 | 2 | 3 | 5 | 3 | 57.5% | 2 | 3 |  | 5 | 3 | 4
2 | 2 | 3 | 3 | 2 | 3 | 4 | 5 | 60% | 2 | 4 |  | 3 | 2 | 5
1 | 1 | 1 | 5 | 4 | 5 | 1 | 4 | 55% | 1 | 4 |  | 3 | 2 | 9
2 | 1 | 5 | 1 | 1 | 4 | 3 | 2 | 47.5% | 3 | 1 |  | 5 | 2 | 9
1 | 1 | 1 | 2 | 3 | 2 | 3 | 2 | 37.5% | 5 | 5 |  | 5 | 3 | 4
1 | 3 | 3 | 2 | 1 | 3 | 2 | 3 | 45% | 4 | 2 |  | 2 | 1 | 2
4 | 4 | 4 | 5 | 5 | 4 | 4 | 5 | 87.5% | 1 | 1 |  | 1 | 1 | 3
4 | 1 | 5 | 5 | 4 | 1 | 1 | 1 | 55% | 2 | 2 |  | 4 | 2 | 4
1 | 1 | 1 | 2 | 5 | 2 | 2 | 2 | 40% | 5 | 3 |  | 3 | 5 | 6
2 | 2 | 5 | 1 | 5 | 3 | 3 | 5 | 65% | 2 | 5 |  | 1 | 5 | 4
4 | 4 | 4 | 4 | 3 | 5 | 2 | 4 | 75% | 4 | 4 |  | 2 | 3 | 8
1 | 2 | 3 | 5 | 5 | 3 | 1 | 1 | 52.5% | 2 | 1 |  | 2 | 2 | 8
2 | 4 | 5 | 5 | 5 | 1 | 4 | 4 | 75% | 3 | 1 |  | 4 | 4 | 6
4 | 5 | 5 | 2 | 5 | 1 | 3 | 5 | 75% | 5 | 4 |  | 2 | 3 | 7
3 | 2 | 2 | 2 | 1 | 1 | 2 | 4 | 42.5% | 5 | 1 |  | 3 | 5 | 3
3 | 2 | 5 | 5 | 2 | 4 | 1 | 3 | 62.5% | 5 | 1 |  | 4 | 3 | 3
5 | 2 | 3 | 2 | 4 | 5 | 4 | 3 | 70% | 3 | 4 |  | 5 | 3 | 5
5 | 3 | 4 | 5 | 2 | 1 | 2 | 4 | 65% | 3 | 5 |  | 1 | 1 | 7
2 | 1 | 2 | 4 | 5 | 1 | 4 | 4 | 57.5% | 1 | 5 |  | 5 | 4 | 7
3 | 5 | 5 | 4 | 3 | 3 | 3 | 4 | 75% | 3 | 4 |  | 2 | 3 | 8
4 | 2 | 5 | 3 | 4 | 2 | 1 | 2 | 57.5% | 5 | 2 |  | 2 | 3 | 9
2 | 1 | 4 | 5 | 3 | 3 | 2 | 2 | 55% | 3 | 2 |  | 2 | 4 | 8
1 | 5 | 3 | 2 | 1 | 4 | 1 | 2 | 47.5% | 3 | 4 |  | 3 | 2 | 4
1 | 2 | 3 | 1 | 3 | 3 | 4 | 3 | 50% | 3 | 1 |  | 4 | 5 | 6
5 | 1 | 1 | 3 | 3 | 4 | 1 | 5 | 57.5% | 1 | 5 |  | 3 | 5 | 6
1 | 1 | 5 | 3 | 3 | 2 | 1 | 1 | 42.5% | 2 | 2 |  | 5 | 1 | 3
4 | 5 | 5 | 1 | 4 | 3 | 5 | 5 | 80% | 5 | 1 |  | 2 | 5 | 4
1 | 3 | 1 | 1 | 4 | 1 | 3 | 5 | 47.5% | 4 | 5 |  | 3 | 2 | 2
2 | 3 | 3 | 5 | 1 | 4 | 5 | 1 | 60% | 4 | 2 |  | 5 | 2 | 2
4 | 5 | 2 | 1 | 3 | 2 | 2 | 1 | 50% | 4 | 5 |  | 1 | 2 | 6
1 | 4 | 4 | 3 | 1 | 5 | 4 | 3 | 62.5% | 4 | 2 |  | 5 | 4 | 9
2 | 2 | 1 | 4 | 5 | 5 | 4 | 3 | 65% | 2 | 4 |  | 4 | 4 | 8
4 | 1 | 4 | 2 | 1 | 3 | 4 | 3 | 55% | 2 | 1 |  | 1 | 5 | 5
5 | 5 | 2 | 3 | 2 | 1 | 2 | 1 | 52.5% | 3 | 2 |  | 4 | 1 | 8
1 | 2 | 3 | 2 | 5 | 1 | 2 | 2 | 45% | 4 | 3 |  | 3 | 2 | 5
5 | 1 | 3 | 4 | 1 | 3 | 1 | 1 | 47.5% | 5 | 5 |  | 3 | 1 | 5
5 | 4 | 3 | 3 | 1 | 3 | 5 | 3 | 67.5% | 4 | 2 |  | 4 | 3 | 7
5 | 1 | 5 | 2 | 2 | 4 | 3 | 3 | 62.5% | 5 | 4 |  | 1 | 4 | 7
5 | 3 | 4 | 3 | 3 | 4 | 3 | 2 | 67.5% | 1 | 4 |  | 1 | 1 | 4
5 | 3 | 3 | 1 | 1 | 1 | 1 | 5 | 50% | 3 | 4 |  | 2 | 2 | 7
5 | 1 | 4 | 4 | 1 | 4 | 2 | 3 | 60% | 2 | 3 |  | 1 | 5 | 2
4 | 2 | 3 | 1 | 4 | 3 | 4 | 5 | 65% | 1 | 5 |  | 4 | 1 | 7
1 | 3 | 3 | 1 | 5 | 1 | 5 | 1 | 50% | 3 | 2 |  | 4 | 3 | 9
2 | 5 | 4 | 1 | 2 | 5 | 2 | 3 | 60% | 2 | 3 |  | 4 | 3 | 4
Note on I17: ====== ID#AAABfVkNeew Microsoft Office User (2025-03-04 21:20:02) Microsoft Office User: